## 2021_HY2_Measures_master
IT Security Initiative Measures (2021 second half-year)
PMO / Head: Ralf Schneider
PMO / Budget: Marina Dührkop
PMO / Progress Tracking: Julian Steinfeld
as of August 31st, 2021 | [13 empty] | Total HY-2 2021 (k€) | 19315.72 | 15687.72 | 1817 | - | 0 | 0 | Progress KPIs
# | Focus Area | MID | PSP Element | Measure name | Measure description / work package | Security Domain | Contract partner | Provider | Focus Area Lead | Measure Sponsor | Measure Lead | operating ML (only AZ Technology) | Line Org. Sponsor | Solution Manager | Appr. Budget in k€ (11.06.2021) | Appr. Budget labor in k€ (11.06.2021) | Appr. Budget non-labor in k€ (11.06.2021) | Approval Date | Spent in k€ (01.07.2021) | Invoiced in k€ (01.07.2021) | # | Name | Baseline 01.07.2021 | Actuals 01.07.2021 | Target 31.12.2021 | Status 31.12.2021 | Comments Please contact SecurityInvestmentInitiativeOffice@allianz.com if you would like to receive the current status report of all or individual measures. | Comments PMO | TCB
1 | Slow Down Hackers | M274 | AZSE-H4-800247 | Extend currently running TIBER exercise | TIBER-EU* is the EU red-teaming framework to test control effectiveness and improve the cyber resilience of entities by carrying out controlled but realistic cyberattacks incl. social engineering from external experts. Measure 252 was approved and carried out in HY1 2021 to prepare and start the TIBER test. TIBER framework foresees a duration of 40 weeks of all TIBER phases, therefore this measure will complete the TIBER test in HY2 2021 and plan subsequent remediation measures. | Allianz Global IS Governance | Metafinanz | Metafinanz | Robert Klawes | Robert Klawes | Andreas Wagner | not required | Carsten Scholz | Michael Lewandowski | 1838.72 | 1838.72 | 0 | 2021-06-11 |  |  | #1 | # of scenarios tested | 0 |  | 4
2 | Slow Down Hackers | M275 | AZSE-H4-800248 | Cloud Security Competence Center + Secret Mgmt. | The CoE for Cloud Security activities aims to enable Allianz in their Cloud Security Journey on all levels (from App Development to Cloud Hosting) & continuous cultural change. The CoE will handle the coverage and capabilities of the cloud standard security service stack (Prisma, Checkmarx, GitHub Adv. Security, AWS/ Azure Services, Vaults etc.). To ensure standard services fit in the defined cloud security landscape of Allianz. It will design a new secret management service for cloud can provide these capabilities in a secure, manageable way. | Embedded Infrastructure Security Services (Cloud) | Metafinanz | Metafinanz | Robert Klawes | Robert Klawes | Marc Bochtler | not required | Markus Wüpping | Jeslin Thomas John | 800 | 800 | 0 | 2021-06-11 |  |  | #2 | # of Security Consultations | 0 |  | 10
3 | Slow Down Hackers | M276 | AZSE-H4-800249 | Global & Scalable Application Pen Test Service Setup | M257 in HY1/2021 proofed the feasibility for a highly Industrialized Application Penetration Test approach in Allianz. Continues as sprint. The next step is now to establish the full Service Offering in Allianz Technology and to ramp-up Application Pen-Tests. | Allianz IS Shared Services Consumption based | AZT SecOps | AZ Technology | Robert Klawes | Gerrit Rothmaier | Clemens Friedrich | Sven Lierzer | Gerhard Schneider | Martin Gerlowski | 950 | 890 | 60 | 2021-06-11 |  |  | #3 | # of application penetration tests performed | 0 |  | 30
4 | Slow Down Hackers | M277 | AZSE-H4-800271 | Realtime auditing & sec monitoring for Active Directory | A critical security control is required to manage security related events via a single pane of glass for on premise Active Directory, Azure Active Directory and Active Directory Domain Controllers that need to be deployed in a Public Cloud environment as a business enabler. The single and seamless integration to the ACDC global security operations processes and tools allow for a more efficient management of security events from Active Directory. | Embedded Infrastructure Security Services | AZT SecOps | AZ Technology | Robert Klawes | Robert Klawes | Alexander Heinze | Sergej Reißig | Andrea Scotti | Wolfgang Elsner | 670 | 550 | 120 | 2021-06-11 |  |  | #4 | # of event propagation from the source to the SIEM response | 0 |  | 3
5 | Slow Down Hackers | M278 | AZSE-H4-800272 | IAM Password Hash Synchronization to Azure Active Directory | As part of the overarching Allianz IAM strategy currently in creation within the IAMAB, (Identity and Access Management Advisory Board) this proposal takes the first steps in transitioning identity management to the cloud with the creation of a concept and pilot for implementation of “Password Hash Synchronization” to synchronize the "hash of the hash" - multi-hashed (1k+) hash of the original password hash and to integrate Microsoft Identity Protection and Remediation (for example credential abuse etc.) into ACDC security operations processes and tools for monitoring, reporting and alerting. | Embedded Infrastructure Security Services | AZT SecOps | AZ Technology | Robert Klawes | Ralph Oelssner | Alexander Heinze | Itai Schwartz | Andrea Scotti | Wolfgang Elsner | 448 | 448 | 0 | 2021-06-11 |  |  | #5 | # of artefacts completed | 0 |  | 6
6 | Slow Down Hackers | M279 | AZSE-H4-800273 | PTA (Privileged Threat Analytics) | Access to target systems for privileged activities is obligatory according to the Allianz Group Standards. Enhancement of analysis capabilities for attack detection, malicious privileged account activity incl. real time interruption of session based on behavior-based algorithms is required. | Embedded Infrastructure Security Services | AZT SecOps | AZ Technology | Robert Klawes | Ralph Oelssner | Alexander Heinze | Reza Memarian | Andrea Scotti | Walter Hofer | 670 | 550 | 120 | 2021-06-11 |  |  | #6 | # of artefacts achieved and requirements analyzed | 0 |  | 9
7 | Slow Down Hackers | M302 | AZSE-H4-800302 | IAM Role Management & Machine Learning Analytics | The Measure focuses on IAM role management & machine learning analytics to provide automated re-attestation based on “confidence factors” in order to achieve a better control and accuracy of Allianz access management for normal and privileged access. |  | AZT SecOps | AZ Technology |  | Ralph Oelssner | Alexander Heinze | Dirk Addicks | Andrea Scotti | TBD | 811 | [5 empty] | #7 | # of reached milestones | 0 |  | 5
8 | Increase Detection | M280 | AZSE-H4-800274 | Advanced Network-based detection and response | Network based threat detection can supplement endpoint-based detection and response and act as an early warning system to detect breaches or unusual network behavior (e.g. cross-OE traffic or data exfiltration). Allianz currently has DCSO provided systems in place (TDH), which could be benchmarked to other providers. With the market moving fast, an assessment of options in the market, as well as strategy for the service is required | Allianz Global IS Governance | div. 3rd party provider | other | Jawed Zamani | Jawed Zamani | Thomas Wolf | not required | Robert Feser | Patrick Zeitz | 353 | 250 | 103 | 2021-06-11 |  |  | #8 | # of new generation ADH deployment | 0 |  | 10
9 | Increase Detection | M281 | AZSE-H4-800275 | Passive DNS Monitoring & DNS Firewalling | DNS is used to translate domain names (allianz.com) to IP addresses (127.0.0.1), as such it is also used by malware to connect to command & control servers, as well as to potentially exfiltrate information (seen in RedTeam exercises). Currently there is very limited visibility and logging of which DNS requests are performed from within the AGN. | Allianz Global IS Governance | AZT SecOps | AZ Technology | Jawed Zamani | Jawed Zamani | Lucas Tscherter | Krunoslav Rukavina | Robert Feser | Lars König | 337 | 210 | 127 | 2021-06-11 |  |  | #9 | # of DNS Server logs consumed | 0 |  | 2
10 | Increase Detection | M282 | AZSE-H4-800276 | Global Deception rollout | M261 successfully rolled out the Allianz Deception Capability to the European datacenters E1 & E2 and covered the endpoints in those regions. Next step to establish a global Deception Capability is the global rollout to NA and AP region | Allianz IS Global Platform | AZT SecOps | AZ Technology | Jawed Zamani | Jawed Zamani | Lucas Tscherter | Christian Suffel | Robert Feser | Patrick Zeitz | 1620 | 1350 | 270 | 2021-06-11 |  |  | #10 | # of DCs and endpoints covered with deception | 0 |  | 6
11 | Increase Detection | M283 | AZSE-H4-800277 | Enhance Cloud response & Secure Allianz critical Apps | After the successful onboarding of Cloud log sources to ACDC the measure wants to further enhance and foster incident response capabilities of ACDC in the focus area Cloud. In addition, logging and monitoring requirements of business critical Allianz applications (e.g. SAP) will be analyst to prepare potential onboarding to ACDC SIEM. | Allianz IS Global Platform | AZT SecOps | AZ Technology | Jawed Zamani | Jawed Zamani | Lucas Tscherter | Lucas Tscherter | Robert Feser | Thomas Bringewald | 505 | 475 | 30 | 2021-06-11 |  |  | #11 | # of implemented cloud use cases | 0 |  | 10
12 | Increase Detection | M284 | AZSE-H4-800278 | SOAR Rollout and case management implementation | With M260 SOAR has been successfully implemented and integrated with the relevant systems and ACDC processes. Next step and one main activity of this measure is to switch from Incident Management in Archer to Case Management in SOAR. In addition, the user adoption of SOAR within ACDC but also the onboarding of local security teams to SOAR will be done which is directly supporting the Gearshift program. | Allianz IS Global Platform | AZT SecOps | AZ Technology | Jawed Zamani | Jawed Zamani | Lucas Tscherter | Timothy Drost | Robert Feser | Andrei Maslov | 690 | 610 | 80 | 2021-06-11 |  |  | #12 | # of integrations or play books implemented | 0 |  | 8
13 | Increase Detection | M285 | AZSE-H4-800279 | Increase Effectiveness of Micro Segmentation and Rollout in EU | Further Rollout of AMS / Illumio to Business critical applications (Crown jewels) in Europe to support OEs with a need for Micro-segmentation due to regulatory requirements, e.g. NIS, TIBER, CBEST Support moving applications from Build to Enforce mode by developing industrialized process | Allianz IS Global Platform | AZT SecOps | AZ Technology | Jawed Zamani | Jawed Zamani | Clemens Friedrich | Tobias Krichel | Gerhard Schneider | Martin Gerlowski | 420 | 420 | 0 | 2021-06-11 |  |  | #13 | # of business critical applications moved to Enforce-Mode | 0 |  | 30
14 | Increase Detection | M286 | AZSE-H4-800280 | Build Central Dashboard to Increase Transparency and Real Time Monitoring | Continuous security monitoring enables organizations to gauge their security posture in real time to identify weaknesses or potential compromises and mitigate them quickly. To enable that real time continuous security monitoring and support fast mitigation and action, the aim is to rollout a group wide Information Security Operations and Governance Application for all CIOs and ISOs as well as to AZ Tech Information Security Departments.. | Allianz IS Global Platform | AZT SecOps | AZ Technology | Jawed Zamani | Jawed Zamani | Clemens Friedrich | Mike Liebsch (TBC) | Gerhard Schneider | Matthias Kickstein | 285 | 285 | 0 | 2021-06-11 |  |  | #14 | # of Reporting User Stories designed and User Stories implemented | 0 |  | 12
15 | Reduce Damage | M287 | AZSE-H4-800281 | Extension of vulnerability mgmt. to clients and global policy compliance rollout | Enhance current AVM Scope to workplace by rolling out Qualys Agents (incl. Policy Compliance option), especially to non-standard environments Roll-out of Policy Compliance for all Server Service within the established AVM scope | Allianz IS Global Platform | AZT SecOps | AZ Technology | Michael Doberenz | Michael Doberenz | Clemens Friedrich | Daniela Betz | Gerhard Schneider | Marko Koscevic | 1250 | 1150 | 100 | 2021-06-11 |  |  | #15 | # of OEs covered with Qualys agents on clients | 0 |  | 20
16 | Reduce Damage | M288 | AZSE-H4-800282 | AGN Secure Network Access and Segregation | Future proof the AGN access security and control end-to-end in Allianz from user to service (on premise and in the public cloud) The UK TIBER exercise showed some continued weaknesses in the network segregation, which are based on the current approach used for the separation (works as designed, yet weak). | Embedded Infrastructure Security Services (AGN) | AZT AGN ??? | AZ Technology | Michael Doberenz | Ralph Oelssner | Michael Kahlfuss | Ruben Lihet | Stefano Fabbri | Sebastian Bohlmann | 588 | 538 | 50 | 2021-06-11 |  |  | #16 | # of reached milestones | 0 |  | 4
17 | Reduce Damage | M289 | AZSE-H4-800283 | Acceleration of Password Manager service | As part of the MFA security measure, the implementation of a modern cloud-based password manager service was evaluated, and implementation work started. The solution will complement the workplace security service offering and support AZ Group’s end users in the journey to a “password less” experience (on all platforms AMC, AVC, EMS). A technical solution is prepared based on LastPass from LogMeIn. | Embedded Infrastructure Security Services (Workplace) | AZT - Ruttkowski | AZ Technology | Michael Doberenz | Dorit Naveh | Rainer Mahlo | Rainer Mahlo | Dietmar Jewdoschenko | Rainer Mahlo | 350 | 350 | 0 | 2021-06-11 |  |  | #17 | # of users rolled-out to password manager service | 0 |  | 1000
18 | Reduce Damage | M290 | AZSE-H4-800284 | Re-Design Of Cloud Application Discovery Service | Existing technical solution for the GSP CAD is discontinued by the provider for end of year. Actual solution was focused on On-Prem surf-traffic. Develop a concept / solution design in a 3-month sprint to Enhancement of auditing and compliance violation detection capabilities in the cloud (joint solution for on-prem and cloud Proxy environments). Enhancement of the CAD reporting quality by enabling reports on BU-levels | Allianz IS Global Platform | AZT SecOps | AZ Technology | Michael Doberenz | Michael Lewandowski | Clemens Friedrich | Jan General | Gerhard Schneider | Matthias Kickstein | 155 | 155 | 0 | 2021-06-11 |  |  | #18 | # of Service design documents for future CAD service developed | 0 |  | 6
19 | Reduce Damage | M291 | AZSE-H4-800285 | Privileged Access Management for Cloud | Permanent administrative credentials pose a risk for unauthorized access and data leakage. A privileged access management solution for cloud can provide temporary credentials when needed and allows central governance and oversight. | Embedded Infrastructure Security Services (Cloud) | AZT SecOps | AZ Technology | Michael Doberenz | Robert Klawes | Alexander Heinze | Marc Bochtler | Andrea Scotti | Tobias Butz | 200 | 200 | 0 | 2021-06-11 |  |  | #19 | # of validate possible integrations | 0 |  | 4
20 | Reduce Damage | M301 | AZSE-H4-800299 | Global Tier 0 Hosting Platform Preparation & APAC Pilot |  |  | AZT SecOps | AZ Technology | na | Michael Lewandowski | Alexander Heinze | Mitja Ledowski | Andrea Scotti | Michael Holder | 1000 | 750 | 250 | TBD |  |  | #20a | # of Global Service AD (ADTRootdom.net & Rootdom.net Domain Controllers) extended to Tier 0 Hosting Platform in APAC | 0 |  | 8
[21 empty] | #20b | # of Local APAC units of Allianz Partners: Domain Controllers onboarded to Tier 0 Hosting Platform | 0 |  | 4
21 | Streamline Compliance | M292 | AZSE-H4-800286 | Double Key Encryption / Extended Security & Compliance for M365 | In Measure 267 double key encryption for MIP* has been assessed to provide protection against the implications of the US Cloud Act. To rollout the functionality, a license upgrade to "M365 E5 Information Protection and Governance" is required, which enables additional functionalities in the area of MIP*, Record Management and Data Loss Prevention. The goal of this measure is the evaluation, definition and implementation of a complementary security and compliance AZT service to Office 365, which makes the functionality from M365 IP&G available to the OEs. | Embedded Infrastructure Security Services (Workplace) | AZT - Ruttkowski | AZ Technology | Christian Schweda | Dorit Naveh | Julian Bönigk | Julian Bönigk | Dietmar Jewdoschenko | Julian Bönigk | 750 | 690 | 60 | 2021-06-11 |  |  | #21 | # of reached artefacts | 0 |  | 5
22 | Streamline Compliance | M293 | AZSE-H4-800287 | Automated Toxic Tracking for Client-based Assets | The objective is to achieve comprehensive automated toxic tracking for client-based assets (e.g. AVC, AMC and EMS mobile smart devices) as a baseline for OE IT reporting in Archer and independent oversight by OE IS. The information is to be provided via lifecycle management / toxic dashboards in SNOW covering toxic components1 on client-based assets. | Embedded Infrastructure Security Services | AZT - Fabian Topp | AZ Technology | Christian Schweda | Gerrit Rothmaier | Benjamin Warnholz | Ismail Uysal | Fabian Topp | Arun Chandran | 360 | 300 | 60 | 2021-06-11 |  |  | #22 | # of Toxic Asset Dashboard including client IT asset data (e.g. AVC, AMC, fat client, smart mobile de-vices) for minimum of 25 OEs | 0 |  | 25 |  |  | ITOM Zahlen, external/iternal Split
23 | Streamline Compliance | M294 | AZSE-H4-800288 | Integrated Information Risk Management early Live​ | The IIRM entails an organizational and cultural change and needs to be supported as such. The process needs more attention and support by the OEs based on the feedback given (especially the ISO community). Further training as well as improved scoping, mature KPIs and reporting as well as stronger integration to existing information sources needs to be established. | Allianz Global IS Governance | Metafinanz | Metafinanz | Christian Schweda | Christian Schweda | Michael Habel | not required | Christian Schweda | Uta Knebel | 650 | 650 | 0 | 2021-06-11 |  |  | #23 | # of reached milestones | 0 | 0 | 5
24 | Streamline Compliance | M295 | AZSE-H4-800289 | Global Security Platform GITSO blueprint | Group-driven global skill blueprint for IT Service Owner role (GITSO) for Global Security Platform to be used as mandatory framework to normalize baseline maturity of IS Services. Create a basis to enhance the capabilities and personnel setup of Group IS as well as the cooperation between the Group and the Shared IT Service Provider. | Allianz Global IS Governance | Metafinanz | Metafinanz | Christian Schweda | Michael Doberenz | George Dietrichsbruckner | not required | Carsten Scholz | Michael Doberenz | 300 | 298 | 2 | 2021-06-11 |  |  | #24 | # of KPI + SLA vetting draft for 6 Security Services | 0 |  | 12
25 | Build Security Organization / Skills | M296 | AZSE-H4-800290 | Financial Loss Quantification | Develop and implement an overall approach across Allianz Group to enable financial quantification of cyber risks in order to improve overall alignment with Operational Risk Management function demonstrate the ROI of security investments align budgets with programs that impact financial exposure to cyber risk | Allianz Global IS Governance | Bitsight / Metafinanz | Metafinanz | Daria Catalui | Michael Lewandowski | Thomas Thuspass | not required | Carsten Scholz | Michael Lewandowski | 400 | 400 | 0 | 2021-06-11 |  |  | #25 | # of OEs evaluated within BitSight financial model | 0 |  | 10
26 | Build Security Organization / Skills | M297 | AZSE-H4-800291 | Measure and Enhance Global Phishing Resilience | Make User Awareness in Allianz measurable and comparable between OEs globally Further enhance the GUA service by developing several User Awareness building blocks (e.g., Learning Nuggets) and introducing global brand character that will be offered to Allianz OEs worldwide | Allianz Human Firewall | AZT SecOps | AZ Technology | Daria Catalui | Daria Catalui | Clemens Friedrich | Anna Hartl | Gerhard Schneider | Matthias Kickstein | 995 | 720 | 275 | 2021-06-11 |  |  | #26 | # of learning nuggets and OE dashboards created | 0 |  | 10 |  |  | Ab September Daria Catalui
27 | Build Security Organization / Skills | M298 | AZSE-H4-800292 | Strategic THREAT Intelligence and Resulting risk Identification Program | A recent analysis has shown that strategic threat intelligence in Allianz is currently in a state of low maturity, yet it is a vital part of information risk management and information security. Current threat intelligence products mostly come in the form of technical indicators or tactical information, but as strategic threat intelligence (S-TI) is lacking, there is no connection to strategic investment decisions. In addition insider and state funded threats are currently not sufficiently considered. | Allianz Global IS Governance | div. 3rd party provider | other | Daria Catalui | Ralf Schneider | Thomas Wolf | not required | Carsten Scholz | Stefan Balzer | 480 | 480 | 0 | 2021-06-11 |  |  | #27 | # of reached artefacts | 0 |  | 3
28 | Build Security Organization / Skills | M299 | AZSE-H4-800293 | Enforcement of Security Architecture | Group-wise Enterprise Security Architecture Framework and it’s first outcomes have already been delivered. Now it is time to get the benefit out of these outcome by enforcing and checking the usage of the principles and patterns, continue to work on more of them for end to end protection of applications, building stronger bridges in between the security components and as well as converging to the AZ Group Enterprise Architecture standards. | Allianz Global IS Governance | EY / Metafinanz | Ernst & Young | Daria Catalui | Cenk Tasdan | Jan General | not required | Cenk Tasdan | Cenk Tasdan | 430 | 430 | 0 | 2021-06-11 |  |  | #28 | # of architectural documents (e.g. pattern / analysis / methodology) published | 0 |  | 7
29 | Build Security Organization / Skills | M300 | AZSE-H4-800294 | Metrics phase @We protect scale up on skills | We are going through a permanent stress test on the Human Firewall. Recent reporting shows a sustained improvement across AZ ecosystem and training user behavior however the pace and time should only increase in intensity in order to face prepared the external threats. This measure suggests several artefacts in order to follow through this line of thought and having in mind the economics aspects of it. | Allianz Human Firewall | Metafinanz | Metafinanz | Daria Catalui | Daria Catalui | Samuel Hurst | not required | Carsten Scholz | Daria Catalui | 540 | 390 | 150 | 2021-06-11 |  |  | #29 | # of high qualitative metrics for ROI | 0 |  | 5 |  |  | Ab September Daria Catalui
30 | Overarching | M251 | AZSE-H4-800224 | IT Security Initiative Hub |  |  | Metafinanz | Metafinanz |  | Ralf Schneider |  |  |  |  | 470 | 260 | 210 | 2021-06-11
* inclusive budget transfer of 1.338,72 EUR from M252 (HY1) to M274 (HY2)
*

## Contacts Measure Lead Deputies
# | Focus Area | MID | Measure name | Measure Sponsor | Measure Lead | Deputy Measure Lead | Number | Email
1 | Slow Down Hackers | M274 | Extend currently running TIBER exercise | Robert Klawes | Andreas Wagner
2 | Slow Down Hackers | M275 | Cloud Security Competence Center + Secret Mgmt. | Robert Klawes | Marc Bochtler | Robert Klawes | 491797068128 | robert.klawes@allianz.com
3 | Slow Down Hackers | M276 | Global & Scalable Application Pen Test Service Setup | Gerrit Rothmaier | Clemens Friedrich | Lucas Tscherter | +49 171 5617948 | lucas.tscherter@allianz.de
4 | Slow Down Hackers | M277 | Realtime auditing & sec monitoring for Active Directory | Robert Klawes | Alexander Heinze | Itai Schwartz |  | extern.schwartz_itai1@allianz.de
5 | Slow Down Hackers | M278 | IAM Password Hash Synchronization to Azure Active Directory | Ralph Oelssner | Alexander Heinze | Itai Schwartz |  | extern.schwartz_itai1@allianz.de
6 | Slow Down Hackers | M279 | PTA (Privileged Threat Analytics) | Ralph Oelssner | Alexander Heinze | Itai Schwartz |  | extern.schwartz_itai1@allianz.de
7 | Slow Down Hackers | M302 | AZSE-H4-800302 | IAM Role Management & Machine Learning Analytics | Alexander Heinze | Dirk Addicks | +49 162 2187039 | dirk.addicks@allianz.de
7 | Increase Detection | M280 | Advanced Network-based detection and response | Jawed Zamani | Thomas Wolf | Krystian Misztela | +49 172 8160522 | EXTERN.MISZTELA_KRYSTIAN@ALLIANZ.DE
8 | Increase Detection | M281 | Passive DNS Monitoring & DNS Firewalling | Jawed Zamani | Krunoslav Rukavina | Clemens Friedrich | +49 170 7955010 | clemens.friedrich@allianz.de
9 | Increase Detection | M282 | Global Deception rollout | Jawed Zamani | Lucas Tscherter | Clemens Friedrich | +49 170 7955010 | clemens.friedrich@allianz.de
10 | Increase Detection | M283 | Enhance Cloud response & Secure Allianz critical Apps | Jawed Zamani | Lucas Tscherter | Clemens Friedrich | +49 170 7955010 | clemens.friedrich@allianz.de
11 | Increase Detection | M284 | SOAR Rollout and case management implementation | Jawed Zamani | Lucas Tscherter | Clemens Friedrich | +49 170 7955010 | clemens.friedrich@allianz.de
12 | Increase Detection | M285 | Increase Effectiveness of Micro Segmentation and Rollout in EU | Jawed Zamani | Clemens Friedrich | Lucas Tscherter | +49 171 5617948 | lucas.tscherter@allianz.de
13 | Increase Detection | M286 | Build Central Dashboard to Increase Transparency and Real Time Monitoring | Jawed Zamani | Clemens Friedrich | Lucas Tscherter | +49 171 5617948 | lucas.tscherter@allianz.de
14 | Reduce Damage | M287 | Extension of vulnerability mgmt. to clients and global policy compliance rollout | Michael Doberenz | Clemens Friedrich | Lucas Tscherter | +49 171 5617948 | lucas.tscherter@allianz.de
15 | Reduce Damage | M288 | AGN Secure Network Access and Segregation | Ralph Oelssner | Michael Kahlfuss | Axel Krüger | +49 172 83 21 956 | a.krueger@allianz.de
16 | Reduce Damage | M289 | Acceleration of Password Manager service | Dorit Naveh | Rainer Mahlo
17 | Reduce Damage | M290 | Re-Design Of Cloud Application Discovery Service | Michael Lewandowski | Clemens Friedrich | Lucas Tscherter | +49 171 5617948 | lucas.tscherter@allianz.de
18 | Reduce Damage | M291 | Privileged Access Management for Cloud | Robert Klawes | Alexander Heinze | Marc Bochtler | +49 89 360531 5484 | extern.bochtler_marc1@allianz.com
19 | Reduce Damage | M301 | Global Tier 0 Hosting Platform Design and APAC Pilot | Michael Lewandowski | Alexander Heinze | Markus Schnier | +49 175 1828602 | markus.schnier@allianz.com
20 | Streamline Compliance | M292 | Double Key Encryption / Extended Security & Compliance for M365 | Dorit Naveh | Julian Bönigk
21 | Streamline Compliance | M293 | Automated Toxic Tracking for Client-based Assets | Gerrit Rothmaier | Benjamin Warnholz
22 | Streamline Compliance | M294 | Integrated Information Risk Management early Live​ | Christian Schweda | Michael Habel | Gerhard Günther | +49 89 3605315618 | EXTERN.GUENTHER_GERHARD@allianz.com
23 | Streamline Compliance | M295 | Global Security Platform GITSO blueprint | Michael Doberenz | George Dietrichsbruckner | Daniel Woerner | 4915 140528340 | extern.woerner_daniel@allianz.com
24 | Build Security Organization / Skills | M296 | Financial Loss Quantification | Michael Lewandowski | Thomas Thuspass | Michael Lewandowski | +49 89 3800 18954 | michael.lewandowski@allianz.com
25 | Build Security Organization / Skills | M297 | Measure and Enhance Global Phishing Resilience | Carsten Scholz | Clemens Friedrich | Lucas Tscherter | +49 171 5617948 | lucas.tscherter@allianz.de
26 | Build Security Organization / Skills | M298 | Strategic THREAT Intelligence and Resulting risk Identification Program | Ralf Schneider | Thomas Wolf | Krystian Misztela | +49 172 8160522 | EXTERN.MISZTELA_KRYSTIAN@ALLIANZ.DE
27 | Build Security Organization / Skills | M299 | Enforcement of Security Architecture | Cenk Tasdan | Jan General | ElShekeil, Salah | +46 76-118 0545 | extern.elshekeil_salah@allianz.com
28 | Build Security Organization / Skills | M300 | Metrics phase @We protect scale up on skills | Carsten Scholz | Samuel Hurst | Kris Harms | 491795210998 | EXTERN.HARMS_KRIS@ALLIANZ.COM
29 | Overarching | M251 | IT Security Initiative Hub | Ralf Schneider

## Contacts_Measure Lead & Deputy (hidden)
IT Security Initiative Measures (2020 second half-year) | IT Security Initiative Measures (2020 second half-year)
PMO / Head: Ralf Schneider
PMO / Budget: Marina Dührkop
PMO / Progress Tracking: Julian Steinfeld
as of September 4th, 2020 |  |  | Total HY-2 2020 (k€)
# | Focus Area | MID | Measure name | Measure Sponsor | Measure Lead | Deputy Measure Lead | Number | Email
1 | Slow Down Hackers | M252 | Cyber-TIBER, Global Regulatory driven Red-Team | Robert Klawes | Andreas Wagner | George Dietrichsbruckner | +49 152 336 14446 | extern.dietrichsbruckner_george@allianz.com
2 | Slow Down Hackers | M253 | Secret Vault and internal TLS Certificate Mgmt. | Robert Klawes | Alexander Heinze | Jagoda Matys | 4915259613182 | extern.matys_jagoda1@allianz.de
3 | Slow Down Hackers | M254 | DevSecOps Community for Cloud Sec. | Robert Klawes | Marc Bochtler | Robert Klawes | +49 89 3800 63595 | robert.klawes@allianz.com
4 | Slow Down Hackers | M255 | Accelerated MFA & Integration of critical services | Dorit Naveh | Alexander Heinze | Markus Schnier | +49 175 1828602 | markus.schnier@allianz.com
5 | Slow Down Hackers | M256 | Microsoft Native Security stack for end devices | Alexander Pabst | Clemens Friedrich | Lucas Tscherter | +49 89 3800 17800 | lucas.tscherter@allianz.de
6 | Slow Down Hackers | M257 | Industrialized Application Pen Test Approach | Gerrit Rothmaier | Clemens Friedrich | Martin Gerlowski | +49 173 6658083 | martin.gerlowski@allianz.de
7 | Slow Down Hackers | M258 | Cloud WAF set-up | Alexander Pabst | Clemens Friedrich | Martin Gerlowski | +49 173 6658083 | martin.gerlowski@allianz.de
8 | Increase Detection | M259 | Cloud Integration and ITMP onboarding into ACDC | Jawed Zamani | Lucas Tscherter | Clemens Friedrich | +49 170 7955010 | clemens.friedrich@allianz.de
9 | Increase Detection | M260 | Automation & Realtime Reporting of incident response | Jawed Zamani | Lucas Tscherter | Clemens Friedrich | +49 170 7955010 | clemens.friedrich@allianz.de
10 | Increase Detection | M261 | Advanced Detection by Deception Set-up | Jawed Zamani | Lucas Tscherter | Clemens Friedrich | +49 170 7955010 | clemens.friedrich@allianz.de
11 | Increase Detection | M262 | Micro-segmentation of business-critical apps | Jawed Zamani | Clemens Friedrich | Martin Gerlowski | +49 173 6658083 | martin.gerlowski@allianz.de
12 | Reduce Damage | M263 | Actionable Vulnerability Management | Michael Doberenz | Clemens Friedrich | Martin Gerlowski | +49 173 6658083 | martin.gerlowski@allianz.de
13 | Reduce Damage | M265 | Crypsis Retainer Services | Ralf Schneider | Gerhard Günther | Andreas Wagner | +49 151 5353 9284 | EXTERN.WAGNER_ANDREAS@ALLIANZ.DE
14 | Reduce Damage | M266 | Steering Concept for IS Group Services | Michael Doberenz | Rasa Rintallo | Nadine Butzhammer | 49893605316221 | extern.butzhammer_nadine@allianz.com
15 | Streamline Compliance | M267 | Double Key encryption for US Cloud Act | Dorit Naveh | Julian Bönigk | Shilpa Sunderdas | 918129330123 | SHILPA.SUNDERDAS1@ALLIANZ.COM
16 | Streamline Compliance | M268 | Integrated Governance Platform for group solutions | Christian Schweda | Michael Habel | Gerhard Günther | +49 89 3605315618 | EXTERN.GUENTHER_GERHARD@allianz.com
17 | Streamline Compliance | M269 | Automated Toxic Asset tracking | Gerrit Rothmaier | Benjamin Warnholz | Arun Chandran | +91 9947 0738 33 | arun.chandran@allianz.com
18 | Streamline Compliance | M270 | Standardization of security assessments & processes | Christian Schweda | Tim Raffler | Till Teichmann | +49 89 3605315134 | EXTERN.TEICHMANN_TILL@ALLIANZ.DE
19 | Build Security Organization / Skills | M271 | Next Level Phishing Simulation: Shared Service | Daria Catalui | Clemens Friedrich | Lucas Tscherter | +49 89 3800 17800 | lucas.tscherter@allianz.de
20 | Build Security Organization / Skills | M264 | Next Level Phishing Simulation: Email Security | Daria Catalui | Frank Markussen | Marina Hauptmann | +49 89 3605315242 | extern.hauptmann_marina@allianz.com
21 | Build Security Organization / Skills | M272 | Embedding Security into Applications & Architecture | Stephan Dresel | Cenk Tasdan | Jan General | +49 160 9391 7332 | EXTERN.GENERAL_JAN@ALLIANZ.COM
22 | Build Security Organization / Skills | M273 | Distributing the Human Firewall | Daria Catalui | Armin Anzenbacher | Kris Harms | 491795210998 | EXTERN.HARMS_KRIS@ALLIANZ.COM
23 | PMO | M251 | IT Security Initiative Hub