## 1. Overview
1. Overview (2021-10-15)
Focus Area | # | MID | Security Measures | Measure Lead | Measure Sponsor | Start date | End date | Approved |  |  | Approved | Spent | [13 empty] | Spent budget | Invoiced | Plan | Forecast | Delta
[8 empty] | labor | non-labor | Total | Total (2021-06-11) | Labor Metafinanz | Labor AZ TECH | Labor AZ Services | Labor Third Party | Labor | non-Labor Metafinanz | non-Labor AZ TECH | non-Labor AZ Services | non-Labor Third Party | non-Labor | Total Metafinanz | Total AZ TECH | Total Services | Total Third Party | Total (2021-10-15) | Total (2021-10-15) | Total (2021-10-15) | Total (2021-10-01) | Total (2021-10-01) | Comment
Slow down hackers | 1 | M274 | Extend currently running TIBER exercise | Andreas Wagner | Robert Klawes | 2021-07-01 | 2021-12-31 | 1838720 | 0 | 1838720 | 1838720 | 0 | 0 | 0 | 408658.69 | 408658.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 408658.69 | 408658.69 | 291265.69 | 522541.69 | 1363010.09 | 475709.91 | In General (underrun of roughly 500k) we will not be able to start mitigation this year as planned, but have to podstpone that to a new measure next year
Slow down hackers | 2 | M275 | Cloud Security Competence Center + Secret Mgmt. | Marc Bochtler | Robert Klawes | 2021-07-01 | 2021-12-31 | 800000 | 0 | 800000 | 800000 | 183760.625 | 0 | 0 | 181400.72 | 365161.345 | 0 | 0 | 0 | 0 | 0 | 183760.625 | 0 | 0 | 181400.72 | 365161.345 | 325738.85 | 799291.44 | 800000 | 0
Slow down hackers | 3 | M276 | Global & Scalable Application Pen Test Service Setup | Clemens Friedrich | Gerrit Rothmaier | 2021-07-01 | 2021-12-31 | 1090000 | 60000 | 1150000 | 1150000 | 0 | 276810.2324 | 0 | 0 | 276810.2324 | 0 | 0 | 0 | 0 | 0 | 0 | 276810.2324 | 0 | 0 | 276810.2324 | 0 | 1150000 | 1095400.1384 | 54599.8616 | New sourcing of measure lead with lower external dayrate, less SNOW implementation efforts
Slow down hackers | 4 | M277 | Realtime auditing & sec monitoring for Active Directory | Alexander Heinze | Robert Klawes | 2021-07-01 | 2021-12-31 | 670000 | 0 | 670000 | 670000 | 0 | 157099.0619 | 0 | 0 | 157099.0619 | 0 | 0 | 0 | 0 | 0 | 0 | 157099.0619 | 0 | 0 | 157099.0619 | 129581.19 | 670000 | 569341.8392 | 100658.1608 | Planned POC licence costs not needed due to successful negotiations
Slow down hackers | 5 | M278 | IAM Password Hash Synchronization to Azure Active Directory | Alexander Heinze | Ralph Oelssner | 2021-07-01 | 2021-12-31 | 448000 | 0 | 448000 | 448000 | 0 | 173433.2076 | 0 | 0 | 173433.2076 | 0 | 0 | 0 | 0 | 0 | 0 | 173433.2076 | 0 | 0 | 173433.2076 | 84151.6 | 448000 | 443805.3123 | 4194.6877
Slow down hackers | 6 | M279 | PTA (Privileged Threat Analytics) | Alexander Heinze | Ralph Oelssner | 2021-07-01 | 2021-12-31 | 550000 | 120000 | 670000 | 670000 | 0 | 102967.1383 | 0 | 0 | 102967.1383 | 0 | 0 | 0 | 0 | 0 | 0 | 102967.1383 | 0 | 0 | 102967.1383 | 83266.98 | 670000 | 663592.6024 | 6407.3976
Slow down hackers | 7 | M302 | IAM Role Management & Machine Learning Analytics | Alexander Heinze | Ralph Oelssner | 2021-09-15 | 2021-12-31 | 750000 | 61000 | 811000 | 811000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83266.98 | 811000 | 749088.0176 | 61911.9824 | Sourcing mix optimized, dayrate renegotiation of external vendor
Increase Detection | 8 | M280 | Advanced Network-based detection and response | Thomas Wolf | Jawed Zamani | 2021-07-01 | 2021-12-31 | 250000 | 103000 | 353000 | 353000 | 0 | 0 | 0 | 132090 | 132090 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 132090 | 132090 | 0 | 220150 | 270150 | 82850 | 1. Joint project management for M280/M298 out of M298 reduces costs. 2. Some money will need to be be reserved for follow-up activities in 2022.
Increase Detection | 9 | M281 | Passive DNS Monitoring & DNS Firewalling | Lucas Tscherter | Jawed Zamani | 2021-07-01 | 2021-12-31 | 210000 | 127000 | 337000 | 337000 | 0 | 16796.845 | 0 | 0 | 16796.845 | 0 | 0 | 0 | 0 | 0 | 0 | 16796.845 | 0 | 0 | 16796.845 | 7598.02 | 337000 | 263662.35 | 73337.65 | License costs yet unkown. To be clarified in CW43. Reduced overall measure scope due to late measure start on 01.09.2021
Increase Detection | 10 | M282 | Global Deception rollout | Lucas Tscherter | Jawed Zamani | 2021-07-01 | 2021-12-31 | 1350000 | 270000 | 1620000 | 1620000 | 0 | 21557.5 | 0 | 0 | 21557.5 | 0 | 0 | 0 | 0 | 0 | 0 | 21557.5 | 0 | 0 | 21557.5 | 145722.59 | 1620000 | 1137318.4056 | 482681.5944 | 282/1 Less HW invest as expected, less local costs as expected 282/2 Less HW invest as expected, less local costs as expected
Increase Detection | 11 | M283 | Enhance Cloud response & Secure Allianz critical Apps | Lucas Tscherter | Jawed Zamani | 2021-07-01 | 2021-12-31 | 475000 | 30000 | 505000 | 505000 | 0 | 221663.7262 | 0 | 0 | 221663.7262 | 0 | 0 | 0 | 0 | 0 | 0 | 221663.7262 | 0 | 0 | 221663.7262 | 57003.2 | 505000 | 489861.2852 | 15138.7148
Increase Detection | 12 | M284 | SOAR Rollout and case management implementation | Lucas Tscherter | Jawed Zamani | 2021-07-01 | 2021-12-31 | 610000 | 80000 | 690000 | 690000 | 0 | 270824.8831 | 0 | 0 | 270824.8831 | 0 | 74848.62 | 0 | 0 | 74848.62 | 0 | 345673.5031 | 0 | 0 | 345673.5031 | 244700.21 | 690000 | 689012.965 | 987.035
Increase Detection | 13 | M285 | Increase Effectiveness of Micro Segmentation and Rollout in EU | Clemens Friedrich | Jawed Zamani | 2021-07-01 | 2021-12-31 | 420000 | 0 | 420000 | 420000 | 0 | 153138.2055 | 0 | 0 | 153138.2055 | 0 | 0 | 0 | 0 | 0 | 0 | 153138.2055 | 0 | 0 | 153138.2055 | 63446.56 | 420000 | 419735.9982 | 264.0018
Increase Detection | 14 | M286 | Build Central Dashboard to Increase Transparency and Real Time Monitoring | Clemens Friedrich | Jawed Zamani | 2021-07-01 | 2021-12-31 | 285000 | 0 | 285000 | 285000 | 0 | 7850 | 0 | 0 | 7850 | 0 | 0 | 0 | 0 | 0 | 0 | 7850 | 0 | 0 | 7850 | 7850 | 285000 | 283712.601 | 1287.399
Reduce Damage | 15 | M287 | Extension of vulnerability mgmt. to clients and global policy compliance rollout | Clemens Friedrich | Michael Doberenz | 2021-07-01 | 2021-12-31 | 1150000 | 100000 | 1250000 | 1250000 | 0 | 335706.9126 | 0 | 0 | 335706.9126 | 0 | 0 | 0 | 0 | 0 | 0 | 335706.9126 | 0 | 0 | 335706.9126 | 174179.66 | 1250000 | 1099978.4637 | 150021.5363 | 287/1 Planned budget to cover local OE efforts not needed, further computacenter costs in clarification. 287/2 Planned budget for central FMO changes not needed due to internal GPAM solution.
Reduce Damage | 16 | M288 | AGN Secure Network Access and Segregation | Michael Kahlfuss | Ralph Oelssner | 2021-07-01 | 2021-12-31 | 688000 | 397000 | 1085000 | 1085000 | 0 | 342766.6667 | 0 | 0 | 342766.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 342766.6667 | 0 | 0 | 342766.6667 | 0 | 1084600 | 990950 | 94050 | the spending for Nov / Dec are not final planed, corresponding provider offer are pending => the plan is best guess
Reduce Damage | 17 | M289 | Acceleration of Password Manager service | Rainer Mahlo | Dorit Naveh | 2021-07-01 | 2021-12-31 | 350000 | 0 | 350000 | 350000 | 0 | 204166.6667 | 0 | 0 | 204166.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 204166.6667 | 0 | 0 | 204166.6667 | 0 | 350000 | 350000 | 0
Reduce Damage | 18 | M290 | Re-Design Of Cloud Application Discovery Service | Clemens Friedrich | Michael Lewandowski | 2021-07-01 | 2021-09-30 | 410000 | 20000 | 430000 | 430000 | 0 | 32647.4087 | 0 | 0 | 32647.4087 | 0 | 0 | 0 | 0 | 0 | 0 | 32647.4087 | 0 | 0 | 32647.4087 | 0 | 430000 | 419871.0999 | 10128.9001
Reduce Damage | 19 | M291 | Privileged Access Management for Cloud | Alexander Heinze | Robert Klawes | 2021-07-01 | 2021-12-31 | 200000 | 0 | 200000 | 200000 | 0 | 35432.54 | 0 | 0 | 35432.54 | 0 | 0 | 0 | 0 | 0 | 0 | 35432.54 | 0 | 0 | 35432.54 | 11131.64 | 200000 | 197724.7756 | 2275.2244
Reduce Damage | 20 | M301 | Global Tier 0 Hosting Platform Preparation & APAC Pilot | Alexander Heinze | Michael Lewandowski | 2021-08-15 | 2021-12-31 | 750000 | 250000 | 1000000 | 1000000 | 0 | 2114.4735 | 0 | 0 | 2114.4735 | 0 | 0 | 0 | 0 | 0 | 0 | 2114.4735 | 0 | 0 | 2114.4735 | 0 | 1000000 | 998037.9513 | 1962.0487
Streamline Compliance | 21 | M292 | Double Key Encryption / Extended Security & Compliance for M365 | Julian Bönigk | Dorit Naveh | 2021-07-01 | 2021-12-31 | 690000 | 60000 | 750000 | 750000 | 0 | 444921.049 | 0 | 0 | 444921.049 | 0 | 0 | 0 | 0 | 0 | 0 | 444921.049 | 0 | 0 | 444921.049 | 381299.85 | 750000 | 750000 | 0
Streamline Compliance | 22 | M293 | Automated Toxic Tracking for Client-based Assets | Benjamin Warnholz | Gerrit Rothmaier | 2021-07-01 | 2021-12-31 | 300000 | 60000 | 360000 | 360000 | 0 | 125589.2982 | 0 | 0 | 125589.2982 | 0 | 0 | 0 | 0 | 0 | 0 | 125589.2982 | 0 | 0 | 125589.2982 | 76131.57 | 360025 | 345037.6316 | 14962.3684
Streamline Compliance | 23 | M294 | Integrated Information Risk Management early Live​ | Michael Habel | Christian Schweda | 2021-07-01 | 2021-12-31 | 650000 | 0 | 650000 | 650000 | 209831.25 | 0 | 0 | 1755 | 211586.25 | 0 | 0 | 0 | 0 | 0 | 209831.25 | 0 | 0 | 1755 | 211586.25 | 193103.13 | 651755 | 651598.125 | -1598.125
Streamline Compliance | 24 | M295 | Global Security Platform GITSO blueprint | George Dietrichsbruckner | Michael Doberenz | 2021-07-01 | 2021-12-31 | 298000 | 2000 | 300000 | 300000 | 95706.25 | 0 | 0 | 1755 | 97461.25 | 0 | 0 | 0 | 0 | 0 | 95706.25 | 0 | 0 | 1755 | 97461.25 | 84196.88 | 299755 | 298000 | 2000
Build Security Organization / Skills | 25 | M296 | Financial Loss Quantification | Thomas Thuspass | Michael Lewandowski | 2021-07-01 | 2021-12-31 | 400000 | 0 | 400000 | 400000 | 61425 | 297500 | 0 | 1755 | 360680 | 0 | 0 | 0 | 0 | 0 | 61425 | 297500 | 0 | 1755 | 360680 | 348884.38 | 404080 | 399155.375 | 844.625
Build Security Organization / Skills | 26 | M297 | Measure and Enhance Global Phishing Resilience | Clemens Friedrich | Daria Catalui | 2021-07-01 | 2021-12-31 | 720000 | 275000 | 995000 | 995000 | 0 | 157766.1581 | 0 | 0 | 157766.1581 | 0 | 32401.999 | 0 | 0 | 32401.999 | 0 | 190168.1572 | 0 | 0 | 190168.1572 | 42859 | 995000 | 825427.2811 | 169572.7189 | Currently, only 120k out of 240k planned Zerofox SW ordered (only 6 month instead 1 year, 2022 negotiation ongoing)
Build Security Organization / Skills | 27 | M298 | Strategic THREAT Intelligence and Resulting risk Identification Program | Thomas Wolf | Ralf Schneider | 2021-07-01 | 2021-12-31 | 480000 | 0 | 480000 | 480000 | 0 | 0 | 0 | 238058.75 | 238058.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 238058.75 | 238058.75 | 121975 | 457465 | 457464.5 | 22535.5
Build Security Organization / Skills | 28 | M299 | Enforcement of Security Architecture | Jan General | Cenk Tasdan | 2021-07-01 | 2021-12-31 | 430000 | 0 | 430000 | 430000 | 6500 | 0 | 0 | 180047.8387 | 186547.8387 | 0 | 0 | 0 | 0 | 0 | 6500 | 0 | 0 | 180047.8387 | 186547.8387 | 24716.3175 | 432119.36 | 430262.0781 | -262.0781
Build Security Organization / Skills | 22 | M300 | Metrics phase @We protect scale up on skills | Samuel Hurst | Daria Catalui | 2021-07-01 | 2021-12-31 | 390000 | 150000 | 540000 | 540000 | 145990.625 | 0 | 0 | 1755 | 147745.625 | 0 | 0 | 0 | 23000 | 23000 | 145990.625 | 0 | 0 | 24755 | 170745.625 | 124106.26 | 426255 | 540000 | 0
| 23 | M251 | IT Security Initiative Hub | Ralf Schneider |  | 2021-01-01 | 2021-06-30 | 210000 | 260000 | 470000 | 470000 | 155742.25 | 0 | 0 | 1755 | 157497.25 | 0 | 0 | 0 | 114724.2 | 114724.2 | 155742.25 | 0 | 0 | 116479.2 | 272221.45 | 182365.32 | 457968 | 470000 | 0
Total | [7 empty] | 17862720 | 2425000 | 20287720 | 20287720 | 858956 | 3380751.9736 | 0 | 1149030.9988 | 5388738.9723 | 0 | 107250.619 | 0 | 137724.2 | 244974.819 | 858956 | 3488002.5926 | 0 | 1286755.1987 | 5633713.7914 | 3288540.8775 | 18697005.49 | 18461198.8862 | 1826521.1138
Overarching Topics | [28 empty] | 2799.59 | -2799.59
Autobahn | [28 empty] | 846000 | -846000 | Autobahn / Gerhard Schneider
Killswitch/ Illumio | [28 empty] | 476000 | -476000 | Feser und Seitz sind die Nutzer
Andrea Support | [28 empty] | 500000 | -500000
other | [28 empty] | 0 | 0
Total | [7 empty] | 30328720 | 4670000 | 34998720 | 0 | 1534151.375 | 6051194.3069 | 0 | 1708002.5875 | 9293348.2694 | 0 | 214501.2381 | 0 | 275448.4 | 489949.6381 | 1534151.375 | 6265695.545 | 0 | 1983450.9875 | 0 | 0 | 0 | 1824799.59 | -1824799.59
Grant Total | [7 empty] | 29578720 | 4609000 | 34187720 | 20287720 | 1534151.375 | 6051194.3069 | 0 | 1708002.5875 | 9293348.2694 | 0 | 214501.2381 | 0 | 275448.4 | 489949.6381 | 1534151.375 | 6265695.545 | 0 | 1983450.9875 | 5633713.7914 | 3288540.8775 | 18697005.49 | 20285998.4762 | 1721.5238
Budget Overview 2021 (mn€)
[28 empty] | Total Budget 2021 |  | 41.4
[28 empty] | Spent 2021-H1 |  | 15.7
[28 empty] | Forecast 2021-H2 |  | 18.4612
[28 empty] | Remaining Budget |  | 7.2388
[28 empty] | New Topics |  | 1.8248
[28 empty] | Remaining Budget after new Topics |  | 5.414
Other Ideas
[28 empty] | Bitsight |  | 0.595 | Carsten
[28 empty] | Proxy für AMC |  | 0.6 | AZ Tech
[28 empty] | Attivo (AD Effectivenss Testing) |  | 1.2 | Nutzer ist GIT (Prüfen AZ Tech / Huber)
[28 empty] | Zero Fox |  | 1 | Daria / ISO Community
[28 empty] | Sum |  | 3.395

## 2. Detailed view
2. Detailed View (2021-10-15)
| Cost Type | Metafinanz | AZ Technology | DCSO | Third Party | Total
| Spent Labor | 858956 | 3380751.9736 | 132090 | 1016940.9988 | 5388738.9723
| Spent non-Labor | 0 | 0 | 0 | 0 | 0
| Sum | 0 | 0 | 0 | 1016940.9988 | 5388738.9723
| Average Daily Rate |  | 1250
[11 empty] | July |  | August |  | September |  | October |  | November |  | December |  | Total
| # | Measure | Cost type | Resource | Provider | Contract | Start | End | T&M/Fix | Daily Rate | PD1 | EUR1 | PD2 | EUR2 | PD3 | EUR3 | PD4 | EUR4 | PD5 | EUR5 | PD6 | EUR6 | PD Total | EUR Total
Ops | 1 | M277 | Labor | Sergej Reißig | AZ Technology | CNTR0010544 | 2021-07-01 | 2021-12-31 | T&M | 1513.8962 | 0 | 0 | 0 | 0 | 55.0018 | 83266.9815 | 0 | 0 |  |  |  |  | 55.0018 | 83266.9815
| 2 | M277 | Labor | Wolfgang Elsner | AZ Technology | CNTR0010544 | 2021-07-01 | 2021-12-31 | T&M | 1570 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
| 3 | M277 | Labor | Binoj Baburaj | AZ Technology | CNTR0010544 | 2021-07-01 | 2021-12-31 | T&M | 1130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
| 4 | M277 | Labor | Alexander Heinze | AZ Technology | CNTR0010544 | 2021-07-01 | 2021-12-31 | T&M | 1570 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
| 5 | M277 | Labor | Nina Kaufmann | AZ Technology | CNTR0010544 | 2021-07-01 | 2021-12-31 | T&M | 1310.38 | 0 | 0 | 0 | 0 | 20.9999 | 27517.875 | 0 | 0 |  |  |  |  | 20.9999 | 27517.875
| 6 | M277 | Labor | IAM Architect (Cygna) | AZ Technology | CNTR0010544 | 2021-07-01 | 2021-12-31 | T&M | 1310.38 | 0 | 0 | 0 | 0 | 2.4114 | 3159.8592 | 0 | 0 |  |  |  |  | 2.4114 | 3159.8592
| 7 | M277 | Labor | Youssef Dahmouni | AZ Technology | CNTR0010544 | 2021-07-01 | 2021-12-31 | T&M | 1310.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
| 8 | M277 | Labor | Viktoryia Nikifaravets | AZ Technology | CNTR0010544 | 2021-07-01 | 2021-12-31 | T&M | 1346.4013 | 0 | 0 | 0 | 0 | 32.0516 | 43154.3461 | 0 | 0 |  |  |  |  | 32.0516 | 43154.3461
| 9 | M277 | Labor | Jagoda Matys | AZ Technology | CNTR0010544 | 2021-07-01 | 2021-12-31 | T&M | 1130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
| 10 | M277 | Labor | NN india | AZ Technology | CNTR0010544 | 2021-07-01 | 2021-12-31 | T&M | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
| 11 | M277 | Labor | Andrea Scotti | AZ Technology | CNTR0010544 | 2021-07-01 | 2021-12-31 | T&M | 1570 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
| 12 | M277 | Labor | Michael Holder | AZ Technology | CNTR0010544 | 2021-07-01 | 2021-12-31 | T&M | 1570 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
| 13 | M277 | Labor | Markus Schnier | AZ Technology | CNTR0010544 | 2021-07-01 | 2021-12-31 | T&M | 2030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
| 14 | M277 | Labor | Thomas Huber | AZ Technology | CNTR0010544 | 2021-07-01 | 2021-12-31 | T&M | 2030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
| 15 | M278 | Labor | Itai Schwartz | AZ Technology | CNTR0010615 | 2021-07-01 | 2021-12-31 | T&M | 1346.4013 | 0 | 0 | 0 | 0 | 31.2506 | 42075.8024 | 0 | 0 |  |  |  |  | 31.2506 | 42075.8024
| 16 | M278 | Labor | Francois Pernayan | AZ Technology | CNTR0010615 | 2021-07-01 | 2021-12-31 | T&M | 1346.4013 | 0 | 0 | 0 | 0 | 31.2506 | 42075.8024 | 0 | 0 |  |  |  |  | 31.2506 | 42075.8024
| 17 | M278 | Labor | Matt Gibson | AZ Technology | CNTR0010615 | 2021-07-01 | 2021-12-31 | T&M | 1570 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
| 18 | M278 | Labor | Jagoda Matys | AZ Technology | CNTR0010615 | 2021-07-01 | 2021-12-31 | T&M | 1130 | [12 empty] | 0 | 0
| 19 | M278 | Labor | Christian Bolterauer | AZ Technology | CNTR0010615 | 2021-07-01 | 2021-12-31 | T&M | 1415.205 | 0 | 0 | 0 | 0 | 4.25 | 6014.6213 | 0 | 0 |  |  |  |  | 4.25 | 6014.6213
| 20 | M278 | Labor | Alexander Heinze | AZ Technology | CNTR0010615 | 2021-07-01 | 2021-12-31 | T&M | 1570 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
| 21 | M278 | Labor | NN india | AZ Technology | CNTR0010615 | 2021-07-01 | 2021-12-31 | T&M | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
| 22 | M279 | Labor | Reza Memarian | AZ Technology | CNTR0010616 | 2021-07-01 | 2021-12-31 | T&M | 1513.8962 | 0 | 0 | 0 | 0 | 55.0018 | 83266.9815 | 0 | 0 |  |  |  |  | 55.0018 | 83266.9815
| 23 | M279 | Labor | Walter Hofer | AZ Technology | CNTR0010616 | 2021-07-01 | 2021-12-31 | T&M | 1130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
| 24 | M279 | Labor | Balasz Razs | AZ Technology | CNTR0010616 | 2021-07-01 | 2021-12-31 | T&M | 1130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
| 25 | M279 | Labor | Youssef Dahmouni | AZ Technology | CNTR0010616 | 2021-07-01 | 2021-12-31 | T&M | 1048.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
| 26 | M279 | Labor | Alexander Heinze | AZ Technology | CNTR0010616 | 2021-07-01 | 2021-12-31 | T&M | 1570 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
| 27 | M279 | Labor | Thomas Huber | AZ Technology | CNTR0010616 | 2021-07-01 | 2021-12-31 | T&M | 2030 | [12 empty] | 0 | 0
| 28 | M279 | Labor | Markus Schnier | AZ Technology | CNTR0010616 | 2021-07-01 | 2021-12-31 | T&M | 2030 | [12 empty] | 0 | 0
| 29 | M279 | Labor | Ivan Markovic | AZ Technology | CNTR0010616 | 2021-07-01 | 2021-12-31 | T&M | 1496.9724 | 0 | 0 | 0 | 0 | 13.16 | 19700.1568 | 0 | 0 |  |  |  |  | 13.16 | 19700.1568
| 30 | M279 | Labor | Product SME | AZ Technology | CNTR0010616 | 2021-07-01 | 2021-12-31 | T&M | 1310.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
| 31 | M279 | non-Labor | Licence costs | AZ Technology | CNTR0010616 | 2021-07-01 | 2021-12-31 | T&M | 100000 | [12 empty] | 0 | 0
| 32 | M279 | Labor | NN india | AZ Technology | CNTR0010616 | 2021-07-01 | 2021-12-31 | T&M | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
| 33 | M291 | Labor | Marc Bochtler | AZ Technology | CNTR0010576 | 2021-07-01 | 2021-12-31 | T&M | 1415.205 | 0 | 0 | 18 | 25473.69 | 0 | 0 | 0 | 0 |  |  |  |  | 18 | 25473.69
| 34 | M291 | Labor | Tobias Butz | AZ Technology | CNTR0010576 | 2021-07-01 | 2021-12-31 | T&M | 1130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
| 35 | M291 | Labor | Yury Nikolin | AZ Technology | CNTR0010576 | 2021-07-01 | 2021-12-31 | T&M | 1048.3 | 0 | 0 | 9.5 | 9958.85 | 0 | 0 | 0 | 0 |  |  |  |  | 9.5 | 9958.85
| 36 | M291 | Labor | Alexander Heinze | AZ Technology | CNTR0010576 | 2021-07-01 | 2021-12-31 | T&M | 1570 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
| 37 | M291 | Labor | Thomas Felder | AZ Technology | CNTR0010576 | 2021-07-01 | 2021-12-31 | T&M | 1570 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
| 38 | M291 | Labor | NN india | AZ Technology | CNTR0010576 | 2021-07-01 | 2021-12-31 | T&M | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
| 39 | M291 | Labor | NN | AZ Technology | CNTR0010576 | 2021-07-01 | 2021-12-31 | T&M | 1048.3 | [12 empty] | 0 | 0
| 40 | M285 | Labor | Tobias Krichel | AZ Technology | CNTR0010334 | 2021-07-01 | 2021-12-31 | T&M | 1185.1032 | 0 | 0 | 0 | 0 | 62.875 | 74513.3568 | 0 | 0 |  |  |  |  | 62.875 | 74513.3568
| 41 | M285 | Labor | Dan Read | AZ Technology | CNTR0010334 | 2021-07-01 | 2021-12-31 | T&M | 1149.9851 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
| 42 | M285 | Labor | N.N. / Support Dan | AZ Technology | CNTR0010334 | 2021-07-01 | 2021-12-31 | T&M | 1048.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
| 43 | M285 | Labor | Martin Schurm | AZ Technology | CNTR0010334 | 2021-07-01 | 2021-12-31 | T&M | 1559.3463 | 0 | 0 | 0 | 0 | 27 | 42102.3487 | 0 | 0 |  |  |  |  | 27 | 42102.3487
| 44 | M285 | Labor | Ankur Tomar | AZ Technology | CNTR0010334 | 2021-07-01 | 2021-12-31 | T&M | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
| 45 | M285 | Labor | Naman Agrawal | AZ Technology | CNTR0010334 | 2021-07-01 | 2021-12-31 | T&M | 250 | 0 | 0 | 8.75 | 2187.5 | 12.5 | 3125 | 0 | 0 |  |  |  |  | 21.25 | 5312.5
| 46 | M285 | Labor | Clemens Friedrich | AZ Technology | CNTR0010334 | 2021-07-01 | 2021-12-31 | T&M | 1570 | 8 | 12560 | 8 | 12560 | 0 | 0 | 0 | 0 |  |  |  |  | 16 | 25120
| 47 | M285 | Labor | Gerhard Schneider | AZ Technology | CNTR0010334 | 2021-07-01 | 2021-12-31 | T&M | 2030 | 0 | 0 | 1 | 2030 | 0 | 0 | 0 | 0 |  |  |  |  | 1 | 2030
| 48 | M285 | Labor | Markus Schnier | AZ Technology | CNTR0010334 | 2021-07-01 | 2021-12-31 | T&M | 2030 | 1 | 2030 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 1 | 2030
| 49 | M285 | Labor | Thomas Huber | AZ Technology | CNTR0010334 | 2021-07-01 | 2021-12-31 | T&M | 2030 | 1 | 2030 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 1 | 2030
| 50 | M286 | Labor | DGI | AZ Technology | CNTR0010562 | 2021-07-01 | 2021-12-31 | T&M | 265712.601 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
| 51 | M286 | Labor | Clemens Friedrich | AZ Technology | CNTR0010562 | 2021-07-01 | 2021-12-31 | T&M | 1570 | 1 | 1570 | 4 | 6280 | 0 | 0 | 0 | 0 |  |  |  |  | 5 | 7850
| 52 | M286 | Labor | Gerhard Schneider | AZ Technology | CNTR0010562 | 2021-07-01 | 2021-12-31 | T&M | 2030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
| 53 | M286 | Labor | Markus Schnier | AZ Technology | CNTR0010562 | 2021-07-01 | 2021-12-31 | T&M | 2030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
| 54 | M286 | Labor | Thomas Huber | AZ Technology | CNTR0010562 | 2021-07-01 | 2021-12-31 | T&M | 2030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
| 55 | M287 | Labor | Daniela Betz | AZ Technology | CNTR0010336 | 2021-07-01 | 2021-12-31 | T&M | 1415.205 | 22.375 | 31665.2119 | 23.5625 | 33345.7731 | 0 | 0 | 0 | 0 |  |  |  |  | 45.9375 | 65010.9849
| 56 | M287 | Labor | Bastian Kastner | AZ Technology | CNTR0010336 | 2021-07-01 | 2021-12-31 | T&M | 1048.3 | 25.25 | 26469.575 | 20 | 20966 | 0 | 0 | 0 | 0 |  |  |  |  | 45.25 | 47435.575
| 57 | M287 | Labor | Markus Gatter | AZ Technology | CNTR0010335 | 2021-07-01 | 2021-12-31 | T&M | 1153.13 | 0 | 0 | 0 | 0 | 56 | 64575.28 | 0 | 0 |  |  |  |  | 56 | 64575.28
| 58 | M287 | Labor | Jakob Schusser | AZ Technology | CNTR0010335 | 2021-07-01 | 2021-12-31 | T&M | 754.776 | [12 empty] | 0 | 0
| 59 | M287 | Labor | Gabriella Nagy | AZ Technology | CNTR0010335 | 2021-07-01 | 2021-12-31 | T&M | 1048.3 | [12 empty] | 0 | 0
| 60 | M287 | Labor | N.N. // SME 2 | AZ Technology | CNTR0010335 | 2021-07-01 | 2021-12-31 | T&M | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
| 61 | M287 | Labor | N.N. // Sr. Analyst | AZ Technology | CNTR0010335 | 2021-07-01 | 2021-12-31 | T&M | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
| 62 | M287 | Labor | N.N. | AZ Technology | CNTR0010335 | 2021-07-01 | 2021-12-31 | T&M | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
| 63 | M287 | Labor | SR Labs Autobahn | AZ Technology | CNTR0010335 | 2021-07-01 | 2021-12-31 | T&M | 87323.39 | [12 empty] | 0 | 0
| 64 | M287 | Labor | OE Effort | AZ Technology | CNTR0010335 | 2021-07-01 | 2021-12-31 | T&M | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
| 65 | M287 | Labor | Ben Brüggen | AZ Technology | CNTR0010335 | 2021-07-01 | 2021-12-31 | T&M | 1185.1032 | [12 empty] | 0 | 0
| 66 | M287 | Labor | Björn Hansen / Markus Feuerstein | AZ Technology | CNTR0010336 | 2021-07-01 | 2021-12-31 | T&M | 1425.8662 | 0 | 0 | 0 | 0 | 0 | 85551.9727 | 0 | 0 |  |  |  |  | 0 | 85551.9727
| 67 | M287 | Labor | Clemens Friedrich | AZ Technology | CNTR0010336 | 2021-07-01 | 2021-12-31 | T&M | 1570 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
| 68 | M287 | Labor | Gerhard Schneider | AZ Technology | CNTR0010336 | 2021-07-01 | 2021-12-31 | T&M | 2030 | 0 | 0 | 1 | 2030 | 2.77 | 5623.1 | 0 | 0 |  |  |  |  | 3.77 | 7653.1
| 69 | M287 | Labor | Markus Schnier | AZ Technology | CNTR0010336 | 2021-07-01 | 2021-12-31 | T&M | 2030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
| 70 | M287 | Labor | Thomas Huber | AZ Technology | CNTR0010336 | 2021-07-01 | 2021-12-31 | T&M | 2030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
| 71 | M287 | Labor | Rudresh Subramanian | AZ Technology | CNTR0010336 | 2021-07-01 | 2021-12-31 | T&M | 1500 | 0 | 0 | 0 | 0 | 20.22 | 30330 | 0 | 0 |  |  |  |  | 20.22 | 30330
| 72 | M287 | Labor | Guelsah Uestelci | AZ Technology | CNTR0010336 | 2021-07-01 | 2021-12-31 | T&M | 950 | 0 | 0 | 2 | 1900 | 25 | 23750 | 10 | 9500 |  |  |  |  | 37 | 35150
| 73 | M297 | Labor | Anna Hartl | AZ Technology | CNTR0010338 | 2021-07-01 | 2021-12-31 | T&M | 1048.3 | 0 | 0 | 0 | 0 | 53.8125 | 56411.6437 | 0 | 0 |  |  |  |  | 53.8125 | 56411.6437
| 74 | M297 | Labor | Alina Lobova | AZ Technology | CNTR0010338 | 2021-07-01 | 2021-12-31 | T&M | 838.64 | 0 | 0 | 0 | 0 | 55.75 | 46754.18 | 0 | 0 |  |  |  |  | 55.75 | 46754.18
| 75 | M297 | Labor | Stefan Kösters | AZ Technology | CNTR0010338 | 2021-07-01 | 2021-12-31 | T&M | 1048.3 | 0 | 0 | 0 | 0 | 12.2812 | 12874.4344 | 0 | 0 |  |  |  |  | 12.2812 | 12874.4344
| 76 | M297 | Labor | Kühnlenz / 2wmedia | AZ Technology | CNTR0010338 | 2021-07-01 | 2021-12-31 | T&M | 175682.1859 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
| 77 | M297 | Labor | Natalia Nikitana | AZ Technology | CNTR0010338 | 2021-07-01 | 2021-12-31 | T&M | 960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
| 78 | M297 | Labor | Rene Pferner | AZ Technology | CNTR0010338 | 2021-07-01 | 2021-12-31 | T&M | 1900 | [12 empty] | 0 | 0
| 79 | M297 | Labor | N.N. | AZ Technology | CNTR0010338 | 2021-07-01 | 2021-12-31 | T&M | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
| 80 | M297 | non-Labor | Splunk Licenses + Server | AZ Technology | CNTR0010338 | 2021-07-01 | 2021-12-31 | T&M | 17850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
| 81 | M297 | non-Labor | ZeroFox Licenses | AZ Technology | CNTR0010338 | 2021-07-01 | 2021-12-31 | T&M | 124747.7 | 0 | 0 | 0 | 0 | 0 | 32401.999 | 0 | 0 |  |  |  |  | 0 | 32401.999
| 82 | M297 | Labor | IT Seal | AZ Technology | CNTR0010338 | 2021-07-01 | 2021-12-31 | T&M | 21955.5952 | [12 empty] | 0 | 0
| 83 | M297 | Labor | Aishwarya Nangude / Sarabjit Singh | AZ Technology | CNTR0010338 | 2021-07-01 | 2021-12-31 | T&M | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
| 84 | M297 | Labor | Meera Patel | AZ Technology | CNTR0010338 | 2021-07-01 | 2021-12-31 | T&M | 250 | 0 | 0 | 0 | 0 | 3.75 | 937.5 | 3.75 | 937.5 |  |  |  |  | 7.5 | 1875
| 85 | M297 | Labor | Gerhard Schneider | AZ Technology | CNTR0010338 | 2021-07-01 | 2021-12-31 | T&M | 2030 | 0 | 0 | 2.32 | 4709.6 | 2.51 | 5095.3 | 1.2 | 2436 |  |  |  |  | 6.03 | 12240.9
| 86 | M297 | Labor | Markus Schnier | AZ Technology | CNTR0010338 | 2021-07-01 | 2021-12-31 | T&M | 2030 | 1 | 2030 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 1 | 2030
| 87 | M297 | Labor | Thomas Huber | AZ Technology | CNTR0010338 | 2021-07-01 | 2021-12-31 | T&M | 2030 | 1 | 2030 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 1 | 2030
| 88 | M297 | Labor | Clemens Friedrich | AZ Technology | CNTR0010338 | 2021-07-01 | 2021-12-31 | T&M | 1570 | 7 | 10990 | 8 | 12560 | 0 | 0 | 0 | 0 |  |  |  |  | 15 | 23550
| 89 | M276 | Labor | Sven Lierzer | AZ Technology | CNTR0010333 | 2021-07-01 | 2021-12-31 | T&M | 1185.1032 | 0 | 0 | 0 | 0 | 48.875 | 57921.9165 | 0 | 0 |  |  |  |  | 48.875 | 57921.9165
| 90 | M276 | Labor | Tobias Lichtenberg | AZ Technology | CNTR0010333 | 2021-07-01 | 2021-12-31 | T&M | 1415.205 | 0 | 0 | 0 | 0 | 12.6875 | 17955.4134 | 0 | 0 |  |  |  |  | 12.6875 | 17955.4134
| 91 | M276 | Labor | Christoph Lenz | AZ Technology | CNTR0010333 | 2021-07-01 | 2021-12-31 | T&M | 1048.3 | 0 | 0 | 0 | 0 | 31.625 | 33152.4875 | 0 | 0 |  |  |  |  | 31.625 | 33152.4875
| 92 | M276 | Labor | Stanislav Khotinok | AZ Technology | CNTR0010333 | 2021-07-01 | 2021-12-31 | T&M | 1153.13 | 0 | 0 | 0 | 0 | 34.125 | 39350.5613 | 0 | 0 |  |  |  |  | 34.125 | 39350.5613
| 93 | M276 | Labor | Alexander Leonhardt | AZ Technology | CNTR0010333 | 2021-07-01 | 2021-12-31 | T&M | 1153.13 | 0 | 0 | 0 | 0 | 56.75 | 65440.1275 | 0 | 0 |  |  |  |  | 56.75 | 65440.1275
| 94 | M276 | Labor | Yuri Nikulin | AZ Technology | CNTR0010333 | 2021-07-01 | 2021-12-31 | T&M | 1153.13 | 0 | 0 | 0 | 0 | 23.375 | 26954.4138 | 0 | 0 |  |  |  |  | 23.375 | 26954.4138
| 95 | M276 | Labor | Maria Thanner | AZ Technology | CNTR0010333 | 2021-07-01 | 2021-12-31 | T&M | 838.64 | 0 | 0 | 0 | 0 | 18.75 | 15724.5 | 0 | 0 |  |  |  |  | 18.75 | 15724.5
| 96 | M276 | Labor | Corinna Koch | AZ Technology | CNTR0010333 | 2021-07-01 | 2021-12-31 | T&M | 1048.3 | 0 | 0 | 0 | 0 | 19.375 | 20310.8125 | 0 | 0 |  |  |  |  | 19.375 | 20310.8125
| 97 | M276 | Labor | SNOW-Team | AZ Technology | CNTR0010333 | 2021-07-01 | 2021-12-31 | T&M | 601.8814 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
| 98 | M276 | Labor | Splunk Team | AZ Technology | CNTR0010333 | 2021-07-01 | 2021-12-31 | T&M | 365 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
| 99 | M276 | Labor | Vasanthan Dhanasingh | AZ Technology | CNTR0010333 | 2021-07-01 | 2021-12-31 | T&M | 365 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
| 100 | M276 | Labor | Deepak Krishnan | AZ Technology | CNTR0010333 | 2021-07-01 | 2021-12-31 | T&M | 365 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
| 101 | M276 | Labor | K Harikrishnan | AZ Technology | CNTR0010333 | 2021-07-01 | 2021-12-31 | T&M | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
| 102 | M276 | Labor | Ankita Mane | AZ Technology | CNTR0010333 | 2021-07-01 | 2021-12-31 | T&M | 170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
| 103 | M276 | non-Labor | Splunk Licenses + Server | AZ Technology | CNTR0010333 | 2021-07-01 | 2021-12-31 | T&M | 17850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
| 104 | M276 | Labor | Martin Gerlowski | AZ Technology | CNTR0010333 | 2021-07-01 | 2021-12-31 | T&M | 1030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
| 105 | M276 | Labor | Gerhard Schneider | AZ Technology | CNTR0010333 | 2021-07-01 | 2021-12-31 | T&M | 2030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
| 106 | M276 | Labor | Markus Schnier | AZ Technology | CNTR0010333 | 2021-07-01 | 2021-12-31 | T&M | 2030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
| 107 | M276 | Labor | Thomas Huber | AZ Technology | CNTR0010333 | 2021-07-01 | 2021-12-31 | T&M | 2030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
| 108 | M276 | Labor | Clemens Friedrich | AZ Technology | CNTR0010333 | 2021-07-01 | 2021-12-31 | T&M | 1570 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
| 109 | M290 | Labor | Ernst & Young | AZ Technology | CNTR0010337 | 2021-07-01 | 2021-12-31 | T&M | 1695.1277 | 0 | 0 | 0 | 0 | 19.2596 | 32647.4087 | 0 | 0 |  |  |  |  | 19.2596 | 32647.4087
| 110 | M290 | Labor | Computacenter | AZ Technology | CNTR0010337 | 2021-07-01 | 2021-12-31 | T&M | 1390.9369 | [12 empty] | 0 | 0
| 111 | M290 | Labor | Matthias Kickstein | AZ Technology | CNTR0010337 | 2021-07-01 | 2021-12-31 | T&M | 1130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
| 112 | M282 | Labor | Dhanya Kalathil | AZ Technology | CNTR0010325 | 2021-07-01 | 2021-12-31 | T&M | 250 | 6.625 | 1656.25 | 6 | 1500 | 7.125 | 1781.25 | 0 | 0 |  |  |  |  | 19.75 | 4937.5
| 113 | M282 | Labor | Arunlal Nair | AZ Technology | CNTR0010325 | 2021-07-01 | 2021-12-31 | T&M | 250 | [12 empty] | 0 | 0
| 114 | M282 | Labor | Mark de Vera | AZ Technology | CNTR0010325 | 2021-07-01 | 2021-12-31 | T&M | 670 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
| 115 | M282 | Labor | Armando Diaz | AZ Technology | CNTR0010327 | 2021-07-01 | 2021-12-31 | T&M | 1130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
| 116 | M282 | Labor | Alex Lee | AZ Technology | CNTR0010325 | 2021-07-01 | 2021-12-31 | T&M | 1100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
| 117 | M282 | Labor | Local Infra setup support | AZ Technology | CNTR0010325 | 2021-07-01 | 2021-12-31 | T&M | 100000 | [12 empty] | 0 | 0
| 118 | M282 | Labor | Local SMEs for AVC, FMO | AZ Technology | CNTR0010325 | 2021-07-01 | 2021-12-31 | T&M | 140000 | [12 empty] | 0 | 0
| 119 | M282 | non-Labor | HW / infrastructure | AZ Technology | CNTR0010325 | 2021-07-01 | 2021-12-31 | T&M | 110000 | [12 empty] | 0 | 0
| 120 | M282 | Labor | AZ Tech America Labor | AZ Technology | CNTR0010327 | 2021-07-01 | 2021-12-31 | T&M | 47410 | [12 empty] | 0 | 0
| 121 | M282 | non-Labor | AZ Tech America HW | AZ Technology | CNTR0010327 | 2021-07-01 | 2021-12-31 | T&M | 82637 | [12 empty] | 0 | 0
| 122 | M282 | non-Labor | Local SMEs for AVC, FMO | AZ Technology | CNTR0010327 | 2021-07-01 | 2021-12-31 | T&M | 220000 | [12 empty] | 0 | 0
| 123 | M282 | Labor | Ron Johnson | AZ Technology | CNTR0010327 | 2021-07-01 | 2021-12-31 | T&M | 1130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
| 124 | M282 | Labor | Balasz Racz | AZ Technology | CNTR0010325 | 2021-07-01 | 2021-12-31 | T&M | 1130 | 0 | 0 | 10 | 11300 | 0 | 0 | 0 | 0 |  |  |  |  | 10 | 11300
| 125 | M282 | Labor | Lucas Tscherter | AZ Technology | CNTR0010325 | 2021-07-01 | 2021-12-31 | T&M | 1570 | [12 empty] | 0 | 0
| 126 | M282 | Labor | Cabling APAC | AZ Technology | CNTR0010325 | 2021-07-01 | 2021-12-31 | T&M | 1942.4056 | [12 empty] | 0 | 0
| 127 | M282 | Labor | Lucas Tscherter | AZ Technology | CNTR0010327 | 2021-07-01 | 2021-12-31 | T&M | 1570 | [12 empty] | 0 | 0
| 128 | M282 | Labor | Service Manager | AZ Technology | CNTR0010327 | 2021-07-01 | 2021-12-31 | T&M | 670 | [12 empty] | 0 | 0
| 129 | M282 | Labor | Jithin Varghese | AZ Technology | CNTR0010327 | 2021-07-01 | 2021-12-31 | T&M | 170 | 0 | 0 | 0 | 0 | 18 | 3060 | 0 | 0 |  |  |  |  | 18 | 3060
| 130 | M282 | Labor | Patrick Zeitz | AZ Technology | CNTR0010327 | 2021-07-01 | 2021-12-31 | T&M | 1130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
| 131 | M282 | Labor | Thomas Bringewald | AZ Technology | CNTR0010327 | 2021-07-01 | 2021-12-31 | T&M | 1130 | 0 | 0 | 0 | 0 | 2 | 2260 | 0 | 0 |  |  |  |  | 2 | 2260
| 132 | M282 | Labor | Thomas Huber | AZ Technology | CNTR0010327 | 2021-07-01 | 2021-12-31 | T&M | 2030 | [12 empty] | 0 | 0
| 133 | M282 | Labor | Markus Schnier | AZ Technology | CNTR0010327 | 2021-07-01 | 2021-12-31 | T&M | 2030 | [12 empty] | 0 | 0
| 134 | M282 | Labor | Andrei Maslov | AZ Technology | CNTR0010327 | 2021-07-01 | 2021-12-31 | T&M | 1130 | [12 empty] | 0 | 0
| 135 | M282 | Labor | Gereon Volker | AZ Technology | CNTR0010327 | 2021-07-01 | 2021-12-31 | T&M | 1130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
| 136 | M284 | Labor | Markus Schnier | AZ Technology | CNTR0010332 | 2021-07-01 | 2021-12-31 | T&M | 2030 | 1 | 2030 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 1 | 2030
| 137 | M284 | Labor | Thomas Huber | AZ Technology | CNTR0010332 | 2021-07-01 | 2021-12-31 | T&M | 2030 | 1 | 2030 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 1 | 2030
| 138 | M284 | Labor | Lucas Tscherter | AZ Technology | CNTR0010332 | 2021-07-01 | 2021-12-31 | T&M | 1570 | 0 | 0 | 0 | 0 | 20.42 | 32059.4 | 0 | 0 |  |  |  |  | 20.42 | 32059.4
| 139 | M284 | Labor | Timothy Drost | AZ Technology | CNTR0010332 | 2021-07-01 | 2021-12-31 | T&M | 1415.205 | 18 | 9021.9319 | 15 | 21228.075 | 18.25 | 25827.4912 | 0 | 0 |  |  |  |  | 51.25 | 56077.4981
| 140 | M284 | Labor | Andrei Maslov | AZ Technology | CNTR0010332 | 2021-07-01 | 2021-12-31 | T&M | 1130 | 0 | 0 | 0 | 0 | 5 | 5650 | 0 | 0 |  |  |  |  | 5 | 5650
| 141 | M284 | Labor | Holger Steinlechner | AZ Technology | CNTR0010332 | 2021-07-01 | 2021-12-31 | T&M | 1130 | 0 | 0 | 0 | 0 | 1.78 | 2011.4 | 0 | 0 |  |  |  |  | 1.78 | 2011.4
| 142 | M284 | Labor | Rebecca Dengl | AZ Technology | CNTR0010332 | 2021-07-01 | 2021-12-31 | T&M | 1130 | 0 | 0 | 0 | 0 | 0.263 | 297.19 | 0 | 0 |  |  |  |  | 0.263 | 297.19
| 143 | M284 | Labor | Racz Balazs | AZ Technology | CNTR0010332 | 2021-07-01 | 2021-12-31 | T&M | 1130 | 0 | 0 | 2 | 2260 | 0 | 0 | 0 | 0 |  |  |  |  | 2 | 2260
| 144 | M284 | Labor | Jimmy Braun | AZ Technology | CNTR0010332 | 2021-07-01 | 2021-12-31 | T&M | 1048.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
| 145 | M284 | Labor | Olivier Ma | AZ Technology | CNTR0010332 | 2021-07-01 | 2021-12-31 | T&M | 1130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
| 146 | M284 | Labor | CMDB | AZ Technology | CNTR0010332 | 2021-07-01 | 2021-12-31 | T&M | 20000 | [12 empty] | 0 | 0
| 147 | M284 | Labor | Cyarx Siemplify | AZ Technology | CNTR0010332 | 2021-07-01 | 2021-12-31 | T&M | 1772.7305 |  |  |  |  | 95 | 168409.395 | [6 empty] | 95 | 168409.395
| 148 | M284 | non-Labor | Cyarx Siemplify | AZ Technology | CNTR0010332 | 2021-07-01 | 2021-12-31 | T&M | 74848.62 |  |  |  |  | 1 | 74848.62 | [6 empty] | 1 | 74848.62
| 149 | M283 | non-Labor | AWS / Azure cloud | AZ Technology | CNTR0010329 | 2021-07-01 | 2021-12-31 | T&M | 40000 | [12 empty] | 0 | 0
| 150 | M283 | Labor | Markus Schnier | AZ Technology | CNTR0010329 | 2021-07-01 | 2021-12-31 | T&M | 2030 | 1 | 2030 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 1 | 2030
| 151 | M283 | Labor | Thomas Huber | AZ Technology | CNTR0010329 | 2021-07-01 | 2021-12-31 | T&M | 2030 | 1 | 2030 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 1 | 2030
| 152 | M283 | Labor | Lucas Tscherter | AZ Technology | CNTR0010329 | 2021-07-01 | 2021-12-31 | T&M | 1570 | 20 | 31400 | 0 | 0 | 7.79 | 12230.3 | 0 | 0 |  |  |  |  | 27.79 | 43630.3
| 153 | M283 | Labor | Gereon Volker | AZ Technology | CNTR0010329 | 2021-07-01 | 2021-12-31 | T&M | 1130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
| 154 | M283 | Labor | Thomas Bringewald | AZ Technology | CNTR0010329 | 2021-07-01 | 2021-12-31 | T&M | 1130 | 0 | 0 | 5 | 5650 | 0 | 0 | 0 | 0 |  |  |  |  | 5 | 5650
| 155 | M283 | Labor | Rebecca Dengl | AZ Technology | CNTR0010329 | 2021-07-01 | 2021-12-31 | T&M | 1130 | 0 | 0 | 0 | 0 | 0.526 | 594.38 | 0 | 0 |  |  |  |  | 0.526 | 594.38
| 156 | M283 | Labor | Felix Hertin | AZ Technology | CNTR0010329 | 2021-07-01 | 2021-12-31 | T&M | 1627.9575 | 0 | 0 | 1.1665 | 1831.4522 | 2.095 | 3410.5709 | 0 | 0 |  |  |  |  | 3.2615 | 5242.0231
| 157 | M283 | Labor | Lukas Thiele | AZ Technology | CNTR0010329 | 2021-07-01 | 2021-12-31 | T&M | 1627.9575 | 0 | 0 | 7.3258 | 1831.4522 | 2.095 | 3410.5709 | 0 | 0 |  |  |  |  | 9.4208 | 5242.0231
| 158 | M283 | Labor | Holger Wache | AZ Technology | CNTR0010329 | 2021-07-01 | 2021-12-31 | T&M | 3144.9 | 0 | 0 | 0 | 0 | 25 | 78622.5 | 0 | 0 |  |  |  |  | 25 | 78622.5
| 159 | M283 | Labor | Tobias Martin | AZ Technology | CNTR0010329 | 2021-07-01 | 2021-12-31 | T&M | 3144.9 | 0 | 0 | 0 | 0 | 25 | 78622.5 | 0 | 0 |  |  |  |  | 25 | 78622.5
| 160 | M283 | Labor | Deloitte | AZ Technology | CNTR0010329 | 2021-07-01 | 2021-12-31 | T&M | 1260.2064 | [12 empty] | 0 | 0
| 161 | M281 | Labor | Markus Schnier | AZ Technology | CNTR0010709 | 2021-07-01 | 2021-12-31 | T&M | 2030 | 1 | 2030 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 1 | 2030
| 162 | M281 | Labor | Thomas Huber | AZ Technology | CNTR0010709 | 2021-07-01 | 2021-12-31 | T&M | 2030 | 1 | 2030 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 1 | 2030
| 163 | M281 | Labor | Lucas Tscherter | AZ Technology | CNTR0010709 | 2021-07-01 | 2021-12-31 | T&M | 1570 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
| 163 | M281 | Labor | Krunoslav Rukavina | AZ Technology | CNTR0010709 | 2021-07-01 | 2021-12-31 | T&M | 1415.205 | 0 | 0 | 0 | 0 | 9 | 12736.845 | 0 | 0 |  |  |  |  | 9 | 12736.845
| 163 | M301 | Labor | Birgit Jarosch | AZ Technology | CNTR0010618 | 2021-07-01 | 2021-12-31 | T&M | 2643.9944 |  |  |  |  | 0.79973 | 2114.4735 | [6 empty] | 0.79973 | 2114.4735
| 163 | M301 | Labor | Mitja Ledowski | AZ Technology | CNTR0010618 | 2021-07-01 | 2021-12-31 | T&M | 1617.9251 | [12 empty] | 0 | 0
| 163 | M301 | Labor | Ingmar Janßen-Holldiek | AZ Technology | CNTR0010618 | 2021-07-01 | 2021-12-31 | T&M | 1617.9251 | [12 empty] | 0 | 0
| 163 | M301 | non-Labor | HW | AZ Technology | CNTR0010618 | 2021-07-01 | 2021-12-31 | T&M | 130000 | [12 empty] | 0 | 0
| 163 | M301 | Labor | Alexander Heinze | AZ Technology | CNTR0010617 | 2021-07-01 | 2021-12-31 | T&M | 1570 | [12 empty] | 0 | 0
| 163 | M301 | Labor | Christine Schlüter | AZ Technology | CNTR0010617 | 2021-07-01 | 2021-12-31 | T&M | 960 | [12 empty] | 0 | 0
| 163 | M301 | Labor | Günter Sanktjohanser | AZ Technology | CNTR0010617 | 2021-07-01 | 2021-12-31 | T&M | 1130 | [12 empty] | 0 | 0
| 163 | M301 | Labor | Jagoda Matys | AZ Technology | CNTR0010618 | 2021-07-01 | 2021-12-31 | T&M | 1130 | [12 empty] | 0 | 0
| 163 | M301 | Labor | Wolfgang Elsner | AZ Technology | CNTR0010618 | 2021-07-01 | 2021-12-31 | T&M | 1570 | [12 empty] | 0 | 0
| 163 | M301 | Labor | Michael Holder | AZ Technology | CNTR0010618 | 2021-07-01 | 2021-12-31 | T&M | 1570 | [12 empty] | 0 | 0
| 163 | M301 | Labor | Sinoop K S | AZ Technology | CNTR0010618 | 2021-07-01 | 2021-12-31 | T&M | 250 | [12 empty] | 0 | 0
| 163 | M301 | Labor | J. Thomas | AZ Technology | CNTR0010618 | 2021-07-01 | 2021-12-31 | T&M | 250 | [12 empty] | 0 | 0
| 163 | M301 | Labor | Alexander Heinze | AZ Technology | CNTR0010618 | 2021-07-01 | 2021-12-31 | T&M | 1570 | [12 empty] | 0 | 0
| 163 | M301 | Labor | N.N. | AZ Technology | CNTR0010618 | 2021-07-01 | 2021-12-31 | T&M | 1130 | [12 empty] | 0 | 0
| 163 | M301 | Labor | Madalina Paslaru | AZ Technology | CNTR0010618 | 2021-07-01 | 2021-12-31 | T&M | 1130 | [12 empty] | 0 | 0
| 163 | M301 | Labor | Daniel Ettenhuber | AZ Technology | CNTR0010618 | 2021-07-01 | 2021-12-31 | T&M | 1130 | [12 empty] | 0 | 0
| 163 | M302 | Labor | Daming Yang | AZ Technology | OAM302 | 2021-07-01 | 2021-12-31 | T&M | 1511.4251 | [12 empty] | 0 | 0
| 163 | M302 | Labor | Manoj Selvakumar | AZ Technology | OAM302 | 2021-07-01 | 2021-12-31 | T&M | 1511.4251 | [12 empty] | 0 | 0
| 163 | M302 | Labor | David Barton | AZ Technology | OAM302 | 2021-07-01 | 2021-12-31 | T&M | 1511.4251 | [12 empty] | 0 | 0
| 163 | M302 | Labor | Raja Rajcic | AZ Technology | OAM302 | 2021-07-01 | 2021-12-31 | T&M | 1511.4251 | [12 empty] | 0 | 0
| 163 | M302 | Labor | Lawrence Tengan | AZ Technology | OAM302 | 2021-07-01 | 2021-12-31 | T&M | 1511.4251 | [12 empty] | 0 | 0
| 163 | M302 | Labor | Travis Chun | AZ Technology | OAM302 | 2021-07-01 | 2021-12-31 | T&M | 1511.4251 | [12 empty] | 0 | 0
| 163 | M302 | Labor | Johannes Bross | AZ Technology | OAM302 | 2021-07-01 | 2021-12-31 | T&M | 1511.4251 | [12 empty] | 0 | 0
| 163 | M302 | Labor | Tuan Minh Nguyen | AZ Technology | OAM302 | 2021-07-01 | 2021-12-31 | T&M | 1511.4251 | [12 empty] | 0 | 0
| 163 | M302 | Labor | Tobias Tischler | AZ Technology | OAM302 | 2021-07-01 | 2021-12-31 | T&M | 1048.3 | [12 empty] | 0 | 0
| 163 | M302 | Labor | Djamel Tazerout | AZ Technology | OAM302 | 2021-07-01 | 2021-12-31 | T&M | 1048.3 | [12 empty] | 0 | 0
| 163 | M302 | Labor | Forgerock Licence | AZ Technology | OAM302 | 2021-07-01 | 2021-12-31 | T&M | 117816.094 | [12 empty] | 0 | 0
| 163 | M278 | Labor | Srdan Mavrenski | AZ Technology | CNTR0010615 | 2021-07-01 | 2021-12-31 | T&M | 1513.8962 |  |  |  |  | 55.0018 | 83266.9815 | [6 empty] | 55.0018 | 83266.9815
| 163 | M302 | Labor | Dirk Addicks | AZ Technology | OAM302 | 2021-07-01 | 2021-12-31 | T&M | 1570 | [12 empty] | 0 | 0
| 163 | M302 | Labor | Alexander Heinze | AZ Technology | OAM302 | 2021-07-01 | 2021-12-31 | T&M | 1570 | [12 empty] | 0 | 0
| 163 | M282 | Labor | Corinna Koch | AZ Technology | CNTR0010325 | 2021-07-01 | 2021-12-31 | T&M | 1048.3 | [12 empty] | 0 | 0
| 163 | M281 | Labor | Joachim Steinberger | AZ Technology | CNTR0010709 | 2021-07-01 | 2021-12-31 | T&M | 1153.13 | [12 empty] | 0 | 0
| 163 | M281 | Labor | Elastic | AZ Technology | CNTR0010709 | 2021-07-01 | 2021-12-31 | T&M | 50000 | [12 empty] | 0 | 0
| 163 | M281 | Labor | Proofpoint | AZ Technology | CNTR0010709 | 2021-07-01 | 2021-12-31 | T&M | [13 empty] | 0 | 0
[23 empty] | 0 | 0
| 164 | M288 | Labor | Placeholder | AZ Technology | CNTR0010589 | 2021-07-01 | 2021-12-31 | T&M |  |  | 97933.3333 |  | 97933.3333 |  | 97933.3333 |  | 48966.6667 |  |  |  |  | 0 | 342766.6667
| 165 | M289 | Labor | Placeholder | AZ Technology | CNTR0010976 | 2021-07-01 | 2021-12-31 | T&M |  |  | 58333.3333 |  | 58333.3333 |  | 58333.3333 |  | 29166.6667 |  |  |  |  | 0 | 204166.6667
[14 empty] | 0 | [8 empty] | 0 | 0
| 166 | M292 | Labor | Karim, Hasan | AZ Technology | CNTR0010564 | 2021-07-01 | 2021-12-31 | T&M | 1050 | 15 | 15750 | 17 | 17850 | 17 | 17850 | 8 | 8400 |  |  |  |  | 57 | 59850
| 167 | M292 | Labor | Bojarski, Eduard | AZ Technology | CNTR0010564 | 2021-07-01 | 2021-12-31 | T&M | 1967.07 | 15 | 29506.05 | 17 | 33440.19 | 17 | 33440.19 | 8 | 15736.56 |  |  |  |  | 57 | 112122.99
| 168 | M292 | Labor | Kayali, Ismail | AZ Technology | CNTR0010564 | 2021-07-01 | 2021-12-31 | T&M | 1274.49 | 15 | 19117.35 | 17 | 21666.33 | 17 | 21666.33 | 8 | 10195.92 |  |  |  |  | 57 | 72645.93
| 169 | M292 | Labor | Sora Mustafa (AUG-OCT only) | AZ Technology | CNTR0010564 | 2021-07-01 | 2021-12-31 | T&M | 1190 | 15 | 17850 | 15 | 17850 | 15 | 17850 | 7 | 8330 |  |  |  |  | 52 | 61880
| 170 | M292 | Labor | Stettner, Julia | AZ Technology | CNTR0010564 | 2021-07-01 | 2021-12-31 | T&M | 1416.09 | 15 | 21241.35 | 17 | 24073.53 | 17 | 24073.53 | 8 | 11328.72 |  |  |  |  | 57 | 80717.13
| 171 | M292 | Labor | Tulshidas Thamke, Budhesh | AZ Technology | CNTR0010564 | 2021-07-01 | 2021-12-31 | T&M | 160 | 15 | 2400 | 17 | 2720 | 17 | 2720 | 8 | 1280 |  |  |  |  | 57 | 9120
| 172 | M292 | Labor | Sunderdas, Shilpa | AZ Technology | CNTR0010564 | 2021-07-01 | 2021-12-31 | T&M | 160 | 16 | 2560 | 17 | 2720 | 17 | 2720 | 8 | 1280 |  |  |  |  | 58 | 9280
| 173 | M292 | Labor | Bönigk, Julian | AZ Technology | CNTR0010564 | 2021-07-01 | 2021-12-31 | T&M | 1130 | 2 | 2260 | 2 | 2260 | 4 | 4520 | 2 | 2260 |  |  |  |  | 10 | 11300
| 174 | M292 | Labor | Vidya Baskaran Reddy | AZ Technology | CNTR0010564 | 2021-07-01 | 2021-12-31 | T&M | 170 | 15 | 2550 | 17 | 2890 | 17 | 2890 | 8 | 1360 |  |  |  |  | 57 | 9690
| 175 | M292 | Labor | Markus Traumueller | AZ Technology | CNTR0010564 | 2021-07-01 | 2021-12-31 | T&M | 1130 | 2 | 2260 | 2 | 2260 | 4 | 4520 | 2 | 2260 |  |  |  |  | 10 | 11300
| 176 | M292 | Labor | S, Shibi (partily on IP&G) | AZ Technology | CNTR0010564 | 2021-07-01 | 2021-12-31 | T&M | 170 | 10.2647 | 1744.999 | 10 | 1700 | 14 | 2380 | 7 | 1190 |  |  |  |  | 41.2647 | 7014.999
[23 empty] | 0 | 0
| 177 | M293 | Labor | Günther, Gerhard | AZ Technology | CNTR0010563 | 2021-07-01 | 2021-12-31 | T&M | 1350 | 3 | 4050 | 7 | 9450 | 3.1579 | 4263.1579 | 2 | 2700 |  |  |  |  | 15.1579 | 20463.1579
| 178 | M293 | Labor | Poteat, Jade | AZ Technology | CNTR0010563 | 2021-07-01 | 2021-12-31 | T&M | 1000 | 6.3158 | 6315.7895 | 7.5658 | 7565.7895 | 7.1053 | 7105.2632 | 2 | 2000 |  |  |  |  | 22.9868 | 22986.8421
| 179 | M293 | Labor | Uysal, Ismail (Project Manager) | AZ Technology | CNTR0010563 | 2021-07-01 | 2021-12-31 | T&M | 1000 | 18.6842 | 18684.2105 | 1.9737 | 1973.6842 | 20.9211 | 20921.0526 | 9.5667 | 9566.6667 |  |  |  |  | 51.1456 | 51145.614
| 180 | M293 | Labor | Goldschmidt, Andreas (SNOW Principal Architect) | AZ Technology | CNTR0010563 | 2021-07-01 | 2021-12-31 | T&M | 1350 |  | 0 | 4.4737 | 6039.4737 | 4.2105 | 5684.2105 | 2 | 2700 |  |  |  |  | 10.6842 | 14423.6842
| 181 | M293 | Labor | AMC Devops Engineer (Internal) | AZ Technology | CNTR0010563 | 2021-07-01 | 2021-12-31 | T&M | 145 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0
| 182 | M293 | Labor | APM Devops Engineer (Internal) | AZ Technology | CNTR0010563 | 2021-07-01 | 2021-12-31 | T&M | 145 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0
| 183 | M293 | Labor | EMS Devops Engineer (Internal) | AZ Technology | CNTR0010563 | 2021-07-01 | 2021-12-31 | T&M | 145 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0
| 184 | M293 | Labor | Workspace Intelligence Internal – Technical SME | AZ Technology | CNTR0010563 | 2021-07-01 | 2021-12-31 | T&M | 220 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0
| 185 | M293 | Labor | SNOW CMDB | AZ Technology | CNTR0010563 | 2021-07-01 | 2021-12-31 | T&M | 250 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0
| 186 | M293 | Labor | CyNet | AZ Technology | CNTR0010563 | 2021-07-01 | 2021-12-31 | T&M | 250 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0
| 187 | M293 | Labor | Security Foundation Team | AZ Technology | CNTR0010563 | 2021-07-01 | 2021-12-31 | T&M | 1350 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0
| 188 | M293 | Labor | SNOW Performance Analytics team | AZ Technology | CNTR0010563 | 2021-07-01 | 2021-12-31 | T&M | 285 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0
| 189 | M293 | Labor | SNOW Development Teams | AZ Technology | CNTR0010563 | 2021-07-01 | 2021-12-31 | T&M | 285 |  | 0 |  | 0 |  | 0 | 2 | 570 |  |  |  |  | 2 | 570
| 190 | M293 | Labor | Qualys Team (AVM) | AZ Technology | CNTR0010563 | 2021-07-01 | 2021-12-31 | T&M | 250 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0
| 191 | M293 | Labor | Workspace Intelligence Vendor – Technical SME | AZ Technology | CNTR0010563 | 2021-07-01 | 2021-12-31 | T&M | 1600 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0
| 192 | M293 | Labor | SNOW SAM efforts | AZ Technology | CNTR0010563 | 2021-07-01 | 2021-12-31 | T&M | 1350 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0
|  | M293 | Labor | Warnholz, Benjamin | AZ Technology | CNTR0010563 | 2021-07-01 | 2021-12-31 | T&M | 2000 | 2 | 4000 | 2 | 4000 | 2 | 4000 | 2 | 4000 |  |  |  |  | 8 | 16000
[23 empty] | 0 | 0
[11 empty] | 283.5147 | 452189.3844 | 323.638 | 494328.0564 | 1334.2087 | 2067820.4518 | 108.5167 | 176164.7 | 0 | 0 | 0 | 0 | 2049.878 | 3190502.5926
| 193 | M300 | Labor | Anette Hettenkofer | Metafinanz | 21 1068 | 2021-07-01 | 2021-12-31 | T&M | 1000 | 0 | 0 | 0.125 | 125 | 0 | 0 | 0 | 0 |  |  |  |  | 0.125 | 125
| 194 | M295 | Labor | Daniel Wörner | Metafinanz | 21 1079 | 2021-07-01 | 2021-12-31 | T&M | 1000 | 0 | 0 | 11 | 11000 | 9.125 | 9125 | 1.375 | 1375 |  |  |  |  | 21.5 | 21500
| 195 | M300 | Labor | Frank Markussen | Metafinanz | 21 1068 | 2021-07-01 | 2021-12-31 | T&M | 1000 | 0.25 | 250 | 0.125 | 125 | 0.21875 | 218.75 | 0.78125 | 781.25 |  |  |  |  | 1.375 | 1375
| 196 | M295 | Labor | George Dietrichsbruckner | Metafinanz | 21 1079 | 2021-07-01 | 2021-12-31 | T&M | 1350 | 6.25 | 8437.5 | 11.3125 | 15271.875 | 19.25 | 25987.5 | 0.8125 | 1096.875 |  |  |  |  | 37.625 | 50793.75
| 197 | M294 | Labor | Gerhard Günther | Metafinanz | 21 1037 | 2021-07-01 | 2021-12-31 | T&M | 1350 | 5 | 6750 | 7.5 | 10125 | 19 | 25650 | 0 | 0 |  |  |  |  | 31.5 | 42525
| 198 | M299 | Labor | Jade Poteat | Metafinanz | 21 1040 | 2021-07-01 | 2021-12-31 | T&M | 1000 | 1.375 | 1375 | 2.375 | 2375 | 1.5 | 1500 | 1.25 | 1250 |  |  |  |  | 6.5 | 6500
| 199 | M295 | Labor | Jade Poteat | Metafinanz | 21 1079 | 2021-07-01 | 2021-12-31 | T&M | 1000 | 1.3125 | 1312.5 | 2.1875 | 2187.5 | 2.25 | 2250 | 1.875 | 1875 |  |  |  |  | 7.625 | 7625
| 200 | M300 | Labor | Jonathan Reynolds | Metafinanz | 21 1068 | 2021-07-01 | 2021-12-31 | T&M | 1000 | 10.875 | 10875 | 4.625 | 4625 | 1.25 | 1250 | 0 | 0 |  |  |  |  | 16.75 | 16750
| 201 | M300 | Labor | Julia Netesa | Metafinanz | 21 1068 | 2021-07-01 | 2021-12-31 | T&M | 1000 | 5.375 | 5375 | 0.125 | 125 | 0 | 0 | 0 | 0 |  |  |  |  | 5.5 | 5500
| 202 | M251 | Labor | Julian Steinfeld | Metafinanz | 21 0427 | 2021-07-01 | 2021-12-31 | T&M | 1112 | 19.8125 | 22031.5 | 12.5 | 13900 | 20.6875 | 23004.5 | 0 | 0 |  |  |  |  | 53 | 58936
| 203 | M281 | Labor | Krunoslav Rukavina | Metafinanz | 21 1133 | 2021-07-01 | 2021-12-31 | T&M | 1350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
| 204 | M251 | Labor | Manuel Hahn | Metafinanz | 21 0427 | 2021-07-01 | 2021-12-31 | T&M | 980 | 13.3125 | 13046.25 | 12.5625 | 12311.25 | 17.6562 | 17303.125 | 0 | 0 |  |  |  |  | 43.5312 | 42660.625
| 205 | M275 | Labor | Marc Bochtler | Metafinanz | 21 1063 | 2021-07-01 | 2021-12-31 | T&M | 1350 | 17 | 22950 | 8.875 | 11981.25 | 9.625 | 12993.75 | 6.625 | 8943.75 |  |  |  |  | 42.125 | 56868.75
| 206 | M251 | Labor | Matthias Müller | Metafinanz | 21 0427 | 2021-07-01 | 2021-12-31 | T&M | 820 | 21.0312 | 17245.625 | 22.4688 | 18424.375 | 22.5312 | 18475.625 | 0 | 0 |  |  |  |  | 66.0312 | 54145.625
| 207 | M294 | Labor | Maximilian Schellenberger | Metafinanz | 21 1037 | 2021-07-01 | 2021-12-31 | T&M | 1000 | 1.6875 | 1687.5 | 1.5938 | 1593.75 | 0 | 0 | 0 | 0 |  |  |  |  | 3.2812 | 3281.25
| 208 | M294 | Labor | Michael Habel | Metafinanz | 21 1037 | 2021-07-01 | 2021-12-31 | T&M | 1350 | 15.875 | 21431.25 | 19.0625 | 25734.375 | 7.375 | 9956.25 | 11.1875 | 15103.125 |  |  |  |  | 53.5 | 72225
| 209 | M295 | Labor | Nadine Butzhammer | Metafinanz | 21 1079 | 2021-07-01 | 2021-12-31 | T&M | 1000 | 0.3125 | 312.5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0.3125 | 312.5
| 210 | M294 | Labor | Rasa Rintallo | Metafinanz | 21 1037 | 2021-07-01 | 2021-12-31 | T&M | 1000 | 13.375 | 13375 | 12.25 | 12250 | 17.8125 | 17812.5 | 0 | 0 |  |  |  |  | 43.4375 | 43437.5
| 211 | M275 | Labor | Robert Reti | Metafinanz | 21 1063 | 2021-07-01 | 2021-12-31 | T&M | 1570 | 4.25 | 6672.5 | 6.375 | 10008.75 | 4.875 | 7653.75 | 2.375 | 3728.75 |  |  |  |  | 17.875 | 28063.75
| 212 | M300 | Labor | Samuel Hurst | Metafinanz | 21 1068 | 2021-07-01 | 2021-12-31 | T&M | 1350 | 12.2812 | 16579.6875 | 11.5625 | 15609.375 | 6.125 | 8268.75 | 9 | 12150 |  |  |  |  | 38.9688 | 52607.8125
| 213 | M295 | Labor | Sanat Gautam | Metafinanz | 21 1079 | 2021-07-01 | 2021-12-31 | T&M | 1000 | 1.125 | 1125 | 0.25 | 250 | 6.9375 | 6937.5 | 5.8125 | 5812.5 |  |  |  |  | 14.125 | 14125
| 214 | M294 | Labor | Sona Latifyan | Metafinanz | 21 1037 | 2021-07-01 | 2021-12-31 | T&M | 1000 | 10 | 10000 | 15 | 15000 | 18 | 18000 | 0 | 0 |  |  |  |  | 43 | 43000
| 215 | M294 | Labor | Stefan Köstenbauer | Metafinanz | 21 1037 | 2021-07-01 | 2021-12-31 | T&M | 1350 | 0.625 | 843.75 | 0.5 | 675 | 0 | 0 | 0 | 0 |  |  |  |  | 1.125 | 1518.75
| 216 | M296 | Labor | Thomas Thuspaß | Metafinanz | 21 1059 | 2021-07-01 | 2021-12-31 | T&M | 1350 | 11.625 | 15693.75 | 11.1875 | 15103.125 | 15.25 | 20587.5 | 7.4375 | 10040.625 |  |  |  |  | 45.5 | 61425
| 217 | M275 | Labor | Thorsten Deckers | Metafinanz | 21 1063 | 2021-07-01 | 2021-12-31 | T&M | 1570 | 7.375 | 11578.75 | 6 | 9420 | 5.6875 | 8929.375 | 2 | 3140 |  |  |  |  | 21.0625 | 33068.125
| 218 | M294 | Labor | Victor Peters | Metafinanz | 21 1037 | 2021-07-01 | 2021-12-31 | T&M | 1000 | 0.9375 | 937.5 | 0.6875 | 687.5 | 0.59375 | 593.75 | 1.625 | 1625 |  |  |  |  | 3.8438 | 3843.75
| 219 | M275 | Labor | Yury Nikulin | Metafinanz | 21 1063 | 2021-07-01 | 2021-12-31 | T&M | 1000 | 0 | 0 | 8.125 | 8125 | 12.125 | 12125 | 6 | 6000 |  |  |  |  | 26.25 | 26250
| 220 | M275 | Labor | Claudio Cangiotti | Metafinanz | 21 1063 | 2021-07-01 | 2021-12-31 | T&M | 770 | 0 | 0 | 0 | 0 | 13 | 10010 | 0 | 0 |  |  |  |  | 13 | 10010
| 221 | M275 | Labor | Eldho George | Metafinanz | 21 1063 | 2021-07-01 | 2021-12-31 | T&M | 1100 | 0 | 0 | 0 | 0 | 14 | 15400 | 1 | 1100 |  |  |  |  | 15 | 16500
| 222 | M300 | Labor | Nora von Schenckendorff | Metafinanz | 21 1068 | 2021-07-01 | 2021-12-31 | T&M | 1350 | 0 | 0 | 0 | 0 | 5.4688 | 7382.8125 | 0 | 0 |  |  |  |  | 5.4688 | 7382.8125
| 223 | M295 | Labor | Heinrich Schlotthauer | Metafinanz | 21 1079 | 2021-07-01 | 2021-12-31 | T&M | 1350 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1350 |  |  |  |  | 1 | 1350
| 224 | M300 | Labor | Jacqueline Tyc | Metafinanz | 21 1068 | 2021-07-01 | 2021-12-31 | T&M | 1200 | 0 | 0 | 0 | 0 | 4.75 | 5700 | 0 | 0 |  |  |  |  | 4.75 | 5700
| 225 | M275 | Labor | Tobias Butz | Metafinanz | 21 1063 | 2021-07-01 | 2021-12-31 | T&M | 1300 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 13000 |  |  |  |  | 10 | 13000
| 226 | M300 | Labor | Kris Harms | Metafinanz | 21 1068 | 2021-07-01 | 2021-12-31 | T&M | 1450 | 0 | 0 | 0 | 0 | 28.6875 | 41596.875 | 10.3125 | 14953.125 |  |  |  |  | 39 | 56550
[23 empty] | 0 | 0
[23 empty] | 0 | 0
[23 empty] | 0 | 0
[11 empty] | 181.0625 | 209885.5625 |  | 217033.125 |  | 328712.3125 |  | 103325 |  | 0 |  | 0 | 733.6875 | 858956
[23 empty] | 0 | 0
[23 empty] | 0 | 0
[23 empty] | 0 | 0
[23 empty] | 0 | 0
[11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | [10 empty] | 0 | 0
[23 empty] | 0 | 0
[12 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 | 0
| 227 | M251 | Labor |  | other | 0 | 2021-07-01 | 2021-12-31 | Fix |  |  | 1755 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 | 1755
| 228 | M251 | non-Labor |  | other | 0 | 2021-07-01 | 2021-12-31 | Fix |  |  | 22503 |  | 22503 |  | 22503 |  | 22503 |  | 0 |  |  | 0 | 90012
| 229 | M251 | non-Labor |  | other | 0 | 2021-07-01 | 2021-12-31 | Fix |  |  | 2058 |  | 2058 |  | 2058 |  | 2058 |  | 0 |  |  | 0 | 8232
| 230 | M251 | non-Labor |  | other | 0 | 2021-07-01 | 2021-12-31 | Fix |  |  | 4120.05 |  | 4120.05 |  | 4120.05 |  | 4120.05 |  | 0 |  |  | 0 | 16480.2
| 231 | M274 | Labor |  | NCC Group GmbH | 2410164170 | 2021-07-05 | 2021-12-31 | T&M |  |  | 0 |  | 270606 |  | 48016.5 |  | 48016.5 |  | 0 |  |  | 0 | 366639
| 232 | M274 | Labor |  | other | 0 | 0 | 0 | Fix |  |  | 3510 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 | 3510
| 233 | M274 | Labor |  | Osborne Clark | TID0001510089 |  |  | T&M |  |  | 20659.69 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 | 20659.69
| 234 | M275 | Labor |  | Virtual Clarity Ltd | 2410164371 | 2021-08-09 | 2021-12-03 | T&M |  |  | 0 |  | 88945.36 |  | 88945.36 |  | 0 |  | 0 |  |  | 0 | 177890.72
| 235 | M275 | Labor |  | other | 0 | 0 | 0 | T&M |  |  | 3510 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 | 3510
| 236 | M294 | Labor |  | other | 0 | 0 | 0 | T&M |  |  | 1755 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 | 1755
| 237 | M295 | Labor |  | other | 0 | 0 | 0 | T&M |  |  | 1755 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 | 1755
| 238 | M296 | Labor |  | other | 0 | 0 | 0 | T&M |  |  | 1755 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 | 1755
| 239 | M296 | Labor |  | other | 0 | 0 | 0 | T&M |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 | 0
| 240 | M296 | Labor |  | AZ Technology | 0 | 2021-06-17 | 2021-12-31 | Fix |  |  | 297500 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 | 297500
| 241 | M298 | Labor |  | Softwaregilde | 2410159840 | 2021-07-01 | 2021-12-31 | T&M |  |  | 29750 |  | 41650 |  | 50575 |  | 25287.5 |  | 0 |  |  | 0 | 147262.5
| 242 | M298 | Labor |  | Horvath & Partner | 2410160374 | 2021-07-01 | 2021-12-31 | T&M |  |  | 14875 |  | 14875 |  | 14875 |  | 7437.5 |  | 0 |  |  | 0 | 52062.5
| 243 | M299 | Labor |  | Ernst & Young | 2410162165 | 2021-07-01 | 2021-12-31 | T&M |  |  | 15083.25 |  | 4383.0675 |  | 78535.7606 |  | 78535.7606 |  | 0 |  |  | 0 | 176537.8387
| 244 | M299 | Labor |  | other | 0 | 0 | 0 | T&M |  |  | 3510 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 | 3510
| 245 | M300 | Labor |  | other | 0 | 0 | 0 | T&M |  |  | 1755 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 | 1755
| 246 | M300 | non-Labor |  | other | 0 | 0 | 0 | T&M |  |  | 5750 |  | 5750 |  | 5750 |  | 5750 |  | 0 |  |  | 0 | 23000
| 247 | M274 | Labor |  | SRLabs | PR964131 | 0 | 0 | 0 |  |  | 0 |  | 0 |  | 8925 |  | 8925 |  | 0 |  |  | 0 | 17850
| 248 | M301 | Labor |  | AZ Technology | CNTR0010617 | 2021-08-15 | 2021-12-31 | T&M |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 | 0
| 249 | M298 | Labor |  | other | 0 | 0 | 0 | T&M |  |  | 5265 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 | 5265
| 250 | M280 | Labor |  | DCSO | 0 | 2021-07-01 | 2021-12-31 | T&M |  |  | 0 |  | 44030 |  | 44030 |  | 44030 |  | 0 |  |  | 0 | 132090
| 251 | M298 | Labor |  | SecAttack | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 |  | 22312.5 |  | 11156.25 |  | 0 |  |  | 0 | 33468.75
[11 empty] | 0 | 436868.99 | 0 | 498920.4775 | 0 | 390646.1706 | 0 | 76697.55 | 0 | 0 | 0 | 0 | 0 | 1584255.1987
[11 empty] | 464.5772 | 1098943.9369 | 323.638 | 1210281.6589 | 1334.2087 | 2787178.9349 | 108.5167 | 356187.25 | 0 | 0 | 0 | 0 | 2783.5655 | 5633713.7914

## 3. Contracts view
3. Contract view (2021-10-15)
Cost Type | Metafinanz | AZ Technology | DCSO | Third Party | Total | Total
Contract volume | 2152765 | 14403125 | 220150 | 1920965.49 | 18697005.49 | 18697005.49
Spent | 858956 | 3488002.5926 | 132090 | 1154665.1987 | 5633713.7914 | 5633713.7914
Rem. Budget | 1293809 | 10915122.4074 | 88060 | 766300.2912 | 13063291.6986 | 13063291.6986
[12 empty] | July | August | September | October | November | December | Total
# | Measure | Cost type | Provider | Contract | Description2 | Start | End | T&M/Fix | Status | Comment | Plan Total 21 HJ | Spent1 | Spent2 | Spent3 | Spent4 | Spent5 | Spent6 | Spent Total
1 | M277 | Labor | AZ Technology | CNTR0010544 |  | 2021-07-01 | 2021-12-31 | T&M |  |  | 670000 | 0 | 0 | 157099.0619 | 0 | 0 | 0 | 157099.0619
2 | M278 | Labor | AZ Technology | CNTR0010615 |  | 2021-07-01 | 2021-12-31 | T&M |  |  | 448000 | 0 | 0 | 173433.2076 | 0 | 0 | 0 | 173433.2076
3 | M279 | Labor | AZ Technology | CNTR0010616 |  | 2021-07-01 | 2021-12-31 | T&M |  |  | 670000 | 0 | 0 | 102967.1383 | 0 | 0 | 0 | 102967.1383
4 | M291 | Labor | AZ Technology | CNTR0010576 |  | 2021-07-01 | 2021-12-31 | T&M |  |  | 200000 | 0 | 35432.54 | 0 | 0 | 0 | 0 | 35432.54
5 | M285 | Labor | AZ Technology | CNTR0010334 |  | 2021-07-01 | 2021-12-31 | T&M |  |  | 420000 | 16620 | 16777.5 | 119740.7055 | 0 | 0 | 0 | 153138.2055
6 | M286 | Labor | AZ Technology | CNTR0010562 |  | 2021-07-01 | 2021-12-31 | T&M |  |  | 285000 | 1570 | 6280 | 0 | 0 | 0 | 0 | 7850
7 | M287 | Labor | AZ Technology | CNTR0010336 |  | 2021-07-01 | 2021-12-31 | T&M |  |  | 670000 | 58134.7869 | 58241.7731 | 145255.0727 | 9500 | 0 | 0 | 271131.6326
8 | M287 | Labor | AZ Technology | CNTR0010335 |  | 2021-07-01 | 2021-12-31 | T&M |  |  | 580000 | 0 | 0 | 64575.28 | 0 | 0 | 0 | 64575.28
9 | M297 | Labor | AZ Technology | CNTR0010338 |  | 2021-07-01 | 2021-12-31 | T&M |  |  | 995000 | 15050 | 17269.6 | 154475.0572 | 3373.5 | 0 | 0 | 190168.1572
10 | M276 | Labor | AZ Technology | CNTR0010333 |  | 2021-07-01 | 2021-12-31 | T&M |  |  | 1150000 | 0 | 0 | 276810.2324 | 0 | 0 | 0 | 276810.2324
11 | M290 | Labor | AZ Technology | CNTR0010337 |  | 2021-07-01 | 2021-09-30 | T&M |  |  | 430000 | 0 | 0 | 32647.4087 | 0 | 0 | 0 | 32647.4087
12 | M282 | Labor | AZ Technology | CNTR0010325 |  | 2021-07-01 | 2021-12-31 | T&M |  |  | 820000 | 1656.25 | 12800 | 1781.25 | 0 | 0 | 0 | 16237.5
13 | M282 | Labor | AZ Technology | CNTR0010327 |  | 2021-07-01 | 2021-12-31 | T&M |  |  | 800000 | 0 | 0 | 5320 | 0 | 0 | 0 | 5320
14 | M284 | Labor | AZ Technology | CNTR0010332 |  | 2021-07-01 | 2021-12-31 | T&M |  |  | 690000 | 13081.9319 | 23488.075 | 309103.4962 | 0 | 0 | 0 | 345673.5031
15 | M283 | Labor | AZ Technology | CNTR0010329 |  | 2021-07-01 | 2021-12-31 | T&M |  |  | 505000 | 35460 | 9312.9043 | 176890.8219 | 0 | 0 | 0 | 221663.7262
16 | M281 | Labor | AZ Technology | CNTR0010709 |  | 2021-07-01 | 2021-12-31 | T&M |  |  | 337000 | 4060 | 0 | 12736.845 | 0 | 0 | 0 | 16796.845
17 | M302 | Labor | AZ Technology | OAM302 |  | 2021-09-19 | 2021-12-31 | T&M |  |  | 811000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | M288 | Labor | AZ Technology | CNTR0010589 |  | 2021-07-01 | 2021-12-31 | T&M |  |  | 1084600 | 97933.3333 | 97933.3333 | 97933.3333 | 48966.6667 | 0 | 0 | 342766.6667
20 | M289 | Labor | AZ Technology | CNTR0010976 |  | 2021-07-01 | 2021-12-31 | T&M |  |  | 350000 | 58333.3333 | 58333.3333 | 58333.3333 | 29166.6667 | 0 | 0 | 204166.6667
21.3 | M301 | Labor | AZ Technology | CNTR0010618 | Preparation | 2021-08-15 | 2021-12-31 | T&M |  |  | 845000 | 0 | 0 | 2114.4735 | 0 | 0 | 0 | 2114.4735
22.6 | M299 | Labor | AZ Technology | OAM299 |  | 2021-07-01 | 2021-12-31 | T&M |  |  | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23.9 | M292 | Labor | AZ Technology | CNTR0010564 |  | 2021-07-01 | 2021-12-31 | T&M |  |  | 750000 | 117239.749 | 129430.05 | 134630.05 | 63621.2 | 0 | 0 | 444921.049
25.2 | M293 | Labor | AZ Technology | CNTR0010563 |  | 2021-07-01 | 2021-12-31 | T&M |  |  | 360025 | 33050 | 29028.9474 | 41973.6842 | 21536.6667 | 0 | 0 | 125589.2982
0
26.2 | M251 | Labor | Metafinanz | 21 0427 |  | 2021-07-01 | 2021-12-31 | T&M |  |  | 259865 | 52323.375 | 44635.625 | 58783.25 | 0 | 0 | 0 | 155742.25
27.2 | M300 | Labor | Metafinanz | 21 1068 |  | 2021-07-01 | 2021-12-31 | T&M |  |  | 390000 | 33079.6875 | 20609.375 | 64417.1875 | 27884.375 | 0 | 0 | 145990.625
28.2 | M295 | Labor | Metafinanz | 21 1079 |  | 2021-07-01 | 2021-12-31 | T&M |  |  | 298000 | 11187.5 | 28709.375 | 44300 | 11509.375 | 0 | 0 | 95706.25
29.2 | M294 | Labor | Metafinanz | 21 1037 |  | 2021-07-01 | 2021-12-31 | T&M |  |  | 650000 | 55025 | 66065.625 | 72012.5 | 16728.125 | 0 | 0 | 209831.25
30.2 | M299 | Labor | Metafinanz | 21 1040 |  | 2021-07-01 | 2021-12-31 | T&M |  |  | 15000 | 1375 | 2375 | 1500 | 1250 | 0 | 0 | 6500
31.2 | M275 | Labor | Metafinanz | 21 1063 |  | 2021-07-01 | 2021-12-31 | T&M |  |  | 440000 | 41201.25 | 39535 | 67111.875 | 35912.5 | 0 | 0 | 183760.625
32.2 | M296 | Labor | Metafinanz | 21 1059 |  | 2021-07-01 | 2021-12-31 | T&M |  |  | 99900 | 15693.75 | 15103.125 | 20587.5 | 10040.625 | 0 | 0 | 61425
0
33.2 | M251 | Labor | other |  | contracting fee | 2021-07-01 | 2021-12-31 | Fix |  |  | 1755 | 1755 | [5 empty] | 1755
34.2 | M251 | non-Labor | other |  | AVC costs | 2021-07-01 | 2021-12-31 | Fix |  |  | 160000 | 22503 | 22503 | 22503 | 22503 |  |  | 90012
35.2 | M251 | non-Labor | other |  | HW costs | 2021-07-01 | 2021-12-31 | Fix |  |  | 12348 | 2058 | 2058 | 2058 | 2058 |  |  | 8232
36.2 | M251 | non-Labor | other |  | room costs | 2021-07-01 | 2021-12-31 | Fix |  |  | 24000 | 4120.05 | 4120.05 | 4120.05 | 4120.05 |  |  | 16480.2
37.2 | M274 | Labor | NCC Group GmbH | 2410164170 |  | 2021-07-05 | 2021-12-31 | T&M |  |  | 462672 | 0 | 270606 | 48016.5 | 48016.5 |  |  | 366639
38.2 | M274 | Labor | other |  | contracting fee |  |  | Fix |  |  | 3510 | 3510 | [5 empty] | 3510
39.2 | M274 | Labor | Osborne Clark | TID0001510089 | Rechtsberatung für Vertragserstellung mit NCC |  |  | T&M |  |  | 20659.69 | 20659.69 | [5 empty] | 20659.69
40.2 | M275 | Labor | Virtual Clarity Ltd | 2410164371 |  | 2021-08-09 | 2021-12-03 | T&M |  |  | 355781.44 | 0 | 88945.36 | 88945.36 |  |  |  | 177890.72
41.2 | M275 | Labor | other |  | contracting fee |  |  | T&M |  |  | 3510 | 3510 | [5 empty] | 3510
42.2 | M294 | Labor | other |  | contracting fee |  |  | T&M |  |  | 1755 | 1755 | [5 empty] | 1755
43.2 | M295 | Labor | other |  | contracting fee |  |  | T&M |  |  | 1755 | 1755 | [5 empty] | 1755
44.2 | M296 | Labor | other |  | contracting fee |  |  | T&M |  |  | 1755 | 1755 | [5 empty] | 1755
45.2 | M296 | Labor | other |  | Procurement Fee (Bitsight Vertrag) |  |  | T&M |  |  | 4925 | [6 empty] | 0
46.2 | M296 | Labor | AZ Technology |  | Bitsight | 2021-06-17 | 2021-12-31 | Fix |  |  | 297500 | 297500 | [5 empty] | 297500
47.2 | M298 | Labor | Softwaregilde | 2410159840 |  | 2021-07-01 | 2021-12-31 | T&M |  |  | 273700 | 29750 | 41650 | 50575 | 25287.5 |  |  | 147262.5
48.2 | M298 | Labor | Horvath & Partner | 2410160374 |  | 2021-07-01 | 2021-12-31 | T&M |  |  | 89250 | 14875 | 14875 | 14875 | 7437.5 |  |  | 52062.5
49.2 | M299 | Labor | Ernst & Young | 2410162165 |  | 2021-07-01 | 2021-12-31 | T&M |  |  | 333609.36 | 15083.25 | 4383.0675 | 78535.7606 | 78535.7606 |  |  | 176537.8387
50.2 | M299 | Labor | other |  | contracting fee |  |  | T&M |  |  | 3510 | 3510 | [5 empty] | 3510
51.2 | M300 | Labor | other |  | contracting fee |  |  | T&M |  |  | 1755 | 1755 | [5 empty] | 1755
52.2 | M300 | non-Labor | other |  | Trust Net Platform |  |  | T&M |  |  | 34500 | 5750 | 5750 | 5750 | 5750 |  |  | 23000
54 | M274 | Labor | SRLabs | PR964131 | [6 empty] | 35700 |  |  | 8925 | 8925 |  |  | 17850
55 | M301 | Labor | AZ Technology | CNTR0010617 | APAC Pilot | 2021-08-15 | 2021-12-31 | T&M |  |  | 155000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
56 | M298 | Labor | other |  | contracting fee |  |  | T&M |  |  | 5265 | 5265 | [5 empty] | 5265
57 | M280 | Labor | DCSO |  |  | 2021-07-01 | 2021-12-31 | T&M |  |  | 220150 |  | 44030 | 44030 | 44030 |  |  | 132090
58 | M298 | Labor | SecAttack | [7 empty] | 89250 |  |  | 22312.5 | 11156.25 |  |  | 33468.75
0
0
0
Sum | [10 empty] | 18697005.49 | 1098943.9369 | 1210281.6589 | 2787178.9349 | 537309.2606 | 0 | 0 | 5633713.7914

## M83 (hidden)
M83
Measure Lead: Neil Cranstone
Pillar Lead: Carsten Scholz
Duration: 01.07.2017-31.12.2018
Planned Total | #N/A
Approved Total | #N/A
Spent Labor | #N/A
Spent non-Labor | #N/A
Spent Total | #N/A
Forecast Total | #N/A
| Measure | (All)
|  | Jan |  | Feb | Mrz | Apr | Mai | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total
| Resources & Contracts | PD Total | EUR Total
| Labor | 2766.8155 | 4526422.3084
Comment | AZ Technology | 2048.878 | 2833818.6402
| 0 | 0 | 297500
| (blank) | 0 | 297500
| CNTR0010544 | 110.4647 | 157099.0619
| Andrea Scotti | 0 | 0
| Wolfgang Elsner | 0 | 0
| Alexander Heinze | 0 | 0
| Thomas Huber | 0 | 0
| Jagoda Matys | 0 | 0
| Markus Schnier | 0 | 0
| Sergej Reißig | 55.0018 | 83266.9815
| Binoj Baburaj | 0 | 0
| IAM Architect (Cygna) | 2.4114 | 3159.8592
| NN india | 0 | 0
| Michael Holder | 0 | 0
| Youssef Dahmouni | 0 | 0
| Nina Kaufmann | 20.9999 | 27517.875
| Viktoryia Nikifaravets | 32.0516 | 43154.3461
| CNTR0010615 | 121.7529 | 173433.2076
| Alexander Heinze | 0 | 0
| Jagoda Matys | 0 | 0
| Srdan Mavrenski | 55.0018 | 83266.9815
| Itai Schwartz | 31.2506 | 42075.8024
| NN india | 0 | 0
| Francois Pernayan | 31.2506 | 42075.8024
| Matt Gibson | 0 | 0
| Christian Bolterauer | 4.25 | 6014.6213
| CNTR0010616 | 68.1618 | 102967.1383
| Alexander Heinze | 0 | 0
| Thomas Huber | 0 | 0
| Reza Memarian | 55.0018 | 83266.9815
| Markus Schnier | 0 | 0
| NN india | 0 | 0
| Youssef Dahmouni | 0 | 0
| Walter Hofer | 0 | 0
| Balasz Razs | 0 | 0
| Ivan Markovic | 13.16 | 19700.1568
| Product SME | 0 | 0
| CNTR0010562 | 5 | 7850
| Thomas Huber | 0 | 0
| Markus Schnier | 0 | 0
| Clemens Friedrich | 5 | 7850
| Gerhard Schneider | 0 | 0
| DGI | 0 | 0
| CNTR0010336 | 152.1775 | 271131.6326
| Thomas Huber | 0 | 0
| Markus Schnier | 0 | 0
| Daniela Betz | 45.9375 | 65010.9849
| Bastian Kastner | 45.25 | 47435.575
| Clemens Friedrich | 0 | 0
| Gerhard Schneider | 3.77 | 7653.1
| Björn Hansen / Markus Feuerstein | 0 | 85551.9727
| Rudresh Subramanian | 20.22 | 30330
| Guelsah Uestelci | 37 | 35150
| CNTR0010335 | 56 | 64575.28
| N.N. | 0 | 0
| Markus Gatter | 56 | 64575.28
| Jakob Schusser | 0 | 0
| Gabriella Nagy | 0 | 0
| N.N. // SME 2 | 0 | 0
| N.N. // Sr. Analyst | 0 | 0
| SR Labs Autobahn | 0 | 0
| OE Effort | 0 | 0
| Ben Brüggen | 0 | 0
| CNTR0010338 | 152.3738 | 157766.1581
| Rene Pferner | 0 | 0
| Thomas Huber | 1 | 2030
| Markus Schnier | 1 | 2030
| N.N. | 0 | 0
| Clemens Friedrich | 15 | 23550
| Gerhard Schneider | 6.03 | 12240.9
| Anna Hartl | 53.8125 | 56411.6437
| Alina Lobova | 55.75 | 46754.18
| Stefan Kösters | 12.2812 | 12874.4344
| Kühnlenz / 2wmedia | 0 | 0
| Natalia Nikitana | 0 | 0
| IT Seal | 0 | 0
| Aishwarya Nangude / Sarabjit Singh | 0 | 0
| Meera Patel | 7.5 | 1875
| CNTR0010333 | 245.5625 | 276810.2324
| Christoph Lenz | 31.625 | 33152.4875
| Thomas Huber | 0 | 0
| Markus Schnier | 0 | 0
| Corinna Koch | 19.375 | 20310.8125
| Vasanthan Dhanasingh | 0 | 0
| Clemens Friedrich | 0 | 0
| Gerhard Schneider | 0 | 0
| Sven Lierzer | 48.875 | 57921.9165
| Tobias Lichtenberg | 12.6875 | 17955.4134
| Stanislav Khotinok | 34.125 | 39350.5613
| Alexander Leonhardt | 56.75 | 65440.1275
| Yuri Nikulin | 23.375 | 26954.4138
| Maria Thanner | 18.75 | 15724.5
| SNOW-Team | 0 | 0
| Splunk Team | 0 | 0
| Ankita Mane | 0 | 0
| Martin Gerlowski | 0 | 0
| Deepak Krishnan | 0 | 0
| K Harikrishnan | 0 | 0
| CNTR0010337 | 19.2596 | 32647.4087
| Placeholder | 0 | 0
| Matthias Kickstein | 0 | 0
| Computacenter | 0 | 0
| Ernst & Young | 19.2596 | 32647.4087
| CNTR0010325 | 29.75 | 16237.5
| Alex Lee | 0 | 0
| Lucas Tscherter | 0 | 0
| Corinna Koch | 0 | 0
| Dhanya Kalathil | 19.75 | 4937.5
| Mark de Vera | 0 | 0
| Balasz Racz | 10 | 11300
| Arunlal Nair | 0 | 0
| Local Infra setup support | 0 | 0
| Local SMEs for AVC, FMO | 0 | 0
| Cabling APAC | 0 | 0
| CNTR0010327 | 20 | 5320
| Thomas Huber | 0 | 0
| Gereon Volker | 0 | 0
| Lucas Tscherter | 0 | 0
| Markus Schnier | 0 | 0
| Thomas Bringewald | 2 | 2260
| Andrei Maslov | 0 | 0
| Patrick Zeitz | 0 | 0
| Armando Diaz | 0 | 0
| Ron Johnson | 0 | 0
| Jithin Varghese | 18 | 3060
| AZ Tech America Labor | 0 | 0
| Service Manager | 0 | 0
| CNTR0010332 | 177.713 | 270824.8831
| Timothy Drost | 51.25 | 56077.4981
| Thomas Huber | 1 | 2030
| Holger Steinlechner | 1.78 | 2011.4
| Lucas Tscherter | 20.42 | 32059.4
| Markus Schnier | 1 | 2030
| Olivier Ma | 0 | 0
| Rebecca Dengl | 0.263 | 297.19
| Andrei Maslov | 5 | 5650
| Racz Balazs | 2 | 2260
| Jimmy Braun | 0 | 0
| Cyarx Siemplify | 95 | 168409.395
| CMDB | 0 | 0
| CNTR0010329 | 97.9983 | 221663.7262
| Thomas Huber | 1 | 2030
| Gereon Volker | 0 | 0
| Lucas Tscherter | 27.79 | 43630.3
| Markus Schnier | 1 | 2030
| Thomas Bringewald | 5 | 5650
| Rebecca Dengl | 0.526 | 594.38
| Felix Hertin | 3.2615 | 5242.0231
| Lukas Thiele | 9.4208 | 5242.0231
| Holger Wache | 25 | 78622.5
| Tobias Martin | 25 | 78622.5
| Deloitte | 0 | 0
| CNTR0010709 | 11 | 16796.845
| Thomas Huber | 1 | 2030
| Lucas Tscherter | 0 | 0
| Markus Schnier | 1 | 2030
| Krunoslav Rukavina | 9 | 12736.845
| Joachim Steinberger | 0 | 0
| Elastic | 0 | 0
| Proofpoint | 0 | 0
| CNTR0010564 | 513.2647 | 444921.049
| Markus Traumueller | 10 | 11300
| Karim, Hasan | 57 | 59850
| Bojarski, Eduard | 57 | 112122.99
| Kayali, Ismail | 57 | 72645.93
| Stettner, Julia | 57 | 80717.13
| Tulshidas Thamke, Budhesh | 57 | 9120
| Sunderdas, Shilpa | 58 | 9280
| Bönigk, Julian | 10 | 11300
| Sora Mustafa (AUG-OCT only) | 52 | 61880
| Vidya Baskaran Reddy | 57 | 9690
| S, Shibi (partily on IP&G) | 41.2647 | 7014.999
| CNTR0010563 | 109.9746 | 125589.2982
| Günther, Gerhard | 15.1579 | 20463.1579
| Poteat, Jade | 22.9868 | 22986.8421
| Warnholz, Benjamin | 8 | 16000
| Qualys Team (AVM) | 0 | 0
| Uysal, Ismail (Project Manager) | 51.1456 | 51145.614
| Goldschmidt, Andreas (SNOW Principal Architect) | 10.6842 | 14423.6842
| AMC Devops Engineer (Internal) | 0 | 0
| APM Devops Engineer (Internal) | 0 | 0
| EMS Devops Engineer (Internal) | 0 | 0
| Workspace Intelligence Internal – Technical SME | 0 | 0
| SNOW Performance Analytics team | 0 | 0
| SNOW Development Teams | 2 | 570
| Workspace Intelligence Vendor – Technical SME | 0 | 0
| SNOW SAM efforts | 0 | 0
| SNOW CMDB | 0 | 0
| CyNet | 0 | 0
| Security Foundation Team | 0 | 0
| CNTR0010576 | 27.5 | 35432.54
| Marc Bochtler | 18 | 25473.69
| Alexander Heinze | 0 | 0
| Tobias Butz | 0 | 0
| NN | 0 | 0
| NN india | 0 | 0
| Yury Nikolin | 9.5 | 9958.85
| Thomas Felder | 0 | 0
| CNTR0010334 | 130.125 | 153138.2055
| Martin Schurm | 27 | 42102.3487
| Tobias Krichel | 62.875 | 74513.3568
| Thomas Huber | 1 | 2030
| Markus Schnier | 1 | 2030
| Dan Read | 0 | 0
| N.N. / Support Dan | 0 | 0
| Ankur Tomar | 0 | 0
| Naman Agrawal | 21.25 | 5312.5
| Clemens Friedrich | 16 | 25120
| Gerhard Schneider | 1 | 2030
| OAM302 | 0 | 0
| Alexander Heinze | 0 | 0
| Daming Yang | 0 | 0
| Manoj Selvakumar | 0 | 0
| David Barton | 0 | 0
| Raja Rajcic | 0 | 0
| Lawrence Tengan | 0 | 0
| Travis Chun | 0 | 0
| Johannes Bross | 0 | 0
| Tuan Minh Nguyen | 0 | 0
| Tobias Tischler | 0 | 0
| Djamel Tazerout | 0 | 0
| Dirk Addicks | 0 | 0
| Forgerock Licence | 0 | 0
| CNTR0010589 | 0 | 0
| Placeholder | 0 | 0
| OAM299 | 0 | 0
| Placeholder | 0 | 0
| CNTR0010618 | 0.79973 | 2114.4735
| Birgit Jarosch | 0.79973 | 2114.4735
| Wolfgang Elsner | 0 | 0
| Alexander Heinze | 0 | 0
| Jagoda Matys | 0 | 0
| N.N. | 0 | 0
| Mitja Ledowski | 0 | 0
| Ingmar Janßen-Holldiek | 0 | 0
| Michael Holder | 0 | 0
| Sinoop K S | 0 | 0
| J. Thomas | 0 | 0
| Madalina Paslaru | 0 | 0
| Daniel Ettenhuber | 0 | 0
| OAM289 | 0 | 0
| Placeholder | 0 | 0
| CNTR0010617 | 0 | 0
| (blank) | 0 | 0
| Alexander Heinze | 0 | 0
| Christine Schlüter | 0 | 0
| Günter Sanktjohanser | 0 | 0
| Metafinanz | 717.9375 | 838906
| 21 0427 | 162.5625 | 155742.25
| Julian Steinfeld | 53 | 58936
| Manuel Hahn | 43.5312 | 42660.625
| Matthias Müller | 66.0312 | 54145.625
| 21 1068 | 107.1875 | 140290.625
| Jonathan Reynolds | 16.75 | 16750
| Samuel Hurst | 38.9688 | 52607.8125
| Kris Harms | 39 | 56550
| Nora von Schenckendorff | 5.4688 | 7382.8125
| Frank Markussen | 1.375 | 1375
| Anette Hettenkofer | 0.125 | 125
| Julia Netesa | 5.5 | 5500
| 21 1079 | 81.1875 | 94356.25
| George Dietrichsbruckner | 37.625 | 50793.75
| Jade Poteat | 7.625 | 7625
| Nadine Butzhammer | 0.3125 | 312.5
| Daniel Wörner | 21.5 | 21500
| Sanat Gautam | 14.125 | 14125
| 21 1037 | 179.6875 | 209831.25
| Gerhard Günther | 31.5 | 42525
| Rasa Rintallo | 43.4375 | 43437.5
| Stefan Köstenbauer | 1.125 | 1518.75
| Victor Peters | 3.8438 | 3843.75
| Michael Habel | 53.5 | 72225
| Maximilian Schellenberger | 3.2812 | 3281.25
| Sona Latifyan | 43 | 43000
| 21 1040 | 6.5 | 6500
| Jade Poteat | 6.5 | 6500
| 21 1133 | 0 | 0
| Krunoslav Rukavina | 0 | 0
| 21 1063 | 135.3125 | 170760.625
| Marc Bochtler | 42.125 | 56868.75
| Thorsten Deckers | 21.0625 | 33068.125
| Robert Reti | 17.875 | 28063.75
| Claudio Cangiotti | 13 | 10010
| Yury Nikulin | 26.25 | 26250
| Eldho George | 15 | 16500
| 21 1059 | 45.5 | 61425
| Thomas Thuspaß | 45.5 | 61425
| other | 0 | 24570
| 0 | 0 | 24570
| (blank) | 0 | 24570
| NCC Group GmbH | 0 | 363140.4
| 2410164170 | 0 | 363140.4
| (blank) | 0 | 363140.4
| Osborne Clark | 0 | 20659.69
| TID0001510089 | 0 | 20659.69
| (blank) | 0 | 20659.69
| Virtual Clarity Ltd | 0 | 149488
| 2410164371 | 0 | 149488
| (blank) | 0 | 149488
| Softwaregilde | 0 | 121975
| 2410159840 | 0 | 121975
| (blank) | 0 | 121975
| Horvath & Partner | 0 | 44625
| 2410160374 | 0 | 44625
| (blank) | 0 | 44625
| Ernst & Young | 0 | 98002.0781
| 2410162165 | 0 | 98002.0781
| (blank) | 0 | 98002.0781
| SRLabs | 0 | 8925
| PR964131 | 0 | 8925
| (blank) | 0 | 8925
| DCSO | 0 | 0
| 0 | 0 | 0
| (blank) | 0 | 0
| SecAttack | 0 | 22312.5
| 0 | 0 | 22312.5
| (blank) | 0 | 22312.5
| (blank) | 2767.8155 | 3482475.2593
| (blank) | 2767.8155 | 3482475.2593
| (blank) | 2767.8155 | 3482475.2593
| (blank) | 2767.8155 | 3482475.2593
| non-Labor | 1 | 210543.769
| AZ Technology | 1 | 107250.619
| CNTR0010616 | 0 | 0
| Licence costs | 0 | 0
| CNTR0010338 | 0 | 32401.999
| Splunk Licenses + Server | 0 | 0
| ZeroFox Licenses | 0 | 32401.999
| CNTR0010333 | 0 | 0
| Splunk Licenses + Server | 0 | 0
| CNTR0010325 | 0 | 0
| HW / infrastructure | 0 | 0
| CNTR0010327 | 0 | 0
| Local SMEs for AVC, FMO | 0 | 0
| AZ Tech America HW | 0 | 0
| CNTR0010332 | 1 | 74848.62
| Cyarx Siemplify | 1 | 74848.62
| CNTR0010329 | 0 | 0
| AWS / Azure cloud | 0 | 0
| CNTR0010618 | 0 | 0
| HW | 0 | 0
| other | 0 | 103293.15
| 0 | 0 | 103293.15
| (blank) | 0 | 103293.15
| Sum | 5535.6311 | 8219441.3367

## M15 (hidden)
M15
Measure Lead: Andreas Hackel
Pillar Lead: Carsten Scholz
Duration: 01.01.2017-31.12.2018
Planned Total | #N/A
Approved Total | #N/A
Spent Labor | #N/A
Spent non-Labor | #N/A
Spent Total | #N/A
Forecast Total | #N/A
| Measure | (All)
|  | Jan |  | Feb | Mrz | Apr | Mai | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total
| Resources & Contracts | PD Total | EUR Total
| Labor | 2766.8155 | 4526422.3084
Comment | AZ Technology | 2048.878 | 2833818.6402
| 0 | 0 | 297500
| (blank) | 0 | 297500
| CNTR0010544 | 110.4647 | 157099.0619
| Andrea Scotti | 0 | 0
| Wolfgang Elsner | 0 | 0
| Alexander Heinze | 0 | 0
| Thomas Huber | 0 | 0
| Jagoda Matys | 0 | 0
| Markus Schnier | 0 | 0
| Sergej Reißig | 55.0018 | 83266.9815
| Binoj Baburaj | 0 | 0
| IAM Architect (Cygna) | 2.4114 | 3159.8592
| NN india | 0 | 0
| Michael Holder | 0 | 0
| Youssef Dahmouni | 0 | 0
| Nina Kaufmann | 20.9999 | 27517.875
| Viktoryia Nikifaravets | 32.0516 | 43154.3461
| CNTR0010615 | 121.7529 | 173433.2076
| Alexander Heinze | 0 | 0
| Jagoda Matys | 0 | 0
| Srdan Mavrenski | 55.0018 | 83266.9815
| Itai Schwartz | 31.2506 | 42075.8024
| NN india | 0 | 0
| Francois Pernayan | 31.2506 | 42075.8024
| Matt Gibson | 0 | 0
| Christian Bolterauer | 4.25 | 6014.6213
| CNTR0010616 | 68.1618 | 102967.1383
| Alexander Heinze | 0 | 0
| Thomas Huber | 0 | 0
| Reza Memarian | 55.0018 | 83266.9815
| Markus Schnier | 0 | 0
| NN india | 0 | 0
| Youssef Dahmouni | 0 | 0
| Walter Hofer | 0 | 0
| Balasz Razs | 0 | 0
| Ivan Markovic | 13.16 | 19700.1568
| Product SME | 0 | 0
| CNTR0010562 | 5 | 7850
| Thomas Huber | 0 | 0
| Markus Schnier | 0 | 0
| Clemens Friedrich | 5 | 7850
| Gerhard Schneider | 0 | 0
| DGI | 0 | 0
| CNTR0010336 | 152.1775 | 271131.6326
| Thomas Huber | 0 | 0
| Markus Schnier | 0 | 0
| Daniela Betz | 45.9375 | 65010.9849
| Bastian Kastner | 45.25 | 47435.575
| Clemens Friedrich | 0 | 0
| Gerhard Schneider | 3.77 | 7653.1
| Björn Hansen / Markus Feuerstein | 0 | 85551.9727
| Rudresh Subramanian | 20.22 | 30330
| Guelsah Uestelci | 37 | 35150
| CNTR0010335 | 56 | 64575.28
| N.N. | 0 | 0
| Markus Gatter | 56 | 64575.28
| Jakob Schusser | 0 | 0
| Gabriella Nagy | 0 | 0
| N.N. // SME 2 | 0 | 0
| N.N. // Sr. Analyst | 0 | 0
| SR Labs Autobahn | 0 | 0
| OE Effort | 0 | 0
| Ben Brüggen | 0 | 0
| CNTR0010338 | 152.3738 | 157766.1581
| Rene Pferner | 0 | 0
| Thomas Huber | 1 | 2030
| Markus Schnier | 1 | 2030
| N.N. | 0 | 0
| Clemens Friedrich | 15 | 23550
| Gerhard Schneider | 6.03 | 12240.9
| Anna Hartl | 53.8125 | 56411.6437
| Alina Lobova | 55.75 | 46754.18
| Stefan Kösters | 12.2812 | 12874.4344
| Kühnlenz / 2wmedia | 0 | 0
| Natalia Nikitana | 0 | 0
| IT Seal | 0 | 0
| Aishwarya Nangude / Sarabjit Singh | 0 | 0
| Meera Patel | 7.5 | 1875
| CNTR0010333 | 245.5625 | 276810.2324
| Christoph Lenz | 31.625 | 33152.4875
| Thomas Huber | 0 | 0
| Markus Schnier | 0 | 0
| Corinna Koch | 19.375 | 20310.8125
| Vasanthan Dhanasingh | 0 | 0
| Clemens Friedrich | 0 | 0
| Gerhard Schneider | 0 | 0
| Sven Lierzer | 48.875 | 57921.9165
| Tobias Lichtenberg | 12.6875 | 17955.4134
| Stanislav Khotinok | 34.125 | 39350.5613
| Alexander Leonhardt | 56.75 | 65440.1275
| Yuri Nikulin | 23.375 | 26954.4138
| Maria Thanner | 18.75 | 15724.5
| SNOW-Team | 0 | 0
| Splunk Team | 0 | 0
| Ankita Mane | 0 | 0
| Martin Gerlowski | 0 | 0
| Deepak Krishnan | 0 | 0
| K Harikrishnan | 0 | 0
| CNTR0010337 | 19.2596 | 32647.4087
| Placeholder | 0 | 0
| Matthias Kickstein | 0 | 0
| Computacenter | 0 | 0
| Ernst & Young | 19.2596 | 32647.4087
| CNTR0010325 | 29.75 | 16237.5
| Alex Lee | 0 | 0
| Lucas Tscherter | 0 | 0
| Corinna Koch | 0 | 0
| Dhanya Kalathil | 19.75 | 4937.5
| Mark de Vera | 0 | 0
| Balasz Racz | 10 | 11300
| Arunlal Nair | 0 | 0
| Local Infra setup support | 0 | 0
| Local SMEs for AVC, FMO | 0 | 0
| Cabling APAC | 0 | 0
| CNTR0010327 | 20 | 5320
| Thomas Huber | 0 | 0
| Gereon Volker | 0 | 0
| Lucas Tscherter | 0 | 0
| Markus Schnier | 0 | 0
| Thomas Bringewald | 2 | 2260
| Andrei Maslov | 0 | 0
| Patrick Zeitz | 0 | 0
| Armando Diaz | 0 | 0
| Ron Johnson | 0 | 0
| Jithin Varghese | 18 | 3060
| AZ Tech America Labor | 0 | 0
| Service Manager | 0 | 0
| CNTR0010332 | 177.713 | 270824.8831
| Timothy Drost | 51.25 | 56077.4981
| Thomas Huber | 1 | 2030
| Holger Steinlechner | 1.78 | 2011.4
| Lucas Tscherter | 20.42 | 32059.4
| Markus Schnier | 1 | 2030
| Olivier Ma | 0 | 0
| Rebecca Dengl | 0.263 | 297.19
| Andrei Maslov | 5 | 5650
| Racz Balazs | 2 | 2260
| Jimmy Braun | 0 | 0
| Cyarx Siemplify | 95 | 168409.395
| CMDB | 0 | 0
| CNTR0010329 | 97.9983 | 221663.7262
| Thomas Huber | 1 | 2030
| Gereon Volker | 0 | 0
| Lucas Tscherter | 27.79 | 43630.3
| Markus Schnier | 1 | 2030
| Thomas Bringewald | 5 | 5650
| Rebecca Dengl | 0.526 | 594.38
| Felix Hertin | 3.2615 | 5242.0231
| Lukas Thiele | 9.4208 | 5242.0231
| Holger Wache | 25 | 78622.5
| Tobias Martin | 25 | 78622.5
| Deloitte | 0 | 0
| CNTR0010709 | 11 | 16796.845
| Thomas Huber | 1 | 2030
| Lucas Tscherter | 0 | 0
| Markus Schnier | 1 | 2030
| Krunoslav Rukavina | 9 | 12736.845
| Joachim Steinberger | 0 | 0
| Elastic | 0 | 0
| Proofpoint | 0 | 0
| CNTR0010564 | 513.2647 | 444921.049
| Markus Traumueller | 10 | 11300
| Karim, Hasan | 57 | 59850
| Bojarski, Eduard | 57 | 112122.99
| Kayali, Ismail | 57 | 72645.93
| Stettner, Julia | 57 | 80717.13
| Tulshidas Thamke, Budhesh | 57 | 9120
| Sunderdas, Shilpa | 58 | 9280
| Bönigk, Julian | 10 | 11300
| Sora Mustafa (AUG-OCT only) | 52 | 61880
| Vidya Baskaran Reddy | 57 | 9690
| S, Shibi (partily on IP&G) | 41.2647 | 7014.999
| CNTR0010563 | 109.9746 | 125589.2982
| Günther, Gerhard | 15.1579 | 20463.1579
| Poteat, Jade | 22.9868 | 22986.8421
| Warnholz, Benjamin | 8 | 16000
| Qualys Team (AVM) | 0 | 0
| Uysal, Ismail (Project Manager) | 51.1456 | 51145.614
| Goldschmidt, Andreas (SNOW Principal Architect) | 10.6842 | 14423.6842
| AMC Devops Engineer (Internal) | 0 | 0
| APM Devops Engineer (Internal) | 0 | 0
| EMS Devops Engineer (Internal) | 0 | 0
| Workspace Intelligence Internal – Technical SME | 0 | 0
| SNOW Performance Analytics team | 0 | 0
| SNOW Development Teams | 2 | 570
| Workspace Intelligence Vendor – Technical SME | 0 | 0
| SNOW SAM efforts | 0 | 0
| SNOW CMDB | 0 | 0
| CyNet | 0 | 0
| Security Foundation Team | 0 | 0
| CNTR0010576 | 27.5 | 35432.54
| Marc Bochtler | 18 | 25473.69
| Alexander Heinze | 0 | 0
| Tobias Butz | 0 | 0
| NN | 0 | 0
| NN india | 0 | 0
| Yury Nikolin | 9.5 | 9958.85
| Thomas Felder | 0 | 0
| CNTR0010334 | 130.125 | 153138.2055
| Martin Schurm | 27 | 42102.3487
| Tobias Krichel | 62.875 | 74513.3568
| Thomas Huber | 1 | 2030
| Markus Schnier | 1 | 2030
| Dan Read | 0 | 0
| N.N. / Support Dan | 0 | 0
| Ankur Tomar | 0 | 0
| Naman Agrawal | 21.25 | 5312.5
| Clemens Friedrich | 16 | 25120
| Gerhard Schneider | 1 | 2030
| OAM302 | 0 | 0
| Alexander Heinze | 0 | 0
| Daming Yang | 0 | 0
| Manoj Selvakumar | 0 | 0
| David Barton | 0 | 0
| Raja Rajcic | 0 | 0
| Lawrence Tengan | 0 | 0
| Travis Chun | 0 | 0
| Johannes Bross | 0 | 0
| Tuan Minh Nguyen | 0 | 0
| Tobias Tischler | 0 | 0
| Djamel Tazerout | 0 | 0
| Dirk Addicks | 0 | 0
| Forgerock Licence | 0 | 0
| CNTR0010589 | 0 | 0
| Placeholder | 0 | 0
| OAM299 | 0 | 0
| Placeholder | 0 | 0
| CNTR0010618 | 0.79973 | 2114.4735
| Birgit Jarosch | 0.79973 | 2114.4735
| Wolfgang Elsner | 0 | 0
| Alexander Heinze | 0 | 0
| Jagoda Matys | 0 | 0
| N.N. | 0 | 0
| Mitja Ledowski | 0 | 0
| Ingmar Janßen-Holldiek | 0 | 0
| Michael Holder | 0 | 0
| Sinoop K S | 0 | 0
| J. Thomas | 0 | 0
| Madalina Paslaru | 0 | 0
| Daniel Ettenhuber | 0 | 0
| OAM289 | 0 | 0
| Placeholder | 0 | 0
| CNTR0010617 | 0 | 0
| (blank) | 0 | 0
| Alexander Heinze | 0 | 0
| Christine Schlüter | 0 | 0
| Günter Sanktjohanser | 0 | 0
| Metafinanz | 717.9375 | 838906
| 21 0427 | 162.5625 | 155742.25
| Julian Steinfeld | 53 | 58936
| Manuel Hahn | 43.5312 | 42660.625
| Matthias Müller | 66.0312 | 54145.625
| 21 1068 | 107.1875 | 140290.625
| Jonathan Reynolds | 16.75 | 16750
| Samuel Hurst | 38.9688 | 52607.8125
| Kris Harms | 39 | 56550
| Nora von Schenckendorff | 5.4688 | 7382.8125
| Frank Markussen | 1.375 | 1375
| Anette Hettenkofer | 0.125 | 125
| Julia Netesa | 5.5 | 5500
| 21 1079 | 81.1875 | 94356.25
| George Dietrichsbruckner | 37.625 | 50793.75
| Jade Poteat | 7.625 | 7625
| Nadine Butzhammer | 0.3125 | 312.5
| Daniel Wörner | 21.5 | 21500
| Sanat Gautam | 14.125 | 14125
| 21 1037 | 179.6875 | 209831.25
| Gerhard Günther | 31.5 | 42525
| Rasa Rintallo | 43.4375 | 43437.5
| Stefan Köstenbauer | 1.125 | 1518.75
| Victor Peters | 3.8438 | 3843.75
| Michael Habel | 53.5 | 72225
| Maximilian Schellenberger | 3.2812 | 3281.25
| Sona Latifyan | 43 | 43000
| 21 1040 | 6.5 | 6500
| Jade Poteat | 6.5 | 6500
| 21 1133 | 0 | 0
| Krunoslav Rukavina | 0 | 0
| 21 1063 | 135.3125 | 170760.625
| Marc Bochtler | 42.125 | 56868.75
| Thorsten Deckers | 21.0625 | 33068.125
| Robert Reti | 17.875 | 28063.75
| Claudio Cangiotti | 13 | 10010
| Yury Nikulin | 26.25 | 26250
| Eldho George | 15 | 16500
| 21 1059 | 45.5 | 61425
| Thomas Thuspaß | 45.5 | 61425
| other | 0 | 24570
| 0 | 0 | 24570
| (blank) | 0 | 24570
| NCC Group GmbH | 0 | 363140.4
| 2410164170 | 0 | 363140.4
| (blank) | 0 | 363140.4
| Osborne Clark | 0 | 20659.69
| TID0001510089 | 0 | 20659.69
| (blank) | 0 | 20659.69
| Virtual Clarity Ltd | 0 | 149488
| 2410164371 | 0 | 149488
| (blank) | 0 | 149488
| Softwaregilde | 0 | 121975
| 2410159840 | 0 | 121975
| (blank) | 0 | 121975
| Horvath & Partner | 0 | 44625
| 2410160374 | 0 | 44625
| (blank) | 0 | 44625
| Ernst & Young | 0 | 98002.0781
| 2410162165 | 0 | 98002.0781
| (blank) | 0 | 98002.0781
| SRLabs | 0 | 8925
| PR964131 | 0 | 8925
| (blank) | 0 | 8925
| DCSO | 0 | 0
| 0 | 0 | 0
| (blank) | 0 | 0
| SecAttack | 0 | 22312.5
| 0 | 0 | 22312.5
| (blank) | 0 | 22312.5
| (blank) | 2767.8155 | 3482475.2593
| (blank) | 2767.8155 | 3482475.2593
| (blank) | 2767.8155 | 3482475.2593
| (blank) | 2767.8155 | 3482475.2593
| non-Labor | 1 | 210543.769
| AZ Technology | 1 | 107250.619
| CNTR0010616 | 0 | 0
| Licence costs | 0 | 0
| CNTR0010338 | 0 | 32401.999
| Splunk Licenses + Server | 0 | 0
| ZeroFox Licenses | 0 | 32401.999
| CNTR0010333 | 0 | 0
| Splunk Licenses + Server | 0 | 0
| CNTR0010325 | 0 | 0
| HW / infrastructure | 0 | 0
| CNTR0010327 | 0 | 0
| Local SMEs for AVC, FMO | 0 | 0
| AZ Tech America HW | 0 | 0
| CNTR0010332 | 1 | 74848.62
| Cyarx Siemplify | 1 | 74848.62
| CNTR0010329 | 0 | 0
| AWS / Azure cloud | 0 | 0
| CNTR0010618 | 0 | 0
| HW | 0 | 0
| other | 0 | 103293.15
| 0 | 0 | 103293.15
| (blank) | 0 | 103293.15
| Sum | 5535.6311 | 8219441.3367

## M51 (hidden)
M51
Measure Lead: Jürgen Renus
Pillar Lead: Carsten Scholz
Duration: 01.01.2017-31.12.2018
Planned Total | #N/A
Approved Total | #N/A
Spent Labor | #N/A
Spent non-Labor | #N/A
Spent Total | #N/A
Forecast Total | #N/A
| Measure | (All)
|  | Jan |  | Feb | Mrz | Apr | Mai | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total
| Resources & Contracts | PD Total | EUR Total
| Labor | 2766.8155 | 4526422.3084
Comment | AZ Technology | 2048.878 | 2833818.6402
| 0 | 0 | 297500
| (blank) | 0 | 297500
| CNTR0010544 | 110.4647 | 157099.0619
| Andrea Scotti | 0 | 0
| Wolfgang Elsner | 0 | 0
| Alexander Heinze | 0 | 0
| Thomas Huber | 0 | 0
| Jagoda Matys | 0 | 0
| Markus Schnier | 0 | 0
| Sergej Reißig | 55.0018 | 83266.9815
| Binoj Baburaj | 0 | 0
| IAM Architect (Cygna) | 2.4114 | 3159.8592
| NN india | 0 | 0
| Michael Holder | 0 | 0
| Youssef Dahmouni | 0 | 0
| Nina Kaufmann | 20.9999 | 27517.875
| Viktoryia Nikifaravets | 32.0516 | 43154.3461
| CNTR0010615 | 121.7529 | 173433.2076
| Alexander Heinze | 0 | 0
| Jagoda Matys | 0 | 0
| Srdan Mavrenski | 55.0018 | 83266.9815
| Itai Schwartz | 31.2506 | 42075.8024
| NN india | 0 | 0
| Francois Pernayan | 31.2506 | 42075.8024
| Matt Gibson | 0 | 0
| Christian Bolterauer | 4.25 | 6014.6213
| CNTR0010616 | 68.1618 | 102967.1383
| Alexander Heinze | 0 | 0
| Thomas Huber | 0 | 0
| Reza Memarian | 55.0018 | 83266.9815
| Markus Schnier | 0 | 0
| NN india | 0 | 0
| Youssef Dahmouni | 0 | 0
| Walter Hofer | 0 | 0
| Balasz Razs | 0 | 0
| Ivan Markovic | 13.16 | 19700.1568
| Product SME | 0 | 0
| CNTR0010562 | 5 | 7850
| Thomas Huber | 0 | 0
| Markus Schnier | 0 | 0
| Clemens Friedrich | 5 | 7850
| Gerhard Schneider | 0 | 0
| DGI | 0 | 0
| CNTR0010336 | 152.1775 | 271131.6326
| Thomas Huber | 0 | 0
| Markus Schnier | 0 | 0
| Daniela Betz | 45.9375 | 65010.9849
| Bastian Kastner | 45.25 | 47435.575
| Clemens Friedrich | 0 | 0
| Gerhard Schneider | 3.77 | 7653.1
| Björn Hansen / Markus Feuerstein | 0 | 85551.9727
| Rudresh Subramanian | 20.22 | 30330
| Guelsah Uestelci | 37 | 35150
| CNTR0010335 | 56 | 64575.28
| N.N. | 0 | 0
| Markus Gatter | 56 | 64575.28
| Jakob Schusser | 0 | 0
| Gabriella Nagy | 0 | 0
| N.N. // SME 2 | 0 | 0
| N.N. // Sr. Analyst | 0 | 0
| SR Labs Autobahn | 0 | 0
| OE Effort | 0 | 0
| Ben Brüggen | 0 | 0
| CNTR0010338 | 152.3738 | 157766.1581
| Rene Pferner | 0 | 0
| Thomas Huber | 1 | 2030
| Markus Schnier | 1 | 2030
| N.N. | 0 | 0
| Clemens Friedrich | 15 | 23550
| Gerhard Schneider | 6.03 | 12240.9
| Anna Hartl | 53.8125 | 56411.6437
| Alina Lobova | 55.75 | 46754.18
| Stefan Kösters | 12.2812 | 12874.4344
| Kühnlenz / 2wmedia | 0 | 0
| Natalia Nikitana | 0 | 0
| IT Seal | 0 | 0
| Aishwarya Nangude / Sarabjit Singh | 0 | 0
| Meera Patel | 7.5 | 1875
| CNTR0010333 | 245.5625 | 276810.2324
| Christoph Lenz | 31.625 | 33152.4875
| Thomas Huber | 0 | 0
| Markus Schnier | 0 | 0
| Corinna Koch | 19.375 | 20310.8125
| Vasanthan Dhanasingh | 0 | 0
| Clemens Friedrich | 0 | 0
| Gerhard Schneider | 0 | 0
| Sven Lierzer | 48.875 | 57921.9165
| Tobias Lichtenberg | 12.6875 | 17955.4134
| Stanislav Khotinok | 34.125 | 39350.5613
| Alexander Leonhardt | 56.75 | 65440.1275
| Yuri Nikulin | 23.375 | 26954.4138
| Maria Thanner | 18.75 | 15724.5
| SNOW-Team | 0 | 0
| Splunk Team | 0 | 0
| Ankita Mane | 0 | 0
| Martin Gerlowski | 0 | 0
| Deepak Krishnan | 0 | 0
| K Harikrishnan | 0 | 0
| CNTR0010337 | 19.2596 | 32647.4087
| Placeholder | 0 | 0
| Matthias Kickstein | 0 | 0
| Computacenter | 0 | 0
| Ernst & Young | 19.2596 | 32647.4087
| CNTR0010325 | 29.75 | 16237.5
| Alex Lee | 0 | 0
| Lucas Tscherter | 0 | 0
| Corinna Koch | 0 | 0
| Dhanya Kalathil | 19.75 | 4937.5
| Mark de Vera | 0 | 0
| Balasz Racz | 10 | 11300
| Arunlal Nair | 0 | 0
| Local Infra setup support | 0 | 0
| Local SMEs for AVC, FMO | 0 | 0
| Cabling APAC | 0 | 0
| CNTR0010327 | 20 | 5320
| Thomas Huber | 0 | 0
| Gereon Volker | 0 | 0
| Lucas Tscherter | 0 | 0
| Markus Schnier | 0 | 0
| Thomas Bringewald | 2 | 2260
| Andrei Maslov | 0 | 0
| Patrick Zeitz | 0 | 0
| Armando Diaz | 0 | 0
| Ron Johnson | 0 | 0
| Jithin Varghese | 18 | 3060
| AZ Tech America Labor | 0 | 0
| Service Manager | 0 | 0
| CNTR0010332 | 177.713 | 270824.8831
| Timothy Drost | 51.25 | 56077.4981
| Thomas Huber | 1 | 2030
| Holger Steinlechner | 1.78 | 2011.4
| Lucas Tscherter | 20.42 | 32059.4
| Markus Schnier | 1 | 2030
| Olivier Ma | 0 | 0
| Rebecca Dengl | 0.263 | 297.19
| Andrei Maslov | 5 | 5650
| Racz Balazs | 2 | 2260
| Jimmy Braun | 0 | 0
| Cyarx Siemplify | 95 | 168409.395
| CMDB | 0 | 0
| CNTR0010329 | 97.9983 | 221663.7262
| Thomas Huber | 1 | 2030
| Gereon Volker | 0 | 0
| Lucas Tscherter | 27.79 | 43630.3
| Markus Schnier | 1 | 2030
| Thomas Bringewald | 5 | 5650
| Rebecca Dengl | 0.526 | 594.38
| Felix Hertin | 3.2615 | 5242.0231
| Lukas Thiele | 9.4208 | 5242.0231
| Holger Wache | 25 | 78622.5
| Tobias Martin | 25 | 78622.5
| Deloitte | 0 | 0
| CNTR0010709 | 11 | 16796.845
| Thomas Huber | 1 | 2030
| Lucas Tscherter | 0 | 0
| Markus Schnier | 1 | 2030
| Krunoslav Rukavina | 9 | 12736.845
| Joachim Steinberger | 0 | 0
| Elastic | 0 | 0
| Proofpoint | 0 | 0
| CNTR0010564 | 513.2647 | 444921.049
| Markus Traumueller | 10 | 11300
| Karim, Hasan | 57 | 59850
| Bojarski, Eduard | 57 | 112122.99
| Kayali, Ismail | 57 | 72645.93
| Stettner, Julia | 57 | 80717.13
| Tulshidas Thamke, Budhesh | 57 | 9120
| Sunderdas, Shilpa | 58 | 9280
| Bönigk, Julian | 10 | 11300
| Sora Mustafa (AUG-OCT only) | 52 | 61880
| Vidya Baskaran Reddy | 57 | 9690
| S, Shibi (partily on IP&G) | 41.2647 | 7014.999
| CNTR0010563 | 109.9746 | 125589.2982
| Günther, Gerhard | 15.1579 | 20463.1579
| Poteat, Jade | 22.9868 | 22986.8421
| Warnholz, Benjamin | 8 | 16000
| Qualys Team (AVM) | 0 | 0
| Uysal, Ismail (Project Manager) | 51.1456 | 51145.614
| Goldschmidt, Andreas (SNOW Principal Architect) | 10.6842 | 14423.6842
| AMC Devops Engineer (Internal) | 0 | 0
| APM Devops Engineer (Internal) | 0 | 0
| EMS Devops Engineer (Internal) | 0 | 0
| Workspace Intelligence Internal – Technical SME | 0 | 0
| SNOW Performance Analytics team | 0 | 0
| SNOW Development Teams | 2 | 570
| Workspace Intelligence Vendor – Technical SME | 0 | 0
| SNOW SAM efforts | 0 | 0
| SNOW CMDB | 0 | 0
| CyNet | 0 | 0
| Security Foundation Team | 0 | 0
| CNTR0010576 | 27.5 | 35432.54
| Marc Bochtler | 18 | 25473.69
| Alexander Heinze | 0 | 0
| Tobias Butz | 0 | 0
| NN | 0 | 0
| NN india | 0 | 0
| Yury Nikolin | 9.5 | 9958.85
| Thomas Felder | 0 | 0
| CNTR0010334 | 130.125 | 153138.2055
| Martin Schurm | 27 | 42102.3487
| Tobias Krichel | 62.875 | 74513.3568
| Thomas Huber | 1 | 2030
| Markus Schnier | 1 | 2030
| Dan Read | 0 | 0
| N.N. / Support Dan | 0 | 0
| Ankur Tomar | 0 | 0
| Naman Agrawal | 21.25 | 5312.5
| Clemens Friedrich | 16 | 25120
| Gerhard Schneider | 1 | 2030
| OAM302 | 0 | 0
| Alexander Heinze | 0 | 0
| Daming Yang | 0 | 0
| Manoj Selvakumar | 0 | 0
| David Barton | 0 | 0
| Raja Rajcic | 0 | 0
| Lawrence Tengan | 0 | 0
| Travis Chun | 0 | 0
| Johannes Bross | 0 | 0
| Tuan Minh Nguyen | 0 | 0
| Tobias Tischler | 0 | 0
| Djamel Tazerout | 0 | 0
| Dirk Addicks | 0 | 0
| Forgerock Licence | 0 | 0
| CNTR0010589 | 0 | 0
| Placeholder | 0 | 0
| OAM299 | 0 | 0
| Placeholder | 0 | 0
| CNTR0010618 | 0.79973 | 2114.4735
| Birgit Jarosch | 0.79973 | 2114.4735
| Wolfgang Elsner | 0 | 0
| Alexander Heinze | 0 | 0
| Jagoda Matys | 0 | 0
| N.N. | 0 | 0
| Mitja Ledowski | 0 | 0
| Ingmar Janßen-Holldiek | 0 | 0
| Michael Holder | 0 | 0
| Sinoop K S | 0 | 0
| J. Thomas | 0 | 0
| Madalina Paslaru | 0 | 0
| Daniel Ettenhuber | 0 | 0
| OAM289 | 0 | 0
| Placeholder | 0 | 0
| CNTR0010617 | 0 | 0
| (blank) | 0 | 0
| Alexander Heinze | 0 | 0
| Christine Schlüter | 0 | 0
| Günter Sanktjohanser | 0 | 0
| Metafinanz | 717.9375 | 838906
| 21 0427 | 162.5625 | 155742.25
| Julian Steinfeld | 53 | 58936
| Manuel Hahn | 43.5312 | 42660.625
| Matthias Müller | 66.0312 | 54145.625
| 21 1068 | 107.1875 | 140290.625
| Jonathan Reynolds | 16.75 | 16750
| Samuel Hurst | 38.9688 | 52607.8125
| Kris Harms | 39 | 56550
| Nora von Schenckendorff | 5.4688 | 7382.8125
| Frank Markussen | 1.375 | 1375
| Anette Hettenkofer | 0.125 | 125
| Julia Netesa | 5.5 | 5500
| 21 1079 | 81.1875 | 94356.25
| George Dietrichsbruckner | 37.625 | 50793.75
| Jade Poteat | 7.625 | 7625
| Nadine Butzhammer | 0.3125 | 312.5
| Daniel Wörner | 21.5 | 21500
| Sanat Gautam | 14.125 | 14125
| 21 1037 | 179.6875 | 209831.25
| Gerhard Günther | 31.5 | 42525
| Rasa Rintallo | 43.4375 | 43437.5
| Stefan Köstenbauer | 1.125 | 1518.75
| Victor Peters | 3.8438 | 3843.75
| Michael Habel | 53.5 | 72225
| Maximilian Schellenberger | 3.2812 | 3281.25
| Sona Latifyan | 43 | 43000
| 21 1040 | 6.5 | 6500
| Jade Poteat | 6.5 | 6500
| 21 1133 | 0 | 0
| Krunoslav Rukavina | 0 | 0
| 21 1063 | 135.3125 | 170760.625
| Marc Bochtler | 42.125 | 56868.75
| Thorsten Deckers | 21.0625 | 33068.125
| Robert Reti | 17.875 | 28063.75
| Claudio Cangiotti | 13 | 10010
| Yury Nikulin | 26.25 | 26250
| Eldho George | 15 | 16500
| 21 1059 | 45.5 | 61425
| Thomas Thuspaß | 45.5 | 61425
| other | 0 | 24570
| 0 | 0 | 24570
| (blank) | 0 | 24570
| NCC Group GmbH | 0 | 363140.4
| 2410164170 | 0 | 363140.4
| (blank) | 0 | 363140.4
| Osborne Clark | 0 | 20659.69
| TID0001510089 | 0 | 20659.69
| (blank) | 0 | 20659.69
| Virtual Clarity Ltd | 0 | 149488
| 2410164371 | 0 | 149488
| (blank) | 0 | 149488
| Softwaregilde | 0 | 121975
| 2410159840 | 0 | 121975
| (blank) | 0 | 121975
| Horvath & Partner | 0 | 44625
| 2410160374 | 0 | 44625
| (blank) | 0 | 44625
| Ernst & Young | 0 | 98002.0781
| 2410162165 | 0 | 98002.0781
| (blank) | 0 | 98002.0781
| SRLabs | 0 | 8925
| PR964131 | 0 | 8925
| (blank) | 0 | 8925
| DCSO | 0 | 0
| 0 | 0 | 0
| (blank) | 0 | 0
| SecAttack | 0 | 22312.5
| 0 | 0 | 22312.5
| (blank) | 0 | 22312.5
| (blank) | 2767.8155 | 3482475.2593
| (blank) | 2767.8155 | 3482475.2593
| (blank) | 2767.8155 | 3482475.2593
| (blank) | 2767.8155 | 3482475.2593
| non-Labor | 1 | 210543.769
| AZ Technology | 1 | 107250.619
| CNTR0010616 | 0 | 0
| Licence costs | 0 | 0
| CNTR0010338 | 0 | 32401.999
| Splunk Licenses + Server | 0 | 0
| ZeroFox Licenses | 0 | 32401.999
| CNTR0010333 | 0 | 0
| Splunk Licenses + Server | 0 | 0
| CNTR0010325 | 0 | 0
| HW / infrastructure | 0 | 0
| CNTR0010327 | 0 | 0
| Local SMEs for AVC, FMO | 0 | 0
| AZ Tech America HW | 0 | 0
| CNTR0010332 | 1 | 74848.62
| Cyarx Siemplify | 1 | 74848.62
| CNTR0010329 | 0 | 0
| AWS / Azure cloud | 0 | 0
| CNTR0010618 | 0 | 0
| HW | 0 | 0
| other | 0 | 103293.15
| 0 | 0 | 103293.15
| (blank) | 0 | 103293.15
| Sum | 5535.6311 | 8219441.3367

## M75 (hidden)
M75
Measure Lead: Sven Herrmann
Pillar Lead: Carsten Scholz
Duration: 01.01.2017-31.12.2018
Planned Total | #N/A
Approved Total | #N/A
Spent Labor | #N/A
Spent non-Labor | #N/A
Spent Total | #N/A
Forecast Total | #N/A
| Measure | (All)
|  | Jan |  | Feb | Mrz | Apr | Mai | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total
| Resources & Contracts | PD Total | EUR Total
| Labor | 2766.8155 | 4526422.3084
Comment | AZ Technology | 2048.878 | 2833818.6402
| 0 | 0 | 297500
| (blank) | 0 | 297500
| CNTR0010544 | 110.4647 | 157099.0619
| Andrea Scotti | 0 | 0
| Wolfgang Elsner | 0 | 0
| Alexander Heinze | 0 | 0
| Thomas Huber | 0 | 0
| Jagoda Matys | 0 | 0
| Markus Schnier | 0 | 0
| Sergej Reißig | 55.0018 | 83266.9815
| Binoj Baburaj | 0 | 0
| IAM Architect (Cygna) | 2.4114 | 3159.8592
| NN india | 0 | 0
| Michael Holder | 0 | 0
| Youssef Dahmouni | 0 | 0
| Nina Kaufmann | 20.9999 | 27517.875
| Viktoryia Nikifaravets | 32.0516 | 43154.3461
| CNTR0010615 | 121.7529 | 173433.2076
| Alexander Heinze | 0 | 0
| Jagoda Matys | 0 | 0
| Srdan Mavrenski | 55.0018 | 83266.9815
| Itai Schwartz | 31.2506 | 42075.8024
| NN india | 0 | 0
| Francois Pernayan | 31.2506 | 42075.8024
| Matt Gibson | 0 | 0
| Christian Bolterauer | 4.25 | 6014.6213
| CNTR0010616 | 68.1618 | 102967.1383
| Alexander Heinze | 0 | 0
| Thomas Huber | 0 | 0
| Reza Memarian | 55.0018 | 83266.9815
| Markus Schnier | 0 | 0
| NN india | 0 | 0
| Youssef Dahmouni | 0 | 0
| Walter Hofer | 0 | 0
| Balasz Razs | 0 | 0
| Ivan Markovic | 13.16 | 19700.1568
| Product SME | 0 | 0
| CNTR0010562 | 5 | 7850
| Thomas Huber | 0 | 0
| Markus Schnier | 0 | 0
| Clemens Friedrich | 5 | 7850
| Gerhard Schneider | 0 | 0
| DGI | 0 | 0
| CNTR0010336 | 152.1775 | 271131.6326
| Thomas Huber | 0 | 0
| Markus Schnier | 0 | 0
| Daniela Betz | 45.9375 | 65010.9849
| Bastian Kastner | 45.25 | 47435.575
| Clemens Friedrich | 0 | 0
| Gerhard Schneider | 3.77 | 7653.1
| Björn Hansen / Markus Feuerstein | 0 | 85551.9727
| Rudresh Subramanian | 20.22 | 30330
| Guelsah Uestelci | 37 | 35150
| CNTR0010335 | 56 | 64575.28
| N.N. | 0 | 0
| Markus Gatter | 56 | 64575.28
| Jakob Schusser | 0 | 0
| Gabriella Nagy | 0 | 0
| N.N. // SME 2 | 0 | 0
| N.N. // Sr. Analyst | 0 | 0
| SR Labs Autobahn | 0 | 0
| OE Effort | 0 | 0
| Ben Brüggen | 0 | 0
| CNTR0010338 | 152.3738 | 157766.1581
| Rene Pferner | 0 | 0
| Thomas Huber | 1 | 2030
| Markus Schnier | 1 | 2030
| N.N. | 0 | 0
| Clemens Friedrich | 15 | 23550
| Gerhard Schneider | 6.03 | 12240.9
| Anna Hartl | 53.8125 | 56411.6437
| Alina Lobova | 55.75 | 46754.18
| Stefan Kösters | 12.2812 | 12874.4344
| Kühnlenz / 2wmedia | 0 | 0
| Natalia Nikitana | 0 | 0
| IT Seal | 0 | 0
| Aishwarya Nangude / Sarabjit Singh | 0 | 0
| Meera Patel | 7.5 | 1875
| CNTR0010333 | 245.5625 | 276810.2324
| Christoph Lenz | 31.625 | 33152.4875
| Thomas Huber | 0 | 0
| Markus Schnier | 0 | 0
| Corinna Koch | 19.375 | 20310.8125
| Vasanthan Dhanasingh | 0 | 0
| Clemens Friedrich | 0 | 0
| Gerhard Schneider | 0 | 0
| Sven Lierzer | 48.875 | 57921.9165
| Tobias Lichtenberg | 12.6875 | 17955.4134
| Stanislav Khotinok | 34.125 | 39350.5613
| Alexander Leonhardt | 56.75 | 65440.1275
| Yuri Nikulin | 23.375 | 26954.4138
| Maria Thanner | 18.75 | 15724.5
| SNOW-Team | 0 | 0
| Splunk Team | 0 | 0
| Ankita Mane | 0 | 0
| Martin Gerlowski | 0 | 0
| Deepak Krishnan | 0 | 0
| K Harikrishnan | 0 | 0
| CNTR0010337 | 19.2596 | 32647.4087
| Placeholder | 0 | 0
| Matthias Kickstein | 0 | 0
| Computacenter | 0 | 0
| Ernst & Young | 19.2596 | 32647.4087
| CNTR0010325 | 29.75 | 16237.5
| Alex Lee | 0 | 0
| Lucas Tscherter | 0 | 0
| Corinna Koch | 0 | 0
| Dhanya Kalathil | 19.75 | 4937.5
| Mark de Vera | 0 | 0
| Balasz Racz | 10 | 11300
| Arunlal Nair | 0 | 0
| Local Infra setup support | 0 | 0
| Local SMEs for AVC, FMO | 0 | 0
| Cabling APAC | 0 | 0
| CNTR0010327 | 20 | 5320
| Thomas Huber | 0 | 0
| Gereon Volker | 0 | 0
| Lucas Tscherter | 0 | 0
| Markus Schnier | 0 | 0
| Thomas Bringewald | 2 | 2260
| Andrei Maslov | 0 | 0
| Patrick Zeitz | 0 | 0
| Armando Diaz | 0 | 0
| Ron Johnson | 0 | 0
| Jithin Varghese | 18 | 3060
| AZ Tech America Labor | 0 | 0
| Service Manager | 0 | 0
| CNTR0010332 | 177.713 | 270824.8831
| Timothy Drost | 51.25 | 56077.4981
| Thomas Huber | 1 | 2030
| Holger Steinlechner | 1.78 | 2011.4
| Lucas Tscherter | 20.42 | 32059.4
| Markus Schnier | 1 | 2030
| Olivier Ma | 0 | 0
| Rebecca Dengl | 0.263 | 297.19
| Andrei Maslov | 5 | 5650
| Racz Balazs | 2 | 2260
| Jimmy Braun | 0 | 0
| Cyarx Siemplify | 95 | 168409.395
| CMDB | 0 | 0
| CNTR0010329 | 97.9983 | 221663.7262
| Thomas Huber | 1 | 2030
| Gereon Volker | 0 | 0
| Lucas Tscherter | 27.79 | 43630.3
| Markus Schnier | 1 | 2030
| Thomas Bringewald | 5 | 5650
| Rebecca Dengl | 0.526 | 594.38
| Felix Hertin | 3.2615 | 5242.0231
| Lukas Thiele | 9.4208 | 5242.0231
| Holger Wache | 25 | 78622.5
| Tobias Martin | 25 | 78622.5
| Deloitte | 0 | 0
| CNTR0010709 | 11 | 16796.845
| Thomas Huber | 1 | 2030
| Lucas Tscherter | 0 | 0
| Markus Schnier | 1 | 2030
| Krunoslav Rukavina | 9 | 12736.845
| Joachim Steinberger | 0 | 0
| Elastic | 0 | 0
| Proofpoint | 0 | 0
| CNTR0010564 | 513.2647 | 444921.049
| Markus Traumueller | 10 | 11300
| Karim, Hasan | 57 | 59850
| Bojarski, Eduard | 57 | 112122.99
| Kayali, Ismail | 57 | 72645.93
| Stettner, Julia | 57 | 80717.13
| Tulshidas Thamke, Budhesh | 57 | 9120
| Sunderdas, Shilpa | 58 | 9280
| Bönigk, Julian | 10 | 11300
| Sora Mustafa (AUG-OCT only) | 52 | 61880
| Vidya Baskaran Reddy | 57 | 9690
| S, Shibi (partily on IP&G) | 41.2647 | 7014.999
| CNTR0010563 | 109.9746 | 125589.2982
| Günther, Gerhard | 15.1579 | 20463.1579
| Poteat, Jade | 22.9868 | 22986.8421
| Warnholz, Benjamin | 8 | 16000
| Qualys Team (AVM) | 0 | 0
| Uysal, Ismail (Project Manager) | 51.1456 | 51145.614
| Goldschmidt, Andreas (SNOW Principal Architect) | 10.6842 | 14423.6842
| AMC Devops Engineer (Internal) | 0 | 0
| APM Devops Engineer (Internal) | 0 | 0
| EMS Devops Engineer (Internal) | 0 | 0
| Workspace Intelligence Internal – Technical SME | 0 | 0
| SNOW Performance Analytics team | 0 | 0
| SNOW Development Teams | 2 | 570
| Workspace Intelligence Vendor – Technical SME | 0 | 0
| SNOW SAM efforts | 0 | 0
| SNOW CMDB | 0 | 0
| CyNet | 0 | 0
| Security Foundation Team | 0 | 0
| CNTR0010576 | 27.5 | 35432.54
| Marc Bochtler | 18 | 25473.69
| Alexander Heinze | 0 | 0
| Tobias Butz | 0 | 0
| NN | 0 | 0
| NN india | 0 | 0
| Yury Nikolin | 9.5 | 9958.85
| Thomas Felder | 0 | 0
| CNTR0010334 | 130.125 | 153138.2055
| Martin Schurm | 27 | 42102.3487
| Tobias Krichel | 62.875 | 74513.3568
| Thomas Huber | 1 | 2030
| Markus Schnier | 1 | 2030
| Dan Read | 0 | 0
| N.N. / Support Dan | 0 | 0
| Ankur Tomar | 0 | 0
| Naman Agrawal | 21.25 | 5312.5
| Clemens Friedrich | 16 | 25120
| Gerhard Schneider | 1 | 2030
| OAM302 | 0 | 0
| Alexander Heinze | 0 | 0
| Daming Yang | 0 | 0
| Manoj Selvakumar | 0 | 0
| David Barton | 0 | 0
| Raja Rajcic | 0 | 0
| Lawrence Tengan | 0 | 0
| Travis Chun | 0 | 0
| Johannes Bross | 0 | 0
| Tuan Minh Nguyen | 0 | 0
| Tobias Tischler | 0 | 0
| Djamel Tazerout | 0 | 0
| Dirk Addicks | 0 | 0
| Forgerock Licence | 0 | 0
| CNTR0010589 | 0 | 0
| Placeholder | 0 | 0
| OAM299 | 0 | 0
| Placeholder | 0 | 0
| CNTR0010618 | 0.79973 | 2114.4735
| Birgit Jarosch | 0.79973 | 2114.4735
| Wolfgang Elsner | 0 | 0
| Alexander Heinze | 0 | 0
| Jagoda Matys | 0 | 0
| N.N. | 0 | 0
| Mitja Ledowski | 0 | 0
| Ingmar Janßen-Holldiek | 0 | 0
| Michael Holder | 0 | 0
| Sinoop K S | 0 | 0
| J. Thomas | 0 | 0
| Madalina Paslaru | 0 | 0
| Daniel Ettenhuber | 0 | 0
| OAM289 | 0 | 0
| Placeholder | 0 | 0
| CNTR0010617 | 0 | 0
| (blank) | 0 | 0
| Alexander Heinze | 0 | 0
| Christine Schlüter | 0 | 0
| Günter Sanktjohanser | 0 | 0
| Metafinanz | 717.9375 | 838906
| 21 0427 | 162.5625 | 155742.25
| Julian Steinfeld | 53 | 58936
| Manuel Hahn | 43.5312 | 42660.625
| Matthias Müller | 66.0312 | 54145.625
| 21 1068 | 107.1875 | 140290.625
| Jonathan Reynolds | 16.75 | 16750
| Samuel Hurst | 38.9688 | 52607.8125
| Kris Harms | 39 | 56550
| Nora von Schenckendorff | 5.4688 | 7382.8125
| Frank Markussen | 1.375 | 1375
| Anette Hettenkofer | 0.125 | 125
| Julia Netesa | 5.5 | 5500
| 21 1079 | 81.1875 | 94356.25
| George Dietrichsbruckner | 37.625 | 50793.75
| Jade Poteat | 7.625 | 7625
| Nadine Butzhammer | 0.3125 | 312.5
| Daniel Wörner | 21.5 | 21500
| Sanat Gautam | 14.125 | 14125
| 21 1037 | 179.6875 | 209831.25
| Gerhard Günther | 31.5 | 42525
| Rasa Rintallo | 43.4375 | 43437.5
| Stefan Köstenbauer | 1.125 | 1518.75
| Victor Peters | 3.8438 | 3843.75
| Michael Habel | 53.5 | 72225
| Maximilian Schellenberger | 3.2812 | 3281.25
| Sona Latifyan | 43 | 43000
| 21 1040 | 6.5 | 6500
| Jade Poteat | 6.5 | 6500
| 21 1133 | 0 | 0
| Krunoslav Rukavina | 0 | 0
| 21 1063 | 135.3125 | 170760.625
| Marc Bochtler | 42.125 | 56868.75
| Thorsten Deckers | 21.0625 | 33068.125
| Robert Reti | 17.875 | 28063.75
| Claudio Cangiotti | 13 | 10010
| Yury Nikulin | 26.25 | 26250
| Eldho George | 15 | 16500
| 21 1059 | 45.5 | 61425
| Thomas Thuspaß | 45.5 | 61425
| other | 0 | 24570
| 0 | 0 | 24570
| (blank) | 0 | 24570
| NCC Group GmbH | 0 | 363140.4
| 2410164170 | 0 | 363140.4
| (blank) | 0 | 363140.4
| Osborne Clark | 0 | 20659.69
| TID0001510089 | 0 | 20659.69
| (blank) | 0 | 20659.69
| Virtual Clarity Ltd | 0 | 149488
| 2410164371 | 0 | 149488
| (blank) | 0 | 149488
| Softwaregilde | 0 | 121975
| 2410159840 | 0 | 121975
| (blank) | 0 | 121975
| Horvath & Partner | 0 | 44625
| 2410160374 | 0 | 44625
| (blank) | 0 | 44625
| Ernst & Young | 0 | 98002.0781
| 2410162165 | 0 | 98002.0781
| (blank) | 0 | 98002.0781
| SRLabs | 0 | 8925
| PR964131 | 0 | 8925
| (blank) | 0 | 8925
| DCSO | 0 | 0
| 0 | 0 | 0
| (blank) | 0 | 0
| SecAttack | 0 | 22312.5
| 0 | 0 | 22312.5
| (blank) | 0 | 22312.5
| (blank) | 2767.8155 | 3482475.2593
| (blank) | 2767.8155 | 3482475.2593
| (blank) | 2767.8155 | 3482475.2593
| (blank) | 2767.8155 | 3482475.2593
| non-Labor | 1 | 210543.769
| AZ Technology | 1 | 107250.619
| CNTR0010616 | 0 | 0
| Licence costs | 0 | 0
| CNTR0010338 | 0 | 32401.999
| Splunk Licenses + Server | 0 | 0
| ZeroFox Licenses | 0 | 32401.999
| CNTR0010333 | 0 | 0
| Splunk Licenses + Server | 0 | 0
| CNTR0010325 | 0 | 0
| HW / infrastructure | 0 | 0
| CNTR0010327 | 0 | 0
| Local SMEs for AVC, FMO | 0 | 0
| AZ Tech America HW | 0 | 0
| CNTR0010332 | 1 | 74848.62
| Cyarx Siemplify | 1 | 74848.62
| CNTR0010329 | 0 | 0
| AWS / Azure cloud | 0 | 0
| CNTR0010618 | 0 | 0
| HW | 0 | 0
| other | 0 | 103293.15
| 0 | 0 | 103293.15
| (blank) | 0 | 103293.15
| Sum | 5535.6311 | 8219441.3367

## M12 (hidden)
M12
Measure Lead: Oliver Sgoff
Pillar Lead: Carsten Scholz
Duration: 01.10.2016-31.12.2018
Planned Total | #N/A
Approved Total | #N/A
Spent Labor | #N/A
Spent non-Labor | #N/A
Spent Total | #N/A
Forecast Total | #N/A
| Measure | (All)
|  | Jan |  | Feb | Mrz | Apr | Mai | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total
| Resources & Contracts | PD Total | EUR Total
| Labor | 2766.8155 | 4526422.3084
Comment | AZ Technology | 2048.878 | 2833818.6402
| 0 | 0 | 297500
| (blank) | 0 | 297500
| CNTR0010544 | 110.4647 | 157099.0619
| Andrea Scotti | 0 | 0
| Wolfgang Elsner | 0 | 0
| Alexander Heinze | 0 | 0
| Thomas Huber | 0 | 0
| Jagoda Matys | 0 | 0
| Markus Schnier | 0 | 0
| Sergej Reißig | 55.0018 | 83266.9815
| Binoj Baburaj | 0 | 0
| IAM Architect (Cygna) | 2.4114 | 3159.8592
| NN india | 0 | 0
| Michael Holder | 0 | 0
| Youssef Dahmouni | 0 | 0
| Nina Kaufmann | 20.9999 | 27517.875
| Viktoryia Nikifaravets | 32.0516 | 43154.3461
| CNTR0010615 | 121.7529 | 173433.2076
| Alexander Heinze | 0 | 0
| Jagoda Matys | 0 | 0
| Srdan Mavrenski | 55.0018 | 83266.9815
| Itai Schwartz | 31.2506 | 42075.8024
| NN india | 0 | 0
| Francois Pernayan | 31.2506 | 42075.8024
| Matt Gibson | 0 | 0
| Christian Bolterauer | 4.25 | 6014.6213
| CNTR0010616 | 68.1618 | 102967.1383
| Alexander Heinze | 0 | 0
| Thomas Huber | 0 | 0
| Reza Memarian | 55.0018 | 83266.9815
| Markus Schnier | 0 | 0
| NN india | 0 | 0
| Youssef Dahmouni | 0 | 0
| Walter Hofer | 0 | 0
| Balasz Razs | 0 | 0
| Ivan Markovic | 13.16 | 19700.1568
| Product SME | 0 | 0
| CNTR0010562 | 5 | 7850
| Thomas Huber | 0 | 0
| Markus Schnier | 0 | 0
| Clemens Friedrich | 5 | 7850
| Gerhard Schneider | 0 | 0
| DGI | 0 | 0
| CNTR0010336 | 152.1775 | 271131.6326
| Thomas Huber | 0 | 0
| Markus Schnier | 0 | 0
| Daniela Betz | 45.9375 | 65010.9849
| Bastian Kastner | 45.25 | 47435.575
| Clemens Friedrich | 0 | 0
| Gerhard Schneider | 3.77 | 7653.1
| Björn Hansen / Markus Feuerstein | 0 | 85551.9727
| Rudresh Subramanian | 20.22 | 30330
| Guelsah Uestelci | 37 | 35150
| CNTR0010335 | 56 | 64575.28
| N.N. | 0 | 0
| Markus Gatter | 56 | 64575.28
| Jakob Schusser | 0 | 0
| Gabriella Nagy | 0 | 0
| N.N. // SME 2 | 0 | 0
| N.N. // Sr. Analyst | 0 | 0
| SR Labs Autobahn | 0 | 0
| OE Effort | 0 | 0
| Ben Brüggen | 0 | 0
| CNTR0010338 | 152.3738 | 157766.1581
| Rene Pferner | 0 | 0
| Thomas Huber | 1 | 2030
| Markus Schnier | 1 | 2030
| N.N. | 0 | 0
| Clemens Friedrich | 15 | 23550
| Gerhard Schneider | 6.03 | 12240.9
| Anna Hartl | 53.8125 | 56411.6437
| Alina Lobova | 55.75 | 46754.18
| Stefan Kösters | 12.2812 | 12874.4344
| Kühnlenz / 2wmedia | 0 | 0
| Natalia Nikitana | 0 | 0
| IT Seal | 0 | 0
| Aishwarya Nangude / Sarabjit Singh | 0 | 0
| Meera Patel | 7.5 | 1875
| CNTR0010333 | 245.5625 | 276810.2324
| Christoph Lenz | 31.625 | 33152.4875
| Thomas Huber | 0 | 0
| Markus Schnier | 0 | 0
| Corinna Koch | 19.375 | 20310.8125
| Vasanthan Dhanasingh | 0 | 0
| Clemens Friedrich | 0 | 0
| Gerhard Schneider | 0 | 0
| Sven Lierzer | 48.875 | 57921.9165
| Tobias Lichtenberg | 12.6875 | 17955.4134
| Stanislav Khotinok | 34.125 | 39350.5613
| Alexander Leonhardt | 56.75 | 65440.1275
| Yuri Nikulin | 23.375 | 26954.4138
| Maria Thanner | 18.75 | 15724.5
| SNOW-Team | 0 | 0
| Splunk Team | 0 | 0
| Ankita Mane | 0 | 0
| Martin Gerlowski | 0 | 0
| Deepak Krishnan | 0 | 0
| K Harikrishnan | 0 | 0
| CNTR0010337 | 19.2596 | 32647.4087
| Placeholder | 0 | 0
| Matthias Kickstein | 0 | 0
| Computacenter | 0 | 0
| Ernst & Young | 19.2596 | 32647.4087
| CNTR0010325 | 29.75 | 16237.5
| Alex Lee | 0 | 0
| Lucas Tscherter | 0 | 0
| Corinna Koch | 0 | 0
| Dhanya Kalathil | 19.75 | 4937.5
| Mark de Vera | 0 | 0
| Balasz Racz | 10 | 11300
| Arunlal Nair | 0 | 0
| Local Infra setup support | 0 | 0
| Local SMEs for AVC, FMO | 0 | 0
| Cabling APAC | 0 | 0
| CNTR0010327 | 20 | 5320
| Thomas Huber | 0 | 0
| Gereon Volker | 0 | 0
| Lucas Tscherter | 0 | 0
| Markus Schnier | 0 | 0
| Thomas Bringewald | 2 | 2260
| Andrei Maslov | 0 | 0
| Patrick Zeitz | 0 | 0
| Armando Diaz | 0 | 0
| Ron Johnson | 0 | 0
| Jithin Varghese | 18 | 3060
| AZ Tech America Labor | 0 | 0
| Service Manager | 0 | 0
| CNTR0010332 | 177.713 | 270824.8831
| Timothy Drost | 51.25 | 56077.4981
| Thomas Huber | 1 | 2030
| Holger Steinlechner | 1.78 | 2011.4
| Lucas Tscherter | 20.42 | 32059.4
| Markus Schnier | 1 | 2030
| Olivier Ma | 0 | 0
| Rebecca Dengl | 0.263 | 297.19
| Andrei Maslov | 5 | 5650
| Racz Balazs | 2 | 2260
| Jimmy Braun | 0 | 0
| Cyarx Siemplify | 95 | 168409.395
| CMDB | 0 | 0
| CNTR0010329 | 97.9983 | 221663.7262
| Thomas Huber | 1 | 2030
| Gereon Volker | 0 | 0
| Lucas Tscherter | 27.79 | 43630.3
| Markus Schnier | 1 | 2030
| Thomas Bringewald | 5 | 5650
| Rebecca Dengl | 0.526 | 594.38
| Felix Hertin | 3.2615 | 5242.0231
| Lukas Thiele | 9.4208 | 5242.0231
| Holger Wache | 25 | 78622.5
| Tobias Martin | 25 | 78622.5
| Deloitte | 0 | 0
| CNTR0010709 | 11 | 16796.845
| Thomas Huber | 1 | 2030
| Lucas Tscherter | 0 | 0
| Markus Schnier | 1 | 2030
| Krunoslav Rukavina | 9 | 12736.845
| Joachim Steinberger | 0 | 0
| Elastic | 0 | 0
| Proofpoint | 0 | 0
| CNTR0010564 | 513.2647 | 444921.049
| Markus Traumueller | 10 | 11300
| Karim, Hasan | 57 | 59850
| Bojarski, Eduard | 57 | 112122.99
| Kayali, Ismail | 57 | 72645.93
| Stettner, Julia | 57 | 80717.13
| Tulshidas Thamke, Budhesh | 57 | 9120
| Sunderdas, Shilpa | 58 | 9280
| Bönigk, Julian | 10 | 11300
| Sora Mustafa (AUG-OCT only) | 52 | 61880
| Vidya Baskaran Reddy | 57 | 9690
| S, Shibi (partily on IP&G) | 41.2647 | 7014.999
| CNTR0010563 | 109.9746 | 125589.2982
| Günther, Gerhard | 15.1579 | 20463.1579
| Poteat, Jade | 22.9868 | 22986.8421
| Warnholz, Benjamin | 8 | 16000
| Qualys Team (AVM) | 0 | 0
| Uysal, Ismail (Project Manager) | 51.1456 | 51145.614
| Goldschmidt, Andreas (SNOW Principal Architect) | 10.6842 | 14423.6842
| AMC Devops Engineer (Internal) | 0 | 0
| APM Devops Engineer (Internal) | 0 | 0
| EMS Devops Engineer (Internal) | 0 | 0
| Workspace Intelligence Internal – Technical SME | 0 | 0
| SNOW Performance Analytics team | 0 | 0
| SNOW Development Teams | 2 | 570
| Workspace Intelligence Vendor – Technical SME | 0 | 0
| SNOW SAM efforts | 0 | 0
| SNOW CMDB | 0 | 0
| CyNet | 0 | 0
| Security Foundation Team | 0 | 0
| CNTR0010576 | 27.5 | 35432.54
| Marc Bochtler | 18 | 25473.69
| Alexander Heinze | 0 | 0
| Tobias Butz | 0 | 0
| NN | 0 | 0
| NN india | 0 | 0
| Yury Nikolin | 9.5 | 9958.85
| Thomas Felder | 0 | 0
| CNTR0010334 | 130.125 | 153138.2055
| Martin Schurm | 27 | 42102.3487
| Tobias Krichel | 62.875 | 74513.3568
| Thomas Huber | 1 | 2030
| Markus Schnier | 1 | 2030
| Dan Read | 0 | 0
| N.N. / Support Dan | 0 | 0
| Ankur Tomar | 0 | 0
| Naman Agrawal | 21.25 | 5312.5
| Clemens Friedrich | 16 | 25120
| Gerhard Schneider | 1 | 2030
| OAM302 | 0 | 0
| Alexander Heinze | 0 | 0
| Daming Yang | 0 | 0
| Manoj Selvakumar | 0 | 0
| David Barton | 0 | 0
| Raja Rajcic | 0 | 0
| Lawrence Tengan | 0 | 0
| Travis Chun | 0 | 0
| Johannes Bross | 0 | 0
| Tuan Minh Nguyen | 0 | 0
| Tobias Tischler | 0 | 0
| Djamel Tazerout | 0 | 0
| Dirk Addicks | 0 | 0
| Forgerock Licence | 0 | 0
| CNTR0010589 | 0 | 0
| Placeholder | 0 | 0
| OAM299 | 0 | 0
| Placeholder | 0 | 0
| CNTR0010618 | 0.79973 | 2114.4735
| Birgit Jarosch | 0.79973 | 2114.4735
| Wolfgang Elsner | 0 | 0
| Alexander Heinze | 0 | 0
| Jagoda Matys | 0 | 0
| N.N. | 0 | 0
| Mitja Ledowski | 0 | 0
| Ingmar Janßen-Holldiek | 0 | 0
| Michael Holder | 0 | 0
| Sinoop K S | 0 | 0
| J. Thomas | 0 | 0
| Madalina Paslaru | 0 | 0
| Daniel Ettenhuber | 0 | 0
| OAM289 | 0 | 0
| Placeholder | 0 | 0
| CNTR0010617 | 0 | 0
| (blank) | 0 | 0
| Alexander Heinze | 0 | 0
| Christine Schlüter | 0 | 0
| Günter Sanktjohanser | 0 | 0
| Metafinanz | 717.9375 | 838906
| 21 0427 | 162.5625 | 155742.25
| Julian Steinfeld | 53 | 58936
| Manuel Hahn | 43.5312 | 42660.625
| Matthias Müller | 66.0312 | 54145.625
| 21 1068 | 107.1875 | 140290.625
| Jonathan Reynolds | 16.75 | 16750
| Samuel Hurst | 38.9688 | 52607.8125
| Kris Harms | 39 | 56550
| Nora von Schenckendorff | 5.4688 | 7382.8125
| Frank Markussen | 1.375 | 1375
| Anette Hettenkofer | 0.125 | 125
| Julia Netesa | 5.5 | 5500
| 21 1079 | 81.1875 | 94356.25
| George Dietrichsbruckner | 37.625 | 50793.75
| Jade Poteat | 7.625 | 7625
| Nadine Butzhammer | 0.3125 | 312.5
| Daniel Wörner | 21.5 | 21500
| Sanat Gautam | 14.125 | 14125
| 21 1037 | 179.6875 | 209831.25
| Gerhard Günther | 31.5 | 42525
| Rasa Rintallo | 43.4375 | 43437.5
| Stefan Köstenbauer | 1.125 | 1518.75
| Victor Peters | 3.8438 | 3843.75
| Michael Habel | 53.5 | 72225
| Maximilian Schellenberger | 3.2812 | 3281.25
| Sona Latifyan | 43 | 43000
| 21 1040 | 6.5 | 6500
| Jade Poteat | 6.5 | 6500
| 21 1133 | 0 | 0
| Krunoslav Rukavina | 0 | 0
| 21 1063 | 135.3125 | 170760.625
| Marc Bochtler | 42.125 | 56868.75
| Thorsten Deckers | 21.0625 | 33068.125
| Robert Reti | 17.875 | 28063.75
| Claudio Cangiotti | 13 | 10010
| Yury Nikulin | 26.25 | 26250
| Eldho George | 15 | 16500
| 21 1059 | 45.5 | 61425
| Thomas Thuspaß | 45.5 | 61425
| other | 0 | 24570
| 0 | 0 | 24570
| (blank) | 0 | 24570
| NCC Group GmbH | 0 | 363140.4
| 2410164170 | 0 | 363140.4
| (blank) | 0 | 363140.4
| Osborne Clark | 0 | 20659.69
| TID0001510089 | 0 | 20659.69
| (blank) | 0 | 20659.69
| Virtual Clarity Ltd | 0 | 149488
| 2410164371 | 0 | 149488
| (blank) | 0 | 149488
| Softwaregilde | 0 | 121975
| 2410159840 | 0 | 121975
| (blank) | 0 | 121975
| Horvath & Partner | 0 | 44625
| 2410160374 | 0 | 44625
| (blank) | 0 | 44625
| Ernst & Young | 0 | 98002.0781
| 2410162165 | 0 | 98002.0781
| (blank) | 0 | 98002.0781
| SRLabs | 0 | 8925
| PR964131 | 0 | 8925
| (blank) | 0 | 8925
| DCSO | 0 | 0
| 0 | 0 | 0
| (blank) | 0 | 0
| SecAttack | 0 | 22312.5
| 0 | 0 | 22312.5
| (blank) | 0 | 22312.5
| (blank) | 2767.8155 | 3482475.2593
| (blank) | 2767.8155 | 3482475.2593
| (blank) | 2767.8155 | 3482475.2593
| (blank) | 2767.8155 | 3482475.2593
| non-Labor | 1 | 210543.769
| AZ Technology | 1 | 107250.619
| CNTR0010616 | 0 | 0
| Licence costs | 0 | 0
| CNTR0010338 | 0 | 32401.999
| Splunk Licenses + Server | 0 | 0
| ZeroFox Licenses | 0 | 32401.999
| CNTR0010333 | 0 | 0
| Splunk Licenses + Server | 0 | 0
| CNTR0010325 | 0 | 0
| HW / infrastructure | 0 | 0
| CNTR0010327 | 0 | 0
| Local SMEs for AVC, FMO | 0 | 0
| AZ Tech America HW | 0 | 0
| CNTR0010332 | 1 | 74848.62
| Cyarx Siemplify | 1 | 74848.62
| CNTR0010329 | 0 | 0
| AWS / Azure cloud | 0 | 0
| CNTR0010618 | 0 | 0
| HW | 0 | 0
| other | 0 | 103293.15
| 0 | 0 | 103293.15
| (blank) | 0 | 103293.15
| Sum | 5535.6311 | 8219441.3367

## M16 (hidden)
M16
Measure Lead: Reinhard Groß
Pillar Lead: Carsten Scholz
Duration: 10.10.2016-31.12.2018
Planned Total | #N/A
Approved Total | #N/A
Spent Labor | #N/A
Spent non-Labor | #N/A
Spent Total | #N/A
Forecast Total | #N/A
| Measure | (All)
|  | Jan |  | Feb | Mrz | Apr | Mai | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total
| Resources & Contracts | PD Total | EUR Total
| Labor | 2766.8155 | 4526422.3084
Comment | AZ Technology | 2048.878 | 2833818.6402
| 0 | 0 | 297500
| (blank) | 0 | 297500
| CNTR0010544 | 110.4647 | 157099.0619
| Andrea Scotti | 0 | 0
| Wolfgang Elsner | 0 | 0
| Alexander Heinze | 0 | 0
| Thomas Huber | 0 | 0
| Jagoda Matys | 0 | 0
| Markus Schnier | 0 | 0
| Sergej Reißig | 55.0018 | 83266.9815
| Binoj Baburaj | 0 | 0
| IAM Architect (Cygna) | 2.4114 | 3159.8592
| NN india | 0 | 0
| Michael Holder | 0 | 0
| Youssef Dahmouni | 0 | 0
| Nina Kaufmann | 20.9999 | 27517.875
| Viktoryia Nikifaravets | 32.0516 | 43154.3461
| CNTR0010615 | 121.7529 | 173433.2076
| Alexander Heinze | 0 | 0
| Jagoda Matys | 0 | 0
| Srdan Mavrenski | 55.0018 | 83266.9815
| Itai Schwartz | 31.2506 | 42075.8024
| NN india | 0 | 0
| Francois Pernayan | 31.2506 | 42075.8024
| Matt Gibson | 0 | 0
| Christian Bolterauer | 4.25 | 6014.6213
| CNTR0010616 | 68.1618 | 102967.1383
| Alexander Heinze | 0 | 0
| Thomas Huber | 0 | 0
| Reza Memarian | 55.0018 | 83266.9815
| Markus Schnier | 0 | 0
| NN india | 0 | 0
| Youssef Dahmouni | 0 | 0
| Walter Hofer | 0 | 0
| Balasz Razs | 0 | 0
| Ivan Markovic | 13.16 | 19700.1568
| Product SME | 0 | 0
| CNTR0010562 | 5 | 7850
| Thomas Huber | 0 | 0
| Markus Schnier | 0 | 0
| Clemens Friedrich | 5 | 7850
| Gerhard Schneider | 0 | 0
| DGI | 0 | 0
| CNTR0010336 | 152.1775 | 271131.6326
| Thomas Huber | 0 | 0
| Markus Schnier | 0 | 0
| Daniela Betz | 45.9375 | 65010.9849
| Bastian Kastner | 45.25 | 47435.575
| Clemens Friedrich | 0 | 0
| Gerhard Schneider | 3.77 | 7653.1
| Björn Hansen / Markus Feuerstein | 0 | 85551.9727
| Rudresh Subramanian | 20.22 | 30330
| Guelsah Uestelci | 37 | 35150
| CNTR0010335 | 56 | 64575.28
| N.N. | 0 | 0
| Markus Gatter | 56 | 64575.28
| Jakob Schusser | 0 | 0
| Gabriella Nagy | 0 | 0
| N.N. // SME 2 | 0 | 0
| N.N. // Sr. Analyst | 0 | 0
| SR Labs Autobahn | 0 | 0
| OE Effort | 0 | 0
| Ben Brüggen | 0 | 0
| CNTR0010338 | 152.3738 | 157766.1581
| Rene Pferner | 0 | 0
| Thomas Huber | 1 | 2030
| Markus Schnier | 1 | 2030
| N.N. | 0 | 0
| Clemens Friedrich | 15 | 23550
| Gerhard Schneider | 6.03 | 12240.9
| Anna Hartl | 53.8125 | 56411.6437
| Alina Lobova | 55.75 | 46754.18
| Stefan Kösters | 12.2812 | 12874.4344
| Kühnlenz / 2wmedia | 0 | 0
| Natalia Nikitana | 0 | 0
| IT Seal | 0 | 0
| Aishwarya Nangude / Sarabjit Singh | 0 | 0
| Meera Patel | 7.5 | 1875
| CNTR0010333 | 245.5625 | 276810.2324
| Christoph Lenz | 31.625 | 33152.4875
| Thomas Huber | 0 | 0
| Markus Schnier | 0 | 0
| Corinna Koch | 19.375 | 20310.8125
| Vasanthan Dhanasingh | 0 | 0
| Clemens Friedrich | 0 | 0
| Gerhard Schneider | 0 | 0
| Sven Lierzer | 48.875 | 57921.9165
| Tobias Lichtenberg | 12.6875 | 17955.4134
| Stanislav Khotinok | 34.125 | 39350.5613
| Alexander Leonhardt | 56.75 | 65440.1275
| Yuri Nikulin | 23.375 | 26954.4138
| Maria Thanner | 18.75 | 15724.5
| SNOW-Team | 0 | 0
| Splunk Team | 0 | 0
| Ankita Mane | 0 | 0
| Martin Gerlowski | 0 | 0
| Deepak Krishnan | 0 | 0
| K Harikrishnan | 0 | 0
| CNTR0010337 | 19.2596 | 32647.4087
| Placeholder | 0 | 0
| Matthias Kickstein | 0 | 0
| Computacenter | 0 | 0
| Ernst & Young | 19.2596 | 32647.4087
| CNTR0010325 | 29.75 | 16237.5
| Alex Lee | 0 | 0
| Lucas Tscherter | 0 | 0
| Corinna Koch | 0 | 0
| Dhanya Kalathil | 19.75 | 4937.5
| Mark de Vera | 0 | 0
| Balasz Racz | 10 | 11300
| Arunlal Nair | 0 | 0
| Local Infra setup support | 0 | 0
| Local SMEs for AVC, FMO | 0 | 0
| Cabling APAC | 0 | 0
| CNTR0010327 | 20 | 5320
| Thomas Huber | 0 | 0
| Gereon Volker | 0 | 0
| Lucas Tscherter | 0 | 0
| Markus Schnier | 0 | 0
| Thomas Bringewald | 2 | 2260
| Andrei Maslov | 0 | 0
| Patrick Zeitz | 0 | 0
| Armando Diaz | 0 | 0
| Ron Johnson | 0 | 0
| Jithin Varghese | 18 | 3060
| AZ Tech America Labor | 0 | 0
| Service Manager | 0 | 0
| CNTR0010332 | 177.713 | 270824.8831
| Timothy Drost | 51.25 | 56077.4981
| Thomas Huber | 1 | 2030
| Holger Steinlechner | 1.78 | 2011.4
| Lucas Tscherter | 20.42 | 32059.4
| Markus Schnier | 1 | 2030
| Olivier Ma | 0 | 0
| Rebecca Dengl | 0.263 | 297.19
| Andrei Maslov | 5 | 5650
| Racz Balazs | 2 | 2260
| Jimmy Braun | 0 | 0
| Cyarx Siemplify | 95 | 168409.395
| CMDB | 0 | 0
| CNTR0010329 | 97.9983 | 221663.7262
| Thomas Huber | 1 | 2030
| Gereon Volker | 0 | 0
| Lucas Tscherter | 27.79 | 43630.3
| Markus Schnier | 1 | 2030
| Thomas Bringewald | 5 | 5650
| Rebecca Dengl | 0.526 | 594.38
| Felix Hertin | 3.2615 | 5242.0231
| Lukas Thiele | 9.4208 | 5242.0231
| Holger Wache | 25 | 78622.5
| Tobias Martin | 25 | 78622.5
| Deloitte | 0 | 0
| CNTR0010709 | 11 | 16796.845
| Thomas Huber | 1 | 2030
| Lucas Tscherter | 0 | 0
| Markus Schnier | 1 | 2030
| Krunoslav Rukavina | 9 | 12736.845
| Joachim Steinberger | 0 | 0
| Elastic | 0 | 0
| Proofpoint | 0 | 0
| CNTR0010564 | 513.2647 | 444921.049
| Markus Traumueller | 10 | 11300
| Karim, Hasan | 57 | 59850
| Bojarski, Eduard | 57 | 112122.99
| Kayali, Ismail | 57 | 72645.93
| Stettner, Julia | 57 | 80717.13
| Tulshidas Thamke, Budhesh | 57 | 9120
| Sunderdas, Shilpa | 58 | 9280
| Bönigk, Julian | 10 | 11300
| Sora Mustafa (AUG-OCT only) | 52 | 61880
| Vidya Baskaran Reddy | 57 | 9690
| S, Shibi (partily on IP&G) | 41.2647 | 7014.999
| CNTR0010563 | 109.9746 | 125589.2982
| Günther, Gerhard | 15.1579 | 20463.1579
| Poteat, Jade | 22.9868 | 22986.8421
| Warnholz, Benjamin | 8 | 16000
| Qualys Team (AVM) | 0 | 0
| Uysal, Ismail (Project Manager) | 51.1456 | 51145.614
| Goldschmidt, Andreas (SNOW Principal Architect) | 10.6842 | 14423.6842
| AMC Devops Engineer (Internal) | 0 | 0
| APM Devops Engineer (Internal) | 0 | 0
| EMS Devops Engineer (Internal) | 0 | 0
| Workspace Intelligence Internal – Technical SME | 0 | 0
| SNOW Performance Analytics team | 0 | 0
| SNOW Development Teams | 2 | 570
| Workspace Intelligence Vendor – Technical SME | 0 | 0
| SNOW SAM efforts | 0 | 0
| SNOW CMDB | 0 | 0
| CyNet | 0 | 0
| Security Foundation Team | 0 | 0
| CNTR0010576 | 27.5 | 35432.54
| Marc Bochtler | 18 | 25473.69
| Alexander Heinze | 0 | 0
| Tobias Butz | 0 | 0
| NN | 0 | 0
| NN india | 0 | 0
| Yury Nikolin | 9.5 | 9958.85
| Thomas Felder | 0 | 0
| CNTR0010334 | 130.125 | 153138.2055
| Martin Schurm | 27 | 42102.3487
| Tobias Krichel | 62.875 | 74513.3568
| Thomas Huber | 1 | 2030
| Markus Schnier | 1 | 2030
| Dan Read | 0 | 0
| N.N. / Support Dan | 0 | 0
| Ankur Tomar | 0 | 0
| Naman Agrawal | 21.25 | 5312.5
| Clemens Friedrich | 16 | 25120
| Gerhard Schneider | 1 | 2030
| OAM302 | 0 | 0
| Alexander Heinze | 0 | 0
| Daming Yang | 0 | 0
| Manoj Selvakumar | 0 | 0
| David Barton | 0 | 0
| Raja Rajcic | 0 | 0
| Lawrence Tengan | 0 | 0
| Travis Chun | 0 | 0
| Johannes Bross | 0 | 0
| Tuan Minh Nguyen | 0 | 0
| Tobias Tischler | 0 | 0
| Djamel Tazerout | 0 | 0
| Dirk Addicks | 0 | 0
| Forgerock Licence | 0 | 0
| CNTR0010589 | 0 | 0
| Placeholder | 0 | 0
| OAM299 | 0 | 0
| Placeholder | 0 | 0
| CNTR0010618 | 0.79973 | 2114.4735
| Birgit Jarosch | 0.79973 | 2114.4735
| Wolfgang Elsner | 0 | 0
| Alexander Heinze | 0 | 0
| Jagoda Matys | 0 | 0
| N.N. | 0 | 0
| Mitja Ledowski | 0 | 0
| Ingmar Janßen-Holldiek | 0 | 0
| Michael Holder | 0 | 0
| Sinoop K S | 0 | 0
| J. Thomas | 0 | 0
| Madalina Paslaru | 0 | 0
| Daniel Ettenhuber | 0 | 0
| OAM289 | 0 | 0
| Placeholder | 0 | 0
| CNTR0010617 | 0 | 0
| (blank) | 0 | 0
| Alexander Heinze | 0 | 0
| Christine Schlüter | 0 | 0
| Günter Sanktjohanser | 0 | 0
| Metafinanz | 717.9375 | 838906
| 21 0427 | 162.5625 | 155742.25
| Julian Steinfeld | 53 | 58936
| Manuel Hahn | 43.5312 | 42660.625
| Matthias Müller | 66.0312 | 54145.625
| 21 1068 | 107.1875 | 140290.625
| Jonathan Reynolds | 16.75 | 16750
| Samuel Hurst | 38.9688 | 52607.8125
| Kris Harms | 39 | 56550
| Nora von Schenckendorff | 5.4688 | 7382.8125
| Frank Markussen | 1.375 | 1375
| Anette Hettenkofer | 0.125 | 125
| Julia Netesa | 5.5 | 5500
| 21 1079 | 81.1875 | 94356.25
| George Dietrichsbruckner | 37.625 | 50793.75
| Jade Poteat | 7.625 | 7625
| Nadine Butzhammer | 0.3125 | 312.5
| Daniel Wörner | 21.5 | 21500
| Sanat Gautam | 14.125 | 14125
| 21 1037 | 179.6875 | 209831.25
| Gerhard Günther | 31.5 | 42525
| Rasa Rintallo | 43.4375 | 43437.5
| Stefan Köstenbauer | 1.125 | 1518.75
| Victor Peters | 3.8438 | 3843.75
| Michael Habel | 53.5 | 72225
| Maximilian Schellenberger | 3.2812 | 3281.25
| Sona Latifyan | 43 | 43000
| 21 1040 | 6.5 | 6500
| Jade Poteat | 6.5 | 6500
| 21 1133 | 0 | 0
| Krunoslav Rukavina | 0 | 0
| 21 1063 | 135.3125 | 170760.625
| Marc Bochtler | 42.125 | 56868.75
| Thorsten Deckers | 21.0625 | 33068.125
| Robert Reti | 17.875 | 28063.75
| Claudio Cangiotti | 13 | 10010
| Yury Nikulin | 26.25 | 26250
| Eldho George | 15 | 16500
| 21 1059 | 45.5 | 61425
| Thomas Thuspaß | 45.5 | 61425
| other | 0 | 24570
| 0 | 0 | 24570
| (blank) | 0 | 24570
| NCC Group GmbH | 0 | 363140.4
| 2410164170 | 0 | 363140.4
| (blank) | 0 | 363140.4
| Osborne Clark | 0 | 20659.69
| TID0001510089 | 0 | 20659.69
| (blank) | 0 | 20659.69
| Virtual Clarity Ltd | 0 | 149488
| 2410164371 | 0 | 149488
| (blank) | 0 | 149488
| Softwaregilde | 0 | 121975
| 2410159840 | 0 | 121975
| (blank) | 0 | 121975
| Horvath & Partner | 0 | 44625
| 2410160374 | 0 | 44625
| (blank) | 0 | 44625
| Ernst & Young | 0 | 98002.0781
| 2410162165 | 0 | 98002.0781
| (blank) | 0 | 98002.0781
| SRLabs | 0 | 8925
| PR964131 | 0 | 8925
| (blank) | 0 | 8925
| DCSO | 0 | 0
| 0 | 0 | 0
| (blank) | 0 | 0
| SecAttack | 0 | 22312.5
| 0 | 0 | 22312.5
| (blank) | 0 | 22312.5
| (blank) | 2767.8155 | 3482475.2593
| (blank) | 2767.8155 | 3482475.2593
| (blank) | 2767.8155 | 3482475.2593
| (blank) | 2767.8155 | 3482475.2593
| non-Labor | 1 | 210543.769
| AZ Technology | 1 | 107250.619
| CNTR0010616 | 0 | 0
| Licence costs | 0 | 0
| CNTR0010338 | 0 | 32401.999
| Splunk Licenses + Server | 0 | 0
| ZeroFox Licenses | 0 | 32401.999
| CNTR0010333 | 0 | 0
| Splunk Licenses + Server | 0 | 0
| CNTR0010325 | 0 | 0
| HW / infrastructure | 0 | 0
| CNTR0010327 | 0 | 0
| Local SMEs for AVC, FMO | 0 | 0
| AZ Tech America HW | 0 | 0
| CNTR0010332 | 1 | 74848.62
| Cyarx Siemplify | 1 | 74848.62
| CNTR0010329 | 0 | 0
| AWS / Azure cloud | 0 | 0
| CNTR0010618 | 0 | 0
| HW | 0 | 0
| other | 0 | 103293.15
| 0 | 0 | 103293.15
| (blank) | 0 | 103293.15
| Sum | 5535.6311 | 8219441.3367

## M78 (hidden)
M78
Measure Lead: Itai Schwartz
Pillar Lead: Carsten Scholz
Duration: 01.08.2017-31.12.2018
Planned Total | #N/A
Approved Total | #N/A
Spent Labor | #N/A
Spent non-Labor | #N/A
Spent Total | #N/A
Forecast Total | #N/A
| Measure | (All)
|  | Jan |  | Feb | Mrz | Apr | Mai | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total
| Resources & Contracts | PD Total | EUR Total
| Labor | 2766.8155 | 4526422.3084
Comment | AZ Technology | 2048.878 | 2833818.6402
| 0 | 0 | 297500
| (blank) | 0 | 297500
| CNTR0010544 | 110.4647 | 157099.0619
| Andrea Scotti | 0 | 0
| Wolfgang Elsner | 0 | 0
| Alexander Heinze | 0 | 0
| Thomas Huber | 0 | 0
| Jagoda Matys | 0 | 0
| Markus Schnier | 0 | 0
| Sergej Reißig | 55.0018 | 83266.9815
| Binoj Baburaj | 0 | 0
| IAM Architect (Cygna) | 2.4114 | 3159.8592
| NN india | 0 | 0
| Michael Holder | 0 | 0
| Youssef Dahmouni | 0 | 0
| Nina Kaufmann | 20.9999 | 27517.875
| Viktoryia Nikifaravets | 32.0516 | 43154.3461
| CNTR0010615 | 121.7529 | 173433.2076
| Alexander Heinze | 0 | 0
| Jagoda Matys | 0 | 0
| Srdan Mavrenski | 55.0018 | 83266.9815
| Itai Schwartz | 31.2506 | 42075.8024
| NN india | 0 | 0
| Francois Pernayan | 31.2506 | 42075.8024
| Matt Gibson | 0 | 0
| Christian Bolterauer | 4.25 | 6014.6213
| CNTR0010616 | 68.1618 | 102967.1383
| Alexander Heinze | 0 | 0
| Thomas Huber | 0 | 0
| Reza Memarian | 55.0018 | 83266.9815
| Markus Schnier | 0 | 0
| NN india | 0 | 0
| Youssef Dahmouni | 0 | 0
| Walter Hofer | 0 | 0
| Balasz Razs | 0 | 0
| Ivan Markovic | 13.16 | 19700.1568
| Product SME | 0 | 0
| CNTR0010562 | 5 | 7850
| Thomas Huber | 0 | 0
| Markus Schnier | 0 | 0
| Clemens Friedrich | 5 | 7850
| Gerhard Schneider | 0 | 0
| DGI | 0 | 0
| CNTR0010336 | 152.1775 | 271131.6326
| Thomas Huber | 0 | 0
| Markus Schnier | 0 | 0
| Daniela Betz | 45.9375 | 65010.9849
| Bastian Kastner | 45.25 | 47435.575
| Clemens Friedrich | 0 | 0
| Gerhard Schneider | 3.77 | 7653.1
| Björn Hansen / Markus Feuerstein | 0 | 85551.9727
| Rudresh Subramanian | 20.22 | 30330
| Guelsah Uestelci | 37 | 35150
| CNTR0010335 | 56 | 64575.28
| N.N. | 0 | 0
| Markus Gatter | 56 | 64575.28
| Jakob Schusser | 0 | 0
| Gabriella Nagy | 0 | 0
| N.N. // SME 2 | 0 | 0
| N.N. // Sr. Analyst | 0 | 0
| SR Labs Autobahn | 0 | 0
| OE Effort | 0 | 0
| Ben Brüggen | 0 | 0
| CNTR0010338 | 152.3738 | 157766.1581
| Rene Pferner | 0 | 0
| Thomas Huber | 1 | 2030
| Markus Schnier | 1 | 2030
| N.N. | 0 | 0
| Clemens Friedrich | 15 | 23550
| Gerhard Schneider | 6.03 | 12240.9
| Anna Hartl | 53.8125 | 56411.6437
| Alina Lobova | 55.75 | 46754.18
| Stefan Kösters | 12.2812 | 12874.4344
| Kühnlenz / 2wmedia | 0 | 0
| Natalia Nikitana | 0 | 0
| IT Seal | 0 | 0
| Aishwarya Nangude / Sarabjit Singh | 0 | 0
| Meera Patel | 7.5 | 1875
| CNTR0010333 | 245.5625 | 276810.2324
| Christoph Lenz | 31.625 | 33152.4875
| Thomas Huber | 0 | 0
| Markus Schnier | 0 | 0
| Corinna Koch | 19.375 | 20310.8125
| Vasanthan Dhanasingh | 0 | 0
| Clemens Friedrich | 0 | 0
| Gerhard Schneider | 0 | 0
| Sven Lierzer | 48.875 | 57921.9165
| Tobias Lichtenberg | 12.6875 | 17955.4134
| Stanislav Khotinok | 34.125 | 39350.5613
| Alexander Leonhardt | 56.75 | 65440.1275
| Yuri Nikulin | 23.375 | 26954.4138
| Maria Thanner | 18.75 | 15724.5
| SNOW-Team | 0 | 0
| Splunk Team | 0 | 0
| Ankita Mane | 0 | 0
| Martin Gerlowski | 0 | 0
| Deepak Krishnan | 0 | 0
| K Harikrishnan | 0 | 0
| CNTR0010337 | 19.2596 | 32647.4087
| Placeholder | 0 | 0
| Matthias Kickstein | 0 | 0
| Computacenter | 0 | 0
| Ernst & Young | 19.2596 | 32647.4087
| CNTR0010325 | 29.75 | 16237.5
| Alex Lee | 0 | 0
| Lucas Tscherter | 0 | 0
| Corinna Koch | 0 | 0
| Dhanya Kalathil | 19.75 | 4937.5
| Mark de Vera | 0 | 0
| Balasz Racz | 10 | 11300
| Arunlal Nair | 0 | 0
| Local Infra setup support | 0 | 0
| Local SMEs for AVC, FMO | 0 | 0
| Cabling APAC | 0 | 0
| CNTR0010327 | 20 | 5320
| Thomas Huber | 0 | 0
| Gereon Volker | 0 | 0
| Lucas Tscherter | 0 | 0
| Markus Schnier | 0 | 0
| Thomas Bringewald | 2 | 2260
| Andrei Maslov | 0 | 0
| Patrick Zeitz | 0 | 0
| Armando Diaz | 0 | 0
| Ron Johnson | 0 | 0
| Jithin Varghese | 18 | 3060
| AZ Tech America Labor | 0 | 0
| Service Manager | 0 | 0
| CNTR0010332 | 177.713 | 270824.8831
| Timothy Drost | 51.25 | 56077.4981
| Thomas Huber | 1 | 2030
| Holger Steinlechner | 1.78 | 2011.4
| Lucas Tscherter | 20.42 | 32059.4
| Markus Schnier | 1 | 2030
| Olivier Ma | 0 | 0
| Rebecca Dengl | 0.263 | 297.19
| Andrei Maslov | 5 | 5650
| Racz Balazs | 2 | 2260
| Jimmy Braun | 0 | 0
| Cyarx Siemplify | 95 | 168409.395
| CMDB | 0 | 0
| CNTR0010329 | 97.9983 | 221663.7262
| Thomas Huber | 1 | 2030
| Gereon Volker | 0 | 0
| Lucas Tscherter | 27.79 | 43630.3
| Markus Schnier | 1 | 2030
| Thomas Bringewald | 5 | 5650
| Rebecca Dengl | 0.526 | 594.38
| Felix Hertin | 3.2615 | 5242.0231
| Lukas Thiele | 9.4208 | 5242.0231
| Holger Wache | 25 | 78622.5
| Tobias Martin | 25 | 78622.5
| Deloitte | 0 | 0
| CNTR0010709 | 11 | 16796.845
| Thomas Huber | 1 | 2030
| Lucas Tscherter | 0 | 0
| Markus Schnier | 1 | 2030
| Krunoslav Rukavina | 9 | 12736.845
| Joachim Steinberger | 0 | 0
| Elastic | 0 | 0
| Proofpoint | 0 | 0
| CNTR0010564 | 513.2647 | 444921.049
| Markus Traumueller | 10 | 11300
| Karim, Hasan | 57 | 59850
| Bojarski, Eduard | 57 | 112122.99
| Kayali, Ismail | 57 | 72645.93
| Stettner, Julia | 57 | 80717.13
| Tulshidas Thamke, Budhesh | 57 | 9120
| Sunderdas, Shilpa | 58 | 9280
| Bönigk, Julian | 10 | 11300
| Sora Mustafa (AUG-OCT only) | 52 | 61880
| Vidya Baskaran Reddy | 57 | 9690
| S, Shibi (partily on IP&G) | 41.2647 | 7014.999
| CNTR0010563 | 109.9746 | 125589.2982
| Günther, Gerhard | 15.1579 | 20463.1579
| Poteat, Jade | 22.9868 | 22986.8421
| Warnholz, Benjamin | 8 | 16000
| Qualys Team (AVM) | 0 | 0
| Uysal, Ismail (Project Manager) | 51.1456 | 51145.614
| Goldschmidt, Andreas (SNOW Principal Architect) | 10.6842 | 14423.6842
| AMC Devops Engineer (Internal) | 0 | 0
| APM Devops Engineer (Internal) | 0 | 0
| EMS Devops Engineer (Internal) | 0 | 0
| Workspace Intelligence Internal – Technical SME | 0 | 0
| SNOW Performance Analytics team | 0 | 0
| SNOW Development Teams | 2 | 570
| Workspace Intelligence Vendor – Technical SME | 0 | 0
| SNOW SAM efforts | 0 | 0
| SNOW CMDB | 0 | 0
| CyNet | 0 | 0
| Security Foundation Team | 0 | 0
| CNTR0010576 | 27.5 | 35432.54
| Marc Bochtler | 18 | 25473.69
| Alexander Heinze | 0 | 0
| Tobias Butz | 0 | 0
| NN | 0 | 0
| NN india | 0 | 0
| Yury Nikolin | 9.5 | 9958.85
| Thomas Felder | 0 | 0
| CNTR0010334 | 130.125 | 153138.2055
| Martin Schurm | 27 | 42102.3487
| Tobias Krichel | 62.875 | 74513.3568
| Thomas Huber | 1 | 2030
| Markus Schnier | 1 | 2030
| Dan Read | 0 | 0
| N.N. / Support Dan | 0 | 0
| Ankur Tomar | 0 | 0
| Naman Agrawal | 21.25 | 5312.5
| Clemens Friedrich | 16 | 25120
| Gerhard Schneider | 1 | 2030
| OAM302 | 0 | 0
| Alexander Heinze | 0 | 0
| Daming Yang | 0 | 0
| Manoj Selvakumar | 0 | 0
| David Barton | 0 | 0
| Raja Rajcic | 0 | 0
| Lawrence Tengan | 0 | 0
| Travis Chun | 0 | 0
| Johannes Bross | 0 | 0
| Tuan Minh Nguyen | 0 | 0
| Tobias Tischler | 0 | 0
| Djamel Tazerout | 0 | 0
| Dirk Addicks | 0 | 0
| Forgerock Licence | 0 | 0
| CNTR0010589 | 0 | 0
| Placeholder | 0 | 0
| OAM299 | 0 | 0
| Placeholder | 0 | 0
| CNTR0010618 | 0.79973 | 2114.4735
| Birgit Jarosch | 0.79973 | 2114.4735
| Wolfgang Elsner | 0 | 0
| Alexander Heinze | 0 | 0
| Jagoda Matys | 0 | 0
| N.N. | 0 | 0
| Mitja Ledowski | 0 | 0
| Ingmar Janßen-Holldiek | 0 | 0
| Michael Holder | 0 | 0
| Sinoop K S | 0 | 0
| J. Thomas | 0 | 0
| Madalina Paslaru | 0 | 0
| Daniel Ettenhuber | 0 | 0
| OAM289 | 0 | 0
| Placeholder | 0 | 0
| CNTR0010617 | 0 | 0
| (blank) | 0 | 0
| Alexander Heinze | 0 | 0
| Christine Schlüter | 0 | 0
| Günter Sanktjohanser | 0 | 0
| Metafinanz | 717.9375 | 838906
| 21 0427 | 162.5625 | 155742.25
| Julian Steinfeld | 53 | 58936
| Manuel Hahn | 43.5312 | 42660.625
| Matthias Müller | 66.0312 | 54145.625
| 21 1068 | 107.1875 | 140290.625
| Jonathan Reynolds | 16.75 | 16750
| Samuel Hurst | 38.9688 | 52607.8125
| Kris Harms | 39 | 56550
| Nora von Schenckendorff | 5.4688 | 7382.8125
| Frank Markussen | 1.375 | 1375
| Anette Hettenkofer | 0.125 | 125
| Julia Netesa | 5.5 | 5500
| 21 1079 | 81.1875 | 94356.25
| George Dietrichsbruckner | 37.625 | 50793.75
| Jade Poteat | 7.625 | 7625
| Nadine Butzhammer | 0.3125 | 312.5
| Daniel Wörner | 21.5 | 21500
| Sanat Gautam | 14.125 | 14125
| 21 1037 | 179.6875 | 209831.25
| Gerhard Günther | 31.5 | 42525
| Rasa Rintallo | 43.4375 | 43437.5
| Stefan Köstenbauer | 1.125 | 1518.75
| Victor Peters | 3.8438 | 3843.75
| Michael Habel | 53.5 | 72225
| Maximilian Schellenberger | 3.2812 | 3281.25
| Sona Latifyan | 43 | 43000
| 21 1040 | 6.5 | 6500
| Jade Poteat | 6.5 | 6500
| 21 1133 | 0 | 0
| Krunoslav Rukavina | 0 | 0
| 21 1063 | 135.3125 | 170760.625
| Marc Bochtler | 42.125 | 56868.75
| Thorsten Deckers | 21.0625 | 33068.125
| Robert Reti | 17.875 | 28063.75
| Claudio Cangiotti | 13 | 10010
| Yury Nikulin | 26.25 | 26250
| Eldho George | 15 | 16500
| 21 1059 | 45.5 | 61425
| Thomas Thuspaß | 45.5 | 61425
| other | 0 | 24570
| 0 | 0 | 24570
| (blank) | 0 | 24570
| NCC Group GmbH | 0 | 363140.4
| 2410164170 | 0 | 363140.4
| (blank) | 0 | 363140.4
| Osborne Clark | 0 | 20659.69
| TID0001510089 | 0 | 20659.69
| (blank) | 0 | 20659.69
| Virtual Clarity Ltd | 0 | 149488
| 2410164371 | 0 | 149488
| (blank) | 0 | 149488
| Softwaregilde | 0 | 121975
| 2410159840 | 0 | 121975
| (blank) | 0 | 121975
| Horvath & Partner | 0 | 44625
| 2410160374 | 0 | 44625
| (blank) | 0 | 44625
| Ernst & Young | 0 | 98002.0781
| 2410162165 | 0 | 98002.0781
| (blank) | 0 | 98002.0781
| SRLabs | 0 | 8925
| PR964131 | 0 | 8925
| (blank) | 0 | 8925
| DCSO | 0 | 0
| 0 | 0 | 0
| (blank) | 0 | 0
| SecAttack | 0 | 22312.5
| 0 | 0 | 22312.5
| (blank) | 0 | 22312.5
| (blank) | 2767.8155 | 3482475.2593
| (blank) | 2767.8155 | 3482475.2593
| (blank) | 2767.8155 | 3482475.2593
| (blank) | 2767.8155 | 3482475.2593
| non-Labor | 1 | 210543.769
| AZ Technology | 1 | 107250.619
| CNTR0010616 | 0 | 0
| Licence costs | 0 | 0
| CNTR0010338 | 0 | 32401.999
| Splunk Licenses + Server | 0 | 0
| ZeroFox Licenses | 0 | 32401.999
| CNTR0010333 | 0 | 0
| Splunk Licenses + Server | 0 | 0
| CNTR0010325 | 0 | 0
| HW / infrastructure | 0 | 0
| CNTR0010327 | 0 | 0
| Local SMEs for AVC, FMO | 0 | 0
| AZ Tech America HW | 0 | 0
| CNTR0010332 | 1 | 74848.62
| Cyarx Siemplify | 1 | 74848.62
| CNTR0010329 | 0 | 0
| AWS / Azure cloud | 0 | 0
| CNTR0010618 | 0 | 0
| HW | 0 | 0
| other | 0 | 103293.15
| 0 | 0 | 103293.15
| (blank) | 0 | 103293.15
| Sum | 5535.6311 | 8219441.3367

## M14 (hidden)
M14
Measure Lead: Saskia Günther
Pillar Lead: Carsten Scholz
Duration: 01.10.2017-31.12.2018
Planned Total | #N/A
Approved Total | #N/A
Spent Labor | #N/A
Spent non-Labor | #N/A
Spent Total | #N/A
Forecast Total | #N/A
| Measure | (All)
|  | Jan |  | Feb | Mrz | Apr | Mai | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total
| Resources & Contracts | PD Total | EUR Total
| Labor | 2766.8155 | 4526422.3084
Comment | AZ Technology | 2048.878 | 2833818.6402
| 0 | 0 | 297500
| (blank) | 0 | 297500
| CNTR0010544 | 110.4647 | 157099.0619
| Andrea Scotti | 0 | 0
| Wolfgang Elsner | 0 | 0
| Alexander Heinze | 0 | 0
| Thomas Huber | 0 | 0
| Jagoda Matys | 0 | 0
| Markus Schnier | 0 | 0
| Sergej Reißig | 55.0018 | 83266.9815
| Binoj Baburaj | 0 | 0
| IAM Architect (Cygna) | 2.4114 | 3159.8592
| NN india | 0 | 0
| Michael Holder | 0 | 0
| Youssef Dahmouni | 0 | 0
| Nina Kaufmann | 20.9999 | 27517.875
| Viktoryia Nikifaravets | 32.0516 | 43154.3461
| CNTR0010615 | 121.7529 | 173433.2076
| Alexander Heinze | 0 | 0
| Jagoda Matys | 0 | 0
| Srdan Mavrenski | 55.0018 | 83266.9815
| Itai Schwartz | 31.2506 | 42075.8024
| NN india | 0 | 0
| Francois Pernayan | 31.2506 | 42075.8024
| Matt Gibson | 0 | 0
| Christian Bolterauer | 4.25 | 6014.6213
| CNTR0010616 | 68.1618 | 102967.1383
| Alexander Heinze | 0 | 0
| Thomas Huber | 0 | 0
| Reza Memarian | 55.0018 | 83266.9815
| Markus Schnier | 0 | 0
| NN india | 0 | 0
| Youssef Dahmouni | 0 | 0
| Walter Hofer | 0 | 0
| Balasz Razs | 0 | 0
| Ivan Markovic | 13.16 | 19700.1568
| Product SME | 0 | 0
| CNTR0010562 | 5 | 7850
| Thomas Huber | 0 | 0
| Markus Schnier | 0 | 0
| Clemens Friedrich | 5 | 7850
| Gerhard Schneider | 0 | 0
| DGI | 0 | 0
| CNTR0010336 | 152.1775 | 271131.6326
| Thomas Huber | 0 | 0
| Markus Schnier | 0 | 0
| Daniela Betz | 45.9375 | 65010.9849
| Bastian Kastner | 45.25 | 47435.575
| Clemens Friedrich | 0 | 0
| Gerhard Schneider | 3.77 | 7653.1
| Björn Hansen / Markus Feuerstein | 0 | 85551.9727
| Rudresh Subramanian | 20.22 | 30330
| Guelsah Uestelci | 37 | 35150
| CNTR0010335 | 56 | 64575.28
| N.N. | 0 | 0
| Markus Gatter | 56 | 64575.28
| Jakob Schusser | 0 | 0
| Gabriella Nagy | 0 | 0
| N.N. // SME 2 | 0 | 0
| N.N. // Sr. Analyst | 0 | 0
| SR Labs Autobahn | 0 | 0
| OE Effort | 0 | 0
| Ben Brüggen | 0 | 0
| CNTR0010338 | 152.3738 | 157766.1581
| Rene Pferner | 0 | 0
| Thomas Huber | 1 | 2030
| Markus Schnier | 1 | 2030
| N.N. | 0 | 0
| Clemens Friedrich | 15 | 23550
| Gerhard Schneider | 6.03 | 12240.9
| Anna Hartl | 53.8125 | 56411.6437
| Alina Lobova | 55.75 | 46754.18
| Stefan Kösters | 12.2812 | 12874.4344
| Kühnlenz / 2wmedia | 0 | 0
| Natalia Nikitana | 0 | 0
| IT Seal | 0 | 0
| Aishwarya Nangude / Sarabjit Singh | 0 | 0
| Meera Patel | 7.5 | 1875
| CNTR0010333 | 245.5625 | 276810.2324
| Christoph Lenz | 31.625 | 33152.4875
| Thomas Huber | 0 | 0
| Markus Schnier | 0 | 0
| Corinna Koch | 19.375 | 20310.8125
| Vasanthan Dhanasingh | 0 | 0
| Clemens Friedrich | 0 | 0
| Gerhard Schneider | 0 | 0
| Sven Lierzer | 48.875 | 57921.9165
| Tobias Lichtenberg | 12.6875 | 17955.4134
| Stanislav Khotinok | 34.125 | 39350.5613
| Alexander Leonhardt | 56.75 | 65440.1275
| Yuri Nikulin | 23.375 | 26954.4138
| Maria Thanner | 18.75 | 15724.5
| SNOW-Team | 0 | 0
| Splunk Team | 0 | 0
| Ankita Mane | 0 | 0
| Martin Gerlowski | 0 | 0
| Deepak Krishnan | 0 | 0
| K Harikrishnan | 0 | 0
| CNTR0010337 | 19.2596 | 32647.4087
| Placeholder | 0 | 0
| Matthias Kickstein | 0 | 0
| Computacenter | 0 | 0
| Ernst & Young | 19.2596 | 32647.4087
| CNTR0010325 | 29.75 | 16237.5
| Alex Lee | 0 | 0
| Lucas Tscherter | 0 | 0
| Corinna Koch | 0 | 0
| Dhanya Kalathil | 19.75 | 4937.5
| Mark de Vera | 0 | 0
| Balasz Racz | 10 | 11300
| Arunlal Nair | 0 | 0
| Local Infra setup support | 0 | 0
| Local SMEs for AVC, FMO | 0 | 0
| Cabling APAC | 0 | 0
| CNTR0010327 | 20 | 5320
| Thomas Huber | 0 | 0
| Gereon Volker | 0 | 0
| Lucas Tscherter | 0 | 0
| Markus Schnier | 0 | 0
| Thomas Bringewald | 2 | 2260
| Andrei Maslov | 0 | 0
| Patrick Zeitz | 0 | 0
| Armando Diaz | 0 | 0
| Ron Johnson | 0 | 0
| Jithin Varghese | 18 | 3060
| AZ Tech America Labor | 0 | 0
| Service Manager | 0 | 0
| CNTR0010332 | 177.713 | 270824.8831
| Timothy Drost | 51.25 | 56077.4981
| Thomas Huber | 1 | 2030
| Holger Steinlechner | 1.78 | 2011.4
| Lucas Tscherter | 20.42 | 32059.4
| Markus Schnier | 1 | 2030
| Olivier Ma | 0 | 0
| Rebecca Dengl | 0.263 | 297.19
| Andrei Maslov | 5 | 5650
| Racz Balazs | 2 | 2260
| Jimmy Braun | 0 | 0
| Cyarx Siemplify | 95 | 168409.395
| CMDB | 0 | 0
| CNTR0010329 | 97.9983 | 221663.7262
| Thomas Huber | 1 | 2030
| Gereon Volker | 0 | 0
| Lucas Tscherter | 27.79 | 43630.3
| Markus Schnier | 1 | 2030
| Thomas Bringewald | 5 | 5650
| Rebecca Dengl | 0.526 | 594.38
| Felix Hertin | 3.2615 | 5242.0231
| Lukas Thiele | 9.4208 | 5242.0231
| Holger Wache | 25 | 78622.5
| Tobias Martin | 25 | 78622.5
| Deloitte | 0 | 0
| CNTR0010709 | 11 | 16796.845
| Thomas Huber | 1 | 2030
| Lucas Tscherter | 0 | 0
| Markus Schnier | 1 | 2030
| Krunoslav Rukavina | 9 | 12736.845
| Joachim Steinberger | 0 | 0
| Elastic | 0 | 0
| Proofpoint | 0 | 0
| CNTR0010564 | 513.2647 | 444921.049
| Markus Traumueller | 10 | 11300
| Karim, Hasan | 57 | 59850
| Bojarski, Eduard | 57 | 112122.99
| Kayali, Ismail | 57 | 72645.93
| Stettner, Julia | 57 | 80717.13
| Tulshidas Thamke, Budhesh | 57 | 9120
| Sunderdas, Shilpa | 58 | 9280
| Bönigk, Julian | 10 | 11300
| Sora Mustafa (AUG-OCT only) | 52 | 61880
| Vidya Baskaran Reddy | 57 | 9690
| S, Shibi (partily on IP&G) | 41.2647 | 7014.999
| CNTR0010563 | 109.9746 | 125589.2982
| Günther, Gerhard | 15.1579 | 20463.1579
| Poteat, Jade | 22.9868 | 22986.8421
| Warnholz, Benjamin | 8 | 16000
| Qualys Team (AVM) | 0 | 0
| Uysal, Ismail (Project Manager) | 51.1456 | 51145.614
| Goldschmidt, Andreas (SNOW Principal Architect) | 10.6842 | 14423.6842
| AMC Devops Engineer (Internal) | 0 | 0
| APM Devops Engineer (Internal) | 0 | 0
| EMS Devops Engineer (Internal) | 0 | 0
| Workspace Intelligence Internal – Technical SME | 0 | 0
| SNOW Performance Analytics team | 0 | 0
| SNOW Development Teams | 2 | 570
| Workspace Intelligence Vendor – Technical SME | 0 | 0
| SNOW SAM efforts | 0 | 0
| SNOW CMDB | 0 | 0
| CyNet | 0 | 0
| Security Foundation Team | 0 | 0
| CNTR0010576 | 27.5 | 35432.54
| Marc Bochtler | 18 | 25473.69
| Alexander Heinze | 0 | 0
| Tobias Butz | 0 | 0
| NN | 0 | 0
| NN india | 0 | 0
| Yury Nikolin | 9.5 | 9958.85
| Thomas Felder | 0 | 0
| CNTR0010334 | 130.125 | 153138.2055
| Martin Schurm | 27 | 42102.3487
| Tobias Krichel | 62.875 | 74513.3568
| Thomas Huber | 1 | 2030
| Markus Schnier | 1 | 2030
| Dan Read | 0 | 0
| N.N. / Support Dan | 0 | 0
| Ankur Tomar | 0 | 0
| Naman Agrawal | 21.25 | 5312.5
| Clemens Friedrich | 16 | 25120
| Gerhard Schneider | 1 | 2030
| OAM302 | 0 | 0
| Alexander Heinze | 0 | 0
| Daming Yang | 0 | 0
| Manoj Selvakumar | 0 | 0
| David Barton | 0 | 0
| Raja Rajcic | 0 | 0
| Lawrence Tengan | 0 | 0
| Travis Chun | 0 | 0
| Johannes Bross | 0 | 0
| Tuan Minh Nguyen | 0 | 0
| Tobias Tischler | 0 | 0
| Djamel Tazerout | 0 | 0
| Dirk Addicks | 0 | 0
| Forgerock Licence | 0 | 0
| CNTR0010589 | 0 | 0
| Placeholder | 0 | 0
| OAM299 | 0 | 0
| Placeholder | 0 | 0
| CNTR0010618 | 0.79973 | 2114.4735
| Birgit Jarosch | 0.79973 | 2114.4735
| Wolfgang Elsner | 0 | 0
| Alexander Heinze | 0 | 0
| Jagoda Matys | 0 | 0
| N.N. | 0 | 0
| Mitja Ledowski | 0 | 0
| Ingmar Janßen-Holldiek | 0 | 0
| Michael Holder | 0 | 0
| Sinoop K S | 0 | 0
| J. Thomas | 0 | 0
| Madalina Paslaru | 0 | 0
| Daniel Ettenhuber | 0 | 0
| OAM289 | 0 | 0
| Placeholder | 0 | 0
| CNTR0010617 | 0 | 0
| (blank) | 0 | 0
| Alexander Heinze | 0 | 0
| Christine Schlüter | 0 | 0
| Günter Sanktjohanser | 0 | 0
| Metafinanz | 717.9375 | 838906
| 21 0427 | 162.5625 | 155742.25
| Julian Steinfeld | 53 | 58936
| Manuel Hahn | 43.5312 | 42660.625
| Matthias Müller | 66.0312 | 54145.625
| 21 1068 | 107.1875 | 140290.625
| Jonathan Reynolds | 16.75 | 16750
| Samuel Hurst | 38.9688 | 52607.8125
| Kris Harms | 39 | 56550
| Nora von Schenckendorff | 5.4688 | 7382.8125
| Frank Markussen | 1.375 | 1375
| Anette Hettenkofer | 0.125 | 125
| Julia Netesa | 5.5 | 5500
| 21 1079 | 81.1875 | 94356.25
| George Dietrichsbruckner | 37.625 | 50793.75
| Jade Poteat | 7.625 | 7625
| Nadine Butzhammer | 0.3125 | 312.5
| Daniel Wörner | 21.5 | 21500
| Sanat Gautam | 14.125 | 14125
| 21 1037 | 179.6875 | 209831.25
| Gerhard Günther | 31.5 | 42525
| Rasa Rintallo | 43.4375 | 43437.5
| Stefan Köstenbauer | 1.125 | 1518.75
| Victor Peters | 3.8438 | 3843.75
| Michael Habel | 53.5 | 72225
| Maximilian Schellenberger | 3.2812 | 3281.25
| Sona Latifyan | 43 | 43000
| 21 1040 | 6.5 | 6500
| Jade Poteat | 6.5 | 6500
| 21 1133 | 0 | 0
| Krunoslav Rukavina | 0 | 0
| 21 1063 | 135.3125 | 170760.625
| Marc Bochtler | 42.125 | 56868.75
| Thorsten Deckers | 21.0625 | 33068.125
| Robert Reti | 17.875 | 28063.75
| Claudio Cangiotti | 13 | 10010
| Yury Nikulin | 26.25 | 26250
| Eldho George | 15 | 16500
| 21 1059 | 45.5 | 61425
| Thomas Thuspaß | 45.5 | 61425
| other | 0 | 24570
| 0 | 0 | 24570
| (blank) | 0 | 24570
| NCC Group GmbH | 0 | 363140.4
| 2410164170 | 0 | 363140.4
| (blank) | 0 | 363140.4
| Osborne Clark | 0 | 20659.69
| TID0001510089 | 0 | 20659.69
| (blank) | 0 | 20659.69
| Virtual Clarity Ltd | 0 | 149488
| 2410164371 | 0 | 149488
| (blank) | 0 | 149488
| Softwaregilde | 0 | 121975
| 2410159840 | 0 | 121975
| (blank) | 0 | 121975
| Horvath & Partner | 0 | 44625
| 2410160374 | 0 | 44625
| (blank) | 0 | 44625
| Ernst & Young | 0 | 98002.0781
| 2410162165 | 0 | 98002.0781
| (blank) | 0 | 98002.0781
| SRLabs | 0 | 8925
| PR964131 | 0 | 8925
| (blank) | 0 | 8925
| DCSO | 0 | 0
| 0 | 0 | 0
| (blank) | 0 | 0
| SecAttack | 0 | 22312.5
| 0 | 0 | 22312.5
| (blank) | 0 | 22312.5
| (blank) | 2767.8155 | 3482475.2593
| (blank) | 2767.8155 | 3482475.2593
| (blank) | 2767.8155 | 3482475.2593
| (blank) | 2767.8155 | 3482475.2593
| non-Labor | 1 | 210543.769
| AZ Technology | 1 | 107250.619
| CNTR0010616 | 0 | 0
| Licence costs | 0 | 0
| CNTR0010338 | 0 | 32401.999
| Splunk Licenses + Server | 0 | 0
| ZeroFox Licenses | 0 | 32401.999
| CNTR0010333 | 0 | 0
| Splunk Licenses + Server | 0 | 0
| CNTR0010325 | 0 | 0
| HW / infrastructure | 0 | 0
| CNTR0010327 | 0 | 0
| Local SMEs for AVC, FMO | 0 | 0
| AZ Tech America HW | 0 | 0
| CNTR0010332 | 1 | 74848.62
| Cyarx Siemplify | 1 | 74848.62
| CNTR0010329 | 0 | 0
| AWS / Azure cloud | 0 | 0
| CNTR0010618 | 0 | 0
| HW | 0 | 0
| other | 0 | 103293.15
| 0 | 0 | 103293.15
| (blank) | 0 | 103293.15
| Sum | 5535.6311 | 8219441.3367

## M11 (hidden)
M11
Measure Lead: Jeremy Fareau
Pillar Lead: Carsten Scholz
Duration: 01.02.2017-31.12.2018
Planned Total | #N/A
Approved Total | #N/A
Spent Labor | #N/A
Spent non-Labor | #N/A
Spent Total | #N/A
Forecast Total | #N/A
| Measure | (All)
|  | Jan |  | Feb | Mrz | Apr | Mai | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total
| Resources & Contracts | PD Total | EUR Total
| Labor | 2766.8155 | 4526422.3084
Comment | AZ Technology | 2048.878 | 2833818.6402
| 0 | 0 | 297500
| (blank) | 0 | 297500
| CNTR0010544 | 110.4647 | 157099.0619
| Andrea Scotti | 0 | 0
| Wolfgang Elsner | 0 | 0
| Alexander Heinze | 0 | 0
| Thomas Huber | 0 | 0
| Jagoda Matys | 0 | 0
| Markus Schnier | 0 | 0
| Sergej Reißig | 55.0018 | 83266.9815
| Binoj Baburaj | 0 | 0
| IAM Architect (Cygna) | 2.4114 | 3159.8592
| NN india | 0 | 0
| Michael Holder | 0 | 0
| Youssef Dahmouni | 0 | 0
| Nina Kaufmann | 20.9999 | 27517.875
| Viktoryia Nikifaravets | 32.0516 | 43154.3461
| CNTR0010615 | 121.7529 | 173433.2076
| Alexander Heinze | 0 | 0
| Jagoda Matys | 0 | 0
| Srdan Mavrenski | 55.0018 | 83266.9815
| Itai Schwartz | 31.2506 | 42075.8024
| NN india | 0 | 0
| Francois Pernayan | 31.2506 | 42075.8024
| Matt Gibson | 0 | 0
| Christian Bolterauer | 4.25 | 6014.6213
| CNTR0010616 | 68.1618 | 102967.1383
| Alexander Heinze | 0 | 0
| Thomas Huber | 0 | 0
| Reza Memarian | 55.0018 | 83266.9815
| Markus Schnier | 0 | 0
| NN india | 0 | 0
| Youssef Dahmouni | 0 | 0
| Walter Hofer | 0 | 0
| Balasz Razs | 0 | 0
| Ivan Markovic | 13.16 | 19700.1568
| Product SME | 0 | 0
| CNTR0010562 | 5 | 7850
| Thomas Huber | 0 | 0
| Markus Schnier | 0 | 0
| Clemens Friedrich | 5 | 7850
| Gerhard Schneider | 0 | 0
| DGI | 0 | 0
| CNTR0010336 | 152.1775 | 271131.6326
| Thomas Huber | 0 | 0
| Markus Schnier | 0 | 0
| Daniela Betz | 45.9375 | 65010.9849
| Bastian Kastner | 45.25 | 47435.575
| Clemens Friedrich | 0 | 0
| Gerhard Schneider | 3.77 | 7653.1
| Björn Hansen / Markus Feuerstein | 0 | 85551.9727
| Rudresh Subramanian | 20.22 | 30330
| Guelsah Uestelci | 37 | 35150
| CNTR0010335 | 56 | 64575.28
| N.N. | 0 | 0
| Markus Gatter | 56 | 64575.28
| Jakob Schusser | 0 | 0
| Gabriella Nagy | 0 | 0
| N.N. // SME 2 | 0 | 0
| N.N. // Sr. Analyst | 0 | 0
| SR Labs Autobahn | 0 | 0
| OE Effort | 0 | 0
| Ben Brüggen | 0 | 0
| CNTR0010338 | 152.3738 | 157766.1581
| Rene Pferner | 0 | 0
| Thomas Huber | 1 | 2030
| Markus Schnier | 1 | 2030
| N.N. | 0 | 0
| Clemens Friedrich | 15 | 23550
| Gerhard Schneider | 6.03 | 12240.9
| Anna Hartl | 53.8125 | 56411.6437
| Alina Lobova | 55.75 | 46754.18
| Stefan Kösters | 12.2812 | 12874.4344
| Kühnlenz / 2wmedia | 0 | 0
| Natalia Nikitana | 0 | 0
| IT Seal | 0 | 0
| Aishwarya Nangude / Sarabjit Singh | 0 | 0
| Meera Patel | 7.5 | 1875
| CNTR0010333 | 245.5625 | 276810.2324
| Christoph Lenz | 31.625 | 33152.4875
| Thomas Huber | 0 | 0
| Markus Schnier | 0 | 0
| Corinna Koch | 19.375 | 20310.8125
| Vasanthan Dhanasingh | 0 | 0
| Clemens Friedrich | 0 | 0
| Gerhard Schneider | 0 | 0
| Sven Lierzer | 48.875 | 57921.9165
| Tobias Lichtenberg | 12.6875 | 17955.4134
| Stanislav Khotinok | 34.125 | 39350.5613
| Alexander Leonhardt | 56.75 | 65440.1275
| Yuri Nikulin | 23.375 | 26954.4138
| Maria Thanner | 18.75 | 15724.5
| SNOW-Team | 0 | 0
| Splunk Team | 0 | 0
| Ankita Mane | 0 | 0
| Martin Gerlowski | 0 | 0
| Deepak Krishnan | 0 | 0
| K Harikrishnan | 0 | 0
| CNTR0010337 | 19.2596 | 32647.4087
| Placeholder | 0 | 0
| Matthias Kickstein | 0 | 0
| Computacenter | 0 | 0
| Ernst & Young | 19.2596 | 32647.4087
| CNTR0010325 | 29.75 | 16237.5
| Alex Lee | 0 | 0
| Lucas Tscherter | 0 | 0
| Corinna Koch | 0 | 0
| Dhanya Kalathil | 19.75 | 4937.5
| Mark de Vera | 0 | 0
| Balasz Racz | 10 | 11300
| Arunlal Nair | 0 | 0
| Local Infra setup support | 0 | 0
| Local SMEs for AVC, FMO | 0 | 0
| Cabling APAC | 0 | 0
| CNTR0010327 | 20 | 5320
| Thomas Huber | 0 | 0
| Gereon Volker | 0 | 0
| Lucas Tscherter | 0 | 0
| Markus Schnier | 0 | 0
| Thomas Bringewald | 2 | 2260
| Andrei Maslov | 0 | 0
| Patrick Zeitz | 0 | 0
| Armando Diaz | 0 | 0
| Ron Johnson | 0 | 0
| Jithin Varghese | 18 | 3060
| AZ Tech America Labor | 0 | 0
| Service Manager | 0 | 0
| CNTR0010332 | 177.713 | 270824.8831
| Timothy Drost | 51.25 | 56077.4981
| Thomas Huber | 1 | 2030
| Holger Steinlechner | 1.78 | 2011.4
| Lucas Tscherter | 20.42 | 32059.4
| Markus Schnier | 1 | 2030
| Olivier Ma | 0 | 0
| Rebecca Dengl | 0.263 | 297.19
| Andrei Maslov | 5 | 5650
| Racz Balazs | 2 | 2260
| Jimmy Braun | 0 | 0
| Cyarx Siemplify | 95 | 168409.395
| CMDB | 0 | 0
| CNTR0010329 | 97.9983 | 221663.7262
| Thomas Huber | 1 | 2030
| Gereon Volker | 0 | 0
| Lucas Tscherter | 27.79 | 43630.3
| Markus Schnier | 1 | 2030
| Thomas Bringewald | 5 | 5650
| Rebecca Dengl | 0.526 | 594.38
| Felix Hertin | 3.2615 | 5242.0231
| Lukas Thiele | 9.4208 | 5242.0231
| Holger Wache | 25 | 78622.5
| Tobias Martin | 25 | 78622.5
| Deloitte | 0 | 0
| CNTR0010709 | 11 | 16796.845
| Thomas Huber | 1 | 2030
| Lucas Tscherter | 0 | 0
| Markus Schnier | 1 | 2030
| Krunoslav Rukavina | 9 | 12736.845
| Joachim Steinberger | 0 | 0
| Elastic | 0 | 0
| Proofpoint | 0 | 0
| CNTR0010564 | 513.2647 | 444921.049
| Markus Traumueller | 10 | 11300
| Karim, Hasan | 57 | 59850
| Bojarski, Eduard | 57 | 112122.99
| Kayali, Ismail | 57 | 72645.93
| Stettner, Julia | 57 | 80717.13
| Tulshidas Thamke, Budhesh | 57 | 9120
| Sunderdas, Shilpa | 58 | 9280
| Bönigk, Julian | 10 | 11300
| Sora Mustafa (AUG-OCT only) | 52 | 61880
| Vidya Baskaran Reddy | 57 | 9690
| S, Shibi (partily on IP&G) | 41.2647 | 7014.999
| CNTR0010563 | 109.9746 | 125589.2982
| Günther, Gerhard | 15.1579 | 20463.1579
| Poteat, Jade | 22.9868 | 22986.8421
| Warnholz, Benjamin | 8 | 16000
| Qualys Team (AVM) | 0 | 0
| Uysal, Ismail (Project Manager) | 51.1456 | 51145.614
| Goldschmidt, Andreas (SNOW Principal Architect) | 10.6842 | 14423.6842
| AMC Devops Engineer (Internal) | 0 | 0
| APM Devops Engineer (Internal) | 0 | 0
| EMS Devops Engineer (Internal) | 0 | 0
| Workspace Intelligence Internal – Technical SME | 0 | 0
| SNOW Performance Analytics team | 0 | 0
| SNOW Development Teams | 2 | 570
| Workspace Intelligence Vendor – Technical SME | 0 | 0
| SNOW SAM efforts | 0 | 0
| SNOW CMDB | 0 | 0
| CyNet | 0 | 0
| Security Foundation Team | 0 | 0
| CNTR0010576 | 27.5 | 35432.54
| Marc Bochtler | 18 | 25473.69
| Alexander Heinze | 0 | 0
| Tobias Butz | 0 | 0
| NN | 0 | 0
| NN india | 0 | 0
| Yury Nikolin | 9.5 | 9958.85
| Thomas Felder | 0 | 0
| CNTR0010334 | 130.125 | 153138.2055
| Martin Schurm | 27 | 42102.3487
| Tobias Krichel | 62.875 | 74513.3568
| Thomas Huber | 1 | 2030
| Markus Schnier | 1 | 2030
| Dan Read | 0 | 0
| N.N. / Support Dan | 0 | 0
| Ankur Tomar | 0 | 0
| Naman Agrawal | 21.25 | 5312.5
| Clemens Friedrich | 16 | 25120
| Gerhard Schneider | 1 | 2030
| OAM302 | 0 | 0
| Alexander Heinze | 0 | 0
| Daming Yang | 0 | 0
| Manoj Selvakumar | 0 | 0
| David Barton | 0 | 0
| Raja Rajcic | 0 | 0
| Lawrence Tengan | 0 | 0
| Travis Chun | 0 | 0
| Johannes Bross | 0 | 0
| Tuan Minh Nguyen | 0 | 0
| Tobias Tischler | 0 | 0
| Djamel Tazerout | 0 | 0
| Dirk Addicks | 0 | 0
| Forgerock Licence | 0 | 0
| CNTR0010589 | 0 | 0
| Placeholder | 0 | 0
| OAM299 | 0 | 0
| Placeholder | 0 | 0
| CNTR0010618 | 0.79973 | 2114.4735
| Birgit Jarosch | 0.79973 | 2114.4735
| Wolfgang Elsner | 0 | 0
| Alexander Heinze | 0 | 0
| Jagoda Matys | 0 | 0
| N.N. | 0 | 0
| Mitja Ledowski | 0 | 0
| Ingmar Janßen-Holldiek | 0 | 0
| Michael Holder | 0 | 0
| Sinoop K S | 0 | 0
| J. Thomas | 0 | 0
| Madalina Paslaru | 0 | 0
| Daniel Ettenhuber | 0 | 0
| OAM289 | 0 | 0
| Placeholder | 0 | 0
| CNTR0010617 | 0 | 0
| (blank) | 0 | 0
| Alexander Heinze | 0 | 0
| Christine Schlüter | 0 | 0
| Günter Sanktjohanser | 0 | 0
| Metafinanz | 717.9375 | 838906
| 21 0427 | 162.5625 | 155742.25
| Julian Steinfeld | 53 | 58936
| Manuel Hahn | 43.5312 | 42660.625
| Matthias Müller | 66.0312 | 54145.625
| 21 1068 | 107.1875 | 140290.625
| Jonathan Reynolds | 16.75 | 16750
| Samuel Hurst | 38.9688 | 52607.8125
| Kris Harms | 39 | 56550
| Nora von Schenckendorff | 5.4688 | 7382.8125
| Frank Markussen | 1.375 | 1375
| Anette Hettenkofer | 0.125 | 125
| Julia Netesa | 5.5 | 5500
| 21 1079 | 81.1875 | 94356.25
| George Dietrichsbruckner | 37.625 | 50793.75
| Jade Poteat | 7.625 | 7625
| Nadine Butzhammer | 0.3125 | 312.5
| Daniel Wörner | 21.5 | 21500
| Sanat Gautam | 14.125 | 14125
| 21 1037 | 179.6875 | 209831.25
| Gerhard Günther | 31.5 | 42525
| Rasa Rintallo | 43.4375 | 43437.5
| Stefan Köstenbauer | 1.125 | 1518.75
| Victor Peters | 3.8438 | 3843.75
| Michael Habel | 53.5 | 72225
| Maximilian Schellenberger | 3.2812 | 3281.25
| Sona Latifyan | 43 | 43000
| 21 1040 | 6.5 | 6500
| Jade Poteat | 6.5 | 6500
| 21 1133 | 0 | 0
| Krunoslav Rukavina | 0 | 0
| 21 1063 | 135.3125 | 170760.625
| Marc Bochtler | 42.125 | 56868.75
| Thorsten Deckers | 21.0625 | 33068.125
| Robert Reti | 17.875 | 28063.75
| Claudio Cangiotti | 13 | 10010
| Yury Nikulin | 26.25 | 26250
| Eldho George | 15 | 16500
| 21 1059 | 45.5 | 61425
| Thomas Thuspaß | 45.5 | 61425
| other | 0 | 24570
| 0 | 0 | 24570
| (blank) | 0 | 24570
| NCC Group GmbH | 0 | 363140.4
| 2410164170 | 0 | 363140.4
| (blank) | 0 | 363140.4
| Osborne Clark | 0 | 20659.69
| TID0001510089 | 0 | 20659.69
| (blank) | 0 | 20659.69
| Virtual Clarity Ltd | 0 | 149488
| 2410164371 | 0 | 149488
| (blank) | 0 | 149488
| Softwaregilde | 0 | 121975
| 2410159840 | 0 | 121975
| (blank) | 0 | 121975
| Horvath & Partner | 0 | 44625
| 2410160374 | 0 | 44625
| (blank) | 0 | 44625
| Ernst & Young | 0 | 98002.0781
| 2410162165 | 0 | 98002.0781
| (blank) | 0 | 98002.0781
| SRLabs | 0 | 8925
| PR964131 | 0 | 8925
| (blank) | 0 | 8925
| DCSO | 0 | 0
| 0 | 0 | 0
| (blank) | 0 | 0
| SecAttack | 0 | 22312.5
| 0 | 0 | 22312.5
| (blank) | 0 | 22312.5
| (blank) | 2767.8155 | 3482475.2593
| (blank) | 2767.8155 | 3482475.2593
| (blank) | 2767.8155 | 3482475.2593
| (blank) | 2767.8155 | 3482475.2593
| non-Labor | 1 | 210543.769
| AZ Technology | 1 | 107250.619
| CNTR0010616 | 0 | 0
| Licence costs | 0 | 0
| CNTR0010338 | 0 | 32401.999
| Splunk Licenses + Server | 0 | 0
| ZeroFox Licenses | 0 | 32401.999
| CNTR0010333 | 0 | 0
| Splunk Licenses + Server | 0 | 0
| CNTR0010325 | 0 | 0
| HW / infrastructure | 0 | 0
| CNTR0010327 | 0 | 0
| Local SMEs for AVC, FMO | 0 | 0
| AZ Tech America HW | 0 | 0
| CNTR0010332 | 1 | 74848.62
| Cyarx Siemplify | 1 | 74848.62
| CNTR0010329 | 0 | 0
| AWS / Azure cloud | 0 | 0
| CNTR0010618 | 0 | 0
| HW | 0 | 0
| other | 0 | 103293.15
| 0 | 0 | 103293.15
| (blank) | 0 | 103293.15
| Sum | 5535.6311 | 8219441.3367

## M81 (hidden)
M81
Measure Lead: Robert Feser
Pillar Lead: Carsten Scholz
Duration: 01.08.2017-31.12.2018
Planned Total | #N/A
Approved Total | #N/A
Spent Labor | #N/A
Spent non-Labor | #N/A
Spent Total | #N/A
Forecast Total | #N/A
| Measure | (All)
|  | Jan |  | Feb | Mrz | Apr | Mai | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total
| Resources & Contracts | PD Total | EUR Total
| Labor | 2766.8155 | 4526422.3084
Comment | AZ Technology | 2048.878 | 2833818.6402
| 0 | 0 | 297500
| (blank) | 0 | 297500
| CNTR0010544 | 110.4647 | 157099.0619
| Andrea Scotti | 0 | 0
| Wolfgang Elsner | 0 | 0
| Alexander Heinze | 0 | 0
| Thomas Huber | 0 | 0
| Jagoda Matys | 0 | 0
| Markus Schnier | 0 | 0
| Sergej Reißig | 55.0018 | 83266.9815
| Binoj Baburaj | 0 | 0
| IAM Architect (Cygna) | 2.4114 | 3159.8592
| NN india | 0 | 0
| Michael Holder | 0 | 0
| Youssef Dahmouni | 0 | 0
| Nina Kaufmann | 20.9999 | 27517.875
| Viktoryia Nikifaravets | 32.0516 | 43154.3461
| CNTR0010615 | 121.7529 | 173433.2076
| Alexander Heinze | 0 | 0
| Jagoda Matys | 0 | 0
| Srdan Mavrenski | 55.0018 | 83266.9815
| Itai Schwartz | 31.2506 | 42075.8024
| NN india | 0 | 0
| Francois Pernayan | 31.2506 | 42075.8024
| Matt Gibson | 0 | 0
| Christian Bolterauer | 4.25 | 6014.6213
| CNTR0010616 | 68.1618 | 102967.1383
| Alexander Heinze | 0 | 0
| Thomas Huber | 0 | 0
| Reza Memarian | 55.0018 | 83266.9815
| Markus Schnier | 0 | 0
| NN india | 0 | 0
| Youssef Dahmouni | 0 | 0
| Walter Hofer | 0 | 0
| Balasz Razs | 0 | 0
| Ivan Markovic | 13.16 | 19700.1568
| Product SME | 0 | 0
| CNTR0010562 | 5 | 7850
| Thomas Huber | 0 | 0
| Markus Schnier | 0 | 0
| Clemens Friedrich | 5 | 7850
| Gerhard Schneider | 0 | 0
| DGI | 0 | 0
| CNTR0010336 | 152.1775 | 271131.6326
| Thomas Huber | 0 | 0
| Markus Schnier | 0 | 0
| Daniela Betz | 45.9375 | 65010.9849
| Bastian Kastner | 45.25 | 47435.575
| Clemens Friedrich | 0 | 0
| Gerhard Schneider | 3.77 | 7653.1
| Björn Hansen / Markus Feuerstein | 0 | 85551.9727
| Rudresh Subramanian | 20.22 | 30330
| Guelsah Uestelci | 37 | 35150
| CNTR0010335 | 56 | 64575.28
| N.N. | 0 | 0
| Markus Gatter | 56 | 64575.28
| Jakob Schusser | 0 | 0
| Gabriella Nagy | 0 | 0
| N.N. // SME 2 | 0 | 0
| N.N. // Sr. Analyst | 0 | 0
| SR Labs Autobahn | 0 | 0
| OE Effort | 0 | 0
| Ben Brüggen | 0 | 0
| CNTR0010338 | 152.3738 | 157766.1581
| Rene Pferner | 0 | 0
| Thomas Huber | 1 | 2030
| Markus Schnier | 1 | 2030
| N.N. | 0 | 0
| Clemens Friedrich | 15 | 23550
| Gerhard Schneider | 6.03 | 12240.9
| Anna Hartl | 53.8125 | 56411.6437
| Alina Lobova | 55.75 | 46754.18
| Stefan Kösters | 12.2812 | 12874.4344
| Kühnlenz / 2wmedia | 0 | 0
| Natalia Nikitana | 0 | 0
| IT Seal | 0 | 0
| Aishwarya Nangude / Sarabjit Singh | 0 | 0
| Meera Patel | 7.5 | 1875
| CNTR0010333 | 245.5625 | 276810.2324
| Christoph Lenz | 31.625 | 33152.4875
| Thomas Huber | 0 | 0
| Markus Schnier | 0 | 0
| Corinna Koch | 19.375 | 20310.8125
| Vasanthan Dhanasingh | 0 | 0
| Clemens Friedrich | 0 | 0
| Gerhard Schneider | 0 | 0
| Sven Lierzer | 48.875 | 57921.9165
| Tobias Lichtenberg | 12.6875 | 17955.4134
| Stanislav Khotinok | 34.125 | 39350.5613
| Alexander Leonhardt | 56.75 | 65440.1275
| Yuri Nikulin | 23.375 | 26954.4138
| Maria Thanner | 18.75 | 15724.5
| SNOW-Team | 0 | 0
| Splunk Team | 0 | 0
| Ankita Mane | 0 | 0
| Martin Gerlowski | 0 | 0
| Deepak Krishnan | 0 | 0
| K Harikrishnan | 0 | 0
| CNTR0010337 | 19.2596 | 32647.4087
| Placeholder | 0 | 0
| Matthias Kickstein | 0 | 0
| Computacenter | 0 | 0
| Ernst & Young | 19.2596 | 32647.4087
| CNTR0010325 | 29.75 | 16237.5
| Alex Lee | 0 | 0
| Lucas Tscherter | 0 | 0
| Corinna Koch | 0 | 0
| Dhanya Kalathil | 19.75 | 4937.5
| Mark de Vera | 0 | 0
| Balasz Racz | 10 | 11300
| Arunlal Nair | 0 | 0
| Local Infra setup support | 0 | 0
| Local SMEs for AVC, FMO | 0 | 0
| Cabling APAC | 0 | 0
| CNTR0010327 | 20 | 5320
| Thomas Huber | 0 | 0
| Gereon Volker | 0 | 0
| Lucas Tscherter | 0 | 0
| Markus Schnier | 0 | 0
| Thomas Bringewald | 2 | 2260
| Andrei Maslov | 0 | 0
| Patrick Zeitz | 0 | 0
| Armando Diaz | 0 | 0
| Ron Johnson | 0 | 0
| Jithin Varghese | 18 | 3060
| AZ Tech America Labor | 0 | 0
| Service Manager | 0 | 0
| CNTR0010332 | 177.713 | 270824.8831
| Timothy Drost | 51.25 | 56077.4981
| Thomas Huber | 1 | 2030
| Holger Steinlechner | 1.78 | 2011.4
| Lucas Tscherter | 20.42 | 32059.4
| Markus Schnier | 1 | 2030
| Olivier Ma | 0 | 0
| Rebecca Dengl | 0.263 | 297.19
| Andrei Maslov | 5 | 5650
| Racz Balazs | 2 | 2260
| Jimmy Braun | 0 | 0
| Cyarx Siemplify | 95 | 168409.395
| CMDB | 0 | 0
| CNTR0010329 | 97.9983 | 221663.7262
| Thomas Huber | 1 | 2030
| Gereon Volker | 0 | 0
| Lucas Tscherter | 27.79 | 43630.3
| Markus Schnier | 1 | 2030
| Thomas Bringewald | 5 | 5650
| Rebecca Dengl | 0.526 | 594.38
| Felix Hertin | 3.2615 | 5242.0231
| Lukas Thiele | 9.4208 | 5242.0231
| Holger Wache | 25 | 78622.5
| Tobias Martin | 25 | 78622.5
| Deloitte | 0 | 0
| CNTR0010709 | 11 | 16796.845
| Thomas Huber | 1 | 2030
| Lucas Tscherter | 0 | 0
| Markus Schnier | 1 | 2030
| Krunoslav Rukavina | 9 | 12736.845
| Joachim Steinberger | 0 | 0
| Elastic | 0 | 0
| Proofpoint | 0 | 0
| CNTR0010564 | 513.2647 | 444921.049
| Markus Traumueller | 10 | 11300
| Karim, Hasan | 57 | 59850
| Bojarski, Eduard | 57 | 112122.99
| Kayali, Ismail | 57 | 72645.93
| Stettner, Julia | 57 | 80717.13
| Tulshidas Thamke, Budhesh | 57 | 9120
| Sunderdas, Shilpa | 58 | 9280
| Bönigk, Julian | 10 | 11300
| Sora Mustafa (AUG-OCT only) | 52 | 61880
| Vidya Baskaran Reddy | 57 | 9690
| S, Shibi (partily on IP&G) | 41.2647 | 7014.999
| CNTR0010563 | 109.9746 | 125589.2982
| Günther, Gerhard | 15.1579 | 20463.1579
| Poteat, Jade | 22.9868 | 22986.8421
| Warnholz, Benjamin | 8 | 16000
| Qualys Team (AVM) | 0 | 0
| Uysal, Ismail (Project Manager) | 51.1456 | 51145.614
| Goldschmidt, Andreas (SNOW Principal Architect) | 10.6842 | 14423.6842
| AMC Devops Engineer (Internal) | 0 | 0
| APM Devops Engineer (Internal) | 0 | 0
| EMS Devops Engineer (Internal) | 0 | 0
| Workspace Intelligence Internal – Technical SME | 0 | 0
| SNOW Performance Analytics team | 0 | 0
| SNOW Development Teams | 2 | 570
| Workspace Intelligence Vendor – Technical SME | 0 | 0
| SNOW SAM efforts | 0 | 0
| SNOW CMDB | 0 | 0
| CyNet | 0 | 0
| Security Foundation Team | 0 | 0
| CNTR0010576 | 27.5 | 35432.54
| Marc Bochtler | 18 | 25473.69
| Alexander Heinze | 0 | 0
| Tobias Butz | 0 | 0
| NN | 0 | 0
| NN india | 0 | 0
| Yury Nikolin | 9.5 | 9958.85
| Thomas Felder | 0 | 0
| CNTR0010334 | 130.125 | 153138.2055
| Martin Schurm | 27 | 42102.3487
| Tobias Krichel | 62.875 | 74513.3568
| Thomas Huber | 1 | 2030
| Markus Schnier | 1 | 2030
| Dan Read | 0 | 0
| N.N. / Support Dan | 0 | 0
| Ankur Tomar | 0 | 0
| Naman Agrawal | 21.25 | 5312.5
| Clemens Friedrich | 16 | 25120
| Gerhard Schneider | 1 | 2030
| OAM302 | 0 | 0
| Alexander Heinze | 0 | 0
| Daming Yang | 0 | 0
| Manoj Selvakumar | 0 | 0
| David Barton | 0 | 0
| Raja Rajcic | 0 | 0
| Lawrence Tengan | 0 | 0
| Travis Chun | 0 | 0
| Johannes Bross | 0 | 0
| Tuan Minh Nguyen | 0 | 0
| Tobias Tischler | 0 | 0
| Djamel Tazerout | 0 | 0
| Dirk Addicks | 0 | 0
| Forgerock Licence | 0 | 0
| CNTR0010589 | 0 | 0
| Placeholder | 0 | 0
| OAM299 | 0 | 0
| Placeholder | 0 | 0
| CNTR0010618 | 0.79973 | 2114.4735
| Birgit Jarosch | 0.79973 | 2114.4735
| Wolfgang Elsner | 0 | 0
| Alexander Heinze | 0 | 0
| Jagoda Matys | 0 | 0
| N.N. | 0 | 0
| Mitja Ledowski | 0 | 0
| Ingmar Janßen-Holldiek | 0 | 0
| Michael Holder | 0 | 0
| Sinoop K S | 0 | 0
| J. Thomas | 0 | 0
| Madalina Paslaru | 0 | 0
| Daniel Ettenhuber | 0 | 0
| OAM289 | 0 | 0
| Placeholder | 0 | 0
| CNTR0010617 | 0 | 0
| (blank) | 0 | 0
| Alexander Heinze | 0 | 0
| Christine Schlüter | 0 | 0
| Günter Sanktjohanser | 0 | 0
| Metafinanz | 717.9375 | 838906
| 21 0427 | 162.5625 | 155742.25
| Julian Steinfeld | 53 | 58936
| Manuel Hahn | 43.5312 | 42660.625
| Matthias Müller | 66.0312 | 54145.625
| 21 1068 | 107.1875 | 140290.625
| Jonathan Reynolds | 16.75 | 16750
| Samuel Hurst | 38.9688 | 52607.8125
| Kris Harms | 39 | 56550
| Nora von Schenckendorff | 5.4688 | 7382.8125
| Frank Markussen | 1.375 | 1375
| Anette Hettenkofer | 0.125 | 125
| Julia Netesa | 5.5 | 5500
| 21 1079 | 81.1875 | 94356.25
| George Dietrichsbruckner | 37.625 | 50793.75
| Jade Poteat | 7.625 | 7625
| Nadine Butzhammer | 0.3125 | 312.5
| Daniel Wörner | 21.5 | 21500
| Sanat Gautam | 14.125 | 14125
| 21 1037 | 179.6875 | 209831.25
| Gerhard Günther | 31.5 | 42525
| Rasa Rintallo | 43.4375 | 43437.5
| Stefan Köstenbauer | 1.125 | 1518.75
| Victor Peters | 3.8438 | 3843.75
| Michael Habel | 53.5 | 72225
| Maximilian Schellenberger | 3.2812 | 3281.25
| Sona Latifyan | 43 | 43000
| 21 1040 | 6.5 | 6500
| Jade Poteat | 6.5 | 6500
| 21 1133 | 0 | 0
| Krunoslav Rukavina | 0 | 0
| 21 1063 | 135.3125 | 170760.625
| Marc Bochtler | 42.125 | 56868.75
| Thorsten Deckers | 21.0625 | 33068.125
| Robert Reti | 17.875 | 28063.75
| Claudio Cangiotti | 13 | 10010
| Yury Nikulin | 26.25 | 26250
| Eldho George | 15 | 16500
| 21 1059 | 45.5 | 61425
| Thomas Thuspaß | 45.5 | 61425
| other | 0 | 24570
| 0 | 0 | 24570
| (blank) | 0 | 24570
| NCC Group GmbH | 0 | 363140.4
| 2410164170 | 0 | 363140.4
| (blank) | 0 | 363140.4
| Osborne Clark | 0 | 20659.69
| TID0001510089 | 0 | 20659.69
| (blank) | 0 | 20659.69
| Virtual Clarity Ltd | 0 | 149488
| 2410164371 | 0 | 149488
| (blank) | 0 | 149488
| Softwaregilde | 0 | 121975
| 2410159840 | 0 | 121975
| (blank) | 0 | 121975
| Horvath & Partner | 0 | 44625
| 2410160374 | 0 | 44625
| (blank) | 0 | 44625
| Ernst & Young | 0 | 98002.0781
| 2410162165 | 0 | 98002.0781
| (blank) | 0 | 98002.0781
| SRLabs | 0 | 8925
| PR964131 | 0 | 8925
| (blank) | 0 | 8925
| DCSO | 0 | 0
| 0 | 0 | 0
| (blank) | 0 | 0
| SecAttack | 0 | 22312.5
| 0 | 0 | 22312.5
| (blank) | 0 | 22312.5
| (blank) | 2767.8155 | 3482475.2593
| (blank) | 2767.8155 | 3482475.2593
| (blank) | 2767.8155 | 3482475.2593
| (blank) | 2767.8155 | 3482475.2593
| non-Labor | 1 | 210543.769
| AZ Technology | 1 | 107250.619
| CNTR0010616 | 0 | 0
| Licence costs | 0 | 0
| CNTR0010338 | 0 | 32401.999
| Splunk Licenses + Server | 0 | 0
| ZeroFox Licenses | 0 | 32401.999
| CNTR0010333 | 0 | 0
| Splunk Licenses + Server | 0 | 0
| CNTR0010325 | 0 | 0
| HW / infrastructure | 0 | 0
| CNTR0010327 | 0 | 0
| Local SMEs for AVC, FMO | 0 | 0
| AZ Tech America HW | 0 | 0
| CNTR0010332 | 1 | 74848.62
| Cyarx Siemplify | 1 | 74848.62
| CNTR0010329 | 0 | 0
| AWS / Azure cloud | 0 | 0
| CNTR0010618 | 0 | 0
| HW | 0 | 0
| other | 0 | 103293.15
| 0 | 0 | 103293.15
| (blank) | 0 | 103293.15
| Sum | 5535.6311 | 8219441.3367

## M45 (hidden)
M45
Measure Lead: Andrea Rupprecht
Pillar Lead: Carsten Scholz
Duration: 01.11.2016-31.12.2018
Planned Total | #N/A
Approved Total | #N/A
Spent Labor | #N/A
Spent non-Labor | #N/A
Spent Total | #N/A
Forecast Total | #N/A
| Measure | (All)
|  | Jan |  | Feb | Mrz | Apr | Mai | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total
| Resources & Contracts | PD Total | EUR Total
| Labor | 2766.8155 | 4526422.3084
Comment | AZ Technology | 2048.878 | 2833818.6402
| 0 | 0 | 297500
| (blank) | 0 | 297500
| CNTR0010544 | 110.4647 | 157099.0619
| Andrea Scotti | 0 | 0
| Wolfgang Elsner | 0 | 0
| Alexander Heinze | 0 | 0
| Thomas Huber | 0 | 0
| Jagoda Matys | 0 | 0
| Markus Schnier | 0 | 0
| Sergej Reißig | 55.0018 | 83266.9815
| Binoj Baburaj | 0 | 0
| IAM Architect (Cygna) | 2.4114 | 3159.8592
| NN india | 0 | 0
| Michael Holder | 0 | 0
| Youssef Dahmouni | 0 | 0
| Nina Kaufmann | 20.9999 | 27517.875
| Viktoryia Nikifaravets | 32.0516 | 43154.3461
| CNTR0010615 | 121.7529 | 173433.2076
| Alexander Heinze | 0 | 0
| Jagoda Matys | 0 | 0
| Srdan Mavrenski | 55.0018 | 83266.9815
| Itai Schwartz | 31.2506 | 42075.8024
| NN india | 0 | 0
| Francois Pernayan | 31.2506 | 42075.8024
| Matt Gibson | 0 | 0
| Christian Bolterauer | 4.25 | 6014.6213
| CNTR0010616 | 68.1618 | 102967.1383
| Alexander Heinze | 0 | 0
| Thomas Huber | 0 | 0
| Reza Memarian | 55.0018 | 83266.9815
| Markus Schnier | 0 | 0
| NN india | 0 | 0
| Youssef Dahmouni | 0 | 0
| Walter Hofer | 0 | 0
| Balasz Razs | 0 | 0
| Ivan Markovic | 13.16 | 19700.1568
| Product SME | 0 | 0
| CNTR0010562 | 5 | 7850
| Thomas Huber | 0 | 0
| Markus Schnier | 0 | 0
| Clemens Friedrich | 5 | 7850
| Gerhard Schneider | 0 | 0
| DGI | 0 | 0
| CNTR0010336 | 152.1775 | 271131.6326
| Thomas Huber | 0 | 0
| Markus Schnier | 0 | 0
| Daniela Betz | 45.9375 | 65010.9849
| Bastian Kastner | 45.25 | 47435.575
| Clemens Friedrich | 0 | 0
| Gerhard Schneider | 3.77 | 7653.1
| Björn Hansen / Markus Feuerstein | 0 | 85551.9727
| Rudresh Subramanian | 20.22 | 30330
| Guelsah Uestelci | 37 | 35150
| CNTR0010335 | 56 | 64575.28
| N.N. | 0 | 0
| Markus Gatter | 56 | 64575.28
| Jakob Schusser | 0 | 0
| Gabriella Nagy | 0 | 0
| N.N. // SME 2 | 0 | 0
| N.N. // Sr. Analyst | 0 | 0
| SR Labs Autobahn | 0 | 0
| OE Effort | 0 | 0
| Ben Brüggen | 0 | 0
| CNTR0010338 | 152.3738 | 157766.1581
| Rene Pferner | 0 | 0
| Thomas Huber | 1 | 2030
| Markus Schnier | 1 | 2030
| N.N. | 0 | 0
| Clemens Friedrich | 15 | 23550
| Gerhard Schneider | 6.03 | 12240.9
| Anna Hartl | 53.8125 | 56411.6437
| Alina Lobova | 55.75 | 46754.18
| Stefan Kösters | 12.2812 | 12874.4344
| Kühnlenz / 2wmedia | 0 | 0
| Natalia Nikitana | 0 | 0
| IT Seal | 0 | 0
| Aishwarya Nangude / Sarabjit Singh | 0 | 0
| Meera Patel | 7.5 | 1875
| CNTR0010333 | 245.5625 | 276810.2324
| Christoph Lenz | 31.625 | 33152.4875
| Thomas Huber | 0 | 0
| Markus Schnier | 0 | 0
| Corinna Koch | 19.375 | 20310.8125
| Vasanthan Dhanasingh | 0 | 0
| Clemens Friedrich | 0 | 0
| Gerhard Schneider | 0 | 0
| Sven Lierzer | 48.875 | 57921.9165
| Tobias Lichtenberg | 12.6875 | 17955.4134
| Stanislav Khotinok | 34.125 | 39350.5613
| Alexander Leonhardt | 56.75 | 65440.1275
| Yuri Nikulin | 23.375 | 26954.4138
| Maria Thanner | 18.75 | 15724.5
| SNOW-Team | 0 | 0
| Splunk Team | 0 | 0
| Ankita Mane | 0 | 0
| Martin Gerlowski | 0 | 0
| Deepak Krishnan | 0 | 0
| K Harikrishnan | 0 | 0
| CNTR0010337 | 19.2596 | 32647.4087
| Placeholder | 0 | 0
| Matthias Kickstein | 0 | 0
| Computacenter | 0 | 0
| Ernst & Young | 19.2596 | 32647.4087
| CNTR0010325 | 29.75 | 16237.5
| Alex Lee | 0 | 0
| Lucas Tscherter | 0 | 0
| Corinna Koch | 0 | 0
| Dhanya Kalathil | 19.75 | 4937.5
| Mark de Vera | 0 | 0
| Balasz Racz | 10 | 11300
| Arunlal Nair | 0 | 0
| Local Infra setup support | 0 | 0
| Local SMEs for AVC, FMO | 0 | 0
| Cabling APAC | 0 | 0
| CNTR0010327 | 20 | 5320
| Thomas Huber | 0 | 0
| Gereon Volker | 0 | 0
| Lucas Tscherter | 0 | 0
| Markus Schnier | 0 | 0
| Thomas Bringewald | 2 | 2260
| Andrei Maslov | 0 | 0
| Patrick Zeitz | 0 | 0
| Armando Diaz | 0 | 0
| Ron Johnson | 0 | 0
| Jithin Varghese | 18 | 3060
| AZ Tech America Labor | 0 | 0
| Service Manager | 0 | 0
| CNTR0010332 | 177.713 | 270824.8831
| Timothy Drost | 51.25 | 56077.4981
| Thomas Huber | 1 | 2030
| Holger Steinlechner | 1.78 | 2011.4
| Lucas Tscherter | 20.42 | 32059.4
| Markus Schnier | 1 | 2030
| Olivier Ma | 0 | 0
| Rebecca Dengl | 0.263 | 297.19
| Andrei Maslov | 5 | 5650
| Racz Balazs | 2 | 2260
| Jimmy Braun | 0 | 0
| Cyarx Siemplify | 95 | 168409.395
| CMDB | 0 | 0
| CNTR0010329 | 97.9983 | 221663.7262
| Thomas Huber | 1 | 2030
| Gereon Volker | 0 | 0
| Lucas Tscherter | 27.79 | 43630.3
| Markus Schnier | 1 | 2030
| Thomas Bringewald | 5 | 5650
| Rebecca Dengl | 0.526 | 594.38
| Felix Hertin | 3.2615 | 5242.0231
| Lukas Thiele | 9.4208 | 5242.0231
| Holger Wache | 25 | 78622.5
| Tobias Martin | 25 | 78622.5
| Deloitte | 0 | 0
| CNTR0010709 | 11 | 16796.845
| Thomas Huber | 1 | 2030
| Lucas Tscherter | 0 | 0
| Markus Schnier | 1 | 2030
| Krunoslav Rukavina | 9 | 12736.845
| Joachim Steinberger | 0 | 0
| Elastic | 0 | 0
| Proofpoint | 0 | 0
| CNTR0010564 | 513.2647 | 444921.049
| Markus Traumueller | 10 | 11300
| Karim, Hasan | 57 | 59850
| Bojarski, Eduard | 57 | 112122.99
| Kayali, Ismail | 57 | 72645.93
| Stettner, Julia | 57 | 80717.13
| Tulshidas Thamke, Budhesh | 57 | 9120
| Sunderdas, Shilpa | 58 | 9280
| Bönigk, Julian | 10 | 11300
| Sora Mustafa (AUG-OCT only) | 52 | 61880
| Vidya Baskaran Reddy | 57 | 9690
| S, Shibi (partily on IP&G) | 41.2647 | 7014.999
| CNTR0010563 | 109.9746 | 125589.2982
| Günther, Gerhard | 15.1579 | 20463.1579
| Poteat, Jade | 22.9868 | 22986.8421
| Warnholz, Benjamin | 8 | 16000
| Qualys Team (AVM) | 0 | 0
| Uysal, Ismail (Project Manager) | 51.1456 | 51145.614
| Goldschmidt, Andreas (SNOW Principal Architect) | 10.6842 | 14423.6842
| AMC Devops Engineer (Internal) | 0 | 0
| APM Devops Engineer (Internal) | 0 | 0
| EMS Devops Engineer (Internal) | 0 | 0
| Workspace Intelligence Internal – Technical SME | 0 | 0
| SNOW Performance Analytics team | 0 | 0
| SNOW Development Teams | 2 | 570
| Workspace Intelligence Vendor – Technical SME | 0 | 0
| SNOW SAM efforts | 0 | 0
| SNOW CMDB | 0 | 0
| CyNet | 0 | 0
| Security Foundation Team | 0 | 0
| CNTR0010576 | 27.5 | 35432.54
| Marc Bochtler | 18 | 25473.69
| Alexander Heinze | 0 | 0
| Tobias Butz | 0 | 0
| NN | 0 | 0
| NN india | 0 | 0
| Yury Nikolin | 9.5 | 9958.85
| Thomas Felder | 0 | 0
| CNTR0010334 | 130.125 | 153138.2055
| Martin Schurm | 27 | 42102.3487
| Tobias Krichel | 62.875 | 74513.3568
| Thomas Huber | 1 | 2030
| Markus Schnier | 1 | 2030
| Dan Read | 0 | 0
| N.N. / Support Dan | 0 | 0
| Ankur Tomar | 0 | 0
| Naman Agrawal | 21.25 | 5312.5
| Clemens Friedrich | 16 | 25120
| Gerhard Schneider | 1 | 2030
| OAM302 | 0 | 0
| Alexander Heinze | 0 | 0
| Daming Yang | 0 | 0
| Manoj Selvakumar | 0 | 0
| David Barton | 0 | 0
| Raja Rajcic | 0 | 0
| Lawrence Tengan | 0 | 0
| Travis Chun | 0 | 0
| Johannes Bross | 0 | 0
| Tuan Minh Nguyen | 0 | 0
| Tobias Tischler | 0 | 0
| Djamel Tazerout | 0 | 0
| Dirk Addicks | 0 | 0
| Forgerock Licence | 0 | 0
| CNTR0010589 | 0 | 0
| Placeholder | 0 | 0
| OAM299 | 0 | 0
| Placeholder | 0 | 0
| CNTR0010618 | 0.79973 | 2114.4735
| Birgit Jarosch | 0.79973 | 2114.4735
| Wolfgang Elsner | 0 | 0
| Alexander Heinze | 0 | 0
| Jagoda Matys | 0 | 0
| N.N. | 0 | 0
| Mitja Ledowski | 0 | 0
| Ingmar Janßen-Holldiek | 0 | 0
| Michael Holder | 0 | 0
| Sinoop K S | 0 | 0
| J. Thomas | 0 | 0
| Madalina Paslaru | 0 | 0
| Daniel Ettenhuber | 0 | 0
| OAM289 | 0 | 0
| Placeholder | 0 | 0
| CNTR0010617 | 0 | 0
| (blank) | 0 | 0
| Alexander Heinze | 0 | 0
| Christine Schlüter | 0 | 0
| Günter Sanktjohanser | 0 | 0
| Metafinanz | 717.9375 | 838906
| 21 0427 | 162.5625 | 155742.25
| Julian Steinfeld | 53 | 58936
| Manuel Hahn | 43.5312 | 42660.625
| Matthias Müller | 66.0312 | 54145.625
| 21 1068 | 107.1875 | 140290.625
| Jonathan Reynolds | 16.75 | 16750
| Samuel Hurst | 38.9688 | 52607.8125
| Kris Harms | 39 | 56550
| Nora von Schenckendorff | 5.4688 | 7382.8125
| Frank Markussen | 1.375 | 1375
| Anette Hettenkofer | 0.125 | 125
| Julia Netesa | 5.5 | 5500
| 21 1079 | 81.1875 | 94356.25
| George Dietrichsbruckner | 37.625 | 50793.75
| Jade Poteat | 7.625 | 7625
| Nadine Butzhammer | 0.3125 | 312.5
| Daniel Wörner | 21.5 | 21500
| Sanat Gautam | 14.125 | 14125
| 21 1037 | 179.6875 | 209831.25
| Gerhard Günther | 31.5 | 42525
| Rasa Rintallo | 43.4375 | 43437.5
| Stefan Köstenbauer | 1.125 | 1518.75
| Victor Peters | 3.8438 | 3843.75
| Michael Habel | 53.5 | 72225
| Maximilian Schellenberger | 3.2812 | 3281.25
| Sona Latifyan | 43 | 43000
| 21 1040 | 6.5 | 6500
| Jade Poteat | 6.5 | 6500
| 21 1133 | 0 | 0
| Krunoslav Rukavina | 0 | 0
| 21 1063 | 135.3125 | 170760.625
| Marc Bochtler | 42.125 | 56868.75
| Thorsten Deckers | 21.0625 | 33068.125
| Robert Reti | 17.875 | 28063.75
| Claudio Cangiotti | 13 | 10010
| Yury Nikulin | 26.25 | 26250
| Eldho George | 15 | 16500
| 21 1059 | 45.5 | 61425
| Thomas Thuspaß | 45.5 | 61425
| other | 0 | 24570
| 0 | 0 | 24570
| (blank) | 0 | 24570
| NCC Group GmbH | 0 | 363140.4
| 2410164170 | 0 | 363140.4
| (blank) | 0 | 363140.4
| Osborne Clark | 0 | 20659.69
| TID0001510089 | 0 | 20659.69
| (blank) | 0 | 20659.69
| Virtual Clarity Ltd | 0 | 149488
| 2410164371 | 0 | 149488
| (blank) | 0 | 149488
| Softwaregilde | 0 | 121975
| 2410159840 | 0 | 121975
| (blank) | 0 | 121975
| Horvath & Partner | 0 | 44625
| 2410160374 | 0 | 44625
| (blank) | 0 | 44625
| Ernst & Young | 0 | 98002.0781
| 2410162165 | 0 | 98002.0781
| (blank) | 0 | 98002.0781
| SRLabs | 0 | 8925
| PR964131 | 0 | 8925
| (blank) | 0 | 8925
| DCSO | 0 | 0
| 0 | 0 | 0
| (blank) | 0 | 0
| SecAttack | 0 | 22312.5
| 0 | 0 | 22312.5
| (blank) | 0 | 22312.5
| (blank) | 2767.8155 | 3482475.2593
| (blank) | 2767.8155 | 3482475.2593
| (blank) | 2767.8155 | 3482475.2593
| (blank) | 2767.8155 | 3482475.2593
| non-Labor | 1 | 210543.769
| AZ Technology | 1 | 107250.619
| CNTR0010616 | 0 | 0
| Licence costs | 0 | 0
| CNTR0010338 | 0 | 32401.999
| Splunk Licenses + Server | 0 | 0
| ZeroFox Licenses | 0 | 32401.999
| CNTR0010333 | 0 | 0
| Splunk Licenses + Server | 0 | 0
| CNTR0010325 | 0 | 0
| HW / infrastructure | 0 | 0
| CNTR0010327 | 0 | 0
| Local SMEs for AVC, FMO | 0 | 0
| AZ Tech America HW | 0 | 0
| CNTR0010332 | 1 | 74848.62
| Cyarx Siemplify | 1 | 74848.62
| CNTR0010329 | 0 | 0
| AWS / Azure cloud | 0 | 0
| CNTR0010618 | 0 | 0
| HW | 0 | 0
| other | 0 | 103293.15
| 0 | 0 | 103293.15
| (blank) | 0 | 103293.15
| Sum | 5535.6311 | 8219441.3367

## M77 (hidden)
M77
Measure Lead: Fabian Topp
Pillar Lead: Carsten Scholz
Duration: 01.08.2017-31.12.2018
* Including M67
Planned Total | #N/A
Approved Total | #N/A
Spent Labor | #N/A
Spent non-Labor | #N/A
Spent Total | #N/A
Forecast Total | #N/A
| Measure | (All)
|  | Jan |  | Feb | Mrz | Apr | Mai | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total
| Resources & Contracts | PD Total | EUR Total
| Labor | 2766.8155 | 4526422.3084
Comment | AZ Technology | 2048.878 | 2833818.6402
| 0 | 0 | 297500
| (blank) | 0 | 297500
| CNTR0010544 | 110.4647 | 157099.0619
| Andrea Scotti | 0 | 0
| Wolfgang Elsner | 0 | 0
| Alexander Heinze | 0 | 0
| Thomas Huber | 0 | 0
| Jagoda Matys | 0 | 0
| Markus Schnier | 0 | 0
| Sergej Reißig | 55.0018 | 83266.9815
| Binoj Baburaj | 0 | 0
| IAM Architect (Cygna) | 2.4114 | 3159.8592
| NN india | 0 | 0
| Michael Holder | 0 | 0
| Youssef Dahmouni | 0 | 0
| Nina Kaufmann | 20.9999 | 27517.875
| Viktoryia Nikifaravets | 32.0516 | 43154.3461
| CNTR0010615 | 121.7529 | 173433.2076
| Alexander Heinze | 0 | 0
| Jagoda Matys | 0 | 0
| Srdan Mavrenski | 55.0018 | 83266.9815
| Itai Schwartz | 31.2506 | 42075.8024
| NN india | 0 | 0
| Francois Pernayan | 31.2506 | 42075.8024
| Matt Gibson | 0 | 0
| Christian Bolterauer | 4.25 | 6014.6213
| CNTR0010616 | 68.1618 | 102967.1383
| Alexander Heinze | 0 | 0
| Thomas Huber | 0 | 0
| Reza Memarian | 55.0018 | 83266.9815
| Markus Schnier | 0 | 0
| NN india | 0 | 0
| Youssef Dahmouni | 0 | 0
| Walter Hofer | 0 | 0
| Balasz Razs | 0 | 0
| Ivan Markovic | 13.16 | 19700.1568
| Product SME | 0 | 0
| CNTR0010562 | 5 | 7850
| Thomas Huber | 0 | 0
| Markus Schnier | 0 | 0
| Clemens Friedrich | 5 | 7850
| Gerhard Schneider | 0 | 0
| DGI | 0 | 0
| CNTR0010336 | 152.1775 | 271131.6326
| Thomas Huber | 0 | 0
| Markus Schnier | 0 | 0
| Daniela Betz | 45.9375 | 65010.9849
| Bastian Kastner | 45.25 | 47435.575
| Clemens Friedrich | 0 | 0
| Gerhard Schneider | 3.77 | 7653.1
| Björn Hansen / Markus Feuerstein | 0 | 85551.9727
| Rudresh Subramanian | 20.22 | 30330
| Guelsah Uestelci | 37 | 35150
| CNTR0010335 | 56 | 64575.28
| N.N. | 0 | 0
| Markus Gatter | 56 | 64575.28
| Jakob Schusser | 0 | 0
| Gabriella Nagy | 0 | 0
| N.N. // SME 2 | 0 | 0
| N.N. // Sr. Analyst | 0 | 0
| SR Labs Autobahn | 0 | 0
| OE Effort | 0 | 0
| Ben Brüggen | 0 | 0
| CNTR0010338 | 152.3738 | 157766.1581
| Rene Pferner | 0 | 0
| Thomas Huber | 1 | 2030
| Markus Schnier | 1 | 2030
| N.N. | 0 | 0
| Clemens Friedrich | 15 | 23550
| Gerhard Schneider | 6.03 | 12240.9
| Anna Hartl | 53.8125 | 56411.6437
| Alina Lobova | 55.75 | 46754.18
| Stefan Kösters | 12.2812 | 12874.4344
| Kühnlenz / 2wmedia | 0 | 0
| Natalia Nikitana | 0 | 0
| IT Seal | 0 | 0
| Aishwarya Nangude / Sarabjit Singh | 0 | 0
| Meera Patel | 7.5 | 1875
| CNTR0010333 | 245.5625 | 276810.2324
| Christoph Lenz | 31.625 | 33152.4875
| Thomas Huber | 0 | 0
| Markus Schnier | 0 | 0
| Corinna Koch | 19.375 | 20310.8125
| Vasanthan Dhanasingh | 0 | 0
| Clemens Friedrich | 0 | 0
| Gerhard Schneider | 0 | 0
| Sven Lierzer | 48.875 | 57921.9165
| Tobias Lichtenberg | 12.6875 | 17955.4134
| Stanislav Khotinok | 34.125 | 39350.5613
| Alexander Leonhardt | 56.75 | 65440.1275
| Yuri Nikulin | 23.375 | 26954.4138
| Maria Thanner | 18.75 | 15724.5
| SNOW-Team | 0 | 0
| Splunk Team | 0 | 0
| Ankita Mane | 0 | 0
| Martin Gerlowski | 0 | 0
| Deepak Krishnan | 0 | 0
| K Harikrishnan | 0 | 0
| CNTR0010337 | 19.2596 | 32647.4087
| Placeholder | 0 | 0
| Matthias Kickstein | 0 | 0
| Computacenter | 0 | 0
| Ernst & Young | 19.2596 | 32647.4087
| CNTR0010325 | 29.75 | 16237.5
| Alex Lee | 0 | 0
| Lucas Tscherter | 0 | 0
| Corinna Koch | 0 | 0
| Dhanya Kalathil | 19.75 | 4937.5
| Mark de Vera | 0 | 0
| Balasz Racz | 10 | 11300
| Arunlal Nair | 0 | 0
| Local Infra setup support | 0 | 0
| Local SMEs for AVC, FMO | 0 | 0
| Cabling APAC | 0 | 0
| CNTR0010327 | 20 | 5320
| Thomas Huber | 0 | 0
| Gereon Volker | 0 | 0
| Lucas Tscherter | 0 | 0
| Markus Schnier | 0 | 0
| Thomas Bringewald | 2 | 2260
| Andrei Maslov | 0 | 0
| Patrick Zeitz | 0 | 0
| Armando Diaz | 0 | 0
| Ron Johnson | 0 | 0
| Jithin Varghese | 18 | 3060
| AZ Tech America Labor | 0 | 0
| Service Manager | 0 | 0
| CNTR0010332 | 177.713 | 270824.8831
| Timothy Drost | 51.25 | 56077.4981
| Thomas Huber | 1 | 2030
| Holger Steinlechner | 1.78 | 2011.4
| Lucas Tscherter | 20.42 | 32059.4
| Markus Schnier | 1 | 2030
| Olivier Ma | 0 | 0
| Rebecca Dengl | 0.263 | 297.19
| Andrei Maslov | 5 | 5650
| Racz Balazs | 2 | 2260
| Jimmy Braun | 0 | 0
| Cyarx Siemplify | 95 | 168409.395
| CMDB | 0 | 0
| CNTR0010329 | 97.9983 | 221663.7262
| Thomas Huber | 1 | 2030
| Gereon Volker | 0 | 0
| Lucas Tscherter | 27.79 | 43630.3
| Markus Schnier | 1 | 2030
| Thomas Bringewald | 5 | 5650
| Rebecca Dengl | 0.526 | 594.38
| Felix Hertin | 3.2615 | 5242.0231
| Lukas Thiele | 9.4208 | 5242.0231
| Holger Wache | 25 | 78622.5
| Tobias Martin | 25 | 78622.5
| Deloitte | 0 | 0
| CNTR0010709 | 11 | 16796.845
| Thomas Huber | 1 | 2030
| Lucas Tscherter | 0 | 0
| Markus Schnier | 1 | 2030
| Krunoslav Rukavina | 9 | 12736.845
| Joachim Steinberger | 0 | 0
| Elastic | 0 | 0
| Proofpoint | 0 | 0
| CNTR0010564 | 513.2647 | 444921.049
| Markus Traumueller | 10 | 11300
| Karim, Hasan | 57 | 59850
| Bojarski, Eduard | 57 | 112122.99
| Kayali, Ismail | 57 | 72645.93
| Stettner, Julia | 57 | 80717.13
| Tulshidas Thamke, Budhesh | 57 | 9120
| Sunderdas, Shilpa | 58 | 9280
| Bönigk, Julian | 10 | 11300
| Sora Mustafa (AUG-OCT only) | 52 | 61880
| Vidya Baskaran Reddy | 57 | 9690
| S, Shibi (partily on IP&G) | 41.2647 | 7014.999
| CNTR0010563 | 109.9746 | 125589.2982
| Günther, Gerhard | 15.1579 | 20463.1579
| Poteat, Jade | 22.9868 | 22986.8421
| Warnholz, Benjamin | 8 | 16000
| Qualys Team (AVM) | 0 | 0
| Uysal, Ismail (Project Manager) | 51.1456 | 51145.614
| Goldschmidt, Andreas (SNOW Principal Architect) | 10.6842 | 14423.6842
| AMC Devops Engineer (Internal) | 0 | 0
| APM Devops Engineer (Internal) | 0 | 0
| EMS Devops Engineer (Internal) | 0 | 0
| Workspace Intelligence Internal – Technical SME | 0 | 0
| SNOW Performance Analytics team | 0 | 0
| SNOW Development Teams | 2 | 570
| Workspace Intelligence Vendor – Technical SME | 0 | 0
| SNOW SAM efforts | 0 | 0
| SNOW CMDB | 0 | 0
| CyNet | 0 | 0
| Security Foundation Team | 0 | 0
| CNTR0010576 | 27.5 | 35432.54
| Marc Bochtler | 18 | 25473.69
| Alexander Heinze | 0 | 0
| Tobias Butz | 0 | 0
| NN | 0 | 0
| NN india | 0 | 0
| Yury Nikolin | 9.5 | 9958.85
| Thomas Felder | 0 | 0
| CNTR0010334 | 130.125 | 153138.2055
| Martin Schurm | 27 | 42102.3487
| Tobias Krichel | 62.875 | 74513.3568
| Thomas Huber | 1 | 2030
| Markus Schnier | 1 | 2030
| Dan Read | 0 | 0
| N.N. / Support Dan | 0 | 0
| Ankur Tomar | 0 | 0
| Naman Agrawal | 21.25 | 5312.5
| Clemens Friedrich | 16 | 25120
| Gerhard Schneider | 1 | 2030
| OAM302 | 0 | 0
| Alexander Heinze | 0 | 0
| Daming Yang | 0 | 0
| Manoj Selvakumar | 0 | 0
| David Barton | 0 | 0
| Raja Rajcic | 0 | 0
| Lawrence Tengan | 0 | 0
| Travis Chun | 0 | 0
| Johannes Bross | 0 | 0
| Tuan Minh Nguyen | 0 | 0
| Tobias Tischler | 0 | 0
| Djamel Tazerout | 0 | 0
| Dirk Addicks | 0 | 0
| Forgerock Licence | 0 | 0
| CNTR0010589 | 0 | 0
| Placeholder | 0 | 0
| OAM299 | 0 | 0
| Placeholder | 0 | 0
| CNTR0010618 | 0.79973 | 2114.4735
| Birgit Jarosch | 0.79973 | 2114.4735
| Wolfgang Elsner | 0 | 0
| Alexander Heinze | 0 | 0
| Jagoda Matys | 0 | 0
| N.N. | 0 | 0
| Mitja Ledowski | 0 | 0
| Ingmar Janßen-Holldiek | 0 | 0
| Michael Holder | 0 | 0
| Sinoop K S | 0 | 0
| J. Thomas | 0 | 0
| Madalina Paslaru | 0 | 0
| Daniel Ettenhuber | 0 | 0
| OAM289 | 0 | 0
| Placeholder | 0 | 0
| CNTR0010617 | 0 | 0
| (blank) | 0 | 0
| Alexander Heinze | 0 | 0
| Christine Schlüter | 0 | 0
| Günter Sanktjohanser | 0 | 0
| Metafinanz | 717.9375 | 838906
| 21 0427 | 162.5625 | 155742.25
| Julian Steinfeld | 53 | 58936
| Manuel Hahn | 43.5312 | 42660.625
| Matthias Müller | 66.0312 | 54145.625
| 21 1068 | 107.1875 | 140290.625
| Jonathan Reynolds | 16.75 | 16750
| Samuel Hurst | 38.9688 | 52607.8125
| Kris Harms | 39 | 56550
| Nora von Schenckendorff | 5.4688 | 7382.8125
| Frank Markussen | 1.375 | 1375
| Anette Hettenkofer | 0.125 | 125
| Julia Netesa | 5.5 | 5500
| 21 1079 | 81.1875 | 94356.25
| George Dietrichsbruckner | 37.625 | 50793.75
| Jade Poteat | 7.625 | 7625
| Nadine Butzhammer | 0.3125 | 312.5
| Daniel Wörner | 21.5 | 21500
| Sanat Gautam | 14.125 | 14125
| 21 1037 | 179.6875 | 209831.25
| Gerhard Günther | 31.5 | 42525
| Rasa Rintallo | 43.4375 | 43437.5
| Stefan Köstenbauer | 1.125 | 1518.75
| Victor Peters | 3.8438 | 3843.75
| Michael Habel | 53.5 | 72225
| Maximilian Schellenberger | 3.2812 | 3281.25
| Sona Latifyan | 43 | 43000
| 21 1040 | 6.5 | 6500
| Jade Poteat | 6.5 | 6500
| 21 1133 | 0 | 0
| Krunoslav Rukavina | 0 | 0
| 21 1063 | 135.3125 | 170760.625
| Marc Bochtler | 42.125 | 56868.75
| Thorsten Deckers | 21.0625 | 33068.125
| Robert Reti | 17.875 | 28063.75
| Claudio Cangiotti | 13 | 10010
| Yury Nikulin | 26.25 | 26250
| Eldho George | 15 | 16500
| 21 1059 | 45.5 | 61425
| Thomas Thuspaß | 45.5 | 61425
| other | 0 | 24570
| 0 | 0 | 24570
| (blank) | 0 | 24570
| NCC Group GmbH | 0 | 363140.4
| 2410164170 | 0 | 363140.4
| (blank) | 0 | 363140.4
| Osborne Clark | 0 | 20659.69
| TID0001510089 | 0 | 20659.69
| (blank) | 0 | 20659.69
| Virtual Clarity Ltd | 0 | 149488
| 2410164371 | 0 | 149488
| (blank) | 0 | 149488
| Softwaregilde | 0 | 121975
| 2410159840 | 0 | 121975
| (blank) | 0 | 121975
| Horvath & Partner | 0 | 44625
| 2410160374 | 0 | 44625
| (blank) | 0 | 44625
| Ernst & Young | 0 | 98002.0781
| 2410162165 | 0 | 98002.0781
| (blank) | 0 | 98002.0781
| SRLabs | 0 | 8925
| PR964131 | 0 | 8925
| (blank) | 0 | 8925
| DCSO | 0 | 0
| 0 | 0 | 0
| (blank) | 0 | 0
| SecAttack | 0 | 22312.5
| 0 | 0 | 22312.5
| (blank) | 0 | 22312.5
| (blank) | 2767.8155 | 3482475.2593
| (blank) | 2767.8155 | 3482475.2593
| (blank) | 2767.8155 | 3482475.2593
| (blank) | 2767.8155 | 3482475.2593
| non-Labor | 1 | 210543.769
| AZ Technology | 1 | 107250.619
| CNTR0010616 | 0 | 0
| Licence costs | 0 | 0
| CNTR0010338 | 0 | 32401.999
| Splunk Licenses + Server | 0 | 0
| ZeroFox Licenses | 0 | 32401.999
| CNTR0010333 | 0 | 0
| Splunk Licenses + Server | 0 | 0
| CNTR0010325 | 0 | 0
| HW / infrastructure | 0 | 0
| CNTR0010327 | 0 | 0
| Local SMEs for AVC, FMO | 0 | 0
| AZ Tech America HW | 0 | 0
| CNTR0010332 | 1 | 74848.62
| Cyarx Siemplify | 1 | 74848.62
| CNTR0010329 | 0 | 0
| AWS / Azure cloud | 0 | 0
| CNTR0010618 | 0 | 0
| HW | 0 | 0
| other | 0 | 103293.15
| 0 | 0 | 103293.15
| (blank) | 0 | 103293.15
| Sum | 5535.6311 | 8219441.3367

## M67 (hidden)
M67
Measure Lead: Heinrich Schlotthauer
Pillar Lead: Carsten Scholz
Duration: 01.11.2016-31.12.2018
Planned Total | #N/A
Approved Total | #N/A
Spent Labor | #N/A
Spent non-Labor | #N/A
Spent Total | #N/A
Forecast Total | #N/A
| Measure | (All)
|  | Jan |  | Feb | Mrz | Apr | Mai | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total
| Resources & Contracts | PD Total | EUR Total
| Labor | 2766.8155 | 4526422.3084
Comment | AZ Technology | 2048.878 | 2833818.6402
| 0 | 0 | 297500
| (blank) | 0 | 297500
| CNTR0010544 | 110.4647 | 157099.0619
| Andrea Scotti | 0 | 0
| Wolfgang Elsner | 0 | 0
| Alexander Heinze | 0 | 0
| Thomas Huber | 0 | 0
| Jagoda Matys | 0 | 0
| Markus Schnier | 0 | 0
| Sergej Reißig | 55.0018 | 83266.9815
| Binoj Baburaj | 0 | 0
| IAM Architect (Cygna) | 2.4114 | 3159.8592
| NN india | 0 | 0
| Michael Holder | 0 | 0
| Youssef Dahmouni | 0 | 0
| Nina Kaufmann | 20.9999 | 27517.875
| Viktoryia Nikifaravets | 32.0516 | 43154.3461
| CNTR0010615 | 121.7529 | 173433.2076
| Alexander Heinze | 0 | 0
| Jagoda Matys | 0 | 0
| Srdan Mavrenski | 55.0018 | 83266.9815
| Itai Schwartz | 31.2506 | 42075.8024
| NN india | 0 | 0
| Francois Pernayan | 31.2506 | 42075.8024
| Matt Gibson | 0 | 0
| Christian Bolterauer | 4.25 | 6014.6213
| CNTR0010616 | 68.1618 | 102967.1383
| Alexander Heinze | 0 | 0
| Thomas Huber | 0 | 0
| Reza Memarian | 55.0018 | 83266.9815
| Markus Schnier | 0 | 0
| NN india | 0 | 0
| Youssef Dahmouni | 0 | 0
| Walter Hofer | 0 | 0
| Balasz Razs | 0 | 0
| Ivan Markovic | 13.16 | 19700.1568
| Product SME | 0 | 0
| CNTR0010562 | 5 | 7850
| Thomas Huber | 0 | 0
| Markus Schnier | 0 | 0
| Clemens Friedrich | 5 | 7850
| Gerhard Schneider | 0 | 0
| DGI | 0 | 0
| CNTR0010336 | 152.1775 | 271131.6326
| Thomas Huber | 0 | 0
| Markus Schnier | 0 | 0
| Daniela Betz | 45.9375 | 65010.9849
| Bastian Kastner | 45.25 | 47435.575
| Clemens Friedrich | 0 | 0
| Gerhard Schneider | 3.77 | 7653.1
| Björn Hansen / Markus Feuerstein | 0 | 85551.9727
| Rudresh Subramanian | 20.22 | 30330
| Guelsah Uestelci | 37 | 35150
| CNTR0010335 | 56 | 64575.28
| N.N. | 0 | 0
| Markus Gatter | 56 | 64575.28
| Jakob Schusser | 0 | 0
| Gabriella Nagy | 0 | 0
| N.N. // SME 2 | 0 | 0
| N.N. // Sr. Analyst | 0 | 0
| SR Labs Autobahn | 0 | 0
| OE Effort | 0 | 0
| Ben Brüggen | 0 | 0
| CNTR0010338 | 152.3738 | 157766.1581
| Rene Pferner | 0 | 0
| Thomas Huber | 1 | 2030
| Markus Schnier | 1 | 2030
| N.N. | 0 | 0
| Clemens Friedrich | 15 | 23550
| Gerhard Schneider | 6.03 | 12240.9
| Anna Hartl | 53.8125 | 56411.6437
| Alina Lobova | 55.75 | 46754.18
| Stefan Kösters | 12.2812 | 12874.4344
| Kühnlenz / 2wmedia | 0 | 0
| Natalia Nikitana | 0 | 0
| IT Seal | 0 | 0
| Aishwarya Nangude / Sarabjit Singh | 0 | 0
| Meera Patel | 7.5 | 1875
| CNTR0010333 | 245.5625 | 276810.2324
| Christoph Lenz | 31.625 | 33152.4875
| Thomas Huber | 0 | 0
| Markus Schnier | 0 | 0
| Corinna Koch | 19.375 | 20310.8125
| Vasanthan Dhanasingh | 0 | 0
| Clemens Friedrich | 0 | 0
| Gerhard Schneider | 0 | 0
| Sven Lierzer | 48.875 | 57921.9165
| Tobias Lichtenberg | 12.6875 | 17955.4134
| Stanislav Khotinok | 34.125 | 39350.5613
| Alexander Leonhardt | 56.75 | 65440.1275
| Yuri Nikulin | 23.375 | 26954.4138
| Maria Thanner | 18.75 | 15724.5
| SNOW-Team | 0 | 0
| Splunk Team | 0 | 0
| Ankita Mane | 0 | 0
| Martin Gerlowski | 0 | 0
| Deepak Krishnan | 0 | 0
| K Harikrishnan | 0 | 0
| CNTR0010337 | 19.2596 | 32647.4087
| Placeholder | 0 | 0
| Matthias Kickstein | 0 | 0
| Computacenter | 0 | 0
| Ernst & Young | 19.2596 | 32647.4087
| CNTR0010325 | 29.75 | 16237.5
| Alex Lee | 0 | 0
| Lucas Tscherter | 0 | 0
| Corinna Koch | 0 | 0
| Dhanya Kalathil | 19.75 | 4937.5
| Mark de Vera | 0 | 0
| Balasz Racz | 10 | 11300
| Arunlal Nair | 0 | 0
| Local Infra setup support | 0 | 0
| Local SMEs for AVC, FMO | 0 | 0
| Cabling APAC | 0 | 0
| CNTR0010327 | 20 | 5320
| Thomas Huber | 0 | 0
| Gereon Volker | 0 | 0
| Lucas Tscherter | 0 | 0
| Markus Schnier | 0 | 0
| Thomas Bringewald | 2 | 2260
| Andrei Maslov | 0 | 0
| Patrick Zeitz | 0 | 0
| Armando Diaz | 0 | 0
| Ron Johnson | 0 | 0
| Jithin Varghese | 18 | 3060
| AZ Tech America Labor | 0 | 0
| Service Manager | 0 | 0
| CNTR0010332 | 177.713 | 270824.8831
| Timothy Drost | 51.25 | 56077.4981
| Thomas Huber | 1 | 2030
| Holger Steinlechner | 1.78 | 2011.4
| Lucas Tscherter | 20.42 | 32059.4
| Markus Schnier | 1 | 2030
| Olivier Ma | 0 | 0
| Rebecca Dengl | 0.263 | 297.19
| Andrei Maslov | 5 | 5650
| Racz Balazs | 2 | 2260
| Jimmy Braun | 0 | 0
| Cyarx Siemplify | 95 | 168409.395
| CMDB | 0 | 0
| CNTR0010329 | 97.9983 | 221663.7262
| Thomas Huber | 1 | 2030
| Gereon Volker | 0 | 0
| Lucas Tscherter | 27.79 | 43630.3
| Markus Schnier | 1 | 2030
| Thomas Bringewald | 5 | 5650
| Rebecca Dengl | 0.526 | 594.38
| Felix Hertin | 3.2615 | 5242.0231
| Lukas Thiele | 9.4208 | 5242.0231
| Holger Wache | 25 | 78622.5
| Tobias Martin | 25 | 78622.5
| Deloitte | 0 | 0
| CNTR0010709 | 11 | 16796.845
| Thomas Huber | 1 | 2030
| Lucas Tscherter | 0 | 0
| Markus Schnier | 1 | 2030
| Krunoslav Rukavina | 9 | 12736.845
| Joachim Steinberger | 0 | 0
| Elastic | 0 | 0
| Proofpoint | 0 | 0
| CNTR0010564 | 513.2647 | 444921.049
| Markus Traumueller | 10 | 11300
| Karim, Hasan | 57 | 59850
| Bojarski, Eduard | 57 | 112122.99
| Kayali, Ismail | 57 | 72645.93
| Stettner, Julia | 57 | 80717.13
| Tulshidas Thamke, Budhesh | 57 | 9120
| Sunderdas, Shilpa | 58 | 9280
| Bönigk, Julian | 10 | 11300
| Sora Mustafa (AUG-OCT only) | 52 | 61880
| Vidya Baskaran Reddy | 57 | 9690
| S, Shibi (partily on IP&G) | 41.2647 | 7014.999
| CNTR0010563 | 109.9746 | 125589.2982
| Günther, Gerhard | 15.1579 | 20463.1579
| Poteat, Jade | 22.9868 | 22986.8421
| Warnholz, Benjamin | 8 | 16000
| Qualys Team (AVM) | 0 | 0
| Uysal, Ismail (Project Manager) | 51.1456 | 51145.614
| Goldschmidt, Andreas (SNOW Principal Architect) | 10.6842 | 14423.6842
| AMC Devops Engineer (Internal) | 0 | 0
| APM Devops Engineer (Internal) | 0 | 0
| EMS Devops Engineer (Internal) | 0 | 0
| Workspace Intelligence Internal – Technical SME | 0 | 0
| SNOW Performance Analytics team | 0 | 0
| SNOW Development Teams | 2 | 570
| Workspace Intelligence Vendor – Technical SME | 0 | 0
| SNOW SAM efforts | 0 | 0
| SNOW CMDB | 0 | 0
| CyNet | 0 | 0
| Security Foundation Team | 0 | 0
| CNTR0010576 | 27.5 | 35432.54
| Marc Bochtler | 18 | 25473.69
| Alexander Heinze | 0 | 0
| Tobias Butz | 0 | 0
| NN | 0 | 0
| NN india | 0 | 0
| Yury Nikolin | 9.5 | 9958.85
| Thomas Felder | 0 | 0
| CNTR0010334 | 130.125 | 153138.2055
| Martin Schurm | 27 | 42102.3487
| Tobias Krichel | 62.875 | 74513.3568
| Thomas Huber | 1 | 2030
| Markus Schnier | 1 | 2030
| Dan Read | 0 | 0
| N.N. / Support Dan | 0 | 0
| Ankur Tomar | 0 | 0
| Naman Agrawal | 21.25 | 5312.5
| Clemens Friedrich | 16 | 25120
| Gerhard Schneider | 1 | 2030
| OAM302 | 0 | 0
| Alexander Heinze | 0 | 0
| Daming Yang | 0 | 0
| Manoj Selvakumar | 0 | 0
| David Barton | 0 | 0
| Raja Rajcic | 0 | 0
| Lawrence Tengan | 0 | 0
| Travis Chun | 0 | 0
| Johannes Bross | 0 | 0
| Tuan Minh Nguyen | 0 | 0
| Tobias Tischler | 0 | 0
| Djamel Tazerout | 0 | 0
| Dirk Addicks | 0 | 0
| Forgerock Licence | 0 | 0
| CNTR0010589 | 0 | 0
| Placeholder | 0 | 0
| OAM299 | 0 | 0
| Placeholder | 0 | 0
| CNTR0010618 | 0.79973 | 2114.4735
| Birgit Jarosch | 0.79973 | 2114.4735
| Wolfgang Elsner | 0 | 0
| Alexander Heinze | 0 | 0
| Jagoda Matys | 0 | 0
| N.N. | 0 | 0
| Mitja Ledowski | 0 | 0
| Ingmar Janßen-Holldiek | 0 | 0
| Michael Holder | 0 | 0
| Sinoop K S | 0 | 0
| J. Thomas | 0 | 0
| Madalina Paslaru | 0 | 0
| Daniel Ettenhuber | 0 | 0
| OAM289 | 0 | 0
| Placeholder | 0 | 0
| CNTR0010617 | 0 | 0
| (blank) | 0 | 0
| Alexander Heinze | 0 | 0
| Christine Schlüter | 0 | 0
| Günter Sanktjohanser | 0 | 0
| Metafinanz | 717.9375 | 838906
| 21 0427 | 162.5625 | 155742.25
| Julian Steinfeld | 53 | 58936
| Manuel Hahn | 43.5312 | 42660.625
| Matthias Müller | 66.0312 | 54145.625
| 21 1068 | 107.1875 | 140290.625
| Jonathan Reynolds | 16.75 | 16750
| Samuel Hurst | 38.9688 | 52607.8125
| Kris Harms | 39 | 56550
| Nora von Schenckendorff | 5.4688 | 7382.8125
| Frank Markussen | 1.375 | 1375
| Anette Hettenkofer | 0.125 | 125
| Julia Netesa | 5.5 | 5500
| 21 1079 | 81.1875 | 94356.25
| George Dietrichsbruckner | 37.625 | 50793.75
| Jade Poteat | 7.625 | 7625
| Nadine Butzhammer | 0.3125 | 312.5
| Daniel Wörner | 21.5 | 21500
| Sanat Gautam | 14.125 | 14125
| 21 1037 | 179.6875 | 209831.25
| Gerhard Günther | 31.5 | 42525
| Rasa Rintallo | 43.4375 | 43437.5
| Stefan Köstenbauer | 1.125 | 1518.75
| Victor Peters | 3.8438 | 3843.75
| Michael Habel | 53.5 | 72225
| Maximilian Schellenberger | 3.2812 | 3281.25
| Sona Latifyan | 43 | 43000
| 21 1040 | 6.5 | 6500
| Jade Poteat | 6.5 | 6500
| 21 1133 | 0 | 0
| Krunoslav Rukavina | 0 | 0
| 21 1063 | 135.3125 | 170760.625
| Marc Bochtler | 42.125 | 56868.75
| Thorsten Deckers | 21.0625 | 33068.125
| Robert Reti | 17.875 | 28063.75
| Claudio Cangiotti | 13 | 10010
| Yury Nikulin | 26.25 | 26250
| Eldho George | 15 | 16500
| 21 1059 | 45.5 | 61425
| Thomas Thuspaß | 45.5 | 61425
| other | 0 | 24570
| 0 | 0 | 24570
| (blank) | 0 | 24570
| NCC Group GmbH | 0 | 363140.4
| 2410164170 | 0 | 363140.4
| (blank) | 0 | 363140.4
| Osborne Clark | 0 | 20659.69
| TID0001510089 | 0 | 20659.69
| (blank) | 0 | 20659.69
| Virtual Clarity Ltd | 0 | 149488
| 2410164371 | 0 | 149488
| (blank) | 0 | 149488
| Softwaregilde | 0 | 121975
| 2410159840 | 0 | 121975
| (blank) | 0 | 121975
| Horvath & Partner | 0 | 44625
| 2410160374 | 0 | 44625
| (blank) | 0 | 44625
| Ernst & Young | 0 | 98002.0781
| 2410162165 | 0 | 98002.0781
| (blank) | 0 | 98002.0781
| SRLabs | 0 | 8925
| PR964131 | 0 | 8925
| (blank) | 0 | 8925
| DCSO | 0 | 0
| 0 | 0 | 0
| (blank) | 0 | 0
| SecAttack | 0 | 22312.5
| 0 | 0 | 22312.5
| (blank) | 0 | 22312.5
| (blank) | 2767.8155 | 3482475.2593
| (blank) | 2767.8155 | 3482475.2593
| (blank) | 2767.8155 | 3482475.2593
| (blank) | 2767.8155 | 3482475.2593
| non-Labor | 1 | 210543.769
| AZ Technology | 1 | 107250.619
| CNTR0010616 | 0 | 0
| Licence costs | 0 | 0
| CNTR0010338 | 0 | 32401.999
| Splunk Licenses + Server | 0 | 0
| ZeroFox Licenses | 0 | 32401.999
| CNTR0010333 | 0 | 0
| Splunk Licenses + Server | 0 | 0
| CNTR0010325 | 0 | 0
| HW / infrastructure | 0 | 0
| CNTR0010327 | 0 | 0
| Local SMEs for AVC, FMO | 0 | 0
| AZ Tech America HW | 0 | 0
| CNTR0010332 | 1 | 74848.62
| Cyarx Siemplify | 1 | 74848.62
| CNTR0010329 | 0 | 0
| AWS / Azure cloud | 0 | 0
| CNTR0010618 | 0 | 0
| HW | 0 | 0
| other | 0 | 103293.15
| 0 | 0 | 103293.15
| (blank) | 0 | 103293.15
| Sum | 5535.6311 | 8219441.3367

## M85 (hidden)
M85
Measure Lead: Marco Frank
Pillar Lead: Carsten Scholz
Duration: 01.07.2018-31.12.2018
Planned Total | #N/A
Approved Total | #N/A
Spent Labor | #N/A
Spent non-Labor | #N/A
Spent Total | #N/A
Forecast Total | #N/A
| Measure | (All)
|  | Jan |  | Feb | Mrz | Apr | Mai | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total
| Resources & Contracts | PD Total | EUR Total
| Labor | 2766.8155 | 4526422.3084
Comment | AZ Technology | 2048.878 | 2833818.6402
| 0 | 0 | 297500
| (blank) | 0 | 297500
| CNTR0010544 | 110.4647 | 157099.0619
| Andrea Scotti | 0 | 0
| Wolfgang Elsner | 0 | 0
| Alexander Heinze | 0 | 0
| Thomas Huber | 0 | 0
| Jagoda Matys | 0 | 0
| Markus Schnier | 0 | 0
| Sergej Reißig | 55.0018 | 83266.9815
| Binoj Baburaj | 0 | 0
| IAM Architect (Cygna) | 2.4114 | 3159.8592
| NN india | 0 | 0
| Michael Holder | 0 | 0
| Youssef Dahmouni | 0 | 0
| Nina Kaufmann | 20.9999 | 27517.875
| Viktoryia Nikifaravets | 32.0516 | 43154.3461
| CNTR0010615 | 121.7529 | 173433.2076
| Alexander Heinze | 0 | 0
| Jagoda Matys | 0 | 0
| Srdan Mavrenski | 55.0018 | 83266.9815
| Itai Schwartz | 31.2506 | 42075.8024
| NN india | 0 | 0
| Francois Pernayan | 31.2506 | 42075.8024
| Matt Gibson | 0 | 0
| Christian Bolterauer | 4.25 | 6014.6213
| CNTR0010616 | 68.1618 | 102967.1383
| Alexander Heinze | 0 | 0
| Thomas Huber | 0 | 0
| Reza Memarian | 55.0018 | 83266.9815
| Markus Schnier | 0 | 0
| NN india | 0 | 0
| Youssef Dahmouni | 0 | 0
| Walter Hofer | 0 | 0
| Balasz Razs | 0 | 0
| Ivan Markovic | 13.16 | 19700.1568
| Product SME | 0 | 0
| CNTR0010562 | 5 | 7850
| Thomas Huber | 0 | 0
| Markus Schnier | 0 | 0
| Clemens Friedrich | 5 | 7850
| Gerhard Schneider | 0 | 0
| DGI | 0 | 0
| CNTR0010336 | 152.1775 | 271131.6326
| Thomas Huber | 0 | 0
| Markus Schnier | 0 | 0
| Daniela Betz | 45.9375 | 65010.9849
| Bastian Kastner | 45.25 | 47435.575
| Clemens Friedrich | 0 | 0
| Gerhard Schneider | 3.77 | 7653.1
| Björn Hansen / Markus Feuerstein | 0 | 85551.9727
| Rudresh Subramanian | 20.22 | 30330
| Guelsah Uestelci | 37 | 35150
| CNTR0010335 | 56 | 64575.28
| N.N. | 0 | 0
| Markus Gatter | 56 | 64575.28
| Jakob Schusser | 0 | 0
| Gabriella Nagy | 0 | 0
| N.N. // SME 2 | 0 | 0
| N.N. // Sr. Analyst | 0 | 0
| SR Labs Autobahn | 0 | 0
| OE Effort | 0 | 0
| Ben Brüggen | 0 | 0
| CNTR0010338 | 152.3738 | 157766.1581
| Rene Pferner | 0 | 0
| Thomas Huber | 1 | 2030
| Markus Schnier | 1 | 2030
| N.N. | 0 | 0
| Clemens Friedrich | 15 | 23550
| Gerhard Schneider | 6.03 | 12240.9
| Anna Hartl | 53.8125 | 56411.6437
| Alina Lobova | 55.75 | 46754.18
| Stefan Kösters | 12.2812 | 12874.4344
| Kühnlenz / 2wmedia | 0 | 0
| Natalia Nikitana | 0 | 0
| IT Seal | 0 | 0
| Aishwarya Nangude / Sarabjit Singh | 0 | 0
| Meera Patel | 7.5 | 1875
| CNTR0010333 | 245.5625 | 276810.2324
| Christoph Lenz | 31.625 | 33152.4875
| Thomas Huber | 0 | 0
| Markus Schnier | 0 | 0
| Corinna Koch | 19.375 | 20310.8125
| Vasanthan Dhanasingh | 0 | 0
| Clemens Friedrich | 0 | 0
| Gerhard Schneider | 0 | 0
| Sven Lierzer | 48.875 | 57921.9165
| Tobias Lichtenberg | 12.6875 | 17955.4134
| Stanislav Khotinok | 34.125 | 39350.5613
| Alexander Leonhardt | 56.75 | 65440.1275
| Yuri Nikulin | 23.375 | 26954.4138
| Maria Thanner | 18.75 | 15724.5
| SNOW-Team | 0 | 0
| Splunk Team | 0 | 0
| Ankita Mane | 0 | 0
| Martin Gerlowski | 0 | 0
| Deepak Krishnan | 0 | 0
| K Harikrishnan | 0 | 0
| CNTR0010337 | 19.2596 | 32647.4087
| Placeholder | 0 | 0
| Matthias Kickstein | 0 | 0
| Computacenter | 0 | 0
| Ernst & Young | 19.2596 | 32647.4087
| CNTR0010325 | 29.75 | 16237.5
| Alex Lee | 0 | 0
| Lucas Tscherter | 0 | 0
| Corinna Koch | 0 | 0
| Dhanya Kalathil | 19.75 | 4937.5
| Mark de Vera | 0 | 0
| Balasz Racz | 10 | 11300
| Arunlal Nair | 0 | 0
| Local Infra setup support | 0 | 0
| Local SMEs for AVC, FMO | 0 | 0
| Cabling APAC | 0 | 0
| CNTR0010327 | 20 | 5320
| Thomas Huber | 0 | 0
| Gereon Volker | 0 | 0
| Lucas Tscherter | 0 | 0
| Markus Schnier | 0 | 0
| Thomas Bringewald | 2 | 2260
| Andrei Maslov | 0 | 0
| Patrick Zeitz | 0 | 0
| Armando Diaz | 0 | 0
| Ron Johnson | 0 | 0
| Jithin Varghese | 18 | 3060
| AZ Tech America Labor | 0 | 0
| Service Manager | 0 | 0
| CNTR0010332 | 177.713 | 270824.8831
| Timothy Drost | 51.25 | 56077.4981
| Thomas Huber | 1 | 2030
| Holger Steinlechner | 1.78 | 2011.4
| Lucas Tscherter | 20.42 | 32059.4
| Markus Schnier | 1 | 2030
| Olivier Ma | 0 | 0
| Rebecca Dengl | 0.263 | 297.19
| Andrei Maslov | 5 | 5650
| Racz Balazs | 2 | 2260
| Jimmy Braun | 0 | 0
| Cyarx Siemplify | 95 | 168409.395
| CMDB | 0 | 0
| CNTR0010329 | 97.9983 | 221663.7262
| Thomas Huber | 1 | 2030
| Gereon Volker | 0 | 0
| Lucas Tscherter | 27.79 | 43630.3
| Markus Schnier | 1 | 2030
| Thomas Bringewald | 5 | 5650
| Rebecca Dengl | 0.526 | 594.38
| Felix Hertin | 3.2615 | 5242.0231
| Lukas Thiele | 9.4208 | 5242.0231
| Holger Wache | 25 | 78622.5
| Tobias Martin | 25 | 78622.5
| Deloitte | 0 | 0
| CNTR0010709 | 11 | 16796.845
| Thomas Huber | 1 | 2030
| Lucas Tscherter | 0 | 0
| Markus Schnier | 1 | 2030
| Krunoslav Rukavina | 9 | 12736.845
| Joachim Steinberger | 0 | 0
| Elastic | 0 | 0
| Proofpoint | 0 | 0
| CNTR0010564 | 513.2647 | 444921.049
| Markus Traumueller | 10 | 11300
| Karim, Hasan | 57 | 59850
| Bojarski, Eduard | 57 | 112122.99
| Kayali, Ismail | 57 | 72645.93
| Stettner, Julia | 57 | 80717.13
| Tulshidas Thamke, Budhesh | 57 | 9120
| Sunderdas, Shilpa | 58 | 9280
| Bönigk, Julian | 10 | 11300
| Sora Mustafa (AUG-OCT only) | 52 | 61880
| Vidya Baskaran Reddy | 57 | 9690
| S, Shibi (partily on IP&G) | 41.2647 | 7014.999
| CNTR0010563 | 109.9746 | 125589.2982
| Günther, Gerhard | 15.1579 | 20463.1579
| Poteat, Jade | 22.9868 | 22986.8421
| Warnholz, Benjamin | 8 | 16000
| Qualys Team (AVM) | 0 | 0
| Uysal, Ismail (Project Manager) | 51.1456 | 51145.614
| Goldschmidt, Andreas (SNOW Principal Architect) | 10.6842 | 14423.6842
| AMC Devops Engineer (Internal) | 0 | 0
| APM Devops Engineer (Internal) | 0 | 0
| EMS Devops Engineer (Internal) | 0 | 0
| Workspace Intelligence Internal – Technical SME | 0 | 0
| SNOW Performance Analytics team | 0 | 0
| SNOW Development Teams | 2 | 570
| Workspace Intelligence Vendor – Technical SME | 0 | 0
| SNOW SAM efforts | 0 | 0
| SNOW CMDB | 0 | 0
| CyNet | 0 | 0
| Security Foundation Team | 0 | 0
| CNTR0010576 | 27.5 | 35432.54
| Marc Bochtler | 18 | 25473.69
| Alexander Heinze | 0 | 0
| Tobias Butz | 0 | 0
| NN | 0 | 0
| NN india | 0 | 0
| Yury Nikolin | 9.5 | 9958.85
| Thomas Felder | 0 | 0
| CNTR0010334 | 130.125 | 153138.2055
| Martin Schurm | 27 | 42102.3487
| Tobias Krichel | 62.875 | 74513.3568
| Thomas Huber | 1 | 2030
| Markus Schnier | 1 | 2030
| Dan Read | 0 | 0
| N.N. / Support Dan | 0 | 0
| Ankur Tomar | 0 | 0
| Naman Agrawal | 21.25 | 5312.5
| Clemens Friedrich | 16 | 25120
| Gerhard Schneider | 1 | 2030
| OAM302 | 0 | 0
| Alexander Heinze | 0 | 0
| Daming Yang | 0 | 0
| Manoj Selvakumar | 0 | 0
| David Barton | 0 | 0
| Raja Rajcic | 0 | 0
| Lawrence Tengan | 0 | 0
| Travis Chun | 0 | 0
| Johannes Bross | 0 | 0
| Tuan Minh Nguyen | 0 | 0
| Tobias Tischler | 0 | 0
| Djamel Tazerout | 0 | 0
| Dirk Addicks | 0 | 0
| Forgerock Licence | 0 | 0
| CNTR0010589 | 0 | 0
| Placeholder | 0 | 0
| OAM299 | 0 | 0
| Placeholder | 0 | 0
| CNTR0010618 | 0.79973 | 2114.4735
| Birgit Jarosch | 0.79973 | 2114.4735
| Wolfgang Elsner | 0 | 0
| Alexander Heinze | 0 | 0
| Jagoda Matys | 0 | 0
| N.N. | 0 | 0
| Mitja Ledowski | 0 | 0
| Ingmar Janßen-Holldiek | 0 | 0
| Michael Holder | 0 | 0
| Sinoop K S | 0 | 0
| J. Thomas | 0 | 0
| Madalina Paslaru | 0 | 0
| Daniel Ettenhuber | 0 | 0
| OAM289 | 0 | 0
| Placeholder | 0 | 0
| CNTR0010617 | 0 | 0
| (blank) | 0 | 0
| Alexander Heinze | 0 | 0
| Christine Schlüter | 0 | 0
| Günter Sanktjohanser | 0 | 0
| Metafinanz | 717.9375 | 838906
| 21 0427 | 162.5625 | 155742.25
| Julian Steinfeld | 53 | 58936
| Manuel Hahn | 43.5312 | 42660.625
| Matthias Müller | 66.0312 | 54145.625
| 21 1068 | 107.1875 | 140290.625
| Jonathan Reynolds | 16.75 | 16750
| Samuel Hurst | 38.9688 | 52607.8125
| Kris Harms | 39 | 56550
| Nora von Schenckendorff | 5.4688 | 7382.8125
| Frank Markussen | 1.375 | 1375
| Anette Hettenkofer | 0.125 | 125
| Julia Netesa | 5.5 | 5500
| 21 1079 | 81.1875 | 94356.25
| George Dietrichsbruckner | 37.625 | 50793.75
| Jade Poteat | 7.625 | 7625
| Nadine Butzhammer | 0.3125 | 312.5
| Daniel Wörner | 21.5 | 21500
| Sanat Gautam | 14.125 | 14125
| 21 1037 | 179.6875 | 209831.25
| Gerhard Günther | 31.5 | 42525
| Rasa Rintallo | 43.4375 | 43437.5
| Stefan Köstenbauer | 1.125 | 1518.75
| Victor Peters | 3.8438 | 3843.75
| Michael Habel | 53.5 | 72225
| Maximilian Schellenberger | 3.2812 | 3281.25
| Sona Latifyan | 43 | 43000
| 21 1040 | 6.5 | 6500
| Jade Poteat | 6.5 | 6500
| 21 1133 | 0 | 0
| Krunoslav Rukavina | 0 | 0
| 21 1063 | 135.3125 | 170760.625
| Marc Bochtler | 42.125 | 56868.75
| Thorsten Deckers | 21.0625 | 33068.125
| Robert Reti | 17.875 | 28063.75
| Claudio Cangiotti | 13 | 10010
| Yury Nikulin | 26.25 | 26250
| Eldho George | 15 | 16500
| 21 1059 | 45.5 | 61425
| Thomas Thuspaß | 45.5 | 61425
| other | 0 | 24570
| 0 | 0 | 24570
| (blank) | 0 | 24570
| NCC Group GmbH | 0 | 363140.4
| 2410164170 | 0 | 363140.4
| (blank) | 0 | 363140.4
| Osborne Clark | 0 | 20659.69
| TID0001510089 | 0 | 20659.69
| (blank) | 0 | 20659.69
| Virtual Clarity Ltd | 0 | 149488
| 2410164371 | 0 | 149488
| (blank) | 0 | 149488
| Softwaregilde | 0 | 121975
| 2410159840 | 0 | 121975
| (blank) | 0 | 121975
| Horvath & Partner | 0 | 44625
| 2410160374 | 0 | 44625
| (blank) | 0 | 44625
| Ernst & Young | 0 | 98002.0781
| 2410162165 | 0 | 98002.0781
| (blank) | 0 | 98002.0781
| SRLabs | 0 | 8925
| PR964131 | 0 | 8925
| (blank) | 0 | 8925
| DCSO | 0 | 0
| 0 | 0 | 0
| (blank) | 0 | 0
| SecAttack | 0 | 22312.5
| 0 | 0 | 22312.5
| (blank) | 0 | 22312.5
| (blank) | 2767.8155 | 3482475.2593
| (blank) | 2767.8155 | 3482475.2593
| (blank) | 2767.8155 | 3482475.2593
| (blank) | 2767.8155 | 3482475.2593
| non-Labor | 1 | 210543.769
| AZ Technology | 1 | 107250.619
| CNTR0010616 | 0 | 0
| Licence costs | 0 | 0
| CNTR0010338 | 0 | 32401.999
| Splunk Licenses + Server | 0 | 0
| ZeroFox Licenses | 0 | 32401.999
| CNTR0010333 | 0 | 0
| Splunk Licenses + Server | 0 | 0
| CNTR0010325 | 0 | 0
| HW / infrastructure | 0 | 0
| CNTR0010327 | 0 | 0
| Local SMEs for AVC, FMO | 0 | 0
| AZ Tech America HW | 0 | 0
| CNTR0010332 | 1 | 74848.62
| Cyarx Siemplify | 1 | 74848.62
| CNTR0010329 | 0 | 0
| AWS / Azure cloud | 0 | 0
| CNTR0010618 | 0 | 0
| HW | 0 | 0
| other | 0 | 103293.15
| 0 | 0 | 103293.15
| (blank) | 0 | 103293.15
| Sum | 5535.6311 | 8219441.3367

## M86 (hidden)
M86
Measure Lead: Olav Spiegel
Pillar Lead: Carsten Scholz
Duration: 01.09.2018-31.12.2018
Planned Total | #N/A
Approved Total | #N/A
Spent Labor | #N/A
Spent non-Labor | #N/A
Spent Total | #N/A
Forecast Total | #N/A

## M44 (hidden)
M44
Measure Lead: Alexander Heinze
Pillar Lead: Carsten Scholz
Duration: 01.10.2016-31.12.2018
Planned Total | #N/A
Approved Total | #N/A
Spent Labor | #N/A
Spent non-Labor | #N/A
Spent Total | #N/A
Forecast Total | #N/A
| Measure | (All)
|  | Jan |  | Feb | Mrz | Apr | Mai | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total
| Resources & Contracts | PD Total | EUR Total
| Labor | 2766.8155 | 4526422.3084
Comment | AZ Technology | 2048.878 | 2833818.6402
| 0 | 0 | 297500
| (blank) | 0 | 297500
| CNTR0010544 | 110.4647 | 157099.0619
| Andrea Scotti | 0 | 0
| Wolfgang Elsner | 0 | 0
| Alexander Heinze | 0 | 0
| Thomas Huber | 0 | 0
| Jagoda Matys | 0 | 0
| Markus Schnier | 0 | 0
| Sergej Reißig | 55.0018 | 83266.9815
| Binoj Baburaj | 0 | 0
| IAM Architect (Cygna) | 2.4114 | 3159.8592
| NN india | 0 | 0
| Michael Holder | 0 | 0
| Youssef Dahmouni | 0 | 0
| Nina Kaufmann | 20.9999 | 27517.875
| Viktoryia Nikifaravets | 32.0516 | 43154.3461
| CNTR0010615 | 121.7529 | 173433.2076
| Alexander Heinze | 0 | 0
| Jagoda Matys | 0 | 0
| Srdan Mavrenski | 55.0018 | 83266.9815
| Itai Schwartz | 31.2506 | 42075.8024
| NN india | 0 | 0
| Francois Pernayan | 31.2506 | 42075.8024
| Matt Gibson | 0 | 0
| Christian Bolterauer | 4.25 | 6014.6213
| CNTR0010616 | 68.1618 | 102967.1383
| Alexander Heinze | 0 | 0
| Thomas Huber | 0 | 0
| Reza Memarian | 55.0018 | 83266.9815
| Markus Schnier | 0 | 0
| NN india | 0 | 0
| Youssef Dahmouni | 0 | 0
| Walter Hofer | 0 | 0
| Balasz Razs | 0 | 0
| Ivan Markovic | 13.16 | 19700.1568
| Product SME | 0 | 0
| CNTR0010562 | 5 | 7850
| Thomas Huber | 0 | 0
| Markus Schnier | 0 | 0
| Clemens Friedrich | 5 | 7850
| Gerhard Schneider | 0 | 0
| DGI | 0 | 0
| CNTR0010336 | 152.1775 | 271131.6326
| Thomas Huber | 0 | 0
| Markus Schnier | 0 | 0
| Daniela Betz | 45.9375 | 65010.9849
| Bastian Kastner | 45.25 | 47435.575
| Clemens Friedrich | 0 | 0
| Gerhard Schneider | 3.77 | 7653.1
| Björn Hansen / Markus Feuerstein | 0 | 85551.9727
| Rudresh Subramanian | 20.22 | 30330
| Guelsah Uestelci | 37 | 35150
| CNTR0010335 | 56 | 64575.28
| N.N. | 0 | 0
| Markus Gatter | 56 | 64575.28
| Jakob Schusser | 0 | 0
| Gabriella Nagy | 0 | 0
| N.N. // SME 2 | 0 | 0
| N.N. // Sr. Analyst | 0 | 0
| SR Labs Autobahn | 0 | 0
| OE Effort | 0 | 0
| Ben Brüggen | 0 | 0
| CNTR0010338 | 152.3738 | 157766.1581
| Rene Pferner | 0 | 0
| Thomas Huber | 1 | 2030
| Markus Schnier | 1 | 2030
| N.N. | 0 | 0
| Clemens Friedrich | 15 | 23550
| Gerhard Schneider | 6.03 | 12240.9
| Anna Hartl | 53.8125 | 56411.6437
| Alina Lobova | 55.75 | 46754.18
| Stefan Kösters | 12.2812 | 12874.4344
| Kühnlenz / 2wmedia | 0 | 0
| Natalia Nikitana | 0 | 0
| IT Seal | 0 | 0
| Aishwarya Nangude / Sarabjit Singh | 0 | 0
| Meera Patel | 7.5 | 1875
| CNTR0010333 | 245.5625 | 276810.2324
| Christoph Lenz | 31.625 | 33152.4875
| Thomas Huber | 0 | 0
| Markus Schnier | 0 | 0
| Corinna Koch | 19.375 | 20310.8125
| Vasanthan Dhanasingh | 0 | 0
| Clemens Friedrich | 0 | 0
| Gerhard Schneider | 0 | 0
| Sven Lierzer | 48.875 | 57921.9165
| Tobias Lichtenberg | 12.6875 | 17955.4134
| Stanislav Khotinok | 34.125 | 39350.5613
| Alexander Leonhardt | 56.75 | 65440.1275
| Yuri Nikulin | 23.375 | 26954.4138
| Maria Thanner | 18.75 | 15724.5
| SNOW-Team | 0 | 0
| Splunk Team | 0 | 0
| Ankita Mane | 0 | 0
| Martin Gerlowski | 0 | 0
| Deepak Krishnan | 0 | 0
| K Harikrishnan | 0 | 0
| CNTR0010337 | 19.2596 | 32647.4087
| Placeholder | 0 | 0
| Matthias Kickstein | 0 | 0
| Computacenter | 0 | 0
| Ernst & Young | 19.2596 | 32647.4087
| CNTR0010325 | 29.75 | 16237.5
| Alex Lee | 0 | 0
| Lucas Tscherter | 0 | 0
| Corinna Koch | 0 | 0
| Dhanya Kalathil | 19.75 | 4937.5
| Mark de Vera | 0 | 0
| Balasz Racz | 10 | 11300
| Arunlal Nair | 0 | 0
| Local Infra setup support | 0 | 0
| Local SMEs for AVC, FMO | 0 | 0
| Cabling APAC | 0 | 0
| CNTR0010327 | 20 | 5320
| Thomas Huber | 0 | 0
| Gereon Volker | 0 | 0
| Lucas Tscherter | 0 | 0
| Markus Schnier | 0 | 0
| Thomas Bringewald | 2 | 2260
| Andrei Maslov | 0 | 0
| Patrick Zeitz | 0 | 0
| Armando Diaz | 0 | 0
| Ron Johnson | 0 | 0
| Jithin Varghese | 18 | 3060
| AZ Tech America Labor | 0 | 0
| Service Manager | 0 | 0
| CNTR0010332 | 177.713 | 270824.8831
| Timothy Drost | 51.25 | 56077.4981
| Thomas Huber | 1 | 2030
| Holger Steinlechner | 1.78 | 2011.4
| Lucas Tscherter | 20.42 | 32059.4
| Markus Schnier | 1 | 2030
| Olivier Ma | 0 | 0
| Rebecca Dengl | 0.263 | 297.19
| Andrei Maslov | 5 | 5650
| Racz Balazs | 2 | 2260
| Jimmy Braun | 0 | 0
| Cyarx Siemplify | 95 | 168409.395
| CMDB | 0 | 0
| CNTR0010329 | 97.9983 | 221663.7262
| Thomas Huber | 1 | 2030
| Gereon Volker | 0 | 0
| Lucas Tscherter | 27.79 | 43630.3
| Markus Schnier | 1 | 2030
| Thomas Bringewald | 5 | 5650
| Rebecca Dengl | 0.526 | 594.38
| Felix Hertin | 3.2615 | 5242.0231
| Lukas Thiele | 9.4208 | 5242.0231
| Holger Wache | 25 | 78622.5
| Tobias Martin | 25 | 78622.5
| Deloitte | 0 | 0
| CNTR0010709 | 11 | 16796.845
| Thomas Huber | 1 | 2030
| Lucas Tscherter | 0 | 0
| Markus Schnier | 1 | 2030
| Krunoslav Rukavina | 9 | 12736.845
| Joachim Steinberger | 0 | 0
| Elastic | 0 | 0
| Proofpoint | 0 | 0
| CNTR0010564 | 513.2647 | 444921.049
| Markus Traumueller | 10 | 11300
| Karim, Hasan | 57 | 59850
| Bojarski, Eduard | 57 | 112122.99
| Kayali, Ismail | 57 | 72645.93
| Stettner, Julia | 57 | 80717.13
| Tulshidas Thamke, Budhesh | 57 | 9120
| Sunderdas, Shilpa | 58 | 9280
| Bönigk, Julian | 10 | 11300
| Sora Mustafa (AUG-OCT only) | 52 | 61880
| Vidya Baskaran Reddy | 57 | 9690
| S, Shibi (partily on IP&G) | 41.2647 | 7014.999
| CNTR0010563 | 109.9746 | 125589.2982
| Günther, Gerhard | 15.1579 | 20463.1579
| Poteat, Jade | 22.9868 | 22986.8421
| Warnholz, Benjamin | 8 | 16000
| Qualys Team (AVM) | 0 | 0
| Uysal, Ismail (Project Manager) | 51.1456 | 51145.614
| Goldschmidt, Andreas (SNOW Principal Architect) | 10.6842 | 14423.6842
| AMC Devops Engineer (Internal) | 0 | 0
| APM Devops Engineer (Internal) | 0 | 0
| EMS Devops Engineer (Internal) | 0 | 0
| Workspace Intelligence Internal – Technical SME | 0 | 0
| SNOW Performance Analytics team | 0 | 0
| SNOW Development Teams | 2 | 570
| Workspace Intelligence Vendor – Technical SME | 0 | 0
| SNOW SAM efforts | 0 | 0
| SNOW CMDB | 0 | 0
| CyNet | 0 | 0
| Security Foundation Team | 0 | 0
| CNTR0010576 | 27.5 | 35432.54
| Marc Bochtler | 18 | 25473.69
| Alexander Heinze | 0 | 0
| Tobias Butz | 0 | 0
| NN | 0 | 0
| NN india | 0 | 0
| Yury Nikolin | 9.5 | 9958.85
| Thomas Felder | 0 | 0
| CNTR0010334 | 130.125 | 153138.2055
| Martin Schurm | 27 | 42102.3487
| Tobias Krichel | 62.875 | 74513.3568
| Thomas Huber | 1 | 2030
| Markus Schnier | 1 | 2030
| Dan Read | 0 | 0
| N.N. / Support Dan | 0 | 0
| Ankur Tomar | 0 | 0
| Naman Agrawal | 21.25 | 5312.5
| Clemens Friedrich | 16 | 25120
| Gerhard Schneider | 1 | 2030
| OAM302 | 0 | 0
| Alexander Heinze | 0 | 0
| Daming Yang | 0 | 0
| Manoj Selvakumar | 0 | 0
| David Barton | 0 | 0
| Raja Rajcic | 0 | 0
| Lawrence Tengan | 0 | 0
| Travis Chun | 0 | 0
| Johannes Bross | 0 | 0
| Tuan Minh Nguyen | 0 | 0
| Tobias Tischler | 0 | 0
| Djamel Tazerout | 0 | 0
| Dirk Addicks | 0 | 0
| Forgerock Licence | 0 | 0
| CNTR0010589 | 0 | 0
| Placeholder | 0 | 0
| OAM299 | 0 | 0
| Placeholder | 0 | 0
| CNTR0010618 | 0.79973 | 2114.4735
| Birgit Jarosch | 0.79973 | 2114.4735
| Wolfgang Elsner | 0 | 0
| Alexander Heinze | 0 | 0
| Jagoda Matys | 0 | 0
| N.N. | 0 | 0
| Mitja Ledowski | 0 | 0
| Ingmar Janßen-Holldiek | 0 | 0
| Michael Holder | 0 | 0
| Sinoop K S | 0 | 0
| J. Thomas | 0 | 0
| Madalina Paslaru | 0 | 0
| Daniel Ettenhuber | 0 | 0
| OAM289 | 0 | 0
| Placeholder | 0 | 0
| CNTR0010617 | 0 | 0
| (blank) | 0 | 0
| Alexander Heinze | 0 | 0
| Christine Schlüter | 0 | 0
| Günter Sanktjohanser | 0 | 0
| Metafinanz | 717.9375 | 838906
| 21 0427 | 162.5625 | 155742.25
| Julian Steinfeld | 53 | 58936
| Manuel Hahn | 43.5312 | 42660.625
| Matthias Müller | 66.0312 | 54145.625
| 21 1068 | 107.1875 | 140290.625
| Jonathan Reynolds | 16.75 | 16750
| Samuel Hurst | 38.9688 | 52607.8125
| Kris Harms | 39 | 56550
| Nora von Schenckendorff | 5.4688 | 7382.8125
| Frank Markussen | 1.375 | 1375
| Anette Hettenkofer | 0.125 | 125
| Julia Netesa | 5.5 | 5500
| 21 1079 | 81.1875 | 94356.25
| George Dietrichsbruckner | 37.625 | 50793.75
| Jade Poteat | 7.625 | 7625
| Nadine Butzhammer | 0.3125 | 312.5
| Daniel Wörner | 21.5 | 21500
| Sanat Gautam | 14.125 | 14125
| 21 1037 | 179.6875 | 209831.25
| Gerhard Günther | 31.5 | 42525
| Rasa Rintallo | 43.4375 | 43437.5
| Stefan Köstenbauer | 1.125 | 1518.75
| Victor Peters | 3.8438 | 3843.75
| Michael Habel | 53.5 | 72225
| Maximilian Schellenberger | 3.2812 | 3281.25
| Sona Latifyan | 43 | 43000
| 21 1040 | 6.5 | 6500
| Jade Poteat | 6.5 | 6500
| 21 1133 | 0 | 0
| Krunoslav Rukavina | 0 | 0
| 21 1063 | 135.3125 | 170760.625
| Marc Bochtler | 42.125 | 56868.75
| Thorsten Deckers | 21.0625 | 33068.125
| Robert Reti | 17.875 | 28063.75
| Claudio Cangiotti | 13 | 10010
| Yury Nikulin | 26.25 | 26250
| Eldho George | 15 | 16500
| 21 1059 | 45.5 | 61425
| Thomas Thuspaß | 45.5 | 61425
| other | 0 | 24570
| 0 | 0 | 24570
| (blank) | 0 | 24570
| NCC Group GmbH | 0 | 363140.4
| 2410164170 | 0 | 363140.4
| (blank) | 0 | 363140.4
| Osborne Clark | 0 | 20659.69
| TID0001510089 | 0 | 20659.69
| (blank) | 0 | 20659.69
| Virtual Clarity Ltd | 0 | 149488
| 2410164371 | 0 | 149488
| (blank) | 0 | 149488
| Softwaregilde | 0 | 121975
| 2410159840 | 0 | 121975
| (blank) | 0 | 121975
| Horvath & Partner | 0 | 44625
| 2410160374 | 0 | 44625
| (blank) | 0 | 44625
| Ernst & Young | 0 | 98002.0781
| 2410162165 | 0 | 98002.0781
| (blank) | 0 | 98002.0781
| SRLabs | 0 | 8925
| PR964131 | 0 | 8925
| (blank) | 0 | 8925
| DCSO | 0 | 0
| 0 | 0 | 0
| (blank) | 0 | 0
| SecAttack | 0 | 22312.5
| 0 | 0 | 22312.5
| (blank) | 0 | 22312.5
| (blank) | 2767.8155 | 3482475.2593
| (blank) | 2767.8155 | 3482475.2593
| (blank) | 2767.8155 | 3482475.2593
| (blank) | 2767.8155 | 3482475.2593
| non-Labor | 1 | 210543.769
| AZ Technology | 1 | 107250.619
| CNTR0010616 | 0 | 0
| Licence costs | 0 | 0
| CNTR0010338 | 0 | 32401.999
| Splunk Licenses + Server | 0 | 0
| ZeroFox Licenses | 0 | 32401.999
| CNTR0010333 | 0 | 0
| Splunk Licenses + Server | 0 | 0
| CNTR0010325 | 0 | 0
| HW / infrastructure | 0 | 0
| CNTR0010327 | 0 | 0
| Local SMEs for AVC, FMO | 0 | 0
| AZ Tech America HW | 0 | 0
| CNTR0010332 | 1 | 74848.62
| Cyarx Siemplify | 1 | 74848.62
| CNTR0010329 | 0 | 0
| AWS / Azure cloud | 0 | 0
| CNTR0010618 | 0 | 0
| HW | 0 | 0
| other | 0 | 103293.15
| 0 | 0 | 103293.15
| (blank) | 0 | 103293.15
| Sum | 5535.6311 | 8219441.3367

## M13 (hidden)
M13
Measure Lead: Till Teichmann
Pillar Lead: Carsten Scholz
Duration: 01.05.2017-31.03.2018
Planned Total | #N/A
Approved Total | #N/A
Spent Labor | #N/A
Spent non-Labor | #N/A
Spent Total | #N/A
Forecast Total | #N/A
| Measure | (All)
|  | Jan |  | Feb | Mrz | Apr | Mai | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total
| Resources & Contracts | PD Total | EUR Total
| Labor | 2766.8155 | 4526422.3084
Comment | AZ Technology | 2048.878 | 2833818.6402
| 0 | 0 | 297500
| (blank) | 0 | 297500
| CNTR0010544 | 110.4647 | 157099.0619
| Andrea Scotti | 0 | 0
| Wolfgang Elsner | 0 | 0
| Alexander Heinze | 0 | 0
| Thomas Huber | 0 | 0
| Jagoda Matys | 0 | 0
| Markus Schnier | 0 | 0
| Sergej Reißig | 55.0018 | 83266.9815
| Binoj Baburaj | 0 | 0
| IAM Architect (Cygna) | 2.4114 | 3159.8592
| NN india | 0 | 0
| Michael Holder | 0 | 0
| Youssef Dahmouni | 0 | 0
| Nina Kaufmann | 20.9999 | 27517.875
| Viktoryia Nikifaravets | 32.0516 | 43154.3461
| CNTR0010615 | 121.7529 | 173433.2076
| Alexander Heinze | 0 | 0
| Jagoda Matys | 0 | 0
| Srdan Mavrenski | 55.0018 | 83266.9815
| Itai Schwartz | 31.2506 | 42075.8024
| NN india | 0 | 0
| Francois Pernayan | 31.2506 | 42075.8024
| Matt Gibson | 0 | 0
| Christian Bolterauer | 4.25 | 6014.6213
| CNTR0010616 | 68.1618 | 102967.1383
| Alexander Heinze | 0 | 0
| Thomas Huber | 0 | 0
| Reza Memarian | 55.0018 | 83266.9815
| Markus Schnier | 0 | 0
| NN india | 0 | 0
| Youssef Dahmouni | 0 | 0
| Walter Hofer | 0 | 0
| Balasz Razs | 0 | 0
| Ivan Markovic | 13.16 | 19700.1568
| Product SME | 0 | 0
| CNTR0010562 | 5 | 7850
| Thomas Huber | 0 | 0
| Markus Schnier | 0 | 0
| Clemens Friedrich | 5 | 7850
| Gerhard Schneider | 0 | 0
| DGI | 0 | 0
| CNTR0010336 | 152.1775 | 271131.6326
| Thomas Huber | 0 | 0
| Markus Schnier | 0 | 0
| Daniela Betz | 45.9375 | 65010.9849
| Bastian Kastner | 45.25 | 47435.575
| Clemens Friedrich | 0 | 0
| Gerhard Schneider | 3.77 | 7653.1
| Björn Hansen / Markus Feuerstein | 0 | 85551.9727
| Rudresh Subramanian | 20.22 | 30330
| Guelsah Uestelci | 37 | 35150
| CNTR0010335 | 56 | 64575.28
| N.N. | 0 | 0
| Markus Gatter | 56 | 64575.28
| Jakob Schusser | 0 | 0
| Gabriella Nagy | 0 | 0
| N.N. // SME 2 | 0 | 0
| N.N. // Sr. Analyst | 0 | 0
| SR Labs Autobahn | 0 | 0
| OE Effort | 0 | 0
| Ben Brüggen | 0 | 0
| CNTR0010338 | 152.3738 | 157766.1581
| Rene Pferner | 0 | 0
| Thomas Huber | 1 | 2030
| Markus Schnier | 1 | 2030
| N.N. | 0 | 0
| Clemens Friedrich | 15 | 23550
| Gerhard Schneider | 6.03 | 12240.9
| Anna Hartl | 53.8125 | 56411.6437
| Alina Lobova | 55.75 | 46754.18
| Stefan Kösters | 12.2812 | 12874.4344
| Kühnlenz / 2wmedia | 0 | 0
| Natalia Nikitana | 0 | 0
| IT Seal | 0 | 0
| Aishwarya Nangude / Sarabjit Singh | 0 | 0
| Meera Patel | 7.5 | 1875
| CNTR0010333 | 245.5625 | 276810.2324
| Christoph Lenz | 31.625 | 33152.4875
| Thomas Huber | 0 | 0
| Markus Schnier | 0 | 0
| Corinna Koch | 19.375 | 20310.8125
| Vasanthan Dhanasingh | 0 | 0
| Clemens Friedrich | 0 | 0
| Gerhard Schneider | 0 | 0
| Sven Lierzer | 48.875 | 57921.9165
| Tobias Lichtenberg | 12.6875 | 17955.4134
| Stanislav Khotinok | 34.125 | 39350.5613
| Alexander Leonhardt | 56.75 | 65440.1275
| Yuri Nikulin | 23.375 | 26954.4138
| Maria Thanner | 18.75 | 15724.5
| SNOW-Team | 0 | 0
| Splunk Team | 0 | 0
| Ankita Mane | 0 | 0
| Martin Gerlowski | 0 | 0
| Deepak Krishnan | 0 | 0
| K Harikrishnan | 0 | 0
| CNTR0010337 | 19.2596 | 32647.4087
| Placeholder | 0 | 0
| Matthias Kickstein | 0 | 0
| Computacenter | 0 | 0
| Ernst & Young | 19.2596 | 32647.4087
| CNTR0010325 | 29.75 | 16237.5
| Alex Lee | 0 | 0
| Lucas Tscherter | 0 | 0
| Corinna Koch | 0 | 0
| Dhanya Kalathil | 19.75 | 4937.5
| Mark de Vera | 0 | 0
| Balasz Racz | 10 | 11300
| Arunlal Nair | 0 | 0
| Local Infra setup support | 0 | 0
| Local SMEs for AVC, FMO | 0 | 0
| Cabling APAC | 0 | 0
| CNTR0010327 | 20 | 5320
| Thomas Huber | 0 | 0
| Gereon Volker | 0 | 0
| Lucas Tscherter | 0 | 0
| Markus Schnier | 0 | 0
| Thomas Bringewald | 2 | 2260
| Andrei Maslov | 0 | 0
| Patrick Zeitz | 0 | 0
| Armando Diaz | 0 | 0
| Ron Johnson | 0 | 0
| Jithin Varghese | 18 | 3060
| AZ Tech America Labor | 0 | 0
| Service Manager | 0 | 0
| CNTR0010332 | 177.713 | 270824.8831
| Timothy Drost | 51.25 | 56077.4981
| Thomas Huber | 1 | 2030
| Holger Steinlechner | 1.78 | 2011.4
| Lucas Tscherter | 20.42 | 32059.4
| Markus Schnier | 1 | 2030
| Olivier Ma | 0 | 0
| Rebecca Dengl | 0.263 | 297.19
| Andrei Maslov | 5 | 5650
| Racz Balazs | 2 | 2260
| Jimmy Braun | 0 | 0
| Cyarx Siemplify | 95 | 168409.395
| CMDB | 0 | 0
| CNTR0010329 | 97.9983 | 221663.7262
| Thomas Huber | 1 | 2030
| Gereon Volker | 0 | 0
| Lucas Tscherter | 27.79 | 43630.3
| Markus Schnier | 1 | 2030
| Thomas Bringewald | 5 | 5650
| Rebecca Dengl | 0.526 | 594.38
| Felix Hertin | 3.2615 | 5242.0231
| Lukas Thiele | 9.4208 | 5242.0231
| Holger Wache | 25 | 78622.5
| Tobias Martin | 25 | 78622.5
| Deloitte | 0 | 0
| CNTR0010709 | 11 | 16796.845
| Thomas Huber | 1 | 2030
| Lucas Tscherter | 0 | 0
| Markus Schnier | 1 | 2030
| Krunoslav Rukavina | 9 | 12736.845
| Joachim Steinberger | 0 | 0
| Elastic | 0 | 0
| Proofpoint | 0 | 0
| CNTR0010564 | 513.2647 | 444921.049
| Markus Traumueller | 10 | 11300
| Karim, Hasan | 57 | 59850
| Bojarski, Eduard | 57 | 112122.99
| Kayali, Ismail | 57 | 72645.93
| Stettner, Julia | 57 | 80717.13
| Tulshidas Thamke, Budhesh | 57 | 9120
| Sunderdas, Shilpa | 58 | 9280
| Bönigk, Julian | 10 | 11300
| Sora Mustafa (AUG-OCT only) | 52 | 61880
| Vidya Baskaran Reddy | 57 | 9690
| S, Shibi (partily on IP&G) | 41.2647 | 7014.999
| CNTR0010563 | 109.9746 | 125589.2982
| Günther, Gerhard | 15.1579 | 20463.1579
| Poteat, Jade | 22.9868 | 22986.8421
| Warnholz, Benjamin | 8 | 16000
| Qualys Team (AVM) | 0 | 0
| Uysal, Ismail (Project Manager) | 51.1456 | 51145.614
| Goldschmidt, Andreas (SNOW Principal Architect) | 10.6842 | 14423.6842
| AMC Devops Engineer (Internal) | 0 | 0
| APM Devops Engineer (Internal) | 0 | 0
| EMS Devops Engineer (Internal) | 0 | 0
| Workspace Intelligence Internal – Technical SME | 0 | 0
| SNOW Performance Analytics team | 0 | 0
| SNOW Development Teams | 2 | 570
| Workspace Intelligence Vendor – Technical SME | 0 | 0
| SNOW SAM efforts | 0 | 0
| SNOW CMDB | 0 | 0
| CyNet | 0 | 0
| Security Foundation Team | 0 | 0
| CNTR0010576 | 27.5 | 35432.54
| Marc Bochtler | 18 | 25473.69
| Alexander Heinze | 0 | 0
| Tobias Butz | 0 | 0
| NN | 0 | 0
| NN india | 0 | 0
| Yury Nikolin | 9.5 | 9958.85
| Thomas Felder | 0 | 0
| CNTR0010334 | 130.125 | 153138.2055
| Martin Schurm | 27 | 42102.3487
| Tobias Krichel | 62.875 | 74513.3568
| Thomas Huber | 1 | 2030
| Markus Schnier | 1 | 2030
| Dan Read | 0 | 0
| N.N. / Support Dan | 0 | 0
| Ankur Tomar | 0 | 0
| Naman Agrawal | 21.25 | 5312.5
| Clemens Friedrich | 16 | 25120
| Gerhard Schneider | 1 | 2030
| OAM302 | 0 | 0
| Alexander Heinze | 0 | 0
| Daming Yang | 0 | 0
| Manoj Selvakumar | 0 | 0
| David Barton | 0 | 0
| Raja Rajcic | 0 | 0
| Lawrence Tengan | 0 | 0
| Travis Chun | 0 | 0
| Johannes Bross | 0 | 0
| Tuan Minh Nguyen | 0 | 0
| Tobias Tischler | 0 | 0
| Djamel Tazerout | 0 | 0
| Dirk Addicks | 0 | 0
| Forgerock Licence | 0 | 0
| CNTR0010589 | 0 | 0
| Placeholder | 0 | 0
| OAM299 | 0 | 0
| Placeholder | 0 | 0
| CNTR0010618 | 0.79973 | 2114.4735
| Birgit Jarosch | 0.79973 | 2114.4735
| Wolfgang Elsner | 0 | 0
| Alexander Heinze | 0 | 0
| Jagoda Matys | 0 | 0
| N.N. | 0 | 0
| Mitja Ledowski | 0 | 0
| Ingmar Janßen-Holldiek | 0 | 0
| Michael Holder | 0 | 0
| Sinoop K S | 0 | 0
| J. Thomas | 0 | 0
| Madalina Paslaru | 0 | 0
| Daniel Ettenhuber | 0 | 0
| OAM289 | 0 | 0
| Placeholder | 0 | 0
| CNTR0010617 | 0 | 0
| (blank) | 0 | 0
| Alexander Heinze | 0 | 0
| Christine Schlüter | 0 | 0
| Günter Sanktjohanser | 0 | 0
| Metafinanz | 717.9375 | 838906
| 21 0427 | 162.5625 | 155742.25
| Julian Steinfeld | 53 | 58936
| Manuel Hahn | 43.5312 | 42660.625
| Matthias Müller | 66.0312 | 54145.625
| 21 1068 | 107.1875 | 140290.625
| Jonathan Reynolds | 16.75 | 16750
| Samuel Hurst | 38.9688 | 52607.8125
| Kris Harms | 39 | 56550
| Nora von Schenckendorff | 5.4688 | 7382.8125
| Frank Markussen | 1.375 | 1375
| Anette Hettenkofer | 0.125 | 125
| Julia Netesa | 5.5 | 5500
| 21 1079 | 81.1875 | 94356.25
| George Dietrichsbruckner | 37.625 | 50793.75
| Jade Poteat | 7.625 | 7625
| Nadine Butzhammer | 0.3125 | 312.5
| Daniel Wörner | 21.5 | 21500
| Sanat Gautam | 14.125 | 14125
| 21 1037 | 179.6875 | 209831.25
| Gerhard Günther | 31.5 | 42525
| Rasa Rintallo | 43.4375 | 43437.5
| Stefan Köstenbauer | 1.125 | 1518.75
| Victor Peters | 3.8438 | 3843.75
| Michael Habel | 53.5 | 72225
| Maximilian Schellenberger | 3.2812 | 3281.25
| Sona Latifyan | 43 | 43000
| 21 1040 | 6.5 | 6500
| Jade Poteat | 6.5 | 6500
| 21 1133 | 0 | 0
| Krunoslav Rukavina | 0 | 0
| 21 1063 | 135.3125 | 170760.625
| Marc Bochtler | 42.125 | 56868.75
| Thorsten Deckers | 21.0625 | 33068.125
| Robert Reti | 17.875 | 28063.75
| Claudio Cangiotti | 13 | 10010
| Yury Nikulin | 26.25 | 26250
| Eldho George | 15 | 16500
| 21 1059 | 45.5 | 61425
| Thomas Thuspaß | 45.5 | 61425
| other | 0 | 24570
| 0 | 0 | 24570
| (blank) | 0 | 24570
| NCC Group GmbH | 0 | 363140.4
| 2410164170 | 0 | 363140.4
| (blank) | 0 | 363140.4
| Osborne Clark | 0 | 20659.69
| TID0001510089 | 0 | 20659.69
| (blank) | 0 | 20659.69
| Virtual Clarity Ltd | 0 | 149488
| 2410164371 | 0 | 149488
| (blank) | 0 | 149488
| Softwaregilde | 0 | 121975
| 2410159840 | 0 | 121975
| (blank) | 0 | 121975
| Horvath & Partner | 0 | 44625
| 2410160374 | 0 | 44625
| (blank) | 0 | 44625
| Ernst & Young | 0 | 98002.0781
| 2410162165 | 0 | 98002.0781
| (blank) | 0 | 98002.0781
| SRLabs | 0 | 8925
| PR964131 | 0 | 8925
| (blank) | 0 | 8925
| DCSO | 0 | 0
| 0 | 0 | 0
| (blank) | 0 | 0
| SecAttack | 0 | 22312.5
| 0 | 0 | 22312.5
| (blank) | 0 | 22312.5
| (blank) | 2767.8155 | 3482475.2593
| (blank) | 2767.8155 | 3482475.2593
| (blank) | 2767.8155 | 3482475.2593
| (blank) | 2767.8155 | 3482475.2593
| non-Labor | 1 | 210543.769
| AZ Technology | 1 | 107250.619
| CNTR0010616 | 0 | 0
| Licence costs | 0 | 0
| CNTR0010338 | 0 | 32401.999
| Splunk Licenses + Server | 0 | 0
| ZeroFox Licenses | 0 | 32401.999
| CNTR0010333 | 0 | 0
| Splunk Licenses + Server | 0 | 0
| CNTR0010325 | 0 | 0
| HW / infrastructure | 0 | 0
| CNTR0010327 | 0 | 0
| Local SMEs for AVC, FMO | 0 | 0
| AZ Tech America HW | 0 | 0
| CNTR0010332 | 1 | 74848.62
| Cyarx Siemplify | 1 | 74848.62
| CNTR0010329 | 0 | 0
| AWS / Azure cloud | 0 | 0
| CNTR0010618 | 0 | 0
| HW | 0 | 0
| other | 0 | 103293.15
| 0 | 0 | 103293.15
| (blank) | 0 | 103293.15
| Sum | 5535.6311 | 8219441.3367

## M18 (hidden)
M18
Measure Lead: Andreas Wagner
Pillar Lead: Carsten Scholz
Duration: 01.08.2016-30.06.2018
Planned Total | #N/A
Approved Total | #N/A
Spent Labor | #N/A
Spent non-Labor | #N/A
Spent Total | #N/A
Forecast Total | #N/A
| Measure | (All)
|  | Jan |  | Feb | Mrz | Apr | Mai | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total
| Resources & Contracts | PD Total | EUR Total
| Labor | 2766.8155 | 4526422.3084
Comment | AZ Technology | 2048.878 | 2833818.6402
| 0 | 0 | 297500
| (blank) | 0 | 297500
| CNTR0010544 | 110.4647 | 157099.0619
| Andrea Scotti | 0 | 0
| Wolfgang Elsner | 0 | 0
| Alexander Heinze | 0 | 0
| Thomas Huber | 0 | 0
| Jagoda Matys | 0 | 0
| Markus Schnier | 0 | 0
| Sergej Reißig | 55.0018 | 83266.9815
| Binoj Baburaj | 0 | 0
| IAM Architect (Cygna) | 2.4114 | 3159.8592
| NN india | 0 | 0
| Michael Holder | 0 | 0
| Youssef Dahmouni | 0 | 0
| Nina Kaufmann | 20.9999 | 27517.875
| Viktoryia Nikifaravets | 32.0516 | 43154.3461
| CNTR0010615 | 121.7529 | 173433.2076
| Alexander Heinze | 0 | 0
| Jagoda Matys | 0 | 0
| Srdan Mavrenski | 55.0018 | 83266.9815
| Itai Schwartz | 31.2506 | 42075.8024
| NN india | 0 | 0
| Francois Pernayan | 31.2506 | 42075.8024
| Matt Gibson | 0 | 0
| Christian Bolterauer | 4.25 | 6014.6213
| CNTR0010616 | 68.1618 | 102967.1383
| Alexander Heinze | 0 | 0
| Thomas Huber | 0 | 0
| Reza Memarian | 55.0018 | 83266.9815
| Markus Schnier | 0 | 0
| NN india | 0 | 0
| Youssef Dahmouni | 0 | 0
| Walter Hofer | 0 | 0
| Balasz Razs | 0 | 0
| Ivan Markovic | 13.16 | 19700.1568
| Product SME | 0 | 0
| CNTR0010562 | 5 | 7850
| Thomas Huber | 0 | 0
| Markus Schnier | 0 | 0
| Clemens Friedrich | 5 | 7850
| Gerhard Schneider | 0 | 0
| DGI | 0 | 0
| CNTR0010336 | 152.1775 | 271131.6326
| Thomas Huber | 0 | 0
| Markus Schnier | 0 | 0
| Daniela Betz | 45.9375 | 65010.9849
| Bastian Kastner | 45.25 | 47435.575
| Clemens Friedrich | 0 | 0
| Gerhard Schneider | 3.77 | 7653.1
| Björn Hansen / Markus Feuerstein | 0 | 85551.9727
| Rudresh Subramanian | 20.22 | 30330
| Guelsah Uestelci | 37 | 35150
| CNTR0010335 | 56 | 64575.28
| N.N. | 0 | 0
| Markus Gatter | 56 | 64575.28
| Jakob Schusser | 0 | 0
| Gabriella Nagy | 0 | 0
| N.N. // SME 2 | 0 | 0
| N.N. // Sr. Analyst | 0 | 0
| SR Labs Autobahn | 0 | 0
| OE Effort | 0 | 0
| Ben Brüggen | 0 | 0
| CNTR0010338 | 152.3738 | 157766.1581
| Rene Pferner | 0 | 0
| Thomas Huber | 1 | 2030
| Markus Schnier | 1 | 2030
| N.N. | 0 | 0
| Clemens Friedrich | 15 | 23550
| Gerhard Schneider | 6.03 | 12240.9
| Anna Hartl | 53.8125 | 56411.6437
| Alina Lobova | 55.75 | 46754.18
| Stefan Kösters | 12.2812 | 12874.4344
| Kühnlenz / 2wmedia | 0 | 0
| Natalia Nikitana | 0 | 0
| IT Seal | 0 | 0
| Aishwarya Nangude / Sarabjit Singh | 0 | 0
| Meera Patel | 7.5 | 1875
| CNTR0010333 | 245.5625 | 276810.2324
| Christoph Lenz | 31.625 | 33152.4875
| Thomas Huber | 0 | 0
| Markus Schnier | 0 | 0
| Corinna Koch | 19.375 | 20310.8125
| Vasanthan Dhanasingh | 0 | 0
| Clemens Friedrich | 0 | 0
| Gerhard Schneider | 0 | 0
| Sven Lierzer | 48.875 | 57921.9165
| Tobias Lichtenberg | 12.6875 | 17955.4134
| Stanislav Khotinok | 34.125 | 39350.5613
| Alexander Leonhardt | 56.75 | 65440.1275
| Yuri Nikulin | 23.375 | 26954.4138
| Maria Thanner | 18.75 | 15724.5
| SNOW-Team | 0 | 0
| Splunk Team | 0 | 0
| Ankita Mane | 0 | 0
| Martin Gerlowski | 0 | 0
| Deepak Krishnan | 0 | 0
| K Harikrishnan | 0 | 0
| CNTR0010337 | 19.2596 | 32647.4087
| Placeholder | 0 | 0
| Matthias Kickstein | 0 | 0
| Computacenter | 0 | 0
| Ernst & Young | 19.2596 | 32647.4087
| CNTR0010325 | 29.75 | 16237.5
| Alex Lee | 0 | 0
| Lucas Tscherter | 0 | 0
| Corinna Koch | 0 | 0
| Dhanya Kalathil | 19.75 | 4937.5
| Mark de Vera | 0 | 0
| Balasz Racz | 10 | 11300
| Arunlal Nair | 0 | 0
| Local Infra setup support | 0 | 0
| Local SMEs for AVC, FMO | 0 | 0
| Cabling APAC | 0 | 0
| CNTR0010327 | 20 | 5320
| Thomas Huber | 0 | 0
| Gereon Volker | 0 | 0
| Lucas Tscherter | 0 | 0
| Markus Schnier | 0 | 0
| Thomas Bringewald | 2 | 2260
| Andrei Maslov | 0 | 0
| Patrick Zeitz | 0 | 0
| Armando Diaz | 0 | 0
| Ron Johnson | 0 | 0
| Jithin Varghese | 18 | 3060
| AZ Tech America Labor | 0 | 0
| Service Manager | 0 | 0
| CNTR0010332 | 177.713 | 270824.8831
| Timothy Drost | 51.25 | 56077.4981
| Thomas Huber | 1 | 2030
| Holger Steinlechner | 1.78 | 2011.4
| Lucas Tscherter | 20.42 | 32059.4
| Markus Schnier | 1 | 2030
| Olivier Ma | 0 | 0
| Rebecca Dengl | 0.263 | 297.19
| Andrei Maslov | 5 | 5650
| Racz Balazs | 2 | 2260
| Jimmy Braun | 0 | 0
| Cyarx Siemplify | 95 | 168409.395
| CMDB | 0 | 0
| CNTR0010329 | 97.9983 | 221663.7262
| Thomas Huber | 1 | 2030
| Gereon Volker | 0 | 0
| Lucas Tscherter | 27.79 | 43630.3
| Markus Schnier | 1 | 2030
| Thomas Bringewald | 5 | 5650
| Rebecca Dengl | 0.526 | 594.38
| Felix Hertin | 3.2615 | 5242.0231
| Lukas Thiele | 9.4208 | 5242.0231
| Holger Wache | 25 | 78622.5
| Tobias Martin | 25 | 78622.5
| Deloitte | 0 | 0
| CNTR0010709 | 11 | 16796.845
| Thomas Huber | 1 | 2030
| Lucas Tscherter | 0 | 0
| Markus Schnier | 1 | 2030
| Krunoslav Rukavina | 9 | 12736.845
| Joachim Steinberger | 0 | 0
| Elastic | 0 | 0
| Proofpoint | 0 | 0
| CNTR0010564 | 513.2647 | 444921.049
| Markus Traumueller | 10 | 11300
| Karim, Hasan | 57 | 59850
| Bojarski, Eduard | 57 | 112122.99
| Kayali, Ismail | 57 | 72645.93
| Stettner, Julia | 57 | 80717.13
| Tulshidas Thamke, Budhesh | 57 | 9120
| Sunderdas, Shilpa | 58 | 9280
| Bönigk, Julian | 10 | 11300
| Sora Mustafa (AUG-OCT only) | 52 | 61880
| Vidya Baskaran Reddy | 57 | 9690
| S, Shibi (partily on IP&G) | 41.2647 | 7014.999
| CNTR0010563 | 109.9746 | 125589.2982
| Günther, Gerhard | 15.1579 | 20463.1579
| Poteat, Jade | 22.9868 | 22986.8421
| Warnholz, Benjamin | 8 | 16000
| Qualys Team (AVM) | 0 | 0
| Uysal, Ismail (Project Manager) | 51.1456 | 51145.614
| Goldschmidt, Andreas (SNOW Principal Architect) | 10.6842 | 14423.6842
| AMC Devops Engineer (Internal) | 0 | 0
| APM Devops Engineer (Internal) | 0 | 0
| EMS Devops Engineer (Internal) | 0 | 0
| Workspace Intelligence Internal – Technical SME | 0 | 0
| SNOW Performance Analytics team | 0 | 0
| SNOW Development Teams | 2 | 570
| Workspace Intelligence Vendor – Technical SME | 0 | 0
| SNOW SAM efforts | 0 | 0
| SNOW CMDB | 0 | 0
| CyNet | 0 | 0
| Security Foundation Team | 0 | 0
| CNTR0010576 | 27.5 | 35432.54
| Marc Bochtler | 18 | 25473.69
| Alexander Heinze | 0 | 0
| Tobias Butz | 0 | 0
| NN | 0 | 0
| NN india | 0 | 0
| Yury Nikolin | 9.5 | 9958.85
| Thomas Felder | 0 | 0
| CNTR0010334 | 130.125 | 153138.2055
| Martin Schurm | 27 | 42102.3487
| Tobias Krichel | 62.875 | 74513.3568
| Thomas Huber | 1 | 2030
| Markus Schnier | 1 | 2030
| Dan Read | 0 | 0
| N.N. / Support Dan | 0 | 0
| Ankur Tomar | 0 | 0
| Naman Agrawal | 21.25 | 5312.5
| Clemens Friedrich | 16 | 25120
| Gerhard Schneider | 1 | 2030
| OAM302 | 0 | 0
| Alexander Heinze | 0 | 0
| Daming Yang | 0 | 0
| Manoj Selvakumar | 0 | 0
| David Barton | 0 | 0
| Raja Rajcic | 0 | 0
| Lawrence Tengan | 0 | 0
| Travis Chun | 0 | 0
| Johannes Bross | 0 | 0
| Tuan Minh Nguyen | 0 | 0
| Tobias Tischler | 0 | 0
| Djamel Tazerout | 0 | 0
| Dirk Addicks | 0 | 0
| Forgerock Licence | 0 | 0
| CNTR0010589 | 0 | 0
| Placeholder | 0 | 0
| OAM299 | 0 | 0
| Placeholder | 0 | 0
| CNTR0010618 | 0.79973 | 2114.4735
| Birgit Jarosch | 0.79973 | 2114.4735
| Wolfgang Elsner | 0 | 0
| Alexander Heinze | 0 | 0
| Jagoda Matys | 0 | 0
| N.N. | 0 | 0
| Mitja Ledowski | 0 | 0
| Ingmar Janßen-Holldiek | 0 | 0
| Michael Holder | 0 | 0
| Sinoop K S | 0 | 0
| J. Thomas | 0 | 0
| Madalina Paslaru | 0 | 0
| Daniel Ettenhuber | 0 | 0
| OAM289 | 0 | 0
| Placeholder | 0 | 0
| CNTR0010617 | 0 | 0
| (blank) | 0 | 0
| Alexander Heinze | 0 | 0
| Christine Schlüter | 0 | 0
| Günter Sanktjohanser | 0 | 0
| Metafinanz | 717.9375 | 838906
| 21 0427 | 162.5625 | 155742.25
| Julian Steinfeld | 53 | 58936
| Manuel Hahn | 43.5312 | 42660.625
| Matthias Müller | 66.0312 | 54145.625
| 21 1068 | 107.1875 | 140290.625
| Jonathan Reynolds | 16.75 | 16750
| Samuel Hurst | 38.9688 | 52607.8125
| Kris Harms | 39 | 56550
| Nora von Schenckendorff | 5.4688 | 7382.8125
| Frank Markussen | 1.375 | 1375
| Anette Hettenkofer | 0.125 | 125
| Julia Netesa | 5.5 | 5500
| 21 1079 | 81.1875 | 94356.25
| George Dietrichsbruckner | 37.625 | 50793.75
| Jade Poteat | 7.625 | 7625
| Nadine Butzhammer | 0.3125 | 312.5
| Daniel Wörner | 21.5 | 21500
| Sanat Gautam | 14.125 | 14125
| 21 1037 | 179.6875 | 209831.25
| Gerhard Günther | 31.5 | 42525
| Rasa Rintallo | 43.4375 | 43437.5
| Stefan Köstenbauer | 1.125 | 1518.75
| Victor Peters | 3.8438 | 3843.75
| Michael Habel | 53.5 | 72225
| Maximilian Schellenberger | 3.2812 | 3281.25
| Sona Latifyan | 43 | 43000
| 21 1040 | 6.5 | 6500
| Jade Poteat | 6.5 | 6500
| 21 1133 | 0 | 0
| Krunoslav Rukavina | 0 | 0
| 21 1063 | 135.3125 | 170760.625
| Marc Bochtler | 42.125 | 56868.75
| Thorsten Deckers | 21.0625 | 33068.125
| Robert Reti | 17.875 | 28063.75
| Claudio Cangiotti | 13 | 10010
| Yury Nikulin | 26.25 | 26250
| Eldho George | 15 | 16500
| 21 1059 | 45.5 | 61425
| Thomas Thuspaß | 45.5 | 61425
| other | 0 | 24570
| 0 | 0 | 24570
| (blank) | 0 | 24570
| NCC Group GmbH | 0 | 363140.4
| 2410164170 | 0 | 363140.4
| (blank) | 0 | 363140.4
| Osborne Clark | 0 | 20659.69
| TID0001510089 | 0 | 20659.69
| (blank) | 0 | 20659.69
| Virtual Clarity Ltd | 0 | 149488
| 2410164371 | 0 | 149488
| (blank) | 0 | 149488
| Softwaregilde | 0 | 121975
| 2410159840 | 0 | 121975
| (blank) | 0 | 121975
| Horvath & Partner | 0 | 44625
| 2410160374 | 0 | 44625
| (blank) | 0 | 44625
| Ernst & Young | 0 | 98002.0781
| 2410162165 | 0 | 98002.0781
| (blank) | 0 | 98002.0781
| SRLabs | 0 | 8925
| PR964131 | 0 | 8925
| (blank) | 0 | 8925
| DCSO | 0 | 0
| 0 | 0 | 0
| (blank) | 0 | 0
| SecAttack | 0 | 22312.5
| 0 | 0 | 22312.5
| (blank) | 0 | 22312.5
| (blank) | 2767.8155 | 3482475.2593
| (blank) | 2767.8155 | 3482475.2593
| (blank) | 2767.8155 | 3482475.2593
| (blank) | 2767.8155 | 3482475.2593
| non-Labor | 1 | 210543.769
| AZ Technology | 1 | 107250.619
| CNTR0010616 | 0 | 0
| Licence costs | 0 | 0
| CNTR0010338 | 0 | 32401.999
| Splunk Licenses + Server | 0 | 0
| ZeroFox Licenses | 0 | 32401.999
| CNTR0010333 | 0 | 0
| Splunk Licenses + Server | 0 | 0
| CNTR0010325 | 0 | 0
| HW / infrastructure | 0 | 0
| CNTR0010327 | 0 | 0
| Local SMEs for AVC, FMO | 0 | 0
| AZ Tech America HW | 0 | 0
| CNTR0010332 | 1 | 74848.62
| Cyarx Siemplify | 1 | 74848.62
| CNTR0010329 | 0 | 0
| AWS / Azure cloud | 0 | 0
| CNTR0010618 | 0 | 0
| HW | 0 | 0
| other | 0 | 103293.15
| 0 | 0 | 103293.15
| (blank) | 0 | 103293.15
| Sum | 5535.6311 | 8219441.3367

## M84 (hidden)
M84
Measure Lead: Andreas Wagner
Pillar Lead: Carsten Scholz
Duration: 01.07.2016-31.12.2018
Planned Total | #N/A
Approved Total | #N/A
Spent Labor | #N/A
Spent non-Labor | #N/A
Spent Total | #N/A
Forecast Total | #N/A
| Measure | (All)
|  | Jan |  | Feb | Mrz | Apr | Mai | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total
| Resources & Contracts | PD Total | EUR Total
| Labor | 2766.8155 | 4526422.3084
Comment | AZ Technology | 2048.878 | 2833818.6402
| 0 | 0 | 297500
| (blank) | 0 | 297500
| CNTR0010544 | 110.4647 | 157099.0619
| Andrea Scotti | 0 | 0
| Wolfgang Elsner | 0 | 0
| Alexander Heinze | 0 | 0
| Thomas Huber | 0 | 0
| Jagoda Matys | 0 | 0
| Markus Schnier | 0 | 0
| Sergej Reißig | 55.0018 | 83266.9815
| Binoj Baburaj | 0 | 0
| IAM Architect (Cygna) | 2.4114 | 3159.8592
| NN india | 0 | 0
| Michael Holder | 0 | 0
| Youssef Dahmouni | 0 | 0
| Nina Kaufmann | 20.9999 | 27517.875
| Viktoryia Nikifaravets | 32.0516 | 43154.3461
| CNTR0010615 | 121.7529 | 173433.2076
| Alexander Heinze | 0 | 0
| Jagoda Matys | 0 | 0
| Srdan Mavrenski | 55.0018 | 83266.9815
| Itai Schwartz | 31.2506 | 42075.8024
| NN india | 0 | 0
| Francois Pernayan | 31.2506 | 42075.8024
| Matt Gibson | 0 | 0
| Christian Bolterauer | 4.25 | 6014.6213
| CNTR0010616 | 68.1618 | 102967.1383
| Alexander Heinze | 0 | 0
| Thomas Huber | 0 | 0
| Reza Memarian | 55.0018 | 83266.9815
| Markus Schnier | 0 | 0
| NN india | 0 | 0
| Youssef Dahmouni | 0 | 0
| Walter Hofer | 0 | 0
| Balasz Razs | 0 | 0
| Ivan Markovic | 13.16 | 19700.1568
| Product SME | 0 | 0
| CNTR0010562 | 5 | 7850
| Thomas Huber | 0 | 0
| Markus Schnier | 0 | 0
| Clemens Friedrich | 5 | 7850
| Gerhard Schneider | 0 | 0
| DGI | 0 | 0
| CNTR0010336 | 152.1775 | 271131.6326
| Thomas Huber | 0 | 0
| Markus Schnier | 0 | 0
| Daniela Betz | 45.9375 | 65010.9849
| Bastian Kastner | 45.25 | 47435.575
| Clemens Friedrich | 0 | 0
| Gerhard Schneider | 3.77 | 7653.1
| Björn Hansen / Markus Feuerstein | 0 | 85551.9727
| Rudresh Subramanian | 20.22 | 30330
| Guelsah Uestelci | 37 | 35150
| CNTR0010335 | 56 | 64575.28
| N.N. | 0 | 0
| Markus Gatter | 56 | 64575.28
| Jakob Schusser | 0 | 0
| Gabriella Nagy | 0 | 0
| N.N. // SME 2 | 0 | 0
| N.N. // Sr. Analyst | 0 | 0
| SR Labs Autobahn | 0 | 0
| OE Effort | 0 | 0
| Ben Brüggen | 0 | 0
| CNTR0010338 | 152.3738 | 157766.1581
| Rene Pferner | 0 | 0
| Thomas Huber | 1 | 2030
| Markus Schnier | 1 | 2030
| N.N. | 0 | 0
| Clemens Friedrich | 15 | 23550
| Gerhard Schneider | 6.03 | 12240.9
| Anna Hartl | 53.8125 | 56411.6437
| Alina Lobova | 55.75 | 46754.18
| Stefan Kösters | 12.2812 | 12874.4344
| Kühnlenz / 2wmedia | 0 | 0
| Natalia Nikitana | 0 | 0
| IT Seal | 0 | 0
| Aishwarya Nangude / Sarabjit Singh | 0 | 0
| Meera Patel | 7.5 | 1875
| CNTR0010333 | 245.5625 | 276810.2324
| Christoph Lenz | 31.625 | 33152.4875
| Thomas Huber | 0 | 0
| Markus Schnier | 0 | 0
| Corinna Koch | 19.375 | 20310.8125
| Vasanthan Dhanasingh | 0 | 0
| Clemens Friedrich | 0 | 0
| Gerhard Schneider | 0 | 0
| Sven Lierzer | 48.875 | 57921.9165
| Tobias Lichtenberg | 12.6875 | 17955.4134
| Stanislav Khotinok | 34.125 | 39350.5613
| Alexander Leonhardt | 56.75 | 65440.1275
| Yuri Nikulin | 23.375 | 26954.4138
| Maria Thanner | 18.75 | 15724.5
| SNOW-Team | 0 | 0
| Splunk Team | 0 | 0
| Ankita Mane | 0 | 0
| Martin Gerlowski | 0 | 0
| Deepak Krishnan | 0 | 0
| K Harikrishnan | 0 | 0
| CNTR0010337 | 19.2596 | 32647.4087
| Placeholder | 0 | 0
| Matthias Kickstein | 0 | 0
| Computacenter | 0 | 0
| Ernst & Young | 19.2596 | 32647.4087
| CNTR0010325 | 29.75 | 16237.5
| Alex Lee | 0 | 0
| Lucas Tscherter | 0 | 0
| Corinna Koch | 0 | 0
| Dhanya Kalathil | 19.75 | 4937.5
| Mark de Vera | 0 | 0
| Balasz Racz | 10 | 11300
| Arunlal Nair | 0 | 0
| Local Infra setup support | 0 | 0
| Local SMEs for AVC, FMO | 0 | 0
| Cabling APAC | 0 | 0
| CNTR0010327 | 20 | 5320
| Thomas Huber | 0 | 0
| Gereon Volker | 0 | 0
| Lucas Tscherter | 0 | 0
| Markus Schnier | 0 | 0
| Thomas Bringewald | 2 | 2260
| Andrei Maslov | 0 | 0
| Patrick Zeitz | 0 | 0
| Armando Diaz | 0 | 0
| Ron Johnson | 0 | 0
| Jithin Varghese | 18 | 3060
| AZ Tech America Labor | 0 | 0
| Service Manager | 0 | 0
| CNTR0010332 | 177.713 | 270824.8831
| Timothy Drost | 51.25 | 56077.4981
| Thomas Huber | 1 | 2030
| Holger Steinlechner | 1.78 | 2011.4
| Lucas Tscherter | 20.42 | 32059.4
| Markus Schnier | 1 | 2030
| Olivier Ma | 0 | 0
| Rebecca Dengl | 0.263 | 297.19
| Andrei Maslov | 5 | 5650
| Racz Balazs | 2 | 2260
| Jimmy Braun | 0 | 0
| Cyarx Siemplify | 95 | 168409.395
| CMDB | 0 | 0
| CNTR0010329 | 97.9983 | 221663.7262
| Thomas Huber | 1 | 2030
| Gereon Volker | 0 | 0
| Lucas Tscherter | 27.79 | 43630.3
| Markus Schnier | 1 | 2030
| Thomas Bringewald | 5 | 5650
| Rebecca Dengl | 0.526 | 594.38
| Felix Hertin | 3.2615 | 5242.0231
| Lukas Thiele | 9.4208 | 5242.0231
| Holger Wache | 25 | 78622.5
| Tobias Martin | 25 | 78622.5
| Deloitte | 0 | 0
| CNTR0010709 | 11 | 16796.845
| Thomas Huber | 1 | 2030
| Lucas Tscherter | 0 | 0
| Markus Schnier | 1 | 2030
| Krunoslav Rukavina | 9 | 12736.845
| Joachim Steinberger | 0 | 0
| Elastic | 0 | 0
| Proofpoint | 0 | 0
| CNTR0010564 | 513.2647 | 444921.049
| Markus Traumueller | 10 | 11300
| Karim, Hasan | 57 | 59850
| Bojarski, Eduard | 57 | 112122.99
| Kayali, Ismail | 57 | 72645.93
| Stettner, Julia | 57 | 80717.13
| Tulshidas Thamke, Budhesh | 57 | 9120
| Sunderdas, Shilpa | 58 | 9280
| Bönigk, Julian | 10 | 11300
| Sora Mustafa (AUG-OCT only) | 52 | 61880
| Vidya Baskaran Reddy | 57 | 9690
| S, Shibi (partily on IP&G) | 41.2647 | 7014.999
| CNTR0010563 | 109.9746 | 125589.2982
| Günther, Gerhard | 15.1579 | 20463.1579
| Poteat, Jade | 22.9868 | 22986.8421
| Warnholz, Benjamin | 8 | 16000
| Qualys Team (AVM) | 0 | 0
| Uysal, Ismail (Project Manager) | 51.1456 | 51145.614
| Goldschmidt, Andreas (SNOW Principal Architect) | 10.6842 | 14423.6842
| AMC Devops Engineer (Internal) | 0 | 0
| APM Devops Engineer (Internal) | 0 | 0
| EMS Devops Engineer (Internal) | 0 | 0
| Workspace Intelligence Internal – Technical SME | 0 | 0
| SNOW Performance Analytics team | 0 | 0
| SNOW Development Teams | 2 | 570
| Workspace Intelligence Vendor – Technical SME | 0 | 0
| SNOW SAM efforts | 0 | 0
| SNOW CMDB | 0 | 0
| CyNet | 0 | 0
| Security Foundation Team | 0 | 0
| CNTR0010576 | 27.5 | 35432.54
| Marc Bochtler | 18 | 25473.69
| Alexander Heinze | 0 | 0
| Tobias Butz | 0 | 0
| NN | 0 | 0
| NN india | 0 | 0
| Yury Nikolin | 9.5 | 9958.85
| Thomas Felder | 0 | 0
| CNTR0010334 | 130.125 | 153138.2055
| Martin Schurm | 27 | 42102.3487
| Tobias Krichel | 62.875 | 74513.3568
| Thomas Huber | 1 | 2030
| Markus Schnier | 1 | 2030
| Dan Read | 0 | 0
| N.N. / Support Dan | 0 | 0
| Ankur Tomar | 0 | 0
| Naman Agrawal | 21.25 | 5312.5
| Clemens Friedrich | 16 | 25120
| Gerhard Schneider | 1 | 2030
| OAM302 | 0 | 0
| Alexander Heinze | 0 | 0
| Daming Yang | 0 | 0
| Manoj Selvakumar | 0 | 0
| David Barton | 0 | 0
| Raja Rajcic | 0 | 0
| Lawrence Tengan | 0 | 0
| Travis Chun | 0 | 0
| Johannes Bross | 0 | 0
| Tuan Minh Nguyen | 0 | 0
| Tobias Tischler | 0 | 0
| Djamel Tazerout | 0 | 0
| Dirk Addicks | 0 | 0
| Forgerock Licence | 0 | 0
| CNTR0010589 | 0 | 0
| Placeholder | 0 | 0
| OAM299 | 0 | 0
| Placeholder | 0 | 0
| CNTR0010618 | 0.79973 | 2114.4735
| Birgit Jarosch | 0.79973 | 2114.4735
| Wolfgang Elsner | 0 | 0
| Alexander Heinze | 0 | 0
| Jagoda Matys | 0 | 0
| N.N. | 0 | 0
| Mitja Ledowski | 0 | 0
| Ingmar Janßen-Holldiek | 0 | 0
| Michael Holder | 0 | 0
| Sinoop K S | 0 | 0
| J. Thomas | 0 | 0
| Madalina Paslaru | 0 | 0
| Daniel Ettenhuber | 0 | 0
| OAM289 | 0 | 0
| Placeholder | 0 | 0
| CNTR0010617 | 0 | 0
| (blank) | 0 | 0
| Alexander Heinze | 0 | 0
| Christine Schlüter | 0 | 0
| Günter Sanktjohanser | 0 | 0
| Metafinanz | 717.9375 | 838906
| 21 0427 | 162.5625 | 155742.25
| Julian Steinfeld | 53 | 58936
| Manuel Hahn | 43.5312 | 42660.625
| Matthias Müller | 66.0312 | 54145.625
| 21 1068 | 107.1875 | 140290.625
| Jonathan Reynolds | 16.75 | 16750
| Samuel Hurst | 38.9688 | 52607.8125
| Kris Harms | 39 | 56550
| Nora von Schenckendorff | 5.4688 | 7382.8125
| Frank Markussen | 1.375 | 1375
| Anette Hettenkofer | 0.125 | 125
| Julia Netesa | 5.5 | 5500
| 21 1079 | 81.1875 | 94356.25
| George Dietrichsbruckner | 37.625 | 50793.75
| Jade Poteat | 7.625 | 7625
| Nadine Butzhammer | 0.3125 | 312.5
| Daniel Wörner | 21.5 | 21500
| Sanat Gautam | 14.125 | 14125
| 21 1037 | 179.6875 | 209831.25
| Gerhard Günther | 31.5 | 42525
| Rasa Rintallo | 43.4375 | 43437.5
| Stefan Köstenbauer | 1.125 | 1518.75
| Victor Peters | 3.8438 | 3843.75
| Michael Habel | 53.5 | 72225
| Maximilian Schellenberger | 3.2812 | 3281.25
| Sona Latifyan | 43 | 43000
| 21 1040 | 6.5 | 6500
| Jade Poteat | 6.5 | 6500
| 21 1133 | 0 | 0
| Krunoslav Rukavina | 0 | 0
| 21 1063 | 135.3125 | 170760.625
| Marc Bochtler | 42.125 | 56868.75
| Thorsten Deckers | 21.0625 | 33068.125
| Robert Reti | 17.875 | 28063.75
| Claudio Cangiotti | 13 | 10010
| Yury Nikulin | 26.25 | 26250
| Eldho George | 15 | 16500
| 21 1059 | 45.5 | 61425
| Thomas Thuspaß | 45.5 | 61425
| other | 0 | 24570
| 0 | 0 | 24570
| (blank) | 0 | 24570
| NCC Group GmbH | 0 | 363140.4
| 2410164170 | 0 | 363140.4
| (blank) | 0 | 363140.4
| Osborne Clark | 0 | 20659.69
| TID0001510089 | 0 | 20659.69
| (blank) | 0 | 20659.69
| Virtual Clarity Ltd | 0 | 149488
| 2410164371 | 0 | 149488
| (blank) | 0 | 149488
| Softwaregilde | 0 | 121975
| 2410159840 | 0 | 121975
| (blank) | 0 | 121975
| Horvath & Partner | 0 | 44625
| 2410160374 | 0 | 44625
| (blank) | 0 | 44625
| Ernst & Young | 0 | 98002.0781
| 2410162165 | 0 | 98002.0781
| (blank) | 0 | 98002.0781
| SRLabs | 0 | 8925
| PR964131 | 0 | 8925
| (blank) | 0 | 8925
| DCSO | 0 | 0
| 0 | 0 | 0
| (blank) | 0 | 0
| SecAttack | 0 | 22312.5
| 0 | 0 | 22312.5
| (blank) | 0 | 22312.5
| (blank) | 2767.8155 | 3482475.2593
| (blank) | 2767.8155 | 3482475.2593
| (blank) | 2767.8155 | 3482475.2593
| (blank) | 2767.8155 | 3482475.2593
| non-Labor | 1 | 210543.769
| AZ Technology | 1 | 107250.619
| CNTR0010616 | 0 | 0
| Licence costs | 0 | 0
| CNTR0010338 | 0 | 32401.999
| Splunk Licenses + Server | 0 | 0
| ZeroFox Licenses | 0 | 32401.999
| CNTR0010333 | 0 | 0
| Splunk Licenses + Server | 0 | 0
| CNTR0010325 | 0 | 0
| HW / infrastructure | 0 | 0
| CNTR0010327 | 0 | 0
| Local SMEs for AVC, FMO | 0 | 0
| AZ Tech America HW | 0 | 0
| CNTR0010332 | 1 | 74848.62
| Cyarx Siemplify | 1 | 74848.62
| CNTR0010329 | 0 | 0
| AWS / Azure cloud | 0 | 0
| CNTR0010618 | 0 | 0
| HW | 0 | 0
| other | 0 | 103293.15
| 0 | 0 | 103293.15
| (blank) | 0 | 103293.15
| Sum | 5535.6311 | 8219441.3367

## M17 (hidden)
M17
Measure Lead: Jonathan Reynolds
Pillar Lead: Carsten Scholz
Duration: 01.02.2017-31.12.2018
Planned Total | #N/A
Approved Total | #N/A
Spent Labor | #N/A
Spent non-Labor | #N/A
Spent Total | #N/A
Forecast Total | #N/A
| Measure | (All)
|  | Jan |  | Feb | Mrz | Apr | Mai | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total
| Resources & Contracts | PD Total | EUR Total
| Labor | 2766.8155 | 4526422.3084
Comment | AZ Technology | 2048.878 | 2833818.6402
| 0 | 0 | 297500
| (blank) | 0 | 297500
| CNTR0010544 | 110.4647 | 157099.0619
| Andrea Scotti | 0 | 0
| Wolfgang Elsner | 0 | 0
| Alexander Heinze | 0 | 0
| Thomas Huber | 0 | 0
| Jagoda Matys | 0 | 0
| Markus Schnier | 0 | 0
| Sergej Reißig | 55.0018 | 83266.9815
| Binoj Baburaj | 0 | 0
| IAM Architect (Cygna) | 2.4114 | 3159.8592
| NN india | 0 | 0
| Michael Holder | 0 | 0
| Youssef Dahmouni | 0 | 0
| Nina Kaufmann | 20.9999 | 27517.875
| Viktoryia Nikifaravets | 32.0516 | 43154.3461
| CNTR0010615 | 121.7529 | 173433.2076
| Alexander Heinze | 0 | 0
| Jagoda Matys | 0 | 0
| Srdan Mavrenski | 55.0018 | 83266.9815
| Itai Schwartz | 31.2506 | 42075.8024
| NN india | 0 | 0
| Francois Pernayan | 31.2506 | 42075.8024
| Matt Gibson | 0 | 0
| Christian Bolterauer | 4.25 | 6014.6213
| CNTR0010616 | 68.1618 | 102967.1383
| Alexander Heinze | 0 | 0
| Thomas Huber | 0 | 0
| Reza Memarian | 55.0018 | 83266.9815
| Markus Schnier | 0 | 0
| NN india | 0 | 0
| Youssef Dahmouni | 0 | 0
| Walter Hofer | 0 | 0
| Balasz Razs | 0 | 0
| Ivan Markovic | 13.16 | 19700.1568
| Product SME | 0 | 0
| CNTR0010562 | 5 | 7850
| Thomas Huber | 0 | 0
| Markus Schnier | 0 | 0
| Clemens Friedrich | 5 | 7850
| Gerhard Schneider | 0 | 0
| DGI | 0 | 0
| CNTR0010336 | 152.1775 | 271131.6326
| Thomas Huber | 0 | 0
| Markus Schnier | 0 | 0
| Daniela Betz | 45.9375 | 65010.9849
| Bastian Kastner | 45.25 | 47435.575
| Clemens Friedrich | 0 | 0
| Gerhard Schneider | 3.77 | 7653.1
| Björn Hansen / Markus Feuerstein | 0 | 85551.9727
| Rudresh Subramanian | 20.22 | 30330
| Guelsah Uestelci | 37 | 35150
| CNTR0010335 | 56 | 64575.28
| N.N. | 0 | 0
| Markus Gatter | 56 | 64575.28
| Jakob Schusser | 0 | 0
| Gabriella Nagy | 0 | 0
| N.N. // SME 2 | 0 | 0
| N.N. // Sr. Analyst | 0 | 0
| SR Labs Autobahn | 0 | 0
| OE Effort | 0 | 0
| Ben Brüggen | 0 | 0
| CNTR0010338 | 152.3738 | 157766.1581
| Rene Pferner | 0 | 0
| Thomas Huber | 1 | 2030
| Markus Schnier | 1 | 2030
| N.N. | 0 | 0
| Clemens Friedrich | 15 | 23550
| Gerhard Schneider | 6.03 | 12240.9
| Anna Hartl | 53.8125 | 56411.6437
| Alina Lobova | 55.75 | 46754.18
| Stefan Kösters | 12.2812 | 12874.4344
| Kühnlenz / 2wmedia | 0 | 0
| Natalia Nikitana | 0 | 0
| IT Seal | 0 | 0
| Aishwarya Nangude / Sarabjit Singh | 0 | 0
| Meera Patel | 7.5 | 1875
| CNTR0010333 | 245.5625 | 276810.2324
| Christoph Lenz | 31.625 | 33152.4875
| Thomas Huber | 0 | 0
| Markus Schnier | 0 | 0
| Corinna Koch | 19.375 | 20310.8125
| Vasanthan Dhanasingh | 0 | 0
| Clemens Friedrich | 0 | 0
| Gerhard Schneider | 0 | 0
| Sven Lierzer | 48.875 | 57921.9165
| Tobias Lichtenberg | 12.6875 | 17955.4134
| Stanislav Khotinok | 34.125 | 39350.5613
| Alexander Leonhardt | 56.75 | 65440.1275
| Yuri Nikulin | 23.375 | 26954.4138
| Maria Thanner | 18.75 | 15724.5
| SNOW-Team | 0 | 0
| Splunk Team | 0 | 0
| Ankita Mane | 0 | 0
| Martin Gerlowski | 0 | 0
| Deepak Krishnan | 0 | 0
| K Harikrishnan | 0 | 0
| CNTR0010337 | 19.2596 | 32647.4087
| Placeholder | 0 | 0
| Matthias Kickstein | 0 | 0
| Computacenter | 0 | 0
| Ernst & Young | 19.2596 | 32647.4087
| CNTR0010325 | 29.75 | 16237.5
| Alex Lee | 0 | 0
| Lucas Tscherter | 0 | 0
| Corinna Koch | 0 | 0
| Dhanya Kalathil | 19.75 | 4937.5
| Mark de Vera | 0 | 0
| Balasz Racz | 10 | 11300
| Arunlal Nair | 0 | 0
| Local Infra setup support | 0 | 0
| Local SMEs for AVC, FMO | 0 | 0
| Cabling APAC | 0 | 0
| CNTR0010327 | 20 | 5320
| Thomas Huber | 0 | 0
| Gereon Volker | 0 | 0
| Lucas Tscherter | 0 | 0
| Markus Schnier | 0 | 0
| Thomas Bringewald | 2 | 2260
| Andrei Maslov | 0 | 0
| Patrick Zeitz | 0 | 0
| Armando Diaz | 0 | 0
| Ron Johnson | 0 | 0
| Jithin Varghese | 18 | 3060
| AZ Tech America Labor | 0 | 0
| Service Manager | 0 | 0
| CNTR0010332 | 177.713 | 270824.8831
| Timothy Drost | 51.25 | 56077.4981
| Thomas Huber | 1 | 2030
| Holger Steinlechner | 1.78 | 2011.4
| Lucas Tscherter | 20.42 | 32059.4
| Markus Schnier | 1 | 2030
| Olivier Ma | 0 | 0
| Rebecca Dengl | 0.263 | 297.19
| Andrei Maslov | 5 | 5650
| Racz Balazs | 2 | 2260
| Jimmy Braun | 0 | 0
| Cyarx Siemplify | 95 | 168409.395
| CMDB | 0 | 0
| CNTR0010329 | 97.9983 | 221663.7262
| Thomas Huber | 1 | 2030
| Gereon Volker | 0 | 0
| Lucas Tscherter | 27.79 | 43630.3
| Markus Schnier | 1 | 2030
| Thomas Bringewald | 5 | 5650
| Rebecca Dengl | 0.526 | 594.38
| Felix Hertin | 3.2615 | 5242.0231
| Lukas Thiele | 9.4208 | 5242.0231
| Holger Wache | 25 | 78622.5
| Tobias Martin | 25 | 78622.5
| Deloitte | 0 | 0
| CNTR0010709 | 11 | 16796.845
| Thomas Huber | 1 | 2030
| Lucas Tscherter | 0 | 0
| Markus Schnier | 1 | 2030
| Krunoslav Rukavina | 9 | 12736.845
| Joachim Steinberger | 0 | 0
| Elastic | 0 | 0
| Proofpoint | 0 | 0
| CNTR0010564 | 513.2647 | 444921.049
| Markus Traumueller | 10 | 11300
| Karim, Hasan | 57 | 59850
| Bojarski, Eduard | 57 | 112122.99
| Kayali, Ismail | 57 | 72645.93
| Stettner, Julia | 57 | 80717.13
| Tulshidas Thamke, Budhesh | 57 | 9120
| Sunderdas, Shilpa | 58 | 9280
| Bönigk, Julian | 10 | 11300
| Sora Mustafa (AUG-OCT only) | 52 | 61880
| Vidya Baskaran Reddy | 57 | 9690
| S, Shibi (partily on IP&G) | 41.2647 | 7014.999
| CNTR0010563 | 109.9746 | 125589.2982
| Günther, Gerhard | 15.1579 | 20463.1579
| Poteat, Jade | 22.9868 | 22986.8421
| Warnholz, Benjamin | 8 | 16000
| Qualys Team (AVM) | 0 | 0
| Uysal, Ismail (Project Manager) | 51.1456 | 51145.614
| Goldschmidt, Andreas (SNOW Principal Architect) | 10.6842 | 14423.6842
| AMC Devops Engineer (Internal) | 0 | 0
| APM Devops Engineer (Internal) | 0 | 0
| EMS Devops Engineer (Internal) | 0 | 0
| Workspace Intelligence Internal – Technical SME | 0 | 0
| SNOW Performance Analytics team | 0 | 0
| SNOW Development Teams | 2 | 570
| Workspace Intelligence Vendor – Technical SME | 0 | 0
| SNOW SAM efforts | 0 | 0
| SNOW CMDB | 0 | 0
| CyNet | 0 | 0
| Security Foundation Team | 0 | 0
| CNTR0010576 | 27.5 | 35432.54
| Marc Bochtler | 18 | 25473.69
| Alexander Heinze | 0 | 0
| Tobias Butz | 0 | 0
| NN | 0 | 0
| NN india | 0 | 0
| Yury Nikolin | 9.5 | 9958.85
| Thomas Felder | 0 | 0
| CNTR0010334 | 130.125 | 153138.2055
| Martin Schurm | 27 | 42102.3487
| Tobias Krichel | 62.875 | 74513.3568
| Thomas Huber | 1 | 2030
| Markus Schnier | 1 | 2030
| Dan Read | 0 | 0
| N.N. / Support Dan | 0 | 0
| Ankur Tomar | 0 | 0
| Naman Agrawal | 21.25 | 5312.5
| Clemens Friedrich | 16 | 25120
| Gerhard Schneider | 1 | 2030
| OAM302 | 0 | 0
| Alexander Heinze | 0 | 0
| Daming Yang | 0 | 0
| Manoj Selvakumar | 0 | 0
| David Barton | 0 | 0
| Raja Rajcic | 0 | 0
| Lawrence Tengan | 0 | 0
| Travis Chun | 0 | 0
| Johannes Bross | 0 | 0
| Tuan Minh Nguyen | 0 | 0
| Tobias Tischler | 0 | 0
| Djamel Tazerout | 0 | 0
| Dirk Addicks | 0 | 0
| Forgerock Licence | 0 | 0
| CNTR0010589 | 0 | 0
| Placeholder | 0 | 0
| OAM299 | 0 | 0
| Placeholder | 0 | 0
| CNTR0010618 | 0.79973 | 2114.4735
| Birgit Jarosch | 0.79973 | 2114.4735
| Wolfgang Elsner | 0 | 0
| Alexander Heinze | 0 | 0
| Jagoda Matys | 0 | 0
| N.N. | 0 | 0
| Mitja Ledowski | 0 | 0
| Ingmar Janßen-Holldiek | 0 | 0
| Michael Holder | 0 | 0
| Sinoop K S | 0 | 0
| J. Thomas | 0 | 0
| Madalina Paslaru | 0 | 0
| Daniel Ettenhuber | 0 | 0
| OAM289 | 0 | 0
| Placeholder | 0 | 0
| CNTR0010617 | 0 | 0
| (blank) | 0 | 0
| Alexander Heinze | 0 | 0
| Christine Schlüter | 0 | 0
| Günter Sanktjohanser | 0 | 0
| Metafinanz | 717.9375 | 838906
| 21 0427 | 162.5625 | 155742.25
| Julian Steinfeld | 53 | 58936
| Manuel Hahn | 43.5312 | 42660.625
| Matthias Müller | 66.0312 | 54145.625
| 21 1068 | 107.1875 | 140290.625
| Jonathan Reynolds | 16.75 | 16750
| Samuel Hurst | 38.9688 | 52607.8125
| Kris Harms | 39 | 56550
| Nora von Schenckendorff | 5.4688 | 7382.8125
| Frank Markussen | 1.375 | 1375
| Anette Hettenkofer | 0.125 | 125
| Julia Netesa | 5.5 | 5500
| 21 1079 | 81.1875 | 94356.25
| George Dietrichsbruckner | 37.625 | 50793.75
| Jade Poteat | 7.625 | 7625
| Nadine Butzhammer | 0.3125 | 312.5
| Daniel Wörner | 21.5 | 21500
| Sanat Gautam | 14.125 | 14125
| 21 1037 | 179.6875 | 209831.25
| Gerhard Günther | 31.5 | 42525
| Rasa Rintallo | 43.4375 | 43437.5
| Stefan Köstenbauer | 1.125 | 1518.75
| Victor Peters | 3.8438 | 3843.75
| Michael Habel | 53.5 | 72225
| Maximilian Schellenberger | 3.2812 | 3281.25
| Sona Latifyan | 43 | 43000
| 21 1040 | 6.5 | 6500
| Jade Poteat | 6.5 | 6500
| 21 1133 | 0 | 0
| Krunoslav Rukavina | 0 | 0
| 21 1063 | 135.3125 | 170760.625
| Marc Bochtler | 42.125 | 56868.75
| Thorsten Deckers | 21.0625 | 33068.125
| Robert Reti | 17.875 | 28063.75
| Claudio Cangiotti | 13 | 10010
| Yury Nikulin | 26.25 | 26250
| Eldho George | 15 | 16500
| 21 1059 | 45.5 | 61425
| Thomas Thuspaß | 45.5 | 61425
| other | 0 | 24570
| 0 | 0 | 24570
| (blank) | 0 | 24570
| NCC Group GmbH | 0 | 363140.4
| 2410164170 | 0 | 363140.4
| (blank) | 0 | 363140.4
| Osborne Clark | 0 | 20659.69
| TID0001510089 | 0 | 20659.69
| (blank) | 0 | 20659.69
| Virtual Clarity Ltd | 0 | 149488
| 2410164371 | 0 | 149488
| (blank) | 0 | 149488
| Softwaregilde | 0 | 121975
| 2410159840 | 0 | 121975
| (blank) | 0 | 121975
| Horvath & Partner | 0 | 44625
| 2410160374 | 0 | 44625
| (blank) | 0 | 44625
| Ernst & Young | 0 | 98002.0781
| 2410162165 | 0 | 98002.0781
| (blank) | 0 | 98002.0781
| SRLabs | 0 | 8925
| PR964131 | 0 | 8925
| (blank) | 0 | 8925
| DCSO | 0 | 0
| 0 | 0 | 0
| (blank) | 0 | 0
| SecAttack | 0 | 22312.5
| 0 | 0 | 22312.5
| (blank) | 0 | 22312.5
| (blank) | 2767.8155 | 3482475.2593
| (blank) | 2767.8155 | 3482475.2593
| (blank) | 2767.8155 | 3482475.2593
| (blank) | 2767.8155 | 3482475.2593
| non-Labor | 1 | 210543.769
| AZ Technology | 1 | 107250.619
| CNTR0010616 | 0 | 0
| Licence costs | 0 | 0
| CNTR0010338 | 0 | 32401.999
| Splunk Licenses + Server | 0 | 0
| ZeroFox Licenses | 0 | 32401.999
| CNTR0010333 | 0 | 0
| Splunk Licenses + Server | 0 | 0
| CNTR0010325 | 0 | 0
| HW / infrastructure | 0 | 0
| CNTR0010327 | 0 | 0
| Local SMEs for AVC, FMO | 0 | 0
| AZ Tech America HW | 0 | 0
| CNTR0010332 | 1 | 74848.62
| Cyarx Siemplify | 1 | 74848.62
| CNTR0010329 | 0 | 0
| AWS / Azure cloud | 0 | 0
| CNTR0010618 | 0 | 0
| HW | 0 | 0
| other | 0 | 103293.15
| 0 | 0 | 103293.15
| (blank) | 0 | 103293.15
| Sum | 5535.6311 | 8219441.3367

## M49 (hidden)
M49
Measure Lead: Stephan Gerhager
Pillar Lead: Carsten Scholz
Duration: 01.11.2016-31.12.2018
Planned Total | #N/A
Approved Total | #N/A
Spent Labor | #N/A
Spent non-Labor | #N/A
Spent Total | #N/A
Forecast Total | #N/A
| Measure | (All)
|  | Jan |  | Feb | Mrz | Apr | Mai | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total
| Resources & Contracts | PD Total | EUR Total
| Labor | 2766.8155 | 4526422.3084
Comment | AZ Technology | 2048.878 | 2833818.6402
| 0 | 0 | 297500
| (blank) | 0 | 297500
| CNTR0010544 | 110.4647 | 157099.0619
| Andrea Scotti | 0 | 0
| Wolfgang Elsner | 0 | 0
| Alexander Heinze | 0 | 0
| Thomas Huber | 0 | 0
| Jagoda Matys | 0 | 0
| Markus Schnier | 0 | 0
| Sergej Reißig | 55.0018 | 83266.9815
| Binoj Baburaj | 0 | 0
| IAM Architect (Cygna) | 2.4114 | 3159.8592
| NN india | 0 | 0
| Michael Holder | 0 | 0
| Youssef Dahmouni | 0 | 0
| Nina Kaufmann | 20.9999 | 27517.875
| Viktoryia Nikifaravets | 32.0516 | 43154.3461
| CNTR0010615 | 121.7529 | 173433.2076
| Alexander Heinze | 0 | 0
| Jagoda Matys | 0 | 0
| Srdan Mavrenski | 55.0018 | 83266.9815
| Itai Schwartz | 31.2506 | 42075.8024
| NN india | 0 | 0
| Francois Pernayan | 31.2506 | 42075.8024
| Matt Gibson | 0 | 0
| Christian Bolterauer | 4.25 | 6014.6213
| CNTR0010616 | 68.1618 | 102967.1383
| Alexander Heinze | 0 | 0
| Thomas Huber | 0 | 0
| Reza Memarian | 55.0018 | 83266.9815
| Markus Schnier | 0 | 0
| NN india | 0 | 0
| Youssef Dahmouni | 0 | 0
| Walter Hofer | 0 | 0
| Balasz Razs | 0 | 0
| Ivan Markovic | 13.16 | 19700.1568
| Product SME | 0 | 0
| CNTR0010562 | 5 | 7850
| Thomas Huber | 0 | 0
| Markus Schnier | 0 | 0
| Clemens Friedrich | 5 | 7850
| Gerhard Schneider | 0 | 0
| DGI | 0 | 0
| CNTR0010336 | 152.1775 | 271131.6326
| Thomas Huber | 0 | 0
| Markus Schnier | 0 | 0
| Daniela Betz | 45.9375 | 65010.9849
| Bastian Kastner | 45.25 | 47435.575
| Clemens Friedrich | 0 | 0
| Gerhard Schneider | 3.77 | 7653.1
| Björn Hansen / Markus Feuerstein | 0 | 85551.9727
| Rudresh Subramanian | 20.22 | 30330
| Guelsah Uestelci | 37 | 35150
| CNTR0010335 | 56 | 64575.28
| N.N. | 0 | 0
| Markus Gatter | 56 | 64575.28
| Jakob Schusser | 0 | 0
| Gabriella Nagy | 0 | 0
| N.N. // SME 2 | 0 | 0
| N.N. // Sr. Analyst | 0 | 0
| SR Labs Autobahn | 0 | 0
| OE Effort | 0 | 0
| Ben Brüggen | 0 | 0
| CNTR0010338 | 152.3738 | 157766.1581
| Rene Pferner | 0 | 0
| Thomas Huber | 1 | 2030
| Markus Schnier | 1 | 2030
| N.N. | 0 | 0
| Clemens Friedrich | 15 | 23550
| Gerhard Schneider | 6.03 | 12240.9
| Anna Hartl | 53.8125 | 56411.6437
| Alina Lobova | 55.75 | 46754.18
| Stefan Kösters | 12.2812 | 12874.4344
| Kühnlenz / 2wmedia | 0 | 0
| Natalia Nikitana | 0 | 0
| IT Seal | 0 | 0
| Aishwarya Nangude / Sarabjit Singh | 0 | 0
| Meera Patel | 7.5 | 1875
| CNTR0010333 | 245.5625 | 276810.2324
| Christoph Lenz | 31.625 | 33152.4875
| Thomas Huber | 0 | 0
| Markus Schnier | 0 | 0
| Corinna Koch | 19.375 | 20310.8125
| Vasanthan Dhanasingh | 0 | 0
| Clemens Friedrich | 0 | 0
| Gerhard Schneider | 0 | 0
| Sven Lierzer | 48.875 | 57921.9165
| Tobias Lichtenberg | 12.6875 | 17955.4134
| Stanislav Khotinok | 34.125 | 39350.5613
| Alexander Leonhardt | 56.75 | 65440.1275
| Yuri Nikulin | 23.375 | 26954.4138
| Maria Thanner | 18.75 | 15724.5
| SNOW-Team | 0 | 0
| Splunk Team | 0 | 0
| Ankita Mane | 0 | 0
| Martin Gerlowski | 0 | 0
| Deepak Krishnan | 0 | 0
| K Harikrishnan | 0 | 0
| CNTR0010337 | 19.2596 | 32647.4087
| Placeholder | 0 | 0
| Matthias Kickstein | 0 | 0
| Computacenter | 0 | 0
| Ernst & Young | 19.2596 | 32647.4087
| CNTR0010325 | 29.75 | 16237.5
| Alex Lee | 0 | 0
| Lucas Tscherter | 0 | 0
| Corinna Koch | 0 | 0
| Dhanya Kalathil | 19.75 | 4937.5
| Mark de Vera | 0 | 0
| Balasz Racz | 10 | 11300
| Arunlal Nair | 0 | 0
| Local Infra setup support | 0 | 0
| Local SMEs for AVC, FMO | 0 | 0
| Cabling APAC | 0 | 0
| CNTR0010327 | 20 | 5320
| Thomas Huber | 0 | 0
| Gereon Volker | 0 | 0
| Lucas Tscherter | 0 | 0
| Markus Schnier | 0 | 0
| Thomas Bringewald | 2 | 2260
| Andrei Maslov | 0 | 0
| Patrick Zeitz | 0 | 0
| Armando Diaz | 0 | 0
| Ron Johnson | 0 | 0
| Jithin Varghese | 18 | 3060
| AZ Tech America Labor | 0 | 0
| Service Manager | 0 | 0
| CNTR0010332 | 177.713 | 270824.8831
| Timothy Drost | 51.25 | 56077.4981
| Thomas Huber | 1 | 2030
| Holger Steinlechner | 1.78 | 2011.4
| Lucas Tscherter | 20.42 | 32059.4
| Markus Schnier | 1 | 2030
| Olivier Ma | 0 | 0
| Rebecca Dengl | 0.263 | 297.19
| Andrei Maslov | 5 | 5650
| Racz Balazs | 2 | 2260
| Jimmy Braun | 0 | 0
| Cyarx Siemplify | 95 | 168409.395
| CMDB | 0 | 0
| CNTR0010329 | 97.9983 | 221663.7262
| Thomas Huber | 1 | 2030
| Gereon Volker | 0 | 0
| Lucas Tscherter | 27.79 | 43630.3
| Markus Schnier | 1 | 2030
| Thomas Bringewald | 5 | 5650
| Rebecca Dengl | 0.526 | 594.38
| Felix Hertin | 3.2615 | 5242.0231
| Lukas Thiele | 9.4208 | 5242.0231
| Holger Wache | 25 | 78622.5
| Tobias Martin | 25 | 78622.5
| Deloitte | 0 | 0
| CNTR0010709 | 11 | 16796.845
| Thomas Huber | 1 | 2030
| Lucas Tscherter | 0 | 0
| Markus Schnier | 1 | 2030
| Krunoslav Rukavina | 9 | 12736.845
| Joachim Steinberger | 0 | 0
| Elastic | 0 | 0
| Proofpoint | 0 | 0
| CNTR0010564 | 513.2647 | 444921.049
| Markus Traumueller | 10 | 11300
| Karim, Hasan | 57 | 59850
| Bojarski, Eduard | 57 | 112122.99
| Kayali, Ismail | 57 | 72645.93
| Stettner, Julia | 57 | 80717.13
| Tulshidas Thamke, Budhesh | 57 | 9120
| Sunderdas, Shilpa | 58 | 9280
| Bönigk, Julian | 10 | 11300
| Sora Mustafa (AUG-OCT only) | 52 | 61880
| Vidya Baskaran Reddy | 57 | 9690
| S, Shibi (partily on IP&G) | 41.2647 | 7014.999
| CNTR0010563 | 109.9746 | 125589.2982
| Günther, Gerhard | 15.1579 | 20463.1579
| Poteat, Jade | 22.9868 | 22986.8421
| Warnholz, Benjamin | 8 | 16000
| Qualys Team (AVM) | 0 | 0
| Uysal, Ismail (Project Manager) | 51.1456 | 51145.614
| Goldschmidt, Andreas (SNOW Principal Architect) | 10.6842 | 14423.6842
| AMC Devops Engineer (Internal) | 0 | 0
| APM Devops Engineer (Internal) | 0 | 0
| EMS Devops Engineer (Internal) | 0 | 0
| Workspace Intelligence Internal – Technical SME | 0 | 0
| SNOW Performance Analytics team | 0 | 0
| SNOW Development Teams | 2 | 570
| Workspace Intelligence Vendor – Technical SME | 0 | 0
| SNOW SAM efforts | 0 | 0
| SNOW CMDB | 0 | 0
| CyNet | 0 | 0
| Security Foundation Team | 0 | 0
| CNTR0010576 | 27.5 | 35432.54
| Marc Bochtler | 18 | 25473.69
| Alexander Heinze | 0 | 0
| Tobias Butz | 0 | 0
| NN | 0 | 0
| NN india | 0 | 0
| Yury Nikolin | 9.5 | 9958.85
| Thomas Felder | 0 | 0
| CNTR0010334 | 130.125 | 153138.2055
| Martin Schurm | 27 | 42102.3487
| Tobias Krichel | 62.875 | 74513.3568
| Thomas Huber | 1 | 2030
| Markus Schnier | 1 | 2030
| Dan Read | 0 | 0
| N.N. / Support Dan | 0 | 0
| Ankur Tomar | 0 | 0
| Naman Agrawal | 21.25 | 5312.5
| Clemens Friedrich | 16 | 25120
| Gerhard Schneider | 1 | 2030
| OAM302 | 0 | 0
| Alexander Heinze | 0 | 0
| Daming Yang | 0 | 0
| Manoj Selvakumar | 0 | 0
| David Barton | 0 | 0
| Raja Rajcic | 0 | 0
| Lawrence Tengan | 0 | 0
| Travis Chun | 0 | 0
| Johannes Bross | 0 | 0
| Tuan Minh Nguyen | 0 | 0
| Tobias Tischler | 0 | 0
| Djamel Tazerout | 0 | 0
| Dirk Addicks | 0 | 0
| Forgerock Licence | 0 | 0
| CNTR0010589 | 0 | 0
| Placeholder | 0 | 0
| OAM299 | 0 | 0
| Placeholder | 0 | 0
| CNTR0010618 | 0.79973 | 2114.4735
| Birgit Jarosch | 0.79973 | 2114.4735
| Wolfgang Elsner | 0 | 0
| Alexander Heinze | 0 | 0
| Jagoda Matys | 0 | 0
| N.N. | 0 | 0
| Mitja Ledowski | 0 | 0
| Ingmar Janßen-Holldiek | 0 | 0
| Michael Holder | 0 | 0
| Sinoop K S | 0 | 0
| J. Thomas | 0 | 0
| Madalina Paslaru | 0 | 0
| Daniel Ettenhuber | 0 | 0
| OAM289 | 0 | 0
| Placeholder | 0 | 0
| CNTR0010617 | 0 | 0
| (blank) | 0 | 0
| Alexander Heinze | 0 | 0
| Christine Schlüter | 0 | 0
| Günter Sanktjohanser | 0 | 0
| Metafinanz | 717.9375 | 838906
| 21 0427 | 162.5625 | 155742.25
| Julian Steinfeld | 53 | 58936
| Manuel Hahn | 43.5312 | 42660.625
| Matthias Müller | 66.0312 | 54145.625
| 21 1068 | 107.1875 | 140290.625
| Jonathan Reynolds | 16.75 | 16750
| Samuel Hurst | 38.9688 | 52607.8125
| Kris Harms | 39 | 56550
| Nora von Schenckendorff | 5.4688 | 7382.8125
| Frank Markussen | 1.375 | 1375
| Anette Hettenkofer | 0.125 | 125
| Julia Netesa | 5.5 | 5500
| 21 1079 | 81.1875 | 94356.25
| George Dietrichsbruckner | 37.625 | 50793.75
| Jade Poteat | 7.625 | 7625
| Nadine Butzhammer | 0.3125 | 312.5
| Daniel Wörner | 21.5 | 21500
| Sanat Gautam | 14.125 | 14125
| 21 1037 | 179.6875 | 209831.25
| Gerhard Günther | 31.5 | 42525
| Rasa Rintallo | 43.4375 | 43437.5
| Stefan Köstenbauer | 1.125 | 1518.75
| Victor Peters | 3.8438 | 3843.75
| Michael Habel | 53.5 | 72225
| Maximilian Schellenberger | 3.2812 | 3281.25
| Sona Latifyan | 43 | 43000
| 21 1040 | 6.5 | 6500
| Jade Poteat | 6.5 | 6500
| 21 1133 | 0 | 0
| Krunoslav Rukavina | 0 | 0
| 21 1063 | 135.3125 | 170760.625
| Marc Bochtler | 42.125 | 56868.75
| Thorsten Deckers | 21.0625 | 33068.125
| Robert Reti | 17.875 | 28063.75
| Claudio Cangiotti | 13 | 10010
| Yury Nikulin | 26.25 | 26250
| Eldho George | 15 | 16500
| 21 1059 | 45.5 | 61425
| Thomas Thuspaß | 45.5 | 61425
| other | 0 | 24570
| 0 | 0 | 24570
| (blank) | 0 | 24570
| NCC Group GmbH | 0 | 363140.4
| 2410164170 | 0 | 363140.4
| (blank) | 0 | 363140.4
| Osborne Clark | 0 | 20659.69
| TID0001510089 | 0 | 20659.69
| (blank) | 0 | 20659.69
| Virtual Clarity Ltd | 0 | 149488
| 2410164371 | 0 | 149488
| (blank) | 0 | 149488
| Softwaregilde | 0 | 121975
| 2410159840 | 0 | 121975
| (blank) | 0 | 121975
| Horvath & Partner | 0 | 44625
| 2410160374 | 0 | 44625
| (blank) | 0 | 44625
| Ernst & Young | 0 | 98002.0781
| 2410162165 | 0 | 98002.0781
| (blank) | 0 | 98002.0781
| SRLabs | 0 | 8925
| PR964131 | 0 | 8925
| (blank) | 0 | 8925
| DCSO | 0 | 0
| 0 | 0 | 0
| (blank) | 0 | 0
| SecAttack | 0 | 22312.5
| 0 | 0 | 22312.5
| (blank) | 0 | 22312.5
| (blank) | 2767.8155 | 3482475.2593
| (blank) | 2767.8155 | 3482475.2593
| (blank) | 2767.8155 | 3482475.2593
| (blank) | 2767.8155 | 3482475.2593
| non-Labor | 1 | 210543.769
| AZ Technology | 1 | 107250.619
| CNTR0010616 | 0 | 0
| Licence costs | 0 | 0
| CNTR0010338 | 0 | 32401.999
| Splunk Licenses + Server | 0 | 0
| ZeroFox Licenses | 0 | 32401.999
| CNTR0010333 | 0 | 0
| Splunk Licenses + Server | 0 | 0
| CNTR0010325 | 0 | 0
| HW / infrastructure | 0 | 0
| CNTR0010327 | 0 | 0
| Local SMEs for AVC, FMO | 0 | 0
| AZ Tech America HW | 0 | 0
| CNTR0010332 | 1 | 74848.62
| Cyarx Siemplify | 1 | 74848.62
| CNTR0010329 | 0 | 0
| AWS / Azure cloud | 0 | 0
| CNTR0010618 | 0 | 0
| HW | 0 | 0
| other | 0 | 103293.15
| 0 | 0 | 103293.15
| (blank) | 0 | 103293.15
| Sum | 5535.6311 | 8219441.3367

## M33 (hidden)
M33
Measure Lead: Axel Schaffrath
Pillar Lead: Carsten Scholz
Duration: 01.08.2016-31.12.2018
Planned Total | #N/A
Approved Total | #N/A
Spent Labor | #N/A
Spent non-Labor | #N/A
Spent Total | #N/A
Forecast Total | #N/A
| Measure | (All)
|  | Jan |  | Feb | Mrz | Apr | Mai | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total
| Resources & Contracts | PD Total | EUR Total
| Labor | 2766.8155 | 4526422.3084
Comment | AZ Technology | 2048.878 | 2833818.6402
| 0 | 0 | 297500
| (blank) | 0 | 297500
| CNTR0010544 | 110.4647 | 157099.0619
| Andrea Scotti | 0 | 0
| Wolfgang Elsner | 0 | 0
| Alexander Heinze | 0 | 0
| Thomas Huber | 0 | 0
| Jagoda Matys | 0 | 0
| Markus Schnier | 0 | 0
| Sergej Reißig | 55.0018 | 83266.9815
| Binoj Baburaj | 0 | 0
| IAM Architect (Cygna) | 2.4114 | 3159.8592
| NN india | 0 | 0
| Michael Holder | 0 | 0
| Youssef Dahmouni | 0 | 0
| Nina Kaufmann | 20.9999 | 27517.875
| Viktoryia Nikifaravets | 32.0516 | 43154.3461
| CNTR0010615 | 121.7529 | 173433.2076
| Alexander Heinze | 0 | 0
| Jagoda Matys | 0 | 0
| Srdan Mavrenski | 55.0018 | 83266.9815
| Itai Schwartz | 31.2506 | 42075.8024
| NN india | 0 | 0
| Francois Pernayan | 31.2506 | 42075.8024
| Matt Gibson | 0 | 0
| Christian Bolterauer | 4.25 | 6014.6213
| CNTR0010616 | 68.1618 | 102967.1383
| Alexander Heinze | 0 | 0
| Thomas Huber | 0 | 0
| Reza Memarian | 55.0018 | 83266.9815
| Markus Schnier | 0 | 0
| NN india | 0 | 0
| Youssef Dahmouni | 0 | 0
| Walter Hofer | 0 | 0
| Balasz Razs | 0 | 0
| Ivan Markovic | 13.16 | 19700.1568
| Product SME | 0 | 0
| CNTR0010562 | 5 | 7850
| Thomas Huber | 0 | 0
| Markus Schnier | 0 | 0
| Clemens Friedrich | 5 | 7850
| Gerhard Schneider | 0 | 0
| DGI | 0 | 0
| CNTR0010336 | 152.1775 | 271131.6326
| Thomas Huber | 0 | 0
| Markus Schnier | 0 | 0
| Daniela Betz | 45.9375 | 65010.9849
| Bastian Kastner | 45.25 | 47435.575
| Clemens Friedrich | 0 | 0
| Gerhard Schneider | 3.77 | 7653.1
| Björn Hansen / Markus Feuerstein | 0 | 85551.9727
| Rudresh Subramanian | 20.22 | 30330
| Guelsah Uestelci | 37 | 35150
| CNTR0010335 | 56 | 64575.28
| N.N. | 0 | 0
| Markus Gatter | 56 | 64575.28
| Jakob Schusser | 0 | 0
| Gabriella Nagy | 0 | 0
| N.N. // SME 2 | 0 | 0
| N.N. // Sr. Analyst | 0 | 0
| SR Labs Autobahn | 0 | 0
| OE Effort | 0 | 0
| Ben Brüggen | 0 | 0
| CNTR0010338 | 152.3738 | 157766.1581
| Rene Pferner | 0 | 0
| Thomas Huber | 1 | 2030
| Markus Schnier | 1 | 2030
| N.N. | 0 | 0
| Clemens Friedrich | 15 | 23550
| Gerhard Schneider | 6.03 | 12240.9
| Anna Hartl | 53.8125 | 56411.6437
| Alina Lobova | 55.75 | 46754.18
| Stefan Kösters | 12.2812 | 12874.4344
| Kühnlenz / 2wmedia | 0 | 0
| Natalia Nikitana | 0 | 0
| IT Seal | 0 | 0
| Aishwarya Nangude / Sarabjit Singh | 0 | 0
| Meera Patel | 7.5 | 1875
| CNTR0010333 | 245.5625 | 276810.2324
| Christoph Lenz | 31.625 | 33152.4875
| Thomas Huber | 0 | 0
| Markus Schnier | 0 | 0
| Corinna Koch | 19.375 | 20310.8125
| Vasanthan Dhanasingh | 0 | 0
| Clemens Friedrich | 0 | 0
| Gerhard Schneider | 0 | 0
| Sven Lierzer | 48.875 | 57921.9165
| Tobias Lichtenberg | 12.6875 | 17955.4134
| Stanislav Khotinok | 34.125 | 39350.5613
| Alexander Leonhardt | 56.75 | 65440.1275
| Yuri Nikulin | 23.375 | 26954.4138
| Maria Thanner | 18.75 | 15724.5
| SNOW-Team | 0 | 0
| Splunk Team | 0 | 0
| Ankita Mane | 0 | 0
| Martin Gerlowski | 0 | 0
| Deepak Krishnan | 0 | 0
| K Harikrishnan | 0 | 0
| CNTR0010337 | 19.2596 | 32647.4087
| Placeholder | 0 | 0
| Matthias Kickstein | 0 | 0
| Computacenter | 0 | 0
| Ernst & Young | 19.2596 | 32647.4087
| CNTR0010325 | 29.75 | 16237.5
| Alex Lee | 0 | 0
| Lucas Tscherter | 0 | 0
| Corinna Koch | 0 | 0
| Dhanya Kalathil | 19.75 | 4937.5
| Mark de Vera | 0 | 0
| Balasz Racz | 10 | 11300
| Arunlal Nair | 0 | 0
| Local Infra setup support | 0 | 0
| Local SMEs for AVC, FMO | 0 | 0
| Cabling APAC | 0 | 0
| CNTR0010327 | 20 | 5320
| Thomas Huber | 0 | 0
| Gereon Volker | 0 | 0
| Lucas Tscherter | 0 | 0
| Markus Schnier | 0 | 0
| Thomas Bringewald | 2 | 2260
| Andrei Maslov | 0 | 0
| Patrick Zeitz | 0 | 0
| Armando Diaz | 0 | 0
| Ron Johnson | 0 | 0
| Jithin Varghese | 18 | 3060
| AZ Tech America Labor | 0 | 0
| Service Manager | 0 | 0
| CNTR0010332 | 177.713 | 270824.8831
| Timothy Drost | 51.25 | 56077.4981
| Thomas Huber | 1 | 2030
| Holger Steinlechner | 1.78 | 2011.4
| Lucas Tscherter | 20.42 | 32059.4
| Markus Schnier | 1 | 2030
| Olivier Ma | 0 | 0
| Rebecca Dengl | 0.263 | 297.19
| Andrei Maslov | 5 | 5650
| Racz Balazs | 2 | 2260
| Jimmy Braun | 0 | 0
| Cyarx Siemplify | 95 | 168409.395
| CMDB | 0 | 0
| CNTR0010329 | 97.9983 | 221663.7262
| Thomas Huber | 1 | 2030
| Gereon Volker | 0 | 0
| Lucas Tscherter | 27.79 | 43630.3
| Markus Schnier | 1 | 2030
| Thomas Bringewald | 5 | 5650
| Rebecca Dengl | 0.526 | 594.38
| Felix Hertin | 3.2615 | 5242.0231
| Lukas Thiele | 9.4208 | 5242.0231
| Holger Wache | 25 | 78622.5
| Tobias Martin | 25 | 78622.5
| Deloitte | 0 | 0
| CNTR0010709 | 11 | 16796.845
| Thomas Huber | 1 | 2030
| Lucas Tscherter | 0 | 0
| Markus Schnier | 1 | 2030
| Krunoslav Rukavina | 9 | 12736.845
| Joachim Steinberger | 0 | 0
| Elastic | 0 | 0
| Proofpoint | 0 | 0
| CNTR0010564 | 513.2647 | 444921.049
| Markus Traumueller | 10 | 11300
| Karim, Hasan | 57 | 59850
| Bojarski, Eduard | 57 | 112122.99
| Kayali, Ismail | 57 | 72645.93
| Stettner, Julia | 57 | 80717.13
| Tulshidas Thamke, Budhesh | 57 | 9120
| Sunderdas, Shilpa | 58 | 9280
| Bönigk, Julian | 10 | 11300
| Sora Mustafa (AUG-OCT only) | 52 | 61880
| Vidya Baskaran Reddy | 57 | 9690
| S, Shibi (partily on IP&G) | 41.2647 | 7014.999
| CNTR0010563 | 109.9746 | 125589.2982
| Günther, Gerhard | 15.1579 | 20463.1579
| Poteat, Jade | 22.9868 | 22986.8421
| Warnholz, Benjamin | 8 | 16000
| Qualys Team (AVM) | 0 | 0
| Uysal, Ismail (Project Manager) | 51.1456 | 51145.614
| Goldschmidt, Andreas (SNOW Principal Architect) | 10.6842 | 14423.6842
| AMC Devops Engineer (Internal) | 0 | 0
| APM Devops Engineer (Internal) | 0 | 0
| EMS Devops Engineer (Internal) | 0 | 0
| Workspace Intelligence Internal – Technical SME | 0 | 0
| SNOW Performance Analytics team | 0 | 0
| SNOW Development Teams | 2 | 570
| Workspace Intelligence Vendor – Technical SME | 0 | 0
| SNOW SAM efforts | 0 | 0
| SNOW CMDB | 0 | 0
| CyNet | 0 | 0
| Security Foundation Team | 0 | 0
| CNTR0010576 | 27.5 | 35432.54
| Marc Bochtler | 18 | 25473.69
| Alexander Heinze | 0 | 0
| Tobias Butz | 0 | 0
| NN | 0 | 0
| NN india | 0 | 0
| Yury Nikolin | 9.5 | 9958.85
| Thomas Felder | 0 | 0
| CNTR0010334 | 130.125 | 153138.2055
| Martin Schurm | 27 | 42102.3487
| Tobias Krichel | 62.875 | 74513.3568
| Thomas Huber | 1 | 2030
| Markus Schnier | 1 | 2030
| Dan Read | 0 | 0
| N.N. / Support Dan | 0 | 0
| Ankur Tomar | 0 | 0
| Naman Agrawal | 21.25 | 5312.5
| Clemens Friedrich | 16 | 25120
| Gerhard Schneider | 1 | 2030
| OAM302 | 0 | 0
| Alexander Heinze | 0 | 0
| Daming Yang | 0 | 0
| Manoj Selvakumar | 0 | 0
| David Barton | 0 | 0
| Raja Rajcic | 0 | 0
| Lawrence Tengan | 0 | 0
| Travis Chun | 0 | 0
| Johannes Bross | 0 | 0
| Tuan Minh Nguyen | 0 | 0
| Tobias Tischler | 0 | 0
| Djamel Tazerout | 0 | 0
| Dirk Addicks | 0 | 0
| Forgerock Licence | 0 | 0
| CNTR0010589 | 0 | 0
| Placeholder | 0 | 0
| OAM299 | 0 | 0
| Placeholder | 0 | 0
| CNTR0010618 | 0.79973 | 2114.4735
| Birgit Jarosch | 0.79973 | 2114.4735
| Wolfgang Elsner | 0 | 0
| Alexander Heinze | 0 | 0
| Jagoda Matys | 0 | 0
| N.N. | 0 | 0
| Mitja Ledowski | 0 | 0
| Ingmar Janßen-Holldiek | 0 | 0
| Michael Holder | 0 | 0
| Sinoop K S | 0 | 0
| J. Thomas | 0 | 0
| Madalina Paslaru | 0 | 0
| Daniel Ettenhuber | 0 | 0
| OAM289 | 0 | 0
| Placeholder | 0 | 0
| CNTR0010617 | 0 | 0
| (blank) | 0 | 0
| Alexander Heinze | 0 | 0
| Christine Schlüter | 0 | 0
| Günter Sanktjohanser | 0 | 0
| Metafinanz | 717.9375 | 838906
| 21 0427 | 162.5625 | 155742.25
| Julian Steinfeld | 53 | 58936
| Manuel Hahn | 43.5312 | 42660.625
| Matthias Müller | 66.0312 | 54145.625
| 21 1068 | 107.1875 | 140290.625
| Jonathan Reynolds | 16.75 | 16750
| Samuel Hurst | 38.9688 | 52607.8125
| Kris Harms | 39 | 56550
| Nora von Schenckendorff | 5.4688 | 7382.8125
| Frank Markussen | 1.375 | 1375
| Anette Hettenkofer | 0.125 | 125
| Julia Netesa | 5.5 | 5500
| 21 1079 | 81.1875 | 94356.25
| George Dietrichsbruckner | 37.625 | 50793.75
| Jade Poteat | 7.625 | 7625
| Nadine Butzhammer | 0.3125 | 312.5
| Daniel Wörner | 21.5 | 21500
| Sanat Gautam | 14.125 | 14125
| 21 1037 | 179.6875 | 209831.25
| Gerhard Günther | 31.5 | 42525
| Rasa Rintallo | 43.4375 | 43437.5
| Stefan Köstenbauer | 1.125 | 1518.75
| Victor Peters | 3.8438 | 3843.75
| Michael Habel | 53.5 | 72225
| Maximilian Schellenberger | 3.2812 | 3281.25
| Sona Latifyan | 43 | 43000
| 21 1040 | 6.5 | 6500
| Jade Poteat | 6.5 | 6500
| 21 1133 | 0 | 0
| Krunoslav Rukavina | 0 | 0
| 21 1063 | 135.3125 | 170760.625
| Marc Bochtler | 42.125 | 56868.75
| Thorsten Deckers | 21.0625 | 33068.125
| Robert Reti | 17.875 | 28063.75
| Claudio Cangiotti | 13 | 10010
| Yury Nikulin | 26.25 | 26250
| Eldho George | 15 | 16500
| 21 1059 | 45.5 | 61425
| Thomas Thuspaß | 45.5 | 61425
| other | 0 | 24570
| 0 | 0 | 24570
| (blank) | 0 | 24570
| NCC Group GmbH | 0 | 363140.4
| 2410164170 | 0 | 363140.4
| (blank) | 0 | 363140.4
| Osborne Clark | 0 | 20659.69
| TID0001510089 | 0 | 20659.69
| (blank) | 0 | 20659.69
| Virtual Clarity Ltd | 0 | 149488
| 2410164371 | 0 | 149488
| (blank) | 0 | 149488
| Softwaregilde | 0 | 121975
| 2410159840 | 0 | 121975
| (blank) | 0 | 121975
| Horvath & Partner | 0 | 44625
| 2410160374 | 0 | 44625
| (blank) | 0 | 44625
| Ernst & Young | 0 | 98002.0781
| 2410162165 | 0 | 98002.0781
| (blank) | 0 | 98002.0781
| SRLabs | 0 | 8925
| PR964131 | 0 | 8925
| (blank) | 0 | 8925
| DCSO | 0 | 0
| 0 | 0 | 0
| (blank) | 0 | 0
| SecAttack | 0 | 22312.5
| 0 | 0 | 22312.5
| (blank) | 0 | 22312.5
| (blank) | 2767.8155 | 3482475.2593
| (blank) | 2767.8155 | 3482475.2593
| (blank) | 2767.8155 | 3482475.2593
| (blank) | 2767.8155 | 3482475.2593
| non-Labor | 1 | 210543.769
| AZ Technology | 1 | 107250.619
| CNTR0010616 | 0 | 0
| Licence costs | 0 | 0
| CNTR0010338 | 0 | 32401.999
| Splunk Licenses + Server | 0 | 0
| ZeroFox Licenses | 0 | 32401.999
| CNTR0010333 | 0 | 0
| Splunk Licenses + Server | 0 | 0
| CNTR0010325 | 0 | 0
| HW / infrastructure | 0 | 0
| CNTR0010327 | 0 | 0
| Local SMEs for AVC, FMO | 0 | 0
| AZ Tech America HW | 0 | 0
| CNTR0010332 | 1 | 74848.62
| Cyarx Siemplify | 1 | 74848.62
| CNTR0010329 | 0 | 0
| AWS / Azure cloud | 0 | 0
| CNTR0010618 | 0 | 0
| HW | 0 | 0
| other | 0 | 103293.15
| 0 | 0 | 103293.15
| (blank) | 0 | 103293.15
| Sum | 5535.6311 | 8219441.3367

## M34 (hidden)
M34
Measure Lead: Kristine Harms
Pillar Lead: Carsten Scholz
Duration: 01.08.2016-31.12.2018
Planned Total | #N/A
Approved Total | #N/A
Spent Labor | #N/A
Spent non-Labor | #N/A
Spent Total | #N/A
Forecast Total | #N/A
| Measure | (All)
|  | Jan |  | Feb | Mrz | Apr | Mai | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total
| Resources & Contracts | PD Total | EUR Total
| Labor | 2766.8155 | 4526422.3084
Comment | AZ Technology | 2048.878 | 2833818.6402
| 0 | 0 | 297500
| (blank) | 0 | 297500
| CNTR0010544 | 110.4647 | 157099.0619
| Andrea Scotti | 0 | 0
| Wolfgang Elsner | 0 | 0
| Alexander Heinze | 0 | 0
| Thomas Huber | 0 | 0
| Jagoda Matys | 0 | 0
| Markus Schnier | 0 | 0
| Sergej Reißig | 55.0018 | 83266.9815
| Binoj Baburaj | 0 | 0
| IAM Architect (Cygna) | 2.4114 | 3159.8592
| NN india | 0 | 0
| Michael Holder | 0 | 0
| Youssef Dahmouni | 0 | 0
| Nina Kaufmann | 20.9999 | 27517.875
| Viktoryia Nikifaravets | 32.0516 | 43154.3461
| CNTR0010615 | 121.7529 | 173433.2076
| Alexander Heinze | 0 | 0
| Jagoda Matys | 0 | 0
| Srdan Mavrenski | 55.0018 | 83266.9815
| Itai Schwartz | 31.2506 | 42075.8024
| NN india | 0 | 0
| Francois Pernayan | 31.2506 | 42075.8024
| Matt Gibson | 0 | 0
| Christian Bolterauer | 4.25 | 6014.6213
| CNTR0010616 | 68.1618 | 102967.1383
| Alexander Heinze | 0 | 0
| Thomas Huber | 0 | 0
| Reza Memarian | 55.0018 | 83266.9815
| Markus Schnier | 0 | 0
| NN india | 0 | 0
| Youssef Dahmouni | 0 | 0
| Walter Hofer | 0 | 0
| Balasz Razs | 0 | 0
| Ivan Markovic | 13.16 | 19700.1568
| Product SME | 0 | 0
| CNTR0010562 | 5 | 7850
| Thomas Huber | 0 | 0
| Markus Schnier | 0 | 0
| Clemens Friedrich | 5 | 7850
| Gerhard Schneider | 0 | 0
| DGI | 0 | 0
| CNTR0010336 | 152.1775 | 271131.6326
| Thomas Huber | 0 | 0
| Markus Schnier | 0 | 0
| Daniela Betz | 45.9375 | 65010.9849
| Bastian Kastner | 45.25 | 47435.575
| Clemens Friedrich | 0 | 0
| Gerhard Schneider | 3.77 | 7653.1
| Björn Hansen / Markus Feuerstein | 0 | 85551.9727
| Rudresh Subramanian | 20.22 | 30330
| Guelsah Uestelci | 37 | 35150
| CNTR0010335 | 56 | 64575.28
| N.N. | 0 | 0
| Markus Gatter | 56 | 64575.28
| Jakob Schusser | 0 | 0
| Gabriella Nagy | 0 | 0
| N.N. // SME 2 | 0 | 0
| N.N. // Sr. Analyst | 0 | 0
| SR Labs Autobahn | 0 | 0
| OE Effort | 0 | 0
| Ben Brüggen | 0 | 0
| CNTR0010338 | 152.3738 | 157766.1581
| Rene Pferner | 0 | 0
| Thomas Huber | 1 | 2030
| Markus Schnier | 1 | 2030
| N.N. | 0 | 0
| Clemens Friedrich | 15 | 23550
| Gerhard Schneider | 6.03 | 12240.9
| Anna Hartl | 53.8125 | 56411.6437
| Alina Lobova | 55.75 | 46754.18
| Stefan Kösters | 12.2812 | 12874.4344
| Kühnlenz / 2wmedia | 0 | 0
| Natalia Nikitana | 0 | 0
| IT Seal | 0 | 0
| Aishwarya Nangude / Sarabjit Singh | 0 | 0
| Meera Patel | 7.5 | 1875
| CNTR0010333 | 245.5625 | 276810.2324
| Christoph Lenz | 31.625 | 33152.4875
| Thomas Huber | 0 | 0
| Markus Schnier | 0 | 0
| Corinna Koch | 19.375 | 20310.8125
| Vasanthan Dhanasingh | 0 | 0
| Clemens Friedrich | 0 | 0
| Gerhard Schneider | 0 | 0
| Sven Lierzer | 48.875 | 57921.9165
| Tobias Lichtenberg | 12.6875 | 17955.4134
| Stanislav Khotinok | 34.125 | 39350.5613
| Alexander Leonhardt | 56.75 | 65440.1275
| Yuri Nikulin | 23.375 | 26954.4138
| Maria Thanner | 18.75 | 15724.5
| SNOW-Team | 0 | 0
| Splunk Team | 0 | 0
| Ankita Mane | 0 | 0
| Martin Gerlowski | 0 | 0
| Deepak Krishnan | 0 | 0
| K Harikrishnan | 0 | 0
| CNTR0010337 | 19.2596 | 32647.4087
| Placeholder | 0 | 0
| Matthias Kickstein | 0 | 0
| Computacenter | 0 | 0
| Ernst & Young | 19.2596 | 32647.4087
| CNTR0010325 | 29.75 | 16237.5
| Alex Lee | 0 | 0
| Lucas Tscherter | 0 | 0
| Corinna Koch | 0 | 0
| Dhanya Kalathil | 19.75 | 4937.5
| Mark de Vera | 0 | 0
| Balasz Racz | 10 | 11300
| Arunlal Nair | 0 | 0
| Local Infra setup support | 0 | 0
| Local SMEs for AVC, FMO | 0 | 0
| Cabling APAC | 0 | 0
| CNTR0010327 | 20 | 5320
| Thomas Huber | 0 | 0
| Gereon Volker | 0 | 0
| Lucas Tscherter | 0 | 0
| Markus Schnier | 0 | 0
| Thomas Bringewald | 2 | 2260
| Andrei Maslov | 0 | 0
| Patrick Zeitz | 0 | 0
| Armando Diaz | 0 | 0
| Ron Johnson | 0 | 0
| Jithin Varghese | 18 | 3060
| AZ Tech America Labor | 0 | 0
| Service Manager | 0 | 0
| CNTR0010332 | 177.713 | 270824.8831
| Timothy Drost | 51.25 | 56077.4981
| Thomas Huber | 1 | 2030
| Holger Steinlechner | 1.78 | 2011.4
| Lucas Tscherter | 20.42 | 32059.4
| Markus Schnier | 1 | 2030
| Olivier Ma | 0 | 0
| Rebecca Dengl | 0.263 | 297.19
| Andrei Maslov | 5 | 5650
| Racz Balazs | 2 | 2260
| Jimmy Braun | 0 | 0
| Cyarx Siemplify | 95 | 168409.395
| CMDB | 0 | 0
| CNTR0010329 | 97.9983 | 221663.7262
| Thomas Huber | 1 | 2030
| Gereon Volker | 0 | 0
| Lucas Tscherter | 27.79 | 43630.3
| Markus Schnier | 1 | 2030
| Thomas Bringewald | 5 | 5650
| Rebecca Dengl | 0.526 | 594.38
| Felix Hertin | 3.2615 | 5242.0231
| Lukas Thiele | 9.4208 | 5242.0231
| Holger Wache | 25 | 78622.5
| Tobias Martin | 25 | 78622.5
| Deloitte | 0 | 0
| CNTR0010709 | 11 | 16796.845
| Thomas Huber | 1 | 2030
| Lucas Tscherter | 0 | 0
| Markus Schnier | 1 | 2030
| Krunoslav Rukavina | 9 | 12736.845
| Joachim Steinberger | 0 | 0
| Elastic | 0 | 0
| Proofpoint | 0 | 0
| CNTR0010564 | 513.2647 | 444921.049
| Markus Traumueller | 10 | 11300
| Karim, Hasan | 57 | 59850
| Bojarski, Eduard | 57 | 112122.99
| Kayali, Ismail | 57 | 72645.93
| Stettner, Julia | 57 | 80717.13
| Tulshidas Thamke, Budhesh | 57 | 9120
| Sunderdas, Shilpa | 58 | 9280
| Bönigk, Julian | 10 | 11300
| Sora Mustafa (AUG-OCT only) | 52 | 61880
| Vidya Baskaran Reddy | 57 | 9690
| S, Shibi (partily on IP&G) | 41.2647 | 7014.999
| CNTR0010563 | 109.9746 | 125589.2982
| Günther, Gerhard | 15.1579 | 20463.1579
| Poteat, Jade | 22.9868 | 22986.8421
| Warnholz, Benjamin | 8 | 16000
| Qualys Team (AVM) | 0 | 0
| Uysal, Ismail (Project Manager) | 51.1456 | 51145.614
| Goldschmidt, Andreas (SNOW Principal Architect) | 10.6842 | 14423.6842
| AMC Devops Engineer (Internal) | 0 | 0
| APM Devops Engineer (Internal) | 0 | 0
| EMS Devops Engineer (Internal) | 0 | 0
| Workspace Intelligence Internal – Technical SME | 0 | 0
| SNOW Performance Analytics team | 0 | 0
| SNOW Development Teams | 2 | 570
| Workspace Intelligence Vendor – Technical SME | 0 | 0
| SNOW SAM efforts | 0 | 0
| SNOW CMDB | 0 | 0
| CyNet | 0 | 0
| Security Foundation Team | 0 | 0
| CNTR0010576 | 27.5 | 35432.54
| Marc Bochtler | 18 | 25473.69
| Alexander Heinze | 0 | 0
| Tobias Butz | 0 | 0
| NN | 0 | 0
| NN india | 0 | 0
| Yury Nikolin | 9.5 | 9958.85
| Thomas Felder | 0 | 0
| CNTR0010334 | 130.125 | 153138.2055
| Martin Schurm | 27 | 42102.3487
| Tobias Krichel | 62.875 | 74513.3568
| Thomas Huber | 1 | 2030
| Markus Schnier | 1 | 2030
| Dan Read | 0 | 0
| N.N. / Support Dan | 0 | 0
| Ankur Tomar | 0 | 0
| Naman Agrawal | 21.25 | 5312.5
| Clemens Friedrich | 16 | 25120
| Gerhard Schneider | 1 | 2030
| OAM302 | 0 | 0
| Alexander Heinze | 0 | 0
| Daming Yang | 0 | 0
| Manoj Selvakumar | 0 | 0
| David Barton | 0 | 0
| Raja Rajcic | 0 | 0
| Lawrence Tengan | 0 | 0
| Travis Chun | 0 | 0
| Johannes Bross | 0 | 0
| Tuan Minh Nguyen | 0 | 0
| Tobias Tischler | 0 | 0
| Djamel Tazerout | 0 | 0
| Dirk Addicks | 0 | 0
| Forgerock Licence | 0 | 0
| CNTR0010589 | 0 | 0
| Placeholder | 0 | 0
| OAM299 | 0 | 0
| Placeholder | 0 | 0
| CNTR0010618 | 0.79973 | 2114.4735
| Birgit Jarosch | 0.79973 | 2114.4735
| Wolfgang Elsner | 0 | 0
| Alexander Heinze | 0 | 0
| Jagoda Matys | 0 | 0
| N.N. | 0 | 0
| Mitja Ledowski | 0 | 0
| Ingmar Janßen-Holldiek | 0 | 0
| Michael Holder | 0 | 0
| Sinoop K S | 0 | 0
| J. Thomas | 0 | 0
| Madalina Paslaru | 0 | 0
| Daniel Ettenhuber | 0 | 0
| OAM289 | 0 | 0
| Placeholder | 0 | 0
| CNTR0010617 | 0 | 0
| (blank) | 0 | 0
| Alexander Heinze | 0 | 0
| Christine Schlüter | 0 | 0
| Günter Sanktjohanser | 0 | 0
| Metafinanz | 717.9375 | 838906
| 21 0427 | 162.5625 | 155742.25
| Julian Steinfeld | 53 | 58936
| Manuel Hahn | 43.5312 | 42660.625
| Matthias Müller | 66.0312 | 54145.625
| 21 1068 | 107.1875 | 140290.625
| Jonathan Reynolds | 16.75 | 16750
| Samuel Hurst | 38.9688 | 52607.8125
| Kris Harms | 39 | 56550
| Nora von Schenckendorff | 5.4688 | 7382.8125
| Frank Markussen | 1.375 | 1375
| Anette Hettenkofer | 0.125 | 125
| Julia Netesa | 5.5 | 5500
| 21 1079 | 81.1875 | 94356.25
| George Dietrichsbruckner | 37.625 | 50793.75
| Jade Poteat | 7.625 | 7625
| Nadine Butzhammer | 0.3125 | 312.5
| Daniel Wörner | 21.5 | 21500
| Sanat Gautam | 14.125 | 14125
| 21 1037 | 179.6875 | 209831.25
| Gerhard Günther | 31.5 | 42525
| Rasa Rintallo | 43.4375 | 43437.5
| Stefan Köstenbauer | 1.125 | 1518.75
| Victor Peters | 3.8438 | 3843.75
| Michael Habel | 53.5 | 72225
| Maximilian Schellenberger | 3.2812 | 3281.25
| Sona Latifyan | 43 | 43000
| 21 1040 | 6.5 | 6500
| Jade Poteat | 6.5 | 6500
| 21 1133 | 0 | 0
| Krunoslav Rukavina | 0 | 0
| 21 1063 | 135.3125 | 170760.625
| Marc Bochtler | 42.125 | 56868.75
| Thorsten Deckers | 21.0625 | 33068.125
| Robert Reti | 17.875 | 28063.75
| Claudio Cangiotti | 13 | 10010
| Yury Nikulin | 26.25 | 26250
| Eldho George | 15 | 16500
| 21 1059 | 45.5 | 61425
| Thomas Thuspaß | 45.5 | 61425
| other | 0 | 24570
| 0 | 0 | 24570
| (blank) | 0 | 24570
| NCC Group GmbH | 0 | 363140.4
| 2410164170 | 0 | 363140.4
| (blank) | 0 | 363140.4
| Osborne Clark | 0 | 20659.69
| TID0001510089 | 0 | 20659.69
| (blank) | 0 | 20659.69
| Virtual Clarity Ltd | 0 | 149488
| 2410164371 | 0 | 149488
| (blank) | 0 | 149488
| Softwaregilde | 0 | 121975
| 2410159840 | 0 | 121975
| (blank) | 0 | 121975
| Horvath & Partner | 0 | 44625
| 2410160374 | 0 | 44625
| (blank) | 0 | 44625
| Ernst & Young | 0 | 98002.0781
| 2410162165 | 0 | 98002.0781
| (blank) | 0 | 98002.0781
| SRLabs | 0 | 8925
| PR964131 | 0 | 8925
| (blank) | 0 | 8925
| DCSO | 0 | 0
| 0 | 0 | 0
| (blank) | 0 | 0
| SecAttack | 0 | 22312.5
| 0 | 0 | 22312.5
| (blank) | 0 | 22312.5
| (blank) | 2767.8155 | 3482475.2593
| (blank) | 2767.8155 | 3482475.2593
| (blank) | 2767.8155 | 3482475.2593
| (blank) | 2767.8155 | 3482475.2593
| non-Labor | 1 | 210543.769
| AZ Technology | 1 | 107250.619
| CNTR0010616 | 0 | 0
| Licence costs | 0 | 0
| CNTR0010338 | 0 | 32401.999
| Splunk Licenses + Server | 0 | 0
| ZeroFox Licenses | 0 | 32401.999
| CNTR0010333 | 0 | 0
| Splunk Licenses + Server | 0 | 0
| CNTR0010325 | 0 | 0
| HW / infrastructure | 0 | 0
| CNTR0010327 | 0 | 0
| Local SMEs for AVC, FMO | 0 | 0
| AZ Tech America HW | 0 | 0
| CNTR0010332 | 1 | 74848.62
| Cyarx Siemplify | 1 | 74848.62
| CNTR0010329 | 0 | 0
| AWS / Azure cloud | 0 | 0
| CNTR0010618 | 0 | 0
| HW | 0 | 0
| other | 0 | 103293.15
| 0 | 0 | 103293.15
| (blank) | 0 | 103293.15
| Sum | 5535.6311 | 8219441.3367

## Input Resources Meta. T&M
Projektnummer | Measure | Titel Intern | Start geplant | Ende geplant | Datum | Monat | Besitzer | Lieferant | Dauer | Dauer in PT | VK | Gesamt IST
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-07-01 | 7 | Julian Steinfeld | HipSquare GmbH | 6 | 0.75 | 1112 | 834
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-07-01 | 7 | Manuel Hahn | HipSquare GmbH | 0.75 | 0.09375 | 980 | 91.875
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-07-01 | 7 | Manuel Hahn | HipSquare GmbH | 4.75 | 0.59375 | 980 | 581.875
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-07-01 | 7 | Matthias Müller | HipSquare GmbH | 6.75 | 0.84375 | 820 | 691.875
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-07-02 | 7 | Julian Steinfeld | HipSquare GmbH | 7.5 | 0.9375 | 1112 | 1042.5
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-07-02 | 7 | Manuel Hahn | HipSquare GmbH | 0.25 | 0.03125 | 980 | 30.625
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-07-02 | 7 | Manuel Hahn | HipSquare GmbH | 7 | 0.875 | 980 | 857.5
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-07-03 | 7 | Matthias Müller | HipSquare GmbH | 24 | 3 | 820 | 2460
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-07-04 | 7 | Matthias Müller | HipSquare GmbH | 16.75 | 2.0938 | 820 | 1716.875
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-07-05 | 7 | Julian Steinfeld | HipSquare GmbH | 6.5 | 0.8125 | 1112 | 903.5
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-07-05 | 7 | Manuel Hahn | HipSquare GmbH | 3 | 0.375 | 980 | 367.5
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-07-05 | 7 | Manuel Hahn | HipSquare GmbH | 2.75 | 0.34375 | 980 | 336.875
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-07-05 | 7 | Matthias Müller | HipSquare GmbH | 0.25 | 0.03125 | 820 | 25.625
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-07-05 | 7 | Matthias Müller | HipSquare GmbH | 0.5 | 0.0625 | 820 | 51.25
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-07-06 | 7 | Julian Steinfeld | HipSquare GmbH | 7 | 0.875 | 1112 | 973
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-07-06 | 7 | Manuel Hahn | HipSquare GmbH | 3.75 | 0.46875 | 980 | 459.375
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-07-06 | 7 | Manuel Hahn | HipSquare GmbH | 2.5 | 0.3125 | 980 | 306.25
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-07-06 | 7 | Matthias Müller | HipSquare GmbH | 0.75 | 0.09375 | 820 | 76.875
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-07-06 | 7 | Matthias Müller | HipSquare GmbH | 0.75 | 0.09375 | 820 | 76.875
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-07-07 | 7 | Julian Steinfeld | HipSquare GmbH | 8.5 | 1.0625 | 1112 | 1181.5
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-07-07 | 7 | Manuel Hahn | HipSquare GmbH | 4.75 | 0.59375 | 980 | 581.875
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-07-07 | 7 | Manuel Hahn | HipSquare GmbH | 2.25 | 0.28125 | 980 | 275.625
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-07-07 | 7 | Matthias Müller | HipSquare GmbH | 0.25 | 0.03125 | 820 | 25.625
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-07-08 | 7 | Julian Steinfeld | HipSquare GmbH | 8 | 1 | 1112 | 1112
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-07-08 | 7 | Manuel Hahn | HipSquare GmbH | 2.5 | 0.3125 | 980 | 306.25
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-07-08 | 7 | Manuel Hahn | HipSquare GmbH | 4.75 | 0.59375 | 980 | 581.875
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-07-08 | 7 | Matthias Müller | HipSquare GmbH | 1.5 | 0.1875 | 820 | 153.75
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-07-09 | 7 | Julian Steinfeld | HipSquare GmbH | 10 | 1.25 | 1112 | 1390
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-07-10 | 7 | Matthias Müller | HipSquare GmbH | 10.5 | 1.3125 | 820 | 1076.25
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-07-12 | 7 | Julian Steinfeld | HipSquare GmbH | 8.5 | 1.0625 | 1112 | 1181.5
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-07-12 | 7 | Manuel Hahn | HipSquare GmbH | 1.25 | 0.15625 | 980 | 153.125
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-07-12 | 7 | Manuel Hahn | HipSquare GmbH | 4.25 | 0.53125 | 980 | 520.625
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-07-12 | 7 | Matthias Müller | HipSquare GmbH | 6 | 0.75 | 820 | 615
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-07-12 | 7 | Matthias Müller | HipSquare GmbH | 0.25 | 0.03125 | 820 | 25.625
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-07-13 | 7 | Julian Steinfeld | HipSquare GmbH | 9 | 1.125 | 1112 | 1251
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-07-13 | 7 | Manuel Hahn | HipSquare GmbH | 0.75 | 0.09375 | 980 | 91.875
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-07-13 | 7 | Manuel Hahn | HipSquare GmbH | 4.75 | 0.59375 | 980 | 581.875
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-07-13 | 7 | Matthias Müller | HipSquare GmbH | 8 | 1 | 820 | 820
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-07-13 | 7 | Matthias Müller | HipSquare GmbH | 0.75 | 0.09375 | 820 | 76.875
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-07-14 | 7 | Julian Steinfeld | HipSquare GmbH | 8 | 1 | 1112 | 1112
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-07-14 | 7 | Manuel Hahn | HipSquare GmbH | 2.25 | 0.28125 | 980 | 275.625
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-07-14 | 7 | Manuel Hahn | HipSquare GmbH | 3.5 | 0.4375 | 980 | 428.75
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-07-14 | 7 | Matthias Müller | HipSquare GmbH | 5 | 0.625 | 820 | 512.5
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-07-14 | 7 | Matthias Müller | HipSquare GmbH | 0.25 | 0.03125 | 820 | 25.625
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-07-15 | 7 | Julian Steinfeld | HipSquare GmbH | 7 | 0.875 | 1112 | 973
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-07-15 | 7 | Manuel Hahn | HipSquare GmbH | 0.5 | 0.0625 | 980 | 61.25
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-07-15 | 7 | Manuel Hahn | HipSquare GmbH | 4 | 0.5 | 980 | 490
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-07-15 | 7 | Matthias Müller | HipSquare GmbH | 5 | 0.625 | 820 | 512.5
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-07-15 | 7 | Matthias Müller | HipSquare GmbH | 0.25 | 0.03125 | 820 | 25.625
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-07-16 | 7 | Julian Steinfeld | HipSquare GmbH | 5 | 0.625 | 1112 | 695
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-07-16 | 7 | Manuel Hahn | HipSquare GmbH | 2.25 | 0.28125 | 980 | 275.625
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-07-16 | 7 | Manuel Hahn | HipSquare GmbH | 2.25 | 0.28125 | 980 | 275.625
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-07-16 | 7 | Matthias Müller | HipSquare GmbH | 6 | 0.75 | 820 | 615
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-07-16 | 7 | Matthias Müller | HipSquare GmbH | 0.25 | 0.03125 | 820 | 25.625
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-07-18 | 7 | Julian Steinfeld | HipSquare GmbH | 1 | 0.125 | 1112 | 139
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-07-18 | 7 | Julian Steinfeld | HipSquare GmbH | 1 | 0.125 | 1112 | 139
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-07-19 | 7 | Julian Steinfeld | HipSquare GmbH | 8.5 | 1.0625 | 1112 | 1181.5
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-07-19 | 7 | Manuel Hahn | HipSquare GmbH | 1 | 0.125 | 980 | 122.5
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-07-19 | 7 | Manuel Hahn | HipSquare GmbH | 4 | 0.5 | 980 | 490
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-07-19 | 7 | Matthias Müller | HipSquare GmbH | 4 | 0.5 | 820 | 410
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-07-19 | 7 | Matthias Müller | HipSquare GmbH | 0.25 | 0.03125 | 820 | 25.625
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-07-20 | 7 | Julian Steinfeld | HipSquare GmbH | 8.5 | 1.0625 | 1112 | 1181.5
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-07-20 | 7 | Manuel Hahn | HipSquare GmbH | 1.5 | 0.1875 | 980 | 183.75
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-07-20 | 7 | Manuel Hahn | HipSquare GmbH | 4 | 0.5 | 980 | 490
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-07-20 | 7 | Matthias Müller | HipSquare GmbH | 8 | 1 | 820 | 820
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-07-20 | 7 | Matthias Müller | HipSquare GmbH | 5.5 | 0.6875 | 820 | 563.75
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-07-21 | 7 | Julian Steinfeld | HipSquare GmbH | 7.5 | 0.9375 | 1112 | 1042.5
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-07-21 | 7 | Manuel Hahn | HipSquare GmbH | 1.75 | 0.21875 | 980 | 214.375
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-07-21 | 7 | Manuel Hahn | HipSquare GmbH | 4.25 | 0.53125 | 980 | 520.625
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-07-21 | 7 | Matthias Müller | HipSquare GmbH | 8 | 1 | 820 | 820
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-07-21 | 7 | Matthias Müller | HipSquare GmbH | 0.75 | 0.09375 | 820 | 76.875
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-07-22 | 7 | Julian Steinfeld | HipSquare GmbH | 6 | 0.75 | 1112 | 834
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-07-22 | 7 | Manuel Hahn | HipSquare GmbH | 3 | 0.375 | 980 | 367.5
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-07-22 | 7 | Manuel Hahn | HipSquare GmbH | 1.25 | 0.15625 | 980 | 153.125
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-07-22 | 7 | Matthias Müller | HipSquare GmbH | 8 | 1 | 820 | 820
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-07-22 | 7 | Matthias Müller | HipSquare GmbH | 0.25 | 0.03125 | 820 | 25.625
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-07-23 | 7 | Julian Steinfeld | HipSquare GmbH | 5.5 | 0.6875 | 1112 | 764.5
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-07-23 | 7 | Manuel Hahn | HipSquare GmbH | 0.5 | 0.0625 | 980 | 61.25
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-07-23 | 7 | Manuel Hahn | HipSquare GmbH | 1 | 0.125 | 980 | 122.5
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-07-23 | 7 | Matthias Müller | HipSquare GmbH | 8 | 1 | 820 | 820
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-07-26 | 7 | Julian Steinfeld | HipSquare GmbH | 7.5 | 0.9375 | 1112 | 1042.5
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-07-26 | 7 | Manuel Hahn | HipSquare GmbH | 2.75 | 0.34375 | 980 | 336.875
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-07-26 | 7 | Manuel Hahn | HipSquare GmbH | 1.75 | 0.21875 | 980 | 214.375
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-07-26 | 7 | Matthias Müller | HipSquare GmbH | 8 | 1 | 820 | 820
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-07-26 | 7 | Matthias Müller | HipSquare GmbH | 0.25 | 0.03125 | 820 | 25.625
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-07-27 | 7 | Julian Steinfeld | HipSquare GmbH | 3 | 0.375 | 1112 | 417
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-07-27 | 7 | Manuel Hahn | HipSquare GmbH | 1.75 | 0.21875 | 980 | 214.375
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-07-27 | 7 | Manuel Hahn | HipSquare GmbH | 4.25 | 0.53125 | 980 | 520.625
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-07-27 | 7 | Matthias Müller | HipSquare GmbH | 8 | 1 | 820 | 820
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-07-27 | 7 | Matthias Müller | HipSquare GmbH | 1.25 | 0.15625 | 820 | 128.125
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-07-28 | 7 | Julian Steinfeld | HipSquare GmbH | 5.5 | 0.6875 | 1112 | 764.5
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-07-28 | 7 | Manuel Hahn | HipSquare GmbH | 3 | 0.375 | 980 | 367.5
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-07-28 | 7 | Manuel Hahn | HipSquare GmbH | 2.75 | 0.34375 | 980 | 336.875
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-07-28 | 7 | Matthias Müller | HipSquare GmbH | 8 | 1 | 820 | 820
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-07-28 | 7 | Matthias Müller | HipSquare GmbH | 0.75 | 0.09375 | 820 | 76.875
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-07-29 | 7 | Julian Steinfeld | HipSquare GmbH | 6.5 | 0.8125 | 1112 | 903.5
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-07-29 | 7 | Manuel Hahn | HipSquare GmbH | 1 | 0.125 | 980 | 122.5
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-07-29 | 7 | Manuel Hahn | HipSquare GmbH | 2.25 | 0.28125 | 980 | 275.625
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-07-29 | 7 | Matthias Müller | HipSquare GmbH | 0.25 | 0.03125 | 820 | 25.625
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-07-29 | 7 | Matthias Müller | HipSquare GmbH | 4 | 0.5 | 820 | 410
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-07-30 | 7 | Julian Steinfeld | HipSquare GmbH | 7 | 0.875 | 1112 | 973
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-07-30 | 7 | Matthias Müller | HipSquare GmbH | 0.25 | 0.03125 | 820 | 25.625
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-07-30 | 7 | Matthias Müller | HipSquare GmbH | 1 | 0.125 | 820 | 102.5
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-08-02 | 8 | Julian Steinfeld | HipSquare GmbH | 8.5 | 1.0625 | 1112 | 1181.5
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-08-02 | 8 | Manuel Hahn | HipSquare GmbH | 3.25 | 0.40625 | 980 | 398.125
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-08-02 | 8 | Manuel Hahn | HipSquare GmbH | 0.75 | 0.09375 | 980 | 91.875
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-08-02 | 8 | Matthias Müller | HipSquare GmbH | 0.25 | 0.03125 | 820 | 25.625
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-08-02 | 8 | Matthias Müller | HipSquare GmbH | 1 | 0.125 | 820 | 102.5
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-08-03 | 8 | Julian Steinfeld | HipSquare GmbH | 8.5 | 1.0625 | 1112 | 1181.5
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-08-03 | 8 | Manuel Hahn | HipSquare GmbH | 3.25 | 0.40625 | 980 | 398.125
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-08-03 | 8 | Manuel Hahn | HipSquare GmbH | 1.5 | 0.1875 | 980 | 183.75
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-08-03 | 8 | Matthias Müller | HipSquare GmbH | 3.25 | 0.40625 | 820 | 333.125
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-08-03 | 8 | Matthias Müller | HipSquare GmbH | 8 | 1 | 820 | 820
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-08-04 | 8 | Julian Steinfeld | HipSquare GmbH | 7 | 0.875 | 1112 | 973
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-08-04 | 8 | Manuel Hahn | HipSquare GmbH | 2.25 | 0.28125 | 980 | 275.625
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-08-04 | 8 | Manuel Hahn | HipSquare GmbH | 4.25 | 0.53125 | 980 | 520.625
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-08-04 | 8 | Matthias Müller | HipSquare GmbH | 0.75 | 0.09375 | 820 | 76.875
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-08-04 | 8 | Matthias Müller | HipSquare GmbH | 8 | 1 | 820 | 820
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-08-05 | 8 | Julian Steinfeld | HipSquare GmbH | 6 | 0.75 | 1112 | 834
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-08-05 | 8 | Manuel Hahn | HipSquare GmbH | 4 | 0.5 | 980 | 490
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-08-05 | 8 | Manuel Hahn | HipSquare GmbH | 1.5 | 0.1875 | 980 | 183.75
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-08-05 | 8 | Matthias Müller | HipSquare GmbH | 8 | 1 | 820 | 820
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-08-05 | 8 | Matthias Müller | HipSquare GmbH | 0.25 | 0.03125 | 820 | 25.625
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-08-06 | 8 | Julian Steinfeld | HipSquare GmbH | 7 | 0.875 | 1112 | 973
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-08-06 | 8 | Manuel Hahn | HipSquare GmbH | 2.5 | 0.3125 | 980 | 306.25
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-08-06 | 8 | Manuel Hahn | HipSquare GmbH | 2.75 | 0.34375 | 980 | 336.875
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-08-06 | 8 | Matthias Müller | HipSquare GmbH | 8 | 1 | 820 | 820
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-08-06 | 8 | Matthias Müller | HipSquare GmbH | 0.25 | 0.03125 | 820 | 25.625
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-08-09 | 8 | Julian Steinfeld | HipSquare GmbH | 2 | 0.25 | 1112 | 278
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-08-09 | 8 | Manuel Hahn | HipSquare GmbH | 0.25 | 0.03125 | 980 | 30.625
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-08-09 | 8 | Manuel Hahn | HipSquare GmbH | 2.75 | 0.34375 | 980 | 336.875
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-08-09 | 8 | Matthias Müller | HipSquare GmbH | 1 | 0.125 | 820 | 102.5
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-08-10 | 8 | Julian Steinfeld | HipSquare GmbH | 7 | 0.875 | 1112 | 973
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-08-10 | 8 | Manuel Hahn | HipSquare GmbH | 4.5 | 0.5625 | 980 | 551.25
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-08-10 | 8 | Manuel Hahn | HipSquare GmbH | 3.5 | 0.4375 | 980 | 428.75
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-08-10 | 8 | Matthias Müller | HipSquare GmbH | 8 | 1 | 820 | 820
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-08-10 | 8 | Matthias Müller | HipSquare GmbH | 1.25 | 0.15625 | 820 | 128.125
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-08-11 | 8 | Julian Steinfeld | HipSquare GmbH | 3.5 | 0.4375 | 1112 | 486.5
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-08-11 | 8 | Manuel Hahn | HipSquare GmbH | 2.25 | 0.28125 | 980 | 275.625
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-08-11 | 8 | Manuel Hahn | HipSquare GmbH | 4 | 0.5 | 980 | 490
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-08-11 | 8 | Matthias Müller | HipSquare GmbH | 1 | 0.125 | 820 | 102.5
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-08-11 | 8 | Matthias Müller | HipSquare GmbH | 8 | 1 | 820 | 820
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-08-12 | 8 | Julian Steinfeld | HipSquare GmbH | 1.5 | 0.1875 | 1112 | 208.5
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-08-12 | 8 | Manuel Hahn | HipSquare GmbH | 0.5 | 0.0625 | 980 | 61.25
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-08-12 | 8 | Manuel Hahn | HipSquare GmbH | 6.25 | 0.78125 | 980 | 765.625
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-08-12 | 8 | Matthias Müller | HipSquare GmbH | 0.25 | 0.03125 | 820 | 25.625
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-08-12 | 8 | Matthias Müller | HipSquare GmbH | 8 | 1 | 820 | 820
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-08-13 | 8 | Julian Steinfeld | HipSquare GmbH | 2 | 0.25 | 1112 | 278
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-08-13 | 8 | Manuel Hahn | HipSquare GmbH | 2.75 | 0.34375 | 980 | 336.875
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-08-13 | 8 | Manuel Hahn | HipSquare GmbH | 1 | 0.125 | 980 | 122.5
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-08-13 | 8 | Matthias Müller | HipSquare GmbH | 8 | 1 | 820 | 820
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-08-13 | 8 | Matthias Müller | HipSquare GmbH | 0.5 | 0.0625 | 820 | 51.25
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-08-16 | 8 | Julian Steinfeld | HipSquare GmbH | 1 | 0.125 | 1112 | 139
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-08-16 | 8 | Matthias Müller | HipSquare GmbH | 0.5 | 0.0625 | 820 | 51.25
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-08-16 | 8 | Matthias Müller | HipSquare GmbH | 8 | 1 | 820 | 820
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-08-17 | 8 | Matthias Müller | HipSquare GmbH | 0.5 | 0.0625 | 820 | 51.25
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-08-17 | 8 | Matthias Müller | HipSquare GmbH | 8 | 1 | 820 | 820
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-08-18 | 8 | Matthias Müller | HipSquare GmbH | 8 | 1 | 820 | 820
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-08-18 | 8 | Matthias Müller | HipSquare GmbH | 0.25 | 0.03125 | 820 | 25.625
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-08-19 | 8 | Matthias Müller | HipSquare GmbH | 8 | 1 | 820 | 820
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-08-19 | 8 | Matthias Müller | HipSquare GmbH | 0.25 | 0.03125 | 820 | 25.625
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-08-20 | 8 | Matthias Müller | HipSquare GmbH | 0.25 | 0.03125 | 820 | 25.625
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-08-20 | 8 | Matthias Müller | HipSquare GmbH | 8 | 1 | 820 | 820
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-08-23 | 8 | Julian Steinfeld | HipSquare GmbH | 4.5 | 0.5625 | 1112 | 625.5
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-08-23 | 8 | Manuel Hahn | HipSquare GmbH | 1 | 0.125 | 980 | 122.5
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-08-23 | 8 | Manuel Hahn | HipSquare GmbH | 4.5 | 0.5625 | 980 | 551.25
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-08-23 | 8 | Matthias Müller | HipSquare GmbH | 2.25 | 0.28125 | 820 | 230.625
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-08-23 | 8 | Matthias Müller | HipSquare GmbH | 8 | 1 | 820 | 820
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-08-24 | 8 | Julian Steinfeld | HipSquare GmbH | 5.5 | 0.6875 | 1112 | 764.5
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-08-24 | 8 | Manuel Hahn | HipSquare GmbH | 1.75 | 0.21875 | 980 | 214.375
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-08-24 | 8 | Manuel Hahn | HipSquare GmbH | 5.25 | 0.65625 | 980 | 643.125
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-08-24 | 8 | Matthias Müller | HipSquare GmbH | 8 | 1 | 820 | 820
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-08-24 | 8 | Matthias Müller | HipSquare GmbH | 0.75 | 0.09375 | 820 | 76.875
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-08-25 | 8 | Julian Steinfeld | HipSquare GmbH | 7 | 0.875 | 1112 | 973
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-08-25 | 8 | Manuel Hahn | HipSquare GmbH | 1.25 | 0.15625 | 980 | 153.125
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-08-25 | 8 | Manuel Hahn | HipSquare GmbH | 6 | 0.75 | 980 | 735
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-08-25 | 8 | Matthias Müller | HipSquare GmbH | 8 | 1 | 820 | 820
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-08-25 | 8 | Matthias Müller | HipSquare GmbH | 1 | 0.125 | 820 | 102.5
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-08-26 | 8 | Julian Steinfeld | HipSquare GmbH | 6.5 | 0.8125 | 1112 | 903.5
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-08-26 | 8 | Manuel Hahn | HipSquare GmbH | 2.25 | 0.28125 | 980 | 275.625
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-08-26 | 8 | Manuel Hahn | HipSquare GmbH | 4.25 | 0.53125 | 980 | 520.625
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-08-26 | 8 | Matthias Müller | HipSquare GmbH | 8 | 1 | 820 | 820
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-08-26 | 8 | Matthias Müller | HipSquare GmbH | 1.25 | 0.15625 | 820 | 128.125
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-08-27 | 8 | Julian Steinfeld | HipSquare GmbH | 6 | 0.75 | 1112 | 834
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-08-27 | 8 | Manuel Hahn | HipSquare GmbH | 3.5 | 0.4375 | 980 | 428.75
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-08-27 | 8 | Manuel Hahn | HipSquare GmbH | 2.75 | 0.34375 | 980 | 336.875
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-08-27 | 8 | Matthias Müller | HipSquare GmbH | 0.25 | 0.03125 | 820 | 25.625
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-08-27 | 8 | Matthias Müller | HipSquare GmbH | 8 | 1 | 820 | 820
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-08-30 | 8 | Julian Steinfeld | HipSquare GmbH | 8.5 | 1.0625 | 1112 | 1181.5
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-08-30 | 8 | Manuel Hahn | HipSquare GmbH | 6.25 | 0.78125 | 980 | 765.625
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-08-30 | 8 | Manuel Hahn | HipSquare GmbH | 0.75 | 0.09375 | 980 | 91.875
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-08-30 | 8 | Matthias Müller | HipSquare GmbH | 0.25 | 0.03125 | 820 | 25.625
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-08-30 | 8 | Matthias Müller | HipSquare GmbH | 8 | 1 | 820 | 820
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-08-31 | 8 | Julian Steinfeld | HipSquare GmbH | 8 | 1 | 1112 | 1112
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-08-31 | 8 | Manuel Hahn | HipSquare GmbH | 4 | 0.5 | 980 | 490
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-08-31 | 8 | Manuel Hahn | HipSquare GmbH | 3.25 | 0.40625 | 980 | 398.125
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-08-31 | 8 | Matthias Müller | HipSquare GmbH | 2.5 | 0.3125 | 820 | 256.25
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-08-31 | 8 | Matthias Müller | HipSquare GmbH | 8 | 1 | 820 | 820
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-09-01 | 9 | Julian Steinfeld | HipSquare GmbH | 8.5 | 1.0625 | 1112 | 1181.5
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-09-01 | 9 | Manuel Hahn | HipSquare GmbH | 5.25 | 0.65625 | 980 | 643.125
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-09-01 | 9 | Manuel Hahn | HipSquare GmbH | 1.5 | 0.1875 | 980 | 183.75
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-09-01 | 9 | Matthias Müller | HipSquare GmbH | 8 | 1 | 820 | 820
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-09-02 | 9 | Julian Steinfeld | HipSquare GmbH | 10 | 1.25 | 1112 | 1390
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-09-02 | 9 | Manuel Hahn | HipSquare GmbH | 0.5 | 0.0625 | 980 | 61.25
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-09-02 | 9 | Manuel Hahn | HipSquare GmbH | 6 | 0.75 | 980 | 735
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-09-02 | 9 | Matthias Müller | HipSquare GmbH | 8 | 1 | 820 | 820
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-09-03 | 9 | Julian Steinfeld | HipSquare GmbH | 11.5 | 1.4375 | 1112 | 1598.5
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-09-03 | 9 | Manuel Hahn | HipSquare GmbH | 8.25 | 1.0312 | 980 | 1010.625
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-09-03 | 9 | Matthias Müller | HipSquare GmbH | 8 | 1 | 820 | 820
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-09-04 | 9 | Julian Steinfeld | HipSquare GmbH | 1.5 | 0.1875 | 1112 | 208.5
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-09-05 | 9 | Julian Steinfeld | HipSquare GmbH | 3 | 0.375 | 1112 | 417
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-09-06 | 9 | Julian Steinfeld | HipSquare GmbH | 7 | 0.875 | 1112 | 973
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-09-06 | 9 | Manuel Hahn | HipSquare GmbH | 0.75 | 0.09375 | 980 | 91.875
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-09-06 | 9 | Manuel Hahn | HipSquare GmbH | 6.5 | 0.8125 | 980 | 796.25
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-09-06 | 9 | Matthias Müller | HipSquare GmbH | 8 | 1 | 820 | 820
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-09-06 | 9 | Matthias Müller | HipSquare GmbH | 0.25 | 0.03125 | 820 | 25.625
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-09-07 | 9 | Julian Steinfeld | HipSquare GmbH | 6.5 | 0.8125 | 1112 | 903.5
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-09-07 | 9 | Manuel Hahn | HipSquare GmbH | 3.25 | 0.40625 | 980 | 398.125
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-09-07 | 9 | Manuel Hahn | HipSquare GmbH | 4 | 0.5 | 980 | 490
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-09-07 | 9 | Matthias Müller | HipSquare GmbH | 8 | 1 | 820 | 820
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-09-07 | 9 | Matthias Müller | HipSquare GmbH | 3 | 0.375 | 820 | 307.5
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-09-08 | 9 | Julian Steinfeld | HipSquare GmbH | 7.5 | 0.9375 | 1112 | 1042.5
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-09-08 | 9 | Manuel Hahn | HipSquare GmbH | 3.5 | 0.4375 | 980 | 428.75
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-09-08 | 9 | Manuel Hahn | HipSquare GmbH | 2.5 | 0.3125 | 980 | 306.25
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-09-08 | 9 | Matthias Müller | HipSquare GmbH | 8 | 1 | 820 | 820
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-09-08 | 9 | Matthias Müller | HipSquare GmbH | 0.75 | 0.09375 | 820 | 76.875
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-09-09 | 9 | Julian Steinfeld | HipSquare GmbH | 8.5 | 1.0625 | 1112 | 1181.5
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-09-09 | 9 | Manuel Hahn | HipSquare GmbH | 0.5 | 0.0625 | 980 | 61.25
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-09-09 | 9 | Manuel Hahn | HipSquare GmbH | 6.5 | 0.8125 | 980 | 796.25
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-09-09 | 9 | Matthias Müller | HipSquare GmbH | 0.25 | 0.03125 | 820 | 25.625
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-09-09 | 9 | Matthias Müller | HipSquare GmbH | 8 | 1 | 820 | 820
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-09-10 | 9 | Julian Steinfeld | HipSquare GmbH | 6.5 | 0.8125 | 1112 | 903.5
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-09-10 | 9 | Manuel Hahn | HipSquare GmbH | 0.75 | 0.09375 | 980 | 91.875
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-09-10 | 9 | Manuel Hahn | HipSquare GmbH | 3.75 | 0.46875 | 980 | 459.375
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-09-10 | 9 | Matthias Müller | HipSquare GmbH | 0.25 | 0.03125 | 820 | 25.625
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-09-10 | 9 | Matthias Müller | HipSquare GmbH | 8 | 1 | 820 | 820
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-09-13 | 9 | Julian Steinfeld | HipSquare GmbH | 7.5 | 0.9375 | 1112 | 1042.5
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-09-13 | 9 | Manuel Hahn | HipSquare GmbH | 1.5 | 0.1875 | 980 | 183.75
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-09-13 | 9 | Manuel Hahn | HipSquare GmbH | 4 | 0.5 | 980 | 490
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-09-13 | 9 | Matthias Müller | HipSquare GmbH | 8 | 1 | 820 | 820
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-09-13 | 9 | Matthias Müller | HipSquare GmbH | 0.25 | 0.03125 | 820 | 25.625
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-09-14 | 9 | Julian Steinfeld | HipSquare GmbH | 7.5 | 0.9375 | 1112 | 1042.5
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-09-14 | 9 | Manuel Hahn | HipSquare GmbH | 4 | 0.5 | 980 | 490
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-09-14 | 9 | Manuel Hahn | HipSquare GmbH | 1.75 | 0.21875 | 980 | 214.375
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-09-14 | 9 | Matthias Müller | HipSquare GmbH | 8 | 1 | 820 | 820
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-09-14 | 9 | Matthias Müller | HipSquare GmbH | 0.25 | 0.03125 | 820 | 25.625
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-09-15 | 9 | Julian Steinfeld | HipSquare GmbH | 5 | 0.625 | 1112 | 695
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-09-15 | 9 | Manuel Hahn | HipSquare GmbH | 2 | 0.25 | 980 | 245
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-09-15 | 9 | Manuel Hahn | HipSquare GmbH | 3.25 | 0.40625 | 980 | 398.125
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-09-15 | 9 | Matthias Müller | HipSquare GmbH | 8 | 1 | 820 | 820
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-09-15 | 9 | Matthias Müller | HipSquare GmbH | 0.5 | 0.0625 | 820 | 51.25
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-09-16 | 9 | Julian Steinfeld | HipSquare GmbH | 6.5 | 0.8125 | 1112 | 903.5
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-09-16 | 9 | Manuel Hahn | HipSquare GmbH | 3.75 | 0.46875 | 980 | 459.375
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-09-16 | 9 | Manuel Hahn | HipSquare GmbH | 3 | 0.375 | 980 | 367.5
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-09-16 | 9 | Matthias Müller | HipSquare GmbH | 1.5 | 0.1875 | 820 | 153.75
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-09-16 | 9 | Matthias Müller | HipSquare GmbH | 8 | 1 | 820 | 820
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-09-17 | 9 | Julian Steinfeld | HipSquare GmbH | 8 | 1 | 1112 | 1112
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-09-17 | 9 | Manuel Hahn | HipSquare GmbH | 5.5 | 0.6875 | 980 | 673.75
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-09-17 | 9 | Manuel Hahn | HipSquare GmbH | 1.25 | 0.15625 | 980 | 153.125
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-09-17 | 9 | Matthias Müller | HipSquare GmbH | 0.5 | 0.0625 | 820 | 51.25
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-09-17 | 9 | Matthias Müller | HipSquare GmbH | 8 | 1 | 820 | 820
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-09-19 | 9 | Julian Steinfeld | HipSquare GmbH | 0.5 | 0.0625 | 1112 | 69.5
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-09-20 | 9 | Julian Steinfeld | HipSquare GmbH | 7.5 | 0.9375 | 1112 | 1042.5
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-09-20 | 9 | Manuel Hahn | HipSquare GmbH | 5.25 | 0.65625 | 980 | 643.125
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-09-20 | 9 | Manuel Hahn | HipSquare GmbH | 1.5 | 0.1875 | 980 | 183.75
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-09-20 | 9 | Matthias Müller | HipSquare GmbH | 8 | 1 | 820 | 820
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-09-21 | 9 | Julian Steinfeld | HipSquare GmbH | 6.5 | 0.8125 | 1112 | 903.5
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-09-21 | 9 | Manuel Hahn | HipSquare GmbH | 5.25 | 0.65625 | 980 | 643.125
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-09-21 | 9 | Manuel Hahn | HipSquare GmbH | 2 | 0.25 | 980 | 245
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-09-21 | 9 | Matthias Müller | HipSquare GmbH | 8 | 1 | 820 | 820
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-09-22 | 9 | Julian Steinfeld | HipSquare GmbH | 7.5 | 0.9375 | 1112 | 1042.5
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-09-22 | 9 | Manuel Hahn | HipSquare GmbH | 2.25 | 0.28125 | 980 | 275.625
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-09-22 | 9 | Manuel Hahn | HipSquare GmbH | 4.5 | 0.5625 | 980 | 551.25
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-09-22 | 9 | Matthias Müller | HipSquare GmbH | 8 | 1 | 820 | 820
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-09-23 | 9 | Julian Steinfeld | HipSquare GmbH | 7.5 | 0.9375 | 1112 | 1042.5
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-09-23 | 9 | Manuel Hahn | HipSquare GmbH | 1.75 | 0.21875 | 980 | 214.375
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-09-23 | 9 | Manuel Hahn | HipSquare GmbH | 3.5 | 0.4375 | 980 | 428.75
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-09-23 | 9 | Matthias Müller | HipSquare GmbH | 8 | 1 | 820 | 820
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-09-24 | 9 | Julian Steinfeld | HipSquare GmbH | 8 | 1 | 1112 | 1112
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-09-24 | 9 | Manuel Hahn | HipSquare GmbH | 3.25 | 0.40625 | 980 | 398.125
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-09-24 | 9 | Manuel Hahn | HipSquare GmbH | 2.25 | 0.28125 | 980 | 275.625
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-09-24 | 9 | Matthias Müller | HipSquare GmbH | 8 | 1 | 820 | 820
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-09-27 | 9 | Julian Steinfeld | HipSquare GmbH | 5.5 | 0.6875 | 1112 | 764.5
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-09-27 | 9 | Manuel Hahn | HipSquare GmbH | 4 | 0.5 | 980 | 490
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-09-27 | 9 | Manuel Hahn | HipSquare GmbH | 1.5 | 0.1875 | 980 | 183.75
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-09-27 | 9 | Matthias Müller | HipSquare GmbH | 8 | 1 | 820 | 820
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-09-27 | 9 | Matthias Müller | HipSquare GmbH | 1.75 | 0.21875 | 820 | 179.375
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-09-28 | 9 | Julian Steinfeld | HipSquare GmbH | 6 | 0.75 | 1112 | 834
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-09-28 | 9 | Manuel Hahn | HipSquare GmbH | 4.5 | 0.5625 | 980 | 551.25
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-09-28 | 9 | Manuel Hahn | HipSquare GmbH | 3 | 0.375 | 980 | 367.5
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-09-28 | 9 | Matthias Müller | HipSquare GmbH | 8 | 1 | 820 | 820
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-09-28 | 9 | Matthias Müller | HipSquare GmbH | 2 | 0.25 | 820 | 205
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-09-29 | 9 | Julian Steinfeld | HipSquare GmbH | 5.5 | 0.6875 | 1112 | 764.5
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-09-29 | 9 | Manuel Hahn | HipSquare GmbH | 1 | 0.125 | 980 | 122.5
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-09-29 | 9 | Manuel Hahn | HipSquare GmbH | 6.25 | 0.78125 | 980 | 765.625
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-09-29 | 9 | Matthias Müller | HipSquare GmbH | 8 | 1 | 820 | 820
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-09-29 | 9 | Matthias Müller | HipSquare GmbH | 0.5 | 0.0625 | 820 | 51.25
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-09-30 | 9 | Julian Steinfeld | HipSquare GmbH | 6 | 0.75 | 1112 | 834
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-09-30 | 9 | Manuel Hahn | HipSquare GmbH | 1.75 | 0.21875 | 980 | 214.375
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-09-30 | 9 | Manuel Hahn | HipSquare GmbH | 4.25 | 0.53125 | 980 | 520.625
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-09-30 | 9 | Matthias Müller | HipSquare GmbH | 0.25 | 0.03125 | 820 | 25.625
21 0427 | Measure 251 | 21 0427 Measure 251 - IT Security Initiative Hub (meta, HipSquare) | 2021-01-01 | 2021-12-31 | 2021-09-30 | 9 | Matthias Müller | HipSquare GmbH | 0.25 | 0.03125 | 820 | 25.625
21 1040 | Measure 299 | 21 1040 Measure 299-1 - Enforcement of Security Architecture | 2021-07-01 | 2021-12-31 | 2021-07-05 | 7 | Jade Poteat | metafinanz Informationssysteme GmbH | 0.5 | 0.0625 | 1000 | 62.5
21 1040 | Measure 299 | 21 1040 Measure 299-1 - Enforcement of Security Architecture | 2021-07-01 | 2021-12-31 | 2021-07-07 | 7 | Jade Poteat | metafinanz Informationssysteme GmbH | 0.5 | 0.0625 | 1000 | 62.5
21 1040 | Measure 299 | 21 1040 Measure 299-1 - Enforcement of Security Architecture | 2021-07-01 | 2021-12-31 | 2021-07-19 | 7 | Jade Poteat | metafinanz Informationssysteme GmbH | 2 | 0.25 | 1000 | 250
21 1040 | Measure 299 | 21 1040 Measure 299-1 - Enforcement of Security Architecture | 2021-07-01 | 2021-12-31 | 2021-07-20 | 7 | Jade Poteat | metafinanz Informationssysteme GmbH | 2.5 | 0.3125 | 1000 | 312.5
21 1040 | Measure 299 | 21 1040 Measure 299-1 - Enforcement of Security Architecture | 2021-07-01 | 2021-12-31 | 2021-07-21 | 7 | Jade Poteat | metafinanz Informationssysteme GmbH | 2.5 | 0.3125 | 1000 | 312.5
21 1040 | Measure 299 | 21 1040 Measure 299-1 - Enforcement of Security Architecture | 2021-07-01 | 2021-12-31 | 2021-07-26 | 7 | Jade Poteat | metafinanz Informationssysteme GmbH | 3 | 0.375 | 1000 | 375
21 1040 | Measure 299 | 21 1040 Measure 299-1 - Enforcement of Security Architecture | 2021-07-01 | 2021-12-31 | 2021-08-03 | 8 | Jade Poteat | metafinanz Informationssysteme GmbH | 0.5 | 0.0625 | 1000 | 62.5
21 1040 | Measure 299 | 21 1040 Measure 299-1 - Enforcement of Security Architecture | 2021-07-01 | 2021-12-31 | 2021-08-04 | 8 | Jade Poteat | metafinanz Informationssysteme GmbH | 2 | 0.25 | 1000 | 250
21 1040 | Measure 299 | 21 1040 Measure 299-1 - Enforcement of Security Architecture | 2021-07-01 | 2021-12-31 | 2021-08-06 | 8 | Jade Poteat | metafinanz Informationssysteme GmbH | 2 | 0.25 | 1000 | 250
21 1040 | Measure 299 | 21 1040 Measure 299-1 - Enforcement of Security Architecture | 2021-07-01 | 2021-12-31 | 2021-08-09 | 8 | Jade Poteat | metafinanz Informationssysteme GmbH | 3 | 0.375 | 1000 | 375
21 1040 | Measure 299 | 21 1040 Measure 299-1 - Enforcement of Security Architecture | 2021-07-01 | 2021-12-31 | 2021-08-10 | 8 | Jade Poteat | metafinanz Informationssysteme GmbH | 1 | 0.125 | 1000 | 125
21 1040 | Measure 299 | 21 1040 Measure 299-1 - Enforcement of Security Architecture | 2021-07-01 | 2021-12-31 | 2021-08-13 | 8 | Jade Poteat | metafinanz Informationssysteme GmbH | 1 | 0.125 | 1000 | 125
21 1040 | Measure 299 | 21 1040 Measure 299-1 - Enforcement of Security Architecture | 2021-07-01 | 2021-12-31 | 2021-08-23 | 8 | Jade Poteat | metafinanz Informationssysteme GmbH | 2 | 0.25 | 1000 | 250
21 1040 | Measure 299 | 21 1040 Measure 299-1 - Enforcement of Security Architecture | 2021-07-01 | 2021-12-31 | 2021-08-27 | 8 | Jade Poteat | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1000 | 500
21 1040 | Measure 299 | 21 1040 Measure 299-1 - Enforcement of Security Architecture | 2021-07-01 | 2021-12-31 | 2021-08-30 | 8 | Jade Poteat | metafinanz Informationssysteme GmbH | 3.5 | 0.4375 | 1000 | 437.5
21 1040 | Measure 299 | 21 1040 Measure 299-1 - Enforcement of Security Architecture | 2021-07-01 | 2021-12-31 | 2021-09-06 | 9 | Jade Poteat | metafinanz Informationssysteme GmbH | 2 | 0.25 | 1000 | 250
21 1040 | Measure 299 | 21 1040 Measure 299-1 - Enforcement of Security Architecture | 2021-07-01 | 2021-12-31 | 2021-09-08 | 9 | Jade Poteat | metafinanz Informationssysteme GmbH | 2 | 0.25 | 1000 | 250
21 1040 | Measure 299 | 21 1040 Measure 299-1 - Enforcement of Security Architecture | 2021-07-01 | 2021-12-31 | 2021-09-20 | 9 | Jade Poteat | metafinanz Informationssysteme GmbH | 1 | 0.125 | 1000 | 125
21 1040 | Measure 299 | 21 1040 Measure 299-1 - Enforcement of Security Architecture | 2021-07-01 | 2021-12-31 | 2021-09-21 | 9 | Jade Poteat | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1000 | 500
21 1040 | Measure 299 | 21 1040 Measure 299-1 - Enforcement of Security Architecture | 2021-07-01 | 2021-12-31 | 2021-09-27 | 9 | Jade Poteat | metafinanz Informationssysteme GmbH | 1 | 0.125 | 1000 | 125
21 1040 | Measure 299 | 21 1040 Measure 299-1 - Enforcement of Security Architecture | 2021-07-01 | 2021-12-31 | 2021-09-28 | 9 | Jade Poteat | metafinanz Informationssysteme GmbH | 1 | 0.125 | 1000 | 125
21 1040 | Measure 299 | 21 1040 Measure 299-1 - Enforcement of Security Architecture | 2021-07-01 | 2021-12-31 | 2021-09-29 | 9 | Jade Poteat | metafinanz Informationssysteme GmbH | 1 | 0.125 | 1000 | 125
21 1040 | Measure 299 | 21 1040 Measure 299-1 - Enforcement of Security Architecture | 2021-07-01 | 2021-12-31 | 2021-10-01 | 10 | Jade Poteat | metafinanz Informationssysteme GmbH | 1 | 0.125 | 1000 | 125
21 1040 | Measure 299 | 21 1040 Measure 299-1 - Enforcement of Security Architecture | 2021-07-01 | 2021-12-31 | 2021-10-04 | 10 | Jade Poteat | metafinanz Informationssysteme GmbH | 1 | 0.125 | 1000 | 125
21 1040 | Measure 299 | 21 1040 Measure 299-1 - Enforcement of Security Architecture | 2021-07-01 | 2021-12-31 | 2021-10-06 | 10 | Jade Poteat | metafinanz Informationssysteme GmbH | 1 | 0.125 | 1000 | 125
21 1040 | Measure 299 | 21 1040 Measure 299-1 - Enforcement of Security Architecture | 2021-07-01 | 2021-12-31 | 2021-10-07 | 10 | Jade Poteat | metafinanz Informationssysteme GmbH | 1 | 0.125 | 1000 | 125
21 1040 | Measure 299 | 21 1040 Measure 299-1 - Enforcement of Security Architecture | 2021-07-01 | 2021-12-31 | 2021-10-11 | 10 | Jade Poteat | metafinanz Informationssysteme GmbH | 1 | 0.125 | 1000 | 125
21 1040 | Measure 299 | 21 1040 Measure 299-1 - Enforcement of Security Architecture | 2021-07-01 | 2021-12-31 | 2021-10-13 | 10 | Jade Poteat | metafinanz Informationssysteme GmbH | 1 | 0.125 | 1000 | 125
21 1040 | Measure 299 | 21 1040 Measure 299-1 - Enforcement of Security Architecture | 2021-07-01 | 2021-12-31 | 2021-10-14 | 10 | Jade Poteat | metafinanz Informationssysteme GmbH | 2 | 0.25 | 1000 | 250
21 1040 | Measure 299 | 21 1040 Measure 299-1 - Enforcement of Security Architecture | 2021-07-01 | 2021-12-31 | 2021-10-15 | 10 | Jade Poteat | metafinanz Informationssysteme GmbH | 2 | 0.25 | 1000 | 250
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-07-01 | 7 | Michael Habel | metafinanz Informationssysteme GmbH | 10 | 1.25 | 1350 | 1687.5
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-07-02 | 7 | Maximilian Schellenberger | metafinanz Informationssysteme GmbH | 1 | 0.125 | 1000 | 125
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-07-05 | 7 | Rasa Rintallo | metafinanz Informationssysteme GmbH | 3 | 0.375 | 1000 | 375
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-07-06 | 7 | Rasa Rintallo | metafinanz Informationssysteme GmbH | 8 | 1 | 1000 | 1000
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-07-07 | 7 | Rasa Rintallo | metafinanz Informationssysteme GmbH | 8 | 1 | 1000 | 1000
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-07-08 | 7 | Michael Habel | metafinanz Informationssysteme GmbH | 9.5 | 1.1875 | 1350 | 1603.125
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-07-08 | 7 | Rasa Rintallo | metafinanz Informationssysteme GmbH | 8 | 1 | 1000 | 1000
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-07-09 | 7 | Michael Habel | metafinanz Informationssysteme GmbH | 6.5 | 0.8125 | 1350 | 1096.875
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-07-09 | 7 | Rasa Rintallo | metafinanz Informationssysteme GmbH | 8 | 1 | 1000 | 1000
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-07-12 | 7 | Gerhard Günther | metafinanz Informationssysteme GmbH | 8 | 1 | 1350 | 1350
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-07-12 | 7 | Michael Habel | metafinanz Informationssysteme GmbH | 10 | 1.25 | 1350 | 1687.5
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-07-12 | 7 | Rasa Rintallo | metafinanz Informationssysteme GmbH | 8 | 1 | 1000 | 1000
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-07-12 | 7 | Sona Latifyan | metafinanz Informationssysteme GmbH | 8 | 1 | 1000 | 1000
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-07-13 | 7 | Michael Habel | metafinanz Informationssysteme GmbH | 5 | 0.625 | 1350 | 843.75
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-07-13 | 7 | Michael Habel | metafinanz Informationssysteme GmbH | 5 | 0.625 | 1350 | 843.75
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-07-13 | 7 | Rasa Rintallo | metafinanz Informationssysteme GmbH | 8 | 1 | 1000 | 1000
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-07-13 | 7 | Sona Latifyan | metafinanz Informationssysteme GmbH | 8 | 1 | 1000 | 1000
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-07-14 | 7 | Gerhard Günther | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1350 | 675
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-07-14 | 7 | Michael Habel | metafinanz Informationssysteme GmbH | 2 | 0.25 | 1350 | 337.5
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-07-14 | 7 | Michael Habel | metafinanz Informationssysteme GmbH | 8 | 1 | 1350 | 1350
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-07-14 | 7 | Rasa Rintallo | metafinanz Informationssysteme GmbH | 8 | 1 | 1000 | 1000
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-07-14 | 7 | Stefan Köstenbauer | metafinanz Informationssysteme GmbH | 2 | 0.25 | 1350 | 337.5
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-07-15 | 7 | Michael Habel | metafinanz Informationssysteme GmbH | 5 | 0.625 | 1350 | 843.75
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-07-15 | 7 | Michael Habel | metafinanz Informationssysteme GmbH | 5 | 0.625 | 1350 | 843.75
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-07-15 | 7 | Rasa Rintallo | metafinanz Informationssysteme GmbH | 8 | 1 | 1000 | 1000
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-07-15 | 7 | Sona Latifyan | metafinanz Informationssysteme GmbH | 8 | 1 | 1000 | 1000
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-07-16 | 7 | Michael Habel | metafinanz Informationssysteme GmbH | 2 | 0.25 | 1350 | 337.5
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-07-16 | 7 | Michael Habel | metafinanz Informationssysteme GmbH | 6 | 0.75 | 1350 | 1012.5
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-07-16 | 7 | Stefan Köstenbauer | metafinanz Informationssysteme GmbH | 1 | 0.125 | 1350 | 168.75
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-07-19 | 7 | Michael Habel | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1350 | 675
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-07-19 | 7 | Michael Habel | metafinanz Informationssysteme GmbH | 6 | 0.75 | 1350 | 1012.5
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-07-19 | 7 | Rasa Rintallo | metafinanz Informationssysteme GmbH | 8 | 1 | 1000 | 1000
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-07-19 | 7 | Sona Latifyan | metafinanz Informationssysteme GmbH | 8 | 1 | 1000 | 1000
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-07-19 | 7 | Victor Peters | metafinanz Informationssysteme GmbH | 1.5 | 0.1875 | 1000 | 187.5
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-07-20 | 7 | Michael Habel | metafinanz Informationssysteme GmbH | 4.5 | 0.5625 | 1350 | 759.375
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-07-20 | 7 | Michael Habel | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1350 | 675
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-07-20 | 7 | Sona Latifyan | metafinanz Informationssysteme GmbH | 8 | 1 | 1000 | 1000
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-07-21 | 7 | Gerhard Günther | metafinanz Informationssysteme GmbH | 8 | 1 | 1350 | 1350
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-07-21 | 7 | Michael Habel | metafinanz Informationssysteme GmbH | 4.5 | 0.5625 | 1350 | 759.375
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-07-21 | 7 | Michael Habel | metafinanz Informationssysteme GmbH | 3.5 | 0.4375 | 1350 | 590.625
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-07-21 | 7 | Sona Latifyan | metafinanz Informationssysteme GmbH | 8 | 1 | 1000 | 1000
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-07-21 | 7 | Stefan Köstenbauer | metafinanz Informationssysteme GmbH | 1 | 0.125 | 1350 | 168.75
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-07-21 | 7 | Victor Peters | metafinanz Informationssysteme GmbH | 1 | 0.125 | 1000 | 125
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-07-22 | 7 | Gerhard Günther | metafinanz Informationssysteme GmbH | 8 | 1 | 1350 | 1350
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-07-22 | 7 | Michael Habel | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1350 | 675
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-07-22 | 7 | Michael Habel | metafinanz Informationssysteme GmbH | 6 | 0.75 | 1350 | 1012.5
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-07-22 | 7 | Sona Latifyan | metafinanz Informationssysteme GmbH | 8 | 1 | 1000 | 1000
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-07-22 | 7 | Victor Peters | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1000 | 500
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-07-23 | 7 | Michael Habel | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1350 | 675
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-07-23 | 7 | Michael Habel | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1350 | 675
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-07-26 | 7 | Maximilian Schellenberger | metafinanz Informationssysteme GmbH | 1.5 | 0.1875 | 1000 | 187.5
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-07-26 | 7 | Victor Peters | metafinanz Informationssysteme GmbH | 0.5 | 0.0625 | 1000 | 62.5
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-07-27 | 7 | Maximilian Schellenberger | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1000 | 500
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-07-27 | 7 | Rasa Rintallo | metafinanz Informationssysteme GmbH | 8 | 1 | 1000 | 1000
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-07-27 | 7 | Sona Latifyan | metafinanz Informationssysteme GmbH | 8 | 1 | 1000 | 1000
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-07-28 | 7 | Gerhard Günther | metafinanz Informationssysteme GmbH | 8 | 1 | 1350 | 1350
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-07-28 | 7 | Maximilian Schellenberger | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1000 | 500
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-07-28 | 7 | Rasa Rintallo | metafinanz Informationssysteme GmbH | 8 | 1 | 1000 | 1000
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-07-28 | 7 | Sona Latifyan | metafinanz Informationssysteme GmbH | 8 | 1 | 1000 | 1000
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-07-29 | 7 | Gerhard Günther | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1350 | 675
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-07-29 | 7 | Maximilian Schellenberger | metafinanz Informationssysteme GmbH | 3 | 0.375 | 1000 | 375
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-07-29 | 7 | Rasa Rintallo | metafinanz Informationssysteme GmbH | 8 | 1 | 1000 | 1000
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-07-29 | 7 | Sona Latifyan | metafinanz Informationssysteme GmbH | 2 | 0.25 | 1000 | 250
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-07-29 | 7 | Victor Peters | metafinanz Informationssysteme GmbH | 0.5 | 0.0625 | 1000 | 62.5
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-07-30 | 7 | Michael Habel | metafinanz Informationssysteme GmbH | 4.5 | 0.5625 | 1350 | 759.375
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-07-30 | 7 | Michael Habel | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1350 | 675
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-07-30 | 7 | Rasa Rintallo | metafinanz Informationssysteme GmbH | 8 | 1 | 1000 | 1000
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-07-30 | 7 | Sona Latifyan | metafinanz Informationssysteme GmbH | 6 | 0.75 | 1000 | 750
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-07-30 | 7 | Stefan Köstenbauer | metafinanz Informationssysteme GmbH | 1 | 0.125 | 1350 | 168.75
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-08-02 | 8 | Maximilian Schellenberger | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1000 | 500
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-08-02 | 8 | Michael Habel | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1350 | 675
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-08-02 | 8 | Michael Habel | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1350 | 675
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-08-02 | 8 | Rasa Rintallo | metafinanz Informationssysteme GmbH | 6 | 0.75 | 1000 | 750
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-08-02 | 8 | Rasa Rintallo | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1000 | 500
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-08-03 | 8 | Gerhard Günther | metafinanz Informationssysteme GmbH | 8 | 1 | 1350 | 1350
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-08-03 | 8 | Maximilian Schellenberger | metafinanz Informationssysteme GmbH | 1 | 0.125 | 1000 | 125
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-08-03 | 8 | Michael Habel | metafinanz Informationssysteme GmbH | 3 | 0.375 | 1350 | 506.25
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-08-03 | 8 | Michael Habel | metafinanz Informationssysteme GmbH | 5 | 0.625 | 1350 | 843.75
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-08-03 | 8 | Sona Latifyan | metafinanz Informationssysteme GmbH | 8 | 1 | 1000 | 1000
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-08-04 | 8 | Michael Habel | metafinanz Informationssysteme GmbH | 5 | 0.625 | 1350 | 843.75
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-08-04 | 8 | Michael Habel | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1350 | 675
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-08-04 | 8 | Sona Latifyan | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1000 | 500
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-08-04 | 8 | Stefan Köstenbauer | metafinanz Informationssysteme GmbH | 3 | 0.375 | 1350 | 506.25
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-08-05 | 8 | Gerhard Günther | metafinanz Informationssysteme GmbH | 8 | 1 | 1350 | 1350
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-08-05 | 8 | Michael Habel | metafinanz Informationssysteme GmbH | 3.5 | 0.4375 | 1350 | 590.625
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-08-05 | 8 | Michael Habel | metafinanz Informationssysteme GmbH | 4.5 | 0.5625 | 1350 | 759.375
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-08-06 | 8 | Maximilian Schellenberger | metafinanz Informationssysteme GmbH | 1.5 | 0.1875 | 1000 | 187.5
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-08-06 | 8 | Michael Habel | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1350 | 675
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-08-06 | 8 | Michael Habel | metafinanz Informationssysteme GmbH | 3 | 0.375 | 1350 | 506.25
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-08-06 | 8 | Stefan Köstenbauer | metafinanz Informationssysteme GmbH | 1 | 0.125 | 1350 | 168.75
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-08-09 | 8 | Michael Habel | metafinanz Informationssysteme GmbH | 4.5 | 0.5625 | 1350 | 759.375
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-08-09 | 8 | Michael Habel | metafinanz Informationssysteme GmbH | 4.5 | 0.5625 | 1350 | 759.375
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-08-09 | 8 | Rasa Rintallo | metafinanz Informationssysteme GmbH | 5 | 0.625 | 1000 | 625
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-08-09 | 8 | Rasa Rintallo | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1000 | 500
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-08-09 | 8 | Sona Latifyan | metafinanz Informationssysteme GmbH | 8 | 1 | 1000 | 1000
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-08-10 | 8 | Maximilian Schellenberger | metafinanz Informationssysteme GmbH | 2 | 0.25 | 1000 | 250
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-08-10 | 8 | Michael Habel | metafinanz Informationssysteme GmbH | 6 | 0.75 | 1350 | 1012.5
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-08-10 | 8 | Rasa Rintallo | metafinanz Informationssysteme GmbH | 7 | 0.875 | 1000 | 875
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-08-10 | 8 | Rasa Rintallo | metafinanz Informationssysteme GmbH | 2 | 0.25 | 1000 | 250
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-08-10 | 8 | Sona Latifyan | metafinanz Informationssysteme GmbH | 8 | 1 | 1000 | 1000
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-08-11 | 8 | Maximilian Schellenberger | metafinanz Informationssysteme GmbH | 2 | 0.25 | 1000 | 250
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-08-11 | 8 | Rasa Rintallo | metafinanz Informationssysteme GmbH | 6 | 0.75 | 1000 | 750
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-08-11 | 8 | Rasa Rintallo | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1000 | 500
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-08-11 | 8 | Sona Latifyan | metafinanz Informationssysteme GmbH | 8 | 1 | 1000 | 1000
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-08-12 | 8 | Maximilian Schellenberger | metafinanz Informationssysteme GmbH | 1.5 | 0.1875 | 1000 | 187.5
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-08-12 | 8 | Michael Habel | metafinanz Informationssysteme GmbH | 6 | 0.75 | 1350 | 1012.5
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-08-12 | 8 | Michael Habel | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1350 | 675
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-08-12 | 8 | Rasa Rintallo | metafinanz Informationssysteme GmbH | 5.5 | 0.6875 | 1000 | 687.5
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-08-12 | 8 | Rasa Rintallo | metafinanz Informationssysteme GmbH | 3 | 0.375 | 1000 | 375
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-08-12 | 8 | Sona Latifyan | metafinanz Informationssysteme GmbH | 8 | 1 | 1000 | 1000
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-08-12 | 8 | Victor Peters | metafinanz Informationssysteme GmbH | 1 | 0.125 | 1000 | 125
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-08-13 | 8 | Maximilian Schellenberger | metafinanz Informationssysteme GmbH | 0.75 | 0.09375 | 1000 | 93.75
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-08-13 | 8 | Rasa Rintallo | metafinanz Informationssysteme GmbH | 4.5 | 0.5625 | 1000 | 562.5
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-08-13 | 8 | Rasa Rintallo | metafinanz Informationssysteme GmbH | 3.5 | 0.4375 | 1000 | 437.5
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-08-13 | 8 | Sona Latifyan | metafinanz Informationssysteme GmbH | 8 | 1 | 1000 | 1000
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-08-16 | 8 | Michael Habel | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1350 | 675
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-08-16 | 8 | Michael Habel | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1350 | 675
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-08-16 | 8 | Rasa Rintallo | metafinanz Informationssysteme GmbH | 5 | 0.625 | 1000 | 625
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-08-16 | 8 | Rasa Rintallo | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1000 | 500
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-08-16 | 8 | Sona Latifyan | metafinanz Informationssysteme GmbH | 8 | 1 | 1000 | 1000
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-08-17 | 8 | Michael Habel | metafinanz Informationssysteme GmbH | 2 | 0.25 | 1350 | 337.5
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-08-17 | 8 | Michael Habel | metafinanz Informationssysteme GmbH | 6 | 0.75 | 1350 | 1012.5
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-08-17 | 8 | Rasa Rintallo | metafinanz Informationssysteme GmbH | 6 | 0.75 | 1000 | 750
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-08-17 | 8 | Rasa Rintallo | metafinanz Informationssysteme GmbH | 2.5 | 0.3125 | 1000 | 312.5
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-08-17 | 8 | Sona Latifyan | metafinanz Informationssysteme GmbH | 8 | 1 | 1000 | 1000
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-08-17 | 8 | Victor Peters | metafinanz Informationssysteme GmbH | 1 | 0.125 | 1000 | 125
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-08-18 | 8 | Gerhard Günther | metafinanz Informationssysteme GmbH | 8 | 1 | 1350 | 1350
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-08-18 | 8 | Michael Habel | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1350 | 675
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-08-18 | 8 | Michael Habel | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1350 | 675
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-08-18 | 8 | Rasa Rintallo | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1000 | 500
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-08-18 | 8 | Rasa Rintallo | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1000 | 500
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-08-18 | 8 | Sona Latifyan | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1000 | 500
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-08-18 | 8 | Victor Peters | metafinanz Informationssysteme GmbH | 2 | 0.25 | 1000 | 250
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-08-19 | 8 | Gerhard Günther | metafinanz Informationssysteme GmbH | 8 | 1 | 1350 | 1350
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-08-19 | 8 | Rasa Rintallo | metafinanz Informationssysteme GmbH | 5 | 0.625 | 1000 | 625
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-08-19 | 8 | Rasa Rintallo | metafinanz Informationssysteme GmbH | 5 | 0.625 | 1000 | 625
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-08-19 | 8 | Sona Latifyan | metafinanz Informationssysteme GmbH | 8 | 1 | 1000 | 1000
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-08-20 | 8 | Rasa Rintallo | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1000 | 500
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-08-20 | 8 | Rasa Rintallo | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1000 | 500
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-08-23 | 8 | Michael Habel | metafinanz Informationssysteme GmbH | 5.5 | 0.6875 | 1350 | 928.125
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-08-23 | 8 | Michael Habel | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1350 | 675
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-08-24 | 8 | Gerhard Günther | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1350 | 675
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-08-24 | 8 | Michael Habel | metafinanz Informationssysteme GmbH | 6 | 0.75 | 1350 | 1012.5
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-08-24 | 8 | Michael Habel | metafinanz Informationssysteme GmbH | 3 | 0.375 | 1350 | 506.25
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-08-24 | 8 | Sona Latifyan | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1000 | 500
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-08-25 | 8 | Gerhard Günther | metafinanz Informationssysteme GmbH | 8 | 1 | 1350 | 1350
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-08-25 | 8 | Michael Habel | metafinanz Informationssysteme GmbH | 7 | 0.875 | 1350 | 1181.25
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-08-25 | 8 | Michael Habel | metafinanz Informationssysteme GmbH | 2 | 0.25 | 1350 | 337.5
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-08-25 | 8 | Sona Latifyan | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1000 | 500
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-08-25 | 8 | Victor Peters | metafinanz Informationssysteme GmbH | 1 | 0.125 | 1000 | 125
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-08-26 | 8 | Gerhard Günther | metafinanz Informationssysteme GmbH | 8 | 1 | 1350 | 1350
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-08-26 | 8 | Michael Habel | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1350 | 675
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-08-26 | 8 | Michael Habel | metafinanz Informationssysteme GmbH | 5 | 0.625 | 1350 | 843.75
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-08-26 | 8 | Sona Latifyan | metafinanz Informationssysteme GmbH | 8 | 1 | 1000 | 1000
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-08-27 | 8 | Michael Habel | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1350 | 675
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-08-27 | 8 | Michael Habel | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1350 | 675
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-08-27 | 8 | Sona Latifyan | metafinanz Informationssysteme GmbH | 8 | 1 | 1000 | 1000
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-08-30 | 8 | Michael Habel | metafinanz Informationssysteme GmbH | 9.5 | 1.1875 | 1350 | 1603.125
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-08-30 | 8 | Sona Latifyan | metafinanz Informationssysteme GmbH | 8 | 1 | 1000 | 1000
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-08-31 | 8 | Gerhard Günther | metafinanz Informationssysteme GmbH | 8 | 1 | 1350 | 1350
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-08-31 | 8 | Michael Habel | metafinanz Informationssysteme GmbH | 9.5 | 1.1875 | 1350 | 1603.125
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-08-31 | 8 | Sona Latifyan | metafinanz Informationssysteme GmbH | 8 | 1 | 1000 | 1000
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-08-31 | 8 | Victor Peters | metafinanz Informationssysteme GmbH | 0.5 | 0.0625 | 1000 | 62.5
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-09-01 | 9 | Michael Habel | metafinanz Informationssysteme GmbH | 9 | 1.125 | 1350 | 1518.75
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-09-01 | 9 | Sona Latifyan | metafinanz Informationssysteme GmbH | 8 | 1 | 1000 | 1000
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-09-02 | 9 | Gerhard Günther | metafinanz Informationssysteme GmbH | 8 | 1 | 1350 | 1350
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-09-02 | 9 | Michael Habel | metafinanz Informationssysteme GmbH | 8.5 | 1.0625 | 1350 | 1434.375
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-09-02 | 9 | Sona Latifyan | metafinanz Informationssysteme GmbH | 8 | 1 | 1000 | 1000
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-09-03 | 9 | Gerhard Günther | metafinanz Informationssysteme GmbH | 8 | 1 | 1350 | 1350
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-09-03 | 9 | Michael Habel | metafinanz Informationssysteme GmbH | 8 | 1 | 1350 | 1350
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-09-03 | 9 | Sona Latifyan | metafinanz Informationssysteme GmbH | 8 | 1 | 1000 | 1000
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-09-06 | 9 | Gerhard Günther | metafinanz Informationssysteme GmbH | 8 | 1 | 1350 | 1350
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-09-06 | 9 | Sona Latifyan | metafinanz Informationssysteme GmbH | 8 | 1 | 1000 | 1000
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-09-07 | 9 | Gerhard Günther | metafinanz Informationssysteme GmbH | 8 | 1 | 1350 | 1350
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-09-07 | 9 | Rasa Rintallo | metafinanz Informationssysteme GmbH | 8.5 | 1.0625 | 1000 | 1062.5
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-09-07 | 9 | Victor Peters | metafinanz Informationssysteme GmbH | 0.5 | 0.0625 | 1000 | 62.5
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-09-08 | 9 | Gerhard Günther | metafinanz Informationssysteme GmbH | 8 | 1 | 1350 | 1350
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-09-08 | 9 | Rasa Rintallo | metafinanz Informationssysteme GmbH | 8 | 1 | 1000 | 1000
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-09-08 | 9 | Sona Latifyan | metafinanz Informationssysteme GmbH | 8 | 1 | 1000 | 1000
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-09-08 | 9 | Victor Peters | metafinanz Informationssysteme GmbH | 1 | 0.125 | 1000 | 125
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-09-09 | 9 | Gerhard Günther | metafinanz Informationssysteme GmbH | 8 | 1 | 1350 | 1350
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-09-09 | 9 | Rasa Rintallo | metafinanz Informationssysteme GmbH | 9 | 1.125 | 1000 | 1125
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-09-09 | 9 | Sona Latifyan | metafinanz Informationssysteme GmbH | 8 | 1 | 1000 | 1000
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-09-10 | 9 | Gerhard Günther | metafinanz Informationssysteme GmbH | 8 | 1 | 1350 | 1350
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-09-10 | 9 | Rasa Rintallo | metafinanz Informationssysteme GmbH | 7 | 0.875 | 1000 | 875
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-09-13 | 9 | Gerhard Günther | metafinanz Informationssysteme GmbH | 8 | 1 | 1350 | 1350
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-09-13 | 9 | Rasa Rintallo | metafinanz Informationssysteme GmbH | 8 | 1 | 1000 | 1000
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-09-13 | 9 | Sona Latifyan | metafinanz Informationssysteme GmbH | 8 | 1 | 1000 | 1000
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-09-14 | 9 | Gerhard Günther | metafinanz Informationssysteme GmbH | 8 | 1 | 1350 | 1350
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-09-14 | 9 | Rasa Rintallo | metafinanz Informationssysteme GmbH | 9 | 1.125 | 1000 | 1125
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-09-14 | 9 | Sona Latifyan | metafinanz Informationssysteme GmbH | 8 | 1 | 1000 | 1000
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-09-14 | 9 | Victor Peters | metafinanz Informationssysteme GmbH | 1 | 0.125 | 1000 | 125
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-09-15 | 9 | Gerhard Günther | metafinanz Informationssysteme GmbH | 8 | 1 | 1350 | 1350
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-09-15 | 9 | Rasa Rintallo | metafinanz Informationssysteme GmbH | 7.5 | 0.9375 | 1000 | 937.5
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-09-15 | 9 | Sona Latifyan | metafinanz Informationssysteme GmbH | 8 | 1 | 1000 | 1000
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-09-15 | 9 | Victor Peters | metafinanz Informationssysteme GmbH | 1 | 0.125 | 1000 | 125
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-09-16 | 9 | Gerhard Günther | metafinanz Informationssysteme GmbH | 8 | 1 | 1350 | 1350
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-09-16 | 9 | Rasa Rintallo | metafinanz Informationssysteme GmbH | 8 | 1 | 1000 | 1000
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-09-16 | 9 | Sona Latifyan | metafinanz Informationssysteme GmbH | 8 | 1 | 1000 | 1000
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-09-16 | 9 | Victor Peters | metafinanz Informationssysteme GmbH | 1.25 | 0.15625 | 1000 | 156.25
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-09-17 | 9 | Gerhard Günther | metafinanz Informationssysteme GmbH | 8 | 1 | 1350 | 1350
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-09-20 | 9 | Gerhard Günther | metafinanz Informationssysteme GmbH | 8 | 1 | 1350 | 1350
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-09-20 | 9 | Rasa Rintallo | metafinanz Informationssysteme GmbH | 7.5 | 0.9375 | 1000 | 937.5
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-09-20 | 9 | Sona Latifyan | metafinanz Informationssysteme GmbH | 8 | 1 | 1000 | 1000
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-09-21 | 9 | Rasa Rintallo | metafinanz Informationssysteme GmbH | 9.5 | 1.1875 | 1000 | 1187.5
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-09-21 | 9 | Sona Latifyan | metafinanz Informationssysteme GmbH | 8 | 1 | 1000 | 1000
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-09-22 | 9 | Gerhard Günther | metafinanz Informationssysteme GmbH | 8 | 1 | 1350 | 1350
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-09-22 | 9 | Rasa Rintallo | metafinanz Informationssysteme GmbH | 8.5 | 1.0625 | 1000 | 1062.5
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-09-22 | 9 | Sona Latifyan | metafinanz Informationssysteme GmbH | 8 | 1 | 1000 | 1000
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-09-23 | 9 | Gerhard Günther | metafinanz Informationssysteme GmbH | 8 | 1 | 1350 | 1350
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-09-23 | 9 | Rasa Rintallo | metafinanz Informationssysteme GmbH | 8 | 1 | 1000 | 1000
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-09-23 | 9 | Sona Latifyan | metafinanz Informationssysteme GmbH | 8 | 1 | 1000 | 1000
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-09-24 | 9 | Gerhard Günther | metafinanz Informationssysteme GmbH | 8 | 1 | 1350 | 1350
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-09-24 | 9 | Rasa Rintallo | metafinanz Informationssysteme GmbH | 7 | 0.875 | 1000 | 875
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-09-24 | 9 | Sona Latifyan | metafinanz Informationssysteme GmbH | 8 | 1 | 1000 | 1000
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-09-27 | 9 | Gerhard Günther | metafinanz Informationssysteme GmbH | 8 | 1 | 1350 | 1350
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-09-27 | 9 | Michael Habel | metafinanz Informationssysteme GmbH | 3 | 0.375 | 1350 | 506.25
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-09-27 | 9 | Michael Habel | metafinanz Informationssysteme GmbH | 5 | 0.625 | 1350 | 843.75
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-09-27 | 9 | Rasa Rintallo | metafinanz Informationssysteme GmbH | 8 | 1 | 1000 | 1000
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-09-27 | 9 | Sona Latifyan | metafinanz Informationssysteme GmbH | 8 | 1 | 1000 | 1000
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-09-28 | 9 | Michael Habel | metafinanz Informationssysteme GmbH | 9 | 1.125 | 1350 | 1518.75
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-09-28 | 9 | Rasa Rintallo | metafinanz Informationssysteme GmbH | 10 | 1.25 | 1000 | 1250
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-09-28 | 9 | Sona Latifyan | metafinanz Informationssysteme GmbH | 8 | 1 | 1000 | 1000
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-09-29 | 9 | Gerhard Günther | metafinanz Informationssysteme GmbH | 8 | 1 | 1350 | 1350
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-09-29 | 9 | Michael Habel | metafinanz Informationssysteme GmbH | 8 | 1 | 1350 | 1350
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-09-29 | 9 | Rasa Rintallo | metafinanz Informationssysteme GmbH | 9 | 1.125 | 1000 | 1125
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-09-30 | 9 | Gerhard Günther | metafinanz Informationssysteme GmbH | 8 | 1 | 1350 | 1350
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-09-30 | 9 | Michael Habel | metafinanz Informationssysteme GmbH | 8.5 | 1.0625 | 1350 | 1434.375
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-09-30 | 9 | Rasa Rintallo | metafinanz Informationssysteme GmbH | 10 | 1.25 | 1000 | 1250
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-09-30 | 9 | Sona Latifyan | metafinanz Informationssysteme GmbH | 8 | 1 | 1000 | 1000
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-10-01 | 10 | Michael Habel | metafinanz Informationssysteme GmbH | 7 | 0.875 | 1350 | 1181.25
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-10-04 | 10 | Michael Habel | metafinanz Informationssysteme GmbH | 8.5 | 1.0625 | 1350 | 1434.375
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-10-05 | 10 | Michael Habel | metafinanz Informationssysteme GmbH | 8.5 | 1.0625 | 1350 | 1434.375
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-10-05 | 10 | Victor Peters | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1000 | 500
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-10-06 | 10 | Michael Habel | metafinanz Informationssysteme GmbH | 9 | 1.125 | 1350 | 1518.75
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-10-06 | 10 | Victor Peters | metafinanz Informationssysteme GmbH | 1.5 | 0.1875 | 1000 | 187.5
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-10-07 | 10 | Michael Habel | metafinanz Informationssysteme GmbH | 9.5 | 1.1875 | 1350 | 1603.125
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-10-07 | 10 | Victor Peters | metafinanz Informationssysteme GmbH | 0.75 | 0.09375 | 1000 | 93.75
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-10-08 | 10 | Michael Habel | metafinanz Informationssysteme GmbH | 9.5 | 1.1875 | 1350 | 1603.125
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-10-11 | 10 | Michael Habel | metafinanz Informationssysteme GmbH | 5.5 | 0.6875 | 1350 | 928.125
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-10-11 | 10 | Victor Peters | metafinanz Informationssysteme GmbH | 1 | 0.125 | 1000 | 125
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-10-12 | 10 | Michael Habel | metafinanz Informationssysteme GmbH | 8 | 1 | 1350 | 1350
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-10-12 | 10 | Victor Peters | metafinanz Informationssysteme GmbH | 3 | 0.375 | 1000 | 375
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-10-13 | 10 | Michael Habel | metafinanz Informationssysteme GmbH | 9 | 1.125 | 1350 | 1518.75
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-10-13 | 10 | Victor Peters | metafinanz Informationssysteme GmbH | 1 | 0.125 | 1000 | 125
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-10-14 | 10 | Michael Habel | metafinanz Informationssysteme GmbH | 9 | 1.125 | 1350 | 1518.75
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-10-14 | 10 | Victor Peters | metafinanz Informationssysteme GmbH | 1.75 | 0.21875 | 1000 | 218.75
21 1037 | Measure 294 | 21 1037 Measure 294 - Integrated Information Risk Management early Live (meta) | 2021-07-01 | 2021-12-31 | 2021-10-15 | 10 | Michael Habel | metafinanz Informationssysteme GmbH | 6 | 0.75 | 1350 | 1012.5
21 1059 | Measure 296 | 21 1059 Measure 296 - Financial Loss Quantification Service (Thuspaß) | 2021-07-01 | 2021-12-31 | 2021-07-05 | 7 | Thomas Thuspaß | metafinanz Informationssysteme GmbH | 4.5 | 0.5625 | 1350 | 759.375
21 1059 | Measure 296 | 21 1059 Measure 296 - Financial Loss Quantification Service (Thuspaß) | 2021-07-01 | 2021-12-31 | 2021-07-06 | 7 | Thomas Thuspaß | metafinanz Informationssysteme GmbH | 5 | 0.625 | 1350 | 843.75
21 1059 | Measure 296 | 21 1059 Measure 296 - Financial Loss Quantification Service (Thuspaß) | 2021-07-01 | 2021-12-31 | 2021-07-07 | 7 | Thomas Thuspaß | metafinanz Informationssysteme GmbH | 7 | 0.875 | 1350 | 1181.25
21 1059 | Measure 296 | 21 1059 Measure 296 - Financial Loss Quantification Service (Thuspaß) | 2021-07-01 | 2021-12-31 | 2021-07-08 | 7 | Thomas Thuspaß | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1350 | 675
21 1059 | Measure 296 | 21 1059 Measure 296 - Financial Loss Quantification Service (Thuspaß) | 2021-07-01 | 2021-12-31 | 2021-07-09 | 7 | Thomas Thuspaß | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1350 | 675
21 1059 | Measure 296 | 21 1059 Measure 296 - Financial Loss Quantification Service (Thuspaß) | 2021-07-01 | 2021-12-31 | 2021-07-12 | 7 | Thomas Thuspaß | metafinanz Informationssysteme GmbH | 6 | 0.75 | 1350 | 1012.5
21 1059 | Measure 296 | 21 1059 Measure 296 - Financial Loss Quantification Service (Thuspaß) | 2021-07-01 | 2021-12-31 | 2021-07-13 | 7 | Thomas Thuspaß | metafinanz Informationssysteme GmbH | 8 | 1 | 1350 | 1350
21 1059 | Measure 296 | 21 1059 Measure 296 - Financial Loss Quantification Service (Thuspaß) | 2021-07-01 | 2021-12-31 | 2021-07-14 | 7 | Thomas Thuspaß | metafinanz Informationssysteme GmbH | 5.5 | 0.6875 | 1350 | 928.125
21 1059 | Measure 296 | 21 1059 Measure 296 - Financial Loss Quantification Service (Thuspaß) | 2021-07-01 | 2021-12-31 | 2021-07-15 | 7 | Thomas Thuspaß | metafinanz Informationssysteme GmbH | 6 | 0.75 | 1350 | 1012.5
21 1059 | Measure 296 | 21 1059 Measure 296 - Financial Loss Quantification Service (Thuspaß) | 2021-07-01 | 2021-12-31 | 2021-07-16 | 7 | Thomas Thuspaß | metafinanz Informationssysteme GmbH | 2.5 | 0.3125 | 1350 | 421.875
21 1059 | Measure 296 | 21 1059 Measure 296 - Financial Loss Quantification Service (Thuspaß) | 2021-07-01 | 2021-12-31 | 2021-07-19 | 7 | Thomas Thuspaß | metafinanz Informationssysteme GmbH | 6 | 0.75 | 1350 | 1012.5
21 1059 | Measure 296 | 21 1059 Measure 296 - Financial Loss Quantification Service (Thuspaß) | 2021-07-01 | 2021-12-31 | 2021-07-20 | 7 | Thomas Thuspaß | metafinanz Informationssysteme GmbH | 7 | 0.875 | 1350 | 1181.25
21 1059 | Measure 296 | 21 1059 Measure 296 - Financial Loss Quantification Service (Thuspaß) | 2021-07-01 | 2021-12-31 | 2021-07-21 | 7 | Thomas Thuspaß | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1350 | 675
21 1059 | Measure 296 | 21 1059 Measure 296 - Financial Loss Quantification Service (Thuspaß) | 2021-07-01 | 2021-12-31 | 2021-07-22 | 7 | Thomas Thuspaß | metafinanz Informationssysteme GmbH | 3 | 0.375 | 1350 | 506.25
21 1059 | Measure 296 | 21 1059 Measure 296 - Financial Loss Quantification Service (Thuspaß) | 2021-07-01 | 2021-12-31 | 2021-07-23 | 7 | Thomas Thuspaß | metafinanz Informationssysteme GmbH | 5 | 0.625 | 1350 | 843.75
21 1059 | Measure 296 | 21 1059 Measure 296 - Financial Loss Quantification Service (Thuspaß) | 2021-07-01 | 2021-12-31 | 2021-07-26 | 7 | Thomas Thuspaß | metafinanz Informationssysteme GmbH | 5 | 0.625 | 1350 | 843.75
21 1059 | Measure 296 | 21 1059 Measure 296 - Financial Loss Quantification Service (Thuspaß) | 2021-07-01 | 2021-12-31 | 2021-07-27 | 7 | Thomas Thuspaß | metafinanz Informationssysteme GmbH | 3.5 | 0.4375 | 1350 | 590.625
21 1059 | Measure 296 | 21 1059 Measure 296 - Financial Loss Quantification Service (Thuspaß) | 2021-07-01 | 2021-12-31 | 2021-07-28 | 7 | Thomas Thuspaß | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1350 | 675
21 1059 | Measure 296 | 21 1059 Measure 296 - Financial Loss Quantification Service (Thuspaß) | 2021-07-01 | 2021-12-31 | 2021-07-30 | 7 | Thomas Thuspaß | metafinanz Informationssysteme GmbH | 3 | 0.375 | 1350 | 506.25
21 1059 | Measure 296 | 21 1059 Measure 296 - Financial Loss Quantification Service (Thuspaß) | 2021-07-01 | 2021-12-31 | 2021-08-02 | 8 | Thomas Thuspaß | metafinanz Informationssysteme GmbH | 5.5 | 0.6875 | 1350 | 928.125
21 1059 | Measure 296 | 21 1059 Measure 296 - Financial Loss Quantification Service (Thuspaß) | 2021-07-01 | 2021-12-31 | 2021-08-03 | 8 | Thomas Thuspaß | metafinanz Informationssysteme GmbH | 5.5 | 0.6875 | 1350 | 928.125
21 1059 | Measure 296 | 21 1059 Measure 296 - Financial Loss Quantification Service (Thuspaß) | 2021-07-01 | 2021-12-31 | 2021-08-04 | 8 | Thomas Thuspaß | metafinanz Informationssysteme GmbH | 4.5 | 0.5625 | 1350 | 759.375
21 1059 | Measure 296 | 21 1059 Measure 296 - Financial Loss Quantification Service (Thuspaß) | 2021-07-01 | 2021-12-31 | 2021-08-05 | 8 | Thomas Thuspaß | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1350 | 675
21 1059 | Measure 296 | 21 1059 Measure 296 - Financial Loss Quantification Service (Thuspaß) | 2021-07-01 | 2021-12-31 | 2021-08-09 | 8 | Thomas Thuspaß | metafinanz Informationssysteme GmbH | 8 | 1 | 1350 | 1350
21 1059 | Measure 296 | 21 1059 Measure 296 - Financial Loss Quantification Service (Thuspaß) | 2021-07-01 | 2021-12-31 | 2021-08-10 | 8 | Thomas Thuspaß | metafinanz Informationssysteme GmbH | 7 | 0.875 | 1350 | 1181.25
21 1059 | Measure 296 | 21 1059 Measure 296 - Financial Loss Quantification Service (Thuspaß) | 2021-07-01 | 2021-12-31 | 2021-08-11 | 8 | Thomas Thuspaß | metafinanz Informationssysteme GmbH | 3 | 0.375 | 1350 | 506.25
21 1059 | Measure 296 | 21 1059 Measure 296 - Financial Loss Quantification Service (Thuspaß) | 2021-07-01 | 2021-12-31 | 2021-08-12 | 8 | Thomas Thuspaß | metafinanz Informationssysteme GmbH | 6 | 0.75 | 1350 | 1012.5
21 1059 | Measure 296 | 21 1059 Measure 296 - Financial Loss Quantification Service (Thuspaß) | 2021-07-01 | 2021-12-31 | 2021-08-13 | 8 | Thomas Thuspaß | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1350 | 675
21 1059 | Measure 296 | 21 1059 Measure 296 - Financial Loss Quantification Service (Thuspaß) | 2021-07-01 | 2021-12-31 | 2021-08-23 | 8 | Thomas Thuspaß | metafinanz Informationssysteme GmbH | 9 | 1.125 | 1350 | 1518.75
21 1059 | Measure 296 | 21 1059 Measure 296 - Financial Loss Quantification Service (Thuspaß) | 2021-07-01 | 2021-12-31 | 2021-08-24 | 8 | Thomas Thuspaß | metafinanz Informationssysteme GmbH | 7 | 0.875 | 1350 | 1181.25
21 1059 | Measure 296 | 21 1059 Measure 296 - Financial Loss Quantification Service (Thuspaß) | 2021-07-01 | 2021-12-31 | 2021-08-25 | 8 | Thomas Thuspaß | metafinanz Informationssysteme GmbH | 6 | 0.75 | 1350 | 1012.5
21 1059 | Measure 296 | 21 1059 Measure 296 - Financial Loss Quantification Service (Thuspaß) | 2021-07-01 | 2021-12-31 | 2021-08-26 | 8 | Thomas Thuspaß | metafinanz Informationssysteme GmbH | 6.5 | 0.8125 | 1350 | 1096.875
21 1059 | Measure 296 | 21 1059 Measure 296 - Financial Loss Quantification Service (Thuspaß) | 2021-07-01 | 2021-12-31 | 2021-08-27 | 8 | Thomas Thuspaß | metafinanz Informationssysteme GmbH | 3 | 0.375 | 1350 | 506.25
21 1059 | Measure 296 | 21 1059 Measure 296 - Financial Loss Quantification Service (Thuspaß) | 2021-07-01 | 2021-12-31 | 2021-08-30 | 8 | Thomas Thuspaß | metafinanz Informationssysteme GmbH | 5 | 0.625 | 1350 | 843.75
21 1059 | Measure 296 | 21 1059 Measure 296 - Financial Loss Quantification Service (Thuspaß) | 2021-07-01 | 2021-12-31 | 2021-08-31 | 8 | Thomas Thuspaß | metafinanz Informationssysteme GmbH | 5.5 | 0.6875 | 1350 | 928.125
21 1059 | Measure 296 | 21 1059 Measure 296 - Financial Loss Quantification Service (Thuspaß) | 2021-07-01 | 2021-12-31 | 2021-09-01 | 9 | Thomas Thuspaß | metafinanz Informationssysteme GmbH | 7 | 0.875 | 1350 | 1181.25
21 1059 | Measure 296 | 21 1059 Measure 296 - Financial Loss Quantification Service (Thuspaß) | 2021-07-01 | 2021-12-31 | 2021-09-02 | 9 | Thomas Thuspaß | metafinanz Informationssysteme GmbH | 7.5 | 0.9375 | 1350 | 1265.625
21 1059 | Measure 296 | 21 1059 Measure 296 - Financial Loss Quantification Service (Thuspaß) | 2021-07-01 | 2021-12-31 | 2021-09-03 | 9 | Thomas Thuspaß | metafinanz Informationssysteme GmbH | 6.5 | 0.8125 | 1350 | 1096.875
21 1059 | Measure 296 | 21 1059 Measure 296 - Financial Loss Quantification Service (Thuspaß) | 2021-07-01 | 2021-12-31 | 2021-09-06 | 9 | Thomas Thuspaß | metafinanz Informationssysteme GmbH | 5 | 0.625 | 1350 | 843.75
21 1059 | Measure 296 | 21 1059 Measure 296 - Financial Loss Quantification Service (Thuspaß) | 2021-07-01 | 2021-12-31 | 2021-09-07 | 9 | Thomas Thuspaß | metafinanz Informationssysteme GmbH | 3 | 0.375 | 1350 | 506.25
21 1059 | Measure 296 | 21 1059 Measure 296 - Financial Loss Quantification Service (Thuspaß) | 2021-07-01 | 2021-12-31 | 2021-09-08 | 9 | Thomas Thuspaß | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1350 | 675
21 1059 | Measure 296 | 21 1059 Measure 296 - Financial Loss Quantification Service (Thuspaß) | 2021-07-01 | 2021-12-31 | 2021-09-09 | 9 | Thomas Thuspaß | metafinanz Informationssysteme GmbH | 3 | 0.375 | 1350 | 506.25
21 1059 | Measure 296 | 21 1059 Measure 296 - Financial Loss Quantification Service (Thuspaß) | 2021-07-01 | 2021-12-31 | 2021-09-10 | 9 | Thomas Thuspaß | metafinanz Informationssysteme GmbH | 5.5 | 0.6875 | 1350 | 928.125
21 1059 | Measure 296 | 21 1059 Measure 296 - Financial Loss Quantification Service (Thuspaß) | 2021-07-01 | 2021-12-31 | 2021-09-13 | 9 | Thomas Thuspaß | metafinanz Informationssysteme GmbH | 8 | 1 | 1350 | 1350
21 1059 | Measure 296 | 21 1059 Measure 296 - Financial Loss Quantification Service (Thuspaß) | 2021-07-01 | 2021-12-31 | 2021-09-14 | 9 | Thomas Thuspaß | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1350 | 675
21 1059 | Measure 296 | 21 1059 Measure 296 - Financial Loss Quantification Service (Thuspaß) | 2021-07-01 | 2021-12-31 | 2021-09-15 | 9 | Thomas Thuspaß | metafinanz Informationssysteme GmbH | 8 | 1 | 1350 | 1350
21 1059 | Measure 296 | 21 1059 Measure 296 - Financial Loss Quantification Service (Thuspaß) | 2021-07-01 | 2021-12-31 | 2021-09-16 | 9 | Thomas Thuspaß | metafinanz Informationssysteme GmbH | 6 | 0.75 | 1350 | 1012.5
21 1059 | Measure 296 | 21 1059 Measure 296 - Financial Loss Quantification Service (Thuspaß) | 2021-07-01 | 2021-12-31 | 2021-09-20 | 9 | Thomas Thuspaß | metafinanz Informationssysteme GmbH | 5 | 0.625 | 1350 | 843.75
21 1059 | Measure 296 | 21 1059 Measure 296 - Financial Loss Quantification Service (Thuspaß) | 2021-07-01 | 2021-12-31 | 2021-09-21 | 9 | Thomas Thuspaß | metafinanz Informationssysteme GmbH | 6 | 0.75 | 1350 | 1012.5
21 1059 | Measure 296 | 21 1059 Measure 296 - Financial Loss Quantification Service (Thuspaß) | 2021-07-01 | 2021-12-31 | 2021-09-22 | 9 | Thomas Thuspaß | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1350 | 675
21 1059 | Measure 296 | 21 1059 Measure 296 - Financial Loss Quantification Service (Thuspaß) | 2021-07-01 | 2021-12-31 | 2021-09-23 | 9 | Thomas Thuspaß | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1350 | 675
21 1059 | Measure 296 | 21 1059 Measure 296 - Financial Loss Quantification Service (Thuspaß) | 2021-07-01 | 2021-12-31 | 2021-09-24 | 9 | Thomas Thuspaß | metafinanz Informationssysteme GmbH | 8 | 1 | 1350 | 1350
21 1059 | Measure 296 | 21 1059 Measure 296 - Financial Loss Quantification Service (Thuspaß) | 2021-07-01 | 2021-12-31 | 2021-09-27 | 9 | Thomas Thuspaß | metafinanz Informationssysteme GmbH | 7 | 0.875 | 1350 | 1181.25
21 1059 | Measure 296 | 21 1059 Measure 296 - Financial Loss Quantification Service (Thuspaß) | 2021-07-01 | 2021-12-31 | 2021-09-28 | 9 | Thomas Thuspaß | metafinanz Informationssysteme GmbH | 7 | 0.875 | 1350 | 1181.25
21 1059 | Measure 296 | 21 1059 Measure 296 - Financial Loss Quantification Service (Thuspaß) | 2021-07-01 | 2021-12-31 | 2021-09-29 | 9 | Thomas Thuspaß | metafinanz Informationssysteme GmbH | 5.5 | 0.6875 | 1350 | 928.125
21 1059 | Measure 296 | 21 1059 Measure 296 - Financial Loss Quantification Service (Thuspaß) | 2021-07-01 | 2021-12-31 | 2021-09-30 | 9 | Thomas Thuspaß | metafinanz Informationssysteme GmbH | 8 | 1 | 1350 | 1350
21 1059 | Measure 296 | 21 1059 Measure 296 - Financial Loss Quantification Service (Thuspaß) | 2021-07-01 | 2021-12-31 | 2021-10-01 | 10 | Thomas Thuspaß | metafinanz Informationssysteme GmbH | 7 | 0.875 | 1350 | 1181.25
21 1059 | Measure 296 | 21 1059 Measure 296 - Financial Loss Quantification Service (Thuspaß) | 2021-07-01 | 2021-12-31 | 2021-10-04 | 10 | Thomas Thuspaß | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1350 | 675
21 1059 | Measure 296 | 21 1059 Measure 296 - Financial Loss Quantification Service (Thuspaß) | 2021-07-01 | 2021-12-31 | 2021-10-05 | 10 | Thomas Thuspaß | metafinanz Informationssysteme GmbH | 4.5 | 0.5625 | 1350 | 759.375
21 1059 | Measure 296 | 21 1059 Measure 296 - Financial Loss Quantification Service (Thuspaß) | 2021-07-01 | 2021-12-31 | 2021-10-06 | 10 | Thomas Thuspaß | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1350 | 675
21 1059 | Measure 296 | 21 1059 Measure 296 - Financial Loss Quantification Service (Thuspaß) | 2021-07-01 | 2021-12-31 | 2021-10-07 | 10 | Thomas Thuspaß | metafinanz Informationssysteme GmbH | 7 | 0.875 | 1350 | 1181.25
21 1059 | Measure 296 | 21 1059 Measure 296 - Financial Loss Quantification Service (Thuspaß) | 2021-07-01 | 2021-12-31 | 2021-10-08 | 10 | Thomas Thuspaß | metafinanz Informationssysteme GmbH | 3 | 0.375 | 1350 | 506.25
21 1059 | Measure 296 | 21 1059 Measure 296 - Financial Loss Quantification Service (Thuspaß) | 2021-07-01 | 2021-12-31 | 2021-10-11 | 10 | Thomas Thuspaß | metafinanz Informationssysteme GmbH | 8 | 1 | 1350 | 1350
21 1059 | Measure 296 | 21 1059 Measure 296 - Financial Loss Quantification Service (Thuspaß) | 2021-07-01 | 2021-12-31 | 2021-10-12 | 10 | Thomas Thuspaß | metafinanz Informationssysteme GmbH | 8 | 1 | 1350 | 1350
21 1059 | Measure 296 | 21 1059 Measure 296 - Financial Loss Quantification Service (Thuspaß) | 2021-07-01 | 2021-12-31 | 2021-10-13 | 10 | Thomas Thuspaß | metafinanz Informationssysteme GmbH | 7 | 0.875 | 1350 | 1181.25
21 1059 | Measure 296 | 21 1059 Measure 296 - Financial Loss Quantification Service (Thuspaß) | 2021-07-01 | 2021-12-31 | 2021-10-14 | 10 | Thomas Thuspaß | metafinanz Informationssysteme GmbH | 7 | 0.875 | 1350 | 1181.25
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-07-01 | 7 | Marc Bochtler | metafinanz Informationssysteme GmbH | 8 | 1 | 1350 | 1350
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-07-02 | 7 | Marc Bochtler | metafinanz Informationssysteme GmbH | 8 | 1 | 1350 | 1350
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-07-05 | 7 | Thorsten Deckers | NTT DATA Deutschland GmbH | 3.5 | 0.4375 | 1570 | 686.875
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-07-05 | 7 | Marc Bochtler | metafinanz Informationssysteme GmbH | 8 | 1 | 1350 | 1350
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-07-06 | 7 | Marc Bochtler | metafinanz Informationssysteme GmbH | 8 | 1 | 1350 | 1350
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-07-07 | 7 | Thorsten Deckers | NTT DATA Deutschland GmbH | 3.5 | 0.4375 | 1570 | 686.875
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-07-07 | 7 | Marc Bochtler | metafinanz Informationssysteme GmbH | 8 | 1 | 1350 | 1350
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-07-08 | 7 | Marc Bochtler | metafinanz Informationssysteme GmbH | 8 | 1 | 1350 | 1350
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-07-09 | 7 | Marc Bochtler | metafinanz Informationssysteme GmbH | 8 | 1 | 1350 | 1350
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-07-12 | 7 | Robert Reti | NTT DATA Deutschland GmbH | 2 | 0.25 | 1570 | 392.5
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-07-12 | 7 | Thorsten Deckers | NTT DATA Deutschland GmbH | 2 | 0.25 | 1570 | 392.5
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-07-12 | 7 | Marc Bochtler | metafinanz Informationssysteme GmbH | 8 | 1 | 1350 | 1350
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-07-13 | 7 | Robert Reti | NTT DATA Deutschland GmbH | 4 | 0.5 | 1570 | 785
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-07-13 | 7 | Thorsten Deckers | NTT DATA Deutschland GmbH | 1.5 | 0.1875 | 1570 | 294.375
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-07-13 | 7 | Marc Bochtler | metafinanz Informationssysteme GmbH | 8 | 1 | 1350 | 1350
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-07-14 | 7 | Robert Reti | NTT DATA Deutschland GmbH | 1 | 0.125 | 1570 | 196.25
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-07-14 | 7 | Thorsten Deckers | NTT DATA Deutschland GmbH | 1 | 0.125 | 1570 | 196.25
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-07-14 | 7 | Marc Bochtler | metafinanz Informationssysteme GmbH | 8 | 1 | 1350 | 1350
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-07-15 | 7 | Robert Reti | NTT DATA Deutschland GmbH | 2 | 0.25 | 1570 | 392.5
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-07-15 | 7 | Thorsten Deckers | NTT DATA Deutschland GmbH | 3 | 0.375 | 1570 | 588.75
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-07-15 | 7 | Marc Bochtler | metafinanz Informationssysteme GmbH | 8 | 1 | 1350 | 1350
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-07-16 | 7 | Robert Reti | NTT DATA Deutschland GmbH | 4 | 0.5 | 1570 | 785
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-07-16 | 7 | Thorsten Deckers | NTT DATA Deutschland GmbH | 0.5 | 0.0625 | 1570 | 98.125
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-07-16 | 7 | Marc Bochtler | metafinanz Informationssysteme GmbH | 8 | 1 | 1350 | 1350
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-07-19 | 7 | Robert Reti | NTT DATA Deutschland GmbH | 1 | 0.125 | 1570 | 196.25
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-07-19 | 7 | Thorsten Deckers | NTT DATA Deutschland GmbH | 4.5 | 0.5625 | 1570 | 883.125
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-07-19 | 7 | Marc Bochtler | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1350 | 675
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-07-20 | 7 | Robert Reti | NTT DATA Deutschland GmbH | 1 | 0.125 | 1570 | 196.25
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-07-20 | 7 | Thorsten Deckers | NTT DATA Deutschland GmbH | 6.5 | 0.8125 | 1570 | 1275.625
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-07-20 | 7 | Marc Bochtler | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1350 | 675
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-07-21 | 7 | Robert Reti | NTT DATA Deutschland GmbH | 1 | 0.125 | 1570 | 196.25
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-07-21 | 7 | Thorsten Deckers | NTT DATA Deutschland GmbH | 6.5 | 0.8125 | 1570 | 1275.625
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-07-21 | 7 | Marc Bochtler | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1350 | 675
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-07-22 | 7 | Robert Reti | NTT DATA Deutschland GmbH | 1 | 0.125 | 1570 | 196.25
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-07-22 | 7 | Thorsten Deckers | NTT DATA Deutschland GmbH | 6.5 | 0.8125 | 1570 | 1275.625
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-07-22 | 7 | Marc Bochtler | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1350 | 675
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-07-23 | 7 | Robert Reti | NTT DATA Deutschland GmbH | 1 | 0.125 | 1570 | 196.25
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-07-23 | 7 | Thorsten Deckers | NTT DATA Deutschland GmbH | 4 | 0.5 | 1570 | 785
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-07-23 | 7 | Marc Bochtler | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1350 | 675
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-07-26 | 7 | Robert Reti | NTT DATA Deutschland GmbH | 4 | 0.5 | 1570 | 785
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-07-26 | 7 | Thorsten Deckers | NTT DATA Deutschland GmbH | 7 | 0.875 | 1570 | 1373.75
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-07-26 | 7 | Marc Bochtler | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1350 | 675
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-07-27 | 7 | Robert Reti | NTT DATA Deutschland GmbH | 4 | 0.5 | 1570 | 785
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-07-27 | 7 | Thorsten Deckers | NTT DATA Deutschland GmbH | 2 | 0.25 | 1570 | 392.5
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-07-27 | 7 | Marc Bochtler | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1350 | 675
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-07-28 | 7 | Robert Reti | NTT DATA Deutschland GmbH | 4 | 0.5 | 1570 | 785
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-07-28 | 7 | Thorsten Deckers | NTT DATA Deutschland GmbH | 4 | 0.5 | 1570 | 785
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-07-28 | 7 | Marc Bochtler | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1350 | 675
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-07-29 | 7 | Robert Reti | NTT DATA Deutschland GmbH | 4 | 0.5 | 1570 | 785
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-07-29 | 7 | Thorsten Deckers | NTT DATA Deutschland GmbH | 3 | 0.375 | 1570 | 588.75
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-07-29 | 7 | Marc Bochtler | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1350 | 675
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-07-30 | 7 | Marc Bochtler | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1350 | 675
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-08-02 | 8 | Robert Reti | NTT DATA Deutschland GmbH | 2 | 0.25 | 1570 | 392.5
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-08-02 | 8 | Thorsten Deckers | NTT DATA Deutschland GmbH | 6 | 0.75 | 1570 | 1177.5
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-08-02 | 8 | Marc Bochtler | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1350 | 675
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-08-02 | 8 | Yury Nikulin | metafinanz Informationssysteme GmbH | 8 | 1 | 1000 | 1000
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-08-03 | 8 | Robert Reti | NTT DATA Deutschland GmbH | 2 | 0.25 | 1570 | 392.5
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-08-03 | 8 | Thorsten Deckers | NTT DATA Deutschland GmbH | 6 | 0.75 | 1570 | 1177.5
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-08-03 | 8 | Marc Bochtler | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1350 | 675
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-08-04 | 8 | Robert Reti | NTT DATA Deutschland GmbH | 2 | 0.25 | 1570 | 392.5
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-08-04 | 8 | Thorsten Deckers | NTT DATA Deutschland GmbH | 5.5 | 0.6875 | 1570 | 1079.375
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-08-04 | 8 | Marc Bochtler | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1350 | 675
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-08-04 | 8 | Yury Nikulin | metafinanz Informationssysteme GmbH | 5 | 0.625 | 1000 | 625
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-08-05 | 8 | Robert Reti | NTT DATA Deutschland GmbH | 2 | 0.25 | 1570 | 392.5
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-08-05 | 8 | Thorsten Deckers | NTT DATA Deutschland GmbH | 1.5 | 0.1875 | 1570 | 294.375
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-08-05 | 8 | Marc Bochtler | metafinanz Informationssysteme GmbH | 5 | 0.625 | 1350 | 843.75
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-08-06 | 8 | Robert Reti | NTT DATA Deutschland GmbH | 1 | 0.125 | 1570 | 196.25
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-08-06 | 8 | Thorsten Deckers | NTT DATA Deutschland GmbH | 1.5 | 0.1875 | 1570 | 294.375
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-08-06 | 8 | Marc Bochtler | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1350 | 675
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-08-06 | 8 | Yury Nikulin | metafinanz Informationssysteme GmbH | 8 | 1 | 1000 | 1000
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-08-09 | 8 | Robert Reti | NTT DATA Deutschland GmbH | 2 | 0.25 | 1570 | 392.5
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-08-09 | 8 | Thorsten Deckers | NTT DATA Deutschland GmbH | 4.5 | 0.5625 | 1570 | 883.125
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-08-09 | 8 | Marc Bochtler | metafinanz Informationssysteme GmbH | 5 | 0.625 | 1350 | 843.75
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-08-10 | 8 | Robert Reti | NTT DATA Deutschland GmbH | 3 | 0.375 | 1570 | 588.75
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-08-10 | 8 | Thorsten Deckers | NTT DATA Deutschland GmbH | 6 | 0.75 | 1570 | 1177.5
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-08-10 | 8 | Marc Bochtler | metafinanz Informationssysteme GmbH | 5 | 0.625 | 1350 | 843.75
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-08-11 | 8 | Robert Reti | NTT DATA Deutschland GmbH | 2 | 0.25 | 1570 | 392.5
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-08-11 | 8 | Thorsten Deckers | NTT DATA Deutschland GmbH | 2 | 0.25 | 1570 | 392.5
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-08-11 | 8 | Marc Bochtler | metafinanz Informationssysteme GmbH | 5 | 0.625 | 1350 | 843.75
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-08-12 | 8 | Robert Reti | NTT DATA Deutschland GmbH | 1 | 0.125 | 1570 | 196.25
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-08-12 | 8 | Thorsten Deckers | NTT DATA Deutschland GmbH | 3 | 0.375 | 1570 | 588.75
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-08-13 | 8 | Robert Reti | NTT DATA Deutschland GmbH | 2 | 0.25 | 1570 | 392.5
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-08-13 | 8 | Thorsten Deckers | NTT DATA Deutschland GmbH | 2 | 0.25 | 1570 | 392.5
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-08-16 | 8 | Robert Reti | NTT DATA Deutschland GmbH | 3 | 0.375 | 1570 | 588.75
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-08-17 | 8 | Robert Reti | NTT DATA Deutschland GmbH | 4 | 0.5 | 1570 | 785
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-08-18 | 8 | Robert Reti | NTT DATA Deutschland GmbH | 3 | 0.375 | 1570 | 588.75
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-08-19 | 8 | Robert Reti | NTT DATA Deutschland GmbH | 2 | 0.25 | 1570 | 392.5
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-08-20 | 8 | Robert Reti | NTT DATA Deutschland GmbH | 1 | 0.125 | 1570 | 196.25
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-08-23 | 8 | Robert Reti | NTT DATA Deutschland GmbH | 3 | 0.375 | 1570 | 588.75
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-08-23 | 8 | Marc Bochtler | metafinanz Informationssysteme GmbH | 5 | 0.625 | 1350 | 843.75
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-08-23 | 8 | Yury Nikulin | metafinanz Informationssysteme GmbH | 8 | 1 | 1000 | 1000
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-08-24 | 8 | Robert Reti | NTT DATA Deutschland GmbH | 3 | 0.375 | 1570 | 588.75
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-08-24 | 8 | Marc Bochtler | metafinanz Informationssysteme GmbH | 5 | 0.625 | 1350 | 843.75
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-08-24 | 8 | Yury Nikulin | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1000 | 500
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-08-25 | 8 | Robert Reti | NTT DATA Deutschland GmbH | 3 | 0.375 | 1570 | 588.75
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-08-25 | 8 | Marc Bochtler | metafinanz Informationssysteme GmbH | 5 | 0.625 | 1350 | 843.75
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-08-25 | 8 | Yury Nikulin | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1000 | 500
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-08-26 | 8 | Robert Reti | NTT DATA Deutschland GmbH | 3 | 0.375 | 1570 | 588.75
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-08-26 | 8 | Marc Bochtler | metafinanz Informationssysteme GmbH | 5 | 0.625 | 1350 | 843.75
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-08-26 | 8 | Yury Nikulin | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1000 | 500
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-08-27 | 8 | Robert Reti | NTT DATA Deutschland GmbH | 3 | 0.375 | 1570 | 588.75
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-08-27 | 8 | Marc Bochtler | metafinanz Informationssysteme GmbH | 5 | 0.625 | 1350 | 843.75
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-08-27 | 8 | Yury Nikulin | metafinanz Informationssysteme GmbH | 8 | 1 | 1000 | 1000
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-08-30 | 8 | Robert Reti | NTT DATA Deutschland GmbH | 4 | 0.5 | 1570 | 785
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-08-30 | 8 | Thorsten Deckers | NTT DATA Deutschland GmbH | 4.5 | 0.5625 | 1570 | 883.125
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-08-30 | 8 | Marc Bochtler | metafinanz Informationssysteme GmbH | 5 | 0.625 | 1350 | 843.75
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-08-30 | 8 | Yury Nikulin | metafinanz Informationssysteme GmbH | 8 | 1 | 1000 | 1000
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-08-31 | 8 | Thorsten Deckers | NTT DATA Deutschland GmbH | 5.5 | 0.6875 | 1570 | 1079.375
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-08-31 | 8 | Marc Bochtler | metafinanz Informationssysteme GmbH | 5 | 0.625 | 1350 | 843.75
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-08-31 | 8 | Yury Nikulin | metafinanz Informationssysteme GmbH | 8 | 1 | 1000 | 1000
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-09-01 | 9 | Marc Bochtler | metafinanz Informationssysteme GmbH | 5 | 0.625 | 1350 | 843.75
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-09-01 | 9 | Yury Nikulin | metafinanz Informationssysteme GmbH | 8 | 1 | 1000 | 1000
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-09-02 | 9 | Claudio Cangiotti | BTO Forschung GmbH | 8 | 1 | 770 | 770
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-09-02 | 9 | Thorsten Deckers | NTT DATA Deutschland GmbH | 3 | 0.375 | 1570 | 588.75
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-09-02 | 9 | Marc Bochtler | metafinanz Informationssysteme GmbH | 5 | 0.625 | 1350 | 843.75
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-09-02 | 9 | Yury Nikulin | metafinanz Informationssysteme GmbH | 8 | 1 | 1000 | 1000
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-09-03 | 9 | Marc Bochtler | metafinanz Informationssysteme GmbH | 5 | 0.625 | 1350 | 843.75
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-09-03 | 9 | Yury Nikulin | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1000 | 500
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-09-06 | 9 | Claudio Cangiotti | BTO Forschung GmbH | 8 | 1 | 770 | 770
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-09-06 | 9 | Thorsten Deckers | NTT DATA Deutschland GmbH | 4 | 0.5 | 1570 | 785
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-09-06 | 9 | Marc Bochtler | metafinanz Informationssysteme GmbH | 5 | 0.625 | 1350 | 843.75
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-09-06 | 9 | Yury Nikulin | metafinanz Informationssysteme GmbH | 8 | 1 | 1000 | 1000
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-09-07 | 9 | Claudio Cangiotti | BTO Forschung GmbH | 8 | 1 | 770 | 770
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-09-07 | 9 | Thorsten Deckers | NTT DATA Deutschland GmbH | 2 | 0.25 | 1570 | 392.5
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-09-07 | 9 | Marc Bochtler | metafinanz Informationssysteme GmbH | 6 | 0.75 | 1350 | 1012.5
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-09-08 | 9 | Thorsten Deckers | NTT DATA Deutschland GmbH | 2 | 0.25 | 1570 | 392.5
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-09-08 | 9 | Marc Bochtler | metafinanz Informationssysteme GmbH | 5 | 0.625 | 1350 | 843.75
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-09-09 | 9 | Claudio Cangiotti | BTO Forschung GmbH | 8 | 1 | 770 | 770
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-09-09 | 9 | Robert Reti | NTT DATA Deutschland GmbH | 2 | 0.25 | 1570 | 392.5
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-09-09 | 9 | Thorsten Deckers | NTT DATA Deutschland GmbH | 2 | 0.25 | 1570 | 392.5
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-09-09 | 9 | Marc Bochtler | metafinanz Informationssysteme GmbH | 6 | 0.75 | 1350 | 1012.5
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-09-09 | 9 | Yury Nikulin | metafinanz Informationssysteme GmbH | 8 | 1 | 1000 | 1000
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-09-10 | 9 | Robert Reti | NTT DATA Deutschland GmbH | 4 | 0.5 | 1570 | 785
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-09-10 | 9 | Thorsten Deckers | NTT DATA Deutschland GmbH | 0.5 | 0.0625 | 1570 | 98.125
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-09-10 | 9 | Marc Bochtler | metafinanz Informationssysteme GmbH | 5 | 0.625 | 1350 | 843.75
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-09-10 | 9 | Yury Nikulin | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1000 | 500
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-09-13 | 9 | Claudio Cangiotti | BTO Forschung GmbH | 8 | 1 | 770 | 770
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-09-13 | 9 | Eldho George | Computer Futures, ein Geschäftszweig der SThree GmbH | 8 | 1 | 1100 | 1100
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-09-13 | 9 | Robert Reti | NTT DATA Deutschland GmbH | 4 | 0.5 | 1570 | 785
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-09-13 | 9 | Thorsten Deckers | NTT DATA Deutschland GmbH | 4 | 0.5 | 1570 | 785
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-09-13 | 9 | Marc Bochtler | metafinanz Informationssysteme GmbH | 5 | 0.625 | 1350 | 843.75
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-09-13 | 9 | Yury Nikulin | metafinanz Informationssysteme GmbH | 6 | 0.75 | 1000 | 750
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-09-14 | 9 | Claudio Cangiotti | BTO Forschung GmbH | 8 | 1 | 770 | 770
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-09-14 | 9 | Eldho George | Computer Futures, ein Geschäftszweig der SThree GmbH | 8 | 1 | 1100 | 1100
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-09-14 | 9 | Robert Reti | NTT DATA Deutschland GmbH | 4 | 0.5 | 1570 | 785
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-09-14 | 9 | Thorsten Deckers | NTT DATA Deutschland GmbH | 1 | 0.125 | 1570 | 196.25
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-09-14 | 9 | Marc Bochtler | metafinanz Informationssysteme GmbH | 5 | 0.625 | 1350 | 843.75
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-09-14 | 9 | Yury Nikulin | metafinanz Informationssysteme GmbH | 8 | 1 | 1000 | 1000
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-09-15 | 9 | Eldho George | Computer Futures, ein Geschäftszweig der SThree GmbH | 8 | 1 | 1100 | 1100
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-09-15 | 9 | Robert Reti | NTT DATA Deutschland GmbH | 1 | 0.125 | 1570 | 196.25
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-09-15 | 9 | Thorsten Deckers | NTT DATA Deutschland GmbH | 4 | 0.5 | 1570 | 785
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-09-15 | 9 | Marc Bochtler | metafinanz Informationssysteme GmbH | 5 | 0.625 | 1350 | 843.75
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-09-15 | 9 | Yury Nikulin | metafinanz Informationssysteme GmbH | 8 | 1 | 1000 | 1000
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-09-16 | 9 | Claudio Cangiotti | BTO Forschung GmbH | 8 | 1 | 770 | 770
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-09-16 | 9 | Eldho George | Computer Futures, ein Geschäftszweig der SThree GmbH | 8 | 1 | 1100 | 1100
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-09-16 | 9 | Robert Reti | NTT DATA Deutschland GmbH | 1 | 0.125 | 1570 | 196.25
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-09-16 | 9 | Thorsten Deckers | NTT DATA Deutschland GmbH | 1 | 0.125 | 1570 | 196.25
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-09-16 | 9 | Marc Bochtler | metafinanz Informationssysteme GmbH | 5 | 0.625 | 1350 | 843.75
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-09-16 | 9 | Yury Nikulin | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1000 | 500
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-09-17 | 9 | Eldho George | Computer Futures, ein Geschäftszweig der SThree GmbH | 8 | 1 | 1100 | 1100
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-09-17 | 9 | Robert Reti | NTT DATA Deutschland GmbH | 1 | 0.125 | 1570 | 196.25
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-09-17 | 9 | Thorsten Deckers | NTT DATA Deutschland GmbH | 4 | 0.5 | 1570 | 785
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-09-17 | 9 | Marc Bochtler | metafinanz Informationssysteme GmbH | 5 | 0.625 | 1350 | 843.75
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-09-17 | 9 | Yury Nikulin | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1000 | 500
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-09-20 | 9 | Claudio Cangiotti | BTO Forschung GmbH | 8 | 1 | 770 | 770
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-09-20 | 9 | Eldho George | Computer Futures, ein Geschäftszweig der SThree GmbH | 8 | 1 | 1100 | 1100
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-09-20 | 9 | Robert Reti | NTT DATA Deutschland GmbH | 4 | 0.5 | 1570 | 785
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-09-20 | 9 | Thorsten Deckers | NTT DATA Deutschland GmbH | 3 | 0.375 | 1570 | 588.75
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-09-20 | 9 | Marc Bochtler | metafinanz Informationssysteme GmbH | 5 | 0.625 | 1350 | 843.75
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-09-20 | 9 | Yury Nikulin | metafinanz Informationssysteme GmbH | 5 | 0.625 | 1000 | 625
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-09-21 | 9 | Claudio Cangiotti | BTO Forschung GmbH | 8 | 1 | 770 | 770
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-09-21 | 9 | Eldho George | Computer Futures, ein Geschäftszweig der SThree GmbH | 8 | 1 | 1100 | 1100
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-09-21 | 9 | Robert Reti | NTT DATA Deutschland GmbH | 2 | 0.25 | 1570 | 392.5
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-09-21 | 9 | Thorsten Deckers | NTT DATA Deutschland GmbH | 1 | 0.125 | 1570 | 196.25
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-09-21 | 9 | Marc Bochtler | metafinanz Informationssysteme GmbH | 5 | 0.625 | 1350 | 843.75
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-09-21 | 9 | Yury Nikulin | metafinanz Informationssysteme GmbH | 3 | 0.375 | 1000 | 375
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-09-22 | 9 | Eldho George | Computer Futures, ein Geschäftszweig der SThree GmbH | 8 | 1 | 1100 | 1100
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-09-22 | 9 | Robert Reti | NTT DATA Deutschland GmbH | 2 | 0.25 | 1570 | 392.5
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-09-22 | 9 | Thorsten Deckers | NTT DATA Deutschland GmbH | 1.5 | 0.1875 | 1570 | 294.375
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-09-22 | 9 | Yury Nikulin | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1000 | 500
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-09-23 | 9 | Claudio Cangiotti | BTO Forschung GmbH | 8 | 1 | 770 | 770
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-09-23 | 9 | Eldho George | Computer Futures, ein Geschäftszweig der SThree GmbH | 8 | 1 | 1100 | 1100
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-09-23 | 9 | Robert Reti | NTT DATA Deutschland GmbH | 2 | 0.25 | 1570 | 392.5
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-09-23 | 9 | Thorsten Deckers | NTT DATA Deutschland GmbH | 1 | 0.125 | 1570 | 196.25
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-09-24 | 9 | Eldho George | Computer Futures, ein Geschäftszweig der SThree GmbH | 8 | 1 | 1100 | 1100
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-09-24 | 9 | Robert Reti | NTT DATA Deutschland GmbH | 2 | 0.25 | 1570 | 392.5
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-09-24 | 9 | Thorsten Deckers | NTT DATA Deutschland GmbH | 3.5 | 0.4375 | 1570 | 686.875
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-09-24 | 9 | Yury Nikulin | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1000 | 500
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-09-27 | 9 | Claudio Cangiotti | BTO Forschung GmbH | 8 | 1 | 770 | 770
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-09-27 | 9 | Eldho George | Computer Futures, ein Geschäftszweig der SThree GmbH | 8 | 1 | 1100 | 1100
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-09-27 | 9 | Robert Reti | NTT DATA Deutschland GmbH | 4 | 0.5 | 1570 | 785
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-09-27 | 9 | Thorsten Deckers | NTT DATA Deutschland GmbH | 3 | 0.375 | 1570 | 588.75
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-09-27 | 9 | Yury Nikulin | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1000 | 500
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-09-28 | 9 | Claudio Cangiotti | BTO Forschung GmbH | 8 | 1 | 770 | 770
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-09-28 | 9 | Eldho George | Computer Futures, ein Geschäftszweig der SThree GmbH | 8 | 1 | 1100 | 1100
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-09-28 | 9 | Robert Reti | NTT DATA Deutschland GmbH | 2 | 0.25 | 1570 | 392.5
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-09-28 | 9 | Thorsten Deckers | NTT DATA Deutschland GmbH | 2 | 0.25 | 1570 | 392.5
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-09-28 | 9 | Yury Nikulin | metafinanz Informationssysteme GmbH | 5 | 0.625 | 1000 | 625
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-09-29 | 9 | Eldho George | Computer Futures, ein Geschäftszweig der SThree GmbH | 8 | 1 | 1100 | 1100
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-09-29 | 9 | Robert Reti | NTT DATA Deutschland GmbH | 2 | 0.25 | 1570 | 392.5
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-09-29 | 9 | Thorsten Deckers | NTT DATA Deutschland GmbH | 1 | 0.125 | 1570 | 196.25
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-09-30 | 9 | Claudio Cangiotti | BTO Forschung GmbH | 8 | 1 | 770 | 770
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-09-30 | 9 | Eldho George | Computer Futures, ein Geschäftszweig der SThree GmbH | 8 | 1 | 1100 | 1100
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-09-30 | 9 | Robert Reti | NTT DATA Deutschland GmbH | 2 | 0.25 | 1570 | 392.5
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-09-30 | 9 | Thorsten Deckers | NTT DATA Deutschland GmbH | 2 | 0.25 | 1570 | 392.5
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-09-30 | 9 | Yury Nikulin | metafinanz Informationssysteme GmbH | 2 | 0.25 | 1000 | 250
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-10-01 | 10 | Eldho George | Computer Futures, ein Geschäftszweig der SThree GmbH | 8 | 1 | 1100 | 1100
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-10-01 | 10 | Robert Reti | NTT DATA Deutschland GmbH | 2 | 0.25 | 1570 | 392.5
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-10-01 | 10 | Thorsten Deckers | NTT DATA Deutschland GmbH | 0.5 | 0.0625 | 1570 | 98.125
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-10-04 | 10 | Robert Reti | NTT DATA Deutschland GmbH | 1 | 0.125 | 1570 | 196.25
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-10-04 | 10 | Thorsten Deckers | NTT DATA Deutschland GmbH | 4 | 0.5 | 1570 | 785
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-10-04 | 10 | Marc Bochtler | metafinanz Informationssysteme GmbH | 6 | 0.75 | 1350 | 1012.5
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-10-05 | 10 | Robert Reti | NTT DATA Deutschland GmbH | 1 | 0.125 | 1570 | 196.25
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-10-05 | 10 | Thorsten Deckers | NTT DATA Deutschland GmbH | 2 | 0.25 | 1570 | 392.5
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-10-05 | 10 | Marc Bochtler | metafinanz Informationssysteme GmbH | 6 | 0.75 | 1350 | 1012.5
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-10-05 | 10 | Yury Nikulin | metafinanz Informationssysteme GmbH | 3 | 0.375 | 1000 | 375
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-10-06 | 10 | Robert Reti | NTT DATA Deutschland GmbH | 1 | 0.125 | 1570 | 196.25
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-10-06 | 10 | Thorsten Deckers | NTT DATA Deutschland GmbH | 2 | 0.25 | 1570 | 392.5
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-10-06 | 10 | Marc Bochtler | metafinanz Informationssysteme GmbH | 5 | 0.625 | 1350 | 843.75
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-10-06 | 10 | Yury Nikulin | metafinanz Informationssysteme GmbH | 5 | 0.625 | 1000 | 625
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-10-07 | 10 | Robert Reti | NTT DATA Deutschland GmbH | 1 | 0.125 | 1570 | 196.25
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-10-07 | 10 | Thorsten Deckers | NTT DATA Deutschland GmbH | 3 | 0.375 | 1570 | 588.75
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-10-07 | 10 | Marc Bochtler | metafinanz Informationssysteme GmbH | 5 | 0.625 | 1350 | 843.75
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-10-07 | 10 | Yury Nikulin | metafinanz Informationssysteme GmbH | 8 | 1 | 1000 | 1000
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-10-08 | 10 | Robert Reti | NTT DATA Deutschland GmbH | 1 | 0.125 | 1570 | 196.25
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-10-08 | 10 | Thorsten Deckers | NTT DATA Deutschland GmbH | 4.5 | 0.5625 | 1570 | 883.125
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-10-08 | 10 | Marc Bochtler | metafinanz Informationssysteme GmbH | 5 | 0.625 | 1350 | 843.75
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-10-08 | 10 | Yury Nikulin | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1000 | 500
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-10-11 | 10 | Robert Reti | NTT DATA Deutschland GmbH | 4 | 0.5 | 1570 | 785
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-10-11 | 10 | Marc Bochtler | metafinanz Informationssysteme GmbH | 5 | 0.625 | 1350 | 843.75
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-10-11 | 10 | Yury Nikulin | metafinanz Informationssysteme GmbH | 5 | 0.625 | 1000 | 625
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-10-12 | 10 | Robert Reti | NTT DATA Deutschland GmbH | 2 | 0.25 | 1570 | 392.5
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-10-12 | 10 | Marc Bochtler | metafinanz Informationssysteme GmbH | 5 | 0.625 | 1350 | 843.75
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-10-12 | 10 | Yury Nikulin | metafinanz Informationssysteme GmbH | 3 | 0.375 | 1000 | 375
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-10-13 | 10 | Robert Reti | NTT DATA Deutschland GmbH | 2 | 0.25 | 1570 | 392.5
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-10-13 | 10 | Marc Bochtler | metafinanz Informationssysteme GmbH | 6 | 0.75 | 1350 | 1012.5
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-10-13 | 10 | Yury Nikulin | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1000 | 500
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-10-14 | 10 | Robert Reti | NTT DATA Deutschland GmbH | 2 | 0.25 | 1570 | 392.5
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-10-14 | 10 | Marc Bochtler | metafinanz Informationssysteme GmbH | 5 | 0.625 | 1350 | 843.75
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-10-14 | 10 | Yury Nikulin | metafinanz Informationssysteme GmbH | 8 | 1 | 1000 | 1000
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-10-15 | 10 | Robert Reti | NTT DATA Deutschland GmbH | 2 | 0.25 | 1570 | 392.5
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-10-15 | 10 | Tobias Butz | Allianz Technology SE | 80 | 10 | 1300 | 13000
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-10-15 | 10 | Marc Bochtler | metafinanz Informationssysteme GmbH | 5 | 0.625 | 1350 | 843.75
21 1063 | Measure 275 | 21 1063 Measure 275 - Cloud Security Competence Center + Secret Management (divers) | 2021-07-01 | 2021-12-31 | 2021-10-15 | 10 | Yury Nikulin | metafinanz Informationssysteme GmbH | 8 | 1 | 1000 | 1000
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-07-01 | 7 | Jonathan Reynolds | metafinanz Informationssysteme GmbH | 5 | 0.625 | 1000 | 625
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-07-01 | 7 | Julia Netesa | metafinanz Informationssysteme GmbH | 1 | 0.125 | 1000 | 125
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-07-02 | 7 | Jonathan Reynolds | metafinanz Informationssysteme GmbH | 3 | 0.375 | 1000 | 375
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-07-02 | 7 | Julia Netesa | metafinanz Informationssysteme GmbH | 1 | 0.125 | 1000 | 125
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-07-02 | 7 | Samuel Hurst | metafinanz Informationssysteme GmbH | 5 | 0.625 | 1350 | 843.75
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-07-05 | 7 | Jonathan Reynolds | metafinanz Informationssysteme GmbH | 3 | 0.375 | 1000 | 375
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-07-05 | 7 | Julia Netesa | metafinanz Informationssysteme GmbH | 2 | 0.25 | 1000 | 250
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-07-05 | 7 | Samuel Hurst | metafinanz Informationssysteme GmbH | 5.75 | 0.71875 | 1350 | 970.3125
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-07-06 | 7 | Jonathan Reynolds | metafinanz Informationssysteme GmbH | 3 | 0.375 | 1000 | 375
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-07-06 | 7 | Julia Netesa | metafinanz Informationssysteme GmbH | 3 | 0.375 | 1000 | 375
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-07-06 | 7 | Samuel Hurst | metafinanz Informationssysteme GmbH | 7 | 0.875 | 1350 | 1181.25
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-07-07 | 7 | Jonathan Reynolds | metafinanz Informationssysteme GmbH | 3 | 0.375 | 1000 | 375
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-07-07 | 7 | Julia Netesa | metafinanz Informationssysteme GmbH | 2 | 0.25 | 1000 | 250
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-07-07 | 7 | Samuel Hurst | metafinanz Informationssysteme GmbH | 5.5 | 0.6875 | 1350 | 928.125
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-07-08 | 7 | Jonathan Reynolds | metafinanz Informationssysteme GmbH | 3 | 0.375 | 1000 | 375
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-07-08 | 7 | Julia Netesa | metafinanz Informationssysteme GmbH | 3 | 0.375 | 1000 | 375
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-07-09 | 7 | Jonathan Reynolds | metafinanz Informationssysteme GmbH | 3 | 0.375 | 1000 | 375
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-07-09 | 7 | Julia Netesa | metafinanz Informationssysteme GmbH | 1 | 0.125 | 1000 | 125
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-07-11 | 7 | Jonathan Reynolds | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1000 | 500
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-07-12 | 7 | Jonathan Reynolds | metafinanz Informationssysteme GmbH | 3 | 0.375 | 1000 | 375
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-07-12 | 7 | Julia Netesa | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1000 | 500
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-07-12 | 7 | Samuel Hurst | metafinanz Informationssysteme GmbH | 7.5 | 0.9375 | 1350 | 1265.625
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-07-13 | 7 | Jonathan Reynolds | metafinanz Informationssysteme GmbH | 3 | 0.375 | 1000 | 375
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-07-13 | 7 | Julia Netesa | metafinanz Informationssysteme GmbH | 3 | 0.375 | 1000 | 375
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-07-13 | 7 | Samuel Hurst | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1350 | 675
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-07-14 | 7 | Jonathan Reynolds | metafinanz Informationssysteme GmbH | 3 | 0.375 | 1000 | 375
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-07-14 | 7 | Julia Netesa | metafinanz Informationssysteme GmbH | 1 | 0.125 | 1000 | 125
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-07-14 | 7 | Samuel Hurst | metafinanz Informationssysteme GmbH | 6 | 0.75 | 1350 | 1012.5
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-07-15 | 7 | Jonathan Reynolds | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1000 | 500
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-07-15 | 7 | Julia Netesa | metafinanz Informationssysteme GmbH | 1 | 0.125 | 1000 | 125
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-07-15 | 7 | Samuel Hurst | metafinanz Informationssysteme GmbH | 2 | 0.25 | 1350 | 337.5
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-07-16 | 7 | Jonathan Reynolds | metafinanz Informationssysteme GmbH | 2 | 0.25 | 1000 | 250
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-07-16 | 7 | Julia Netesa | metafinanz Informationssysteme GmbH | 1 | 0.125 | 1000 | 125
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-07-16 | 7 | Samuel Hurst | metafinanz Informationssysteme GmbH | 5.5 | 0.6875 | 1350 | 928.125
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-07-17 | 7 | Jonathan Reynolds | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1000 | 500
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-07-19 | 7 | Jonathan Reynolds | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1000 | 500
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-07-19 | 7 | Julia Netesa | metafinanz Informationssysteme GmbH | 3 | 0.375 | 1000 | 375
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-07-19 | 7 | Samuel Hurst | metafinanz Informationssysteme GmbH | 4.25 | 0.53125 | 1350 | 717.1875
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-07-20 | 7 | Jonathan Reynolds | metafinanz Informationssysteme GmbH | 5 | 0.625 | 1000 | 625
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-07-20 | 7 | Julia Netesa | metafinanz Informationssysteme GmbH | 2 | 0.25 | 1000 | 250
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-07-20 | 7 | Samuel Hurst | metafinanz Informationssysteme GmbH | 7.25 | 0.90625 | 1350 | 1223.4375
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-07-21 | 7 | Frank Markussen | metafinanz Informationssysteme GmbH | 1.5 | 0.1875 | 1000 | 187.5
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-07-21 | 7 | Jonathan Reynolds | metafinanz Informationssysteme GmbH | 3 | 0.375 | 1000 | 375
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-07-21 | 7 | Julia Netesa | metafinanz Informationssysteme GmbH | 1 | 0.125 | 1000 | 125
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-07-21 | 7 | Samuel Hurst | metafinanz Informationssysteme GmbH | 7.25 | 0.90625 | 1350 | 1223.4375
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-07-22 | 7 | Jonathan Reynolds | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1000 | 500
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-07-22 | 7 | Julia Netesa | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1000 | 500
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-07-22 | 7 | Samuel Hurst | metafinanz Informationssysteme GmbH | 7.5 | 0.9375 | 1350 | 1265.625
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-07-23 | 7 | Frank Markussen | metafinanz Informationssysteme GmbH | 0.5 | 0.0625 | 1000 | 62.5
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-07-23 | 7 | Jonathan Reynolds | metafinanz Informationssysteme GmbH | 3 | 0.375 | 1000 | 375
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-07-23 | 7 | Julia Netesa | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1000 | 500
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-07-23 | 7 | Samuel Hurst | metafinanz Informationssysteme GmbH | 7.75 | 0.96875 | 1350 | 1307.8125
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-07-25 | 7 | Jonathan Reynolds | metafinanz Informationssysteme GmbH | 2 | 0.25 | 1000 | 250
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-07-26 | 7 | Jonathan Reynolds | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1000 | 500
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-07-26 | 7 | Julia Netesa | metafinanz Informationssysteme GmbH | 1 | 0.125 | 1000 | 125
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-07-26 | 7 | Samuel Hurst | metafinanz Informationssysteme GmbH | 2 | 0.25 | 1350 | 337.5
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-07-27 | 7 | Jonathan Reynolds | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1000 | 500
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-07-27 | 7 | Julia Netesa | metafinanz Informationssysteme GmbH | 1 | 0.125 | 1000 | 125
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-07-27 | 7 | Samuel Hurst | metafinanz Informationssysteme GmbH | 2.5 | 0.3125 | 1350 | 421.875
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-07-28 | 7 | Jonathan Reynolds | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1000 | 500
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-07-28 | 7 | Julia Netesa | metafinanz Informationssysteme GmbH | 1 | 0.125 | 1000 | 125
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-07-28 | 7 | Samuel Hurst | metafinanz Informationssysteme GmbH | 5.75 | 0.71875 | 1350 | 970.3125
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-07-29 | 7 | Jonathan Reynolds | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1000 | 500
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-07-29 | 7 | Julia Netesa | metafinanz Informationssysteme GmbH | 2 | 0.25 | 1000 | 250
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-07-29 | 7 | Samuel Hurst | metafinanz Informationssysteme GmbH | 2 | 0.25 | 1350 | 337.5
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-07-30 | 7 | Jonathan Reynolds | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1000 | 500
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-07-30 | 7 | Julia Netesa | metafinanz Informationssysteme GmbH | 1 | 0.125 | 1000 | 125
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-07-30 | 7 | Samuel Hurst | metafinanz Informationssysteme GmbH | 3.75 | 0.46875 | 1350 | 632.8125
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-08-02 | 8 | Jonathan Reynolds | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1000 | 500
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-08-02 | 8 | Julia Netesa | metafinanz Informationssysteme GmbH | 1 | 0.125 | 1000 | 125
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-08-02 | 8 | Samuel Hurst | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1350 | 675
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-08-05 | 8 | Jonathan Reynolds | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1000 | 500
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-08-05 | 8 | Samuel Hurst | metafinanz Informationssysteme GmbH | 5.25 | 0.65625 | 1350 | 885.9375
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-08-06 | 8 | Samuel Hurst | metafinanz Informationssysteme GmbH | 5 | 0.625 | 1350 | 843.75
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-08-09 | 8 | Samuel Hurst | metafinanz Informationssysteme GmbH | 7 | 0.875 | 1350 | 1181.25
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-08-10 | 8 | Anette Hettenkofer | metafinanz Informationssysteme GmbH | 1 | 0.125 | 1000 | 125
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-08-10 | 8 | Samuel Hurst | metafinanz Informationssysteme GmbH | 7.75 | 0.96875 | 1350 | 1307.8125
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-08-11 | 8 | Samuel Hurst | metafinanz Informationssysteme GmbH | 6.25 | 0.78125 | 1350 | 1054.6875
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-08-12 | 8 | Jonathan Reynolds | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1000 | 500
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-08-12 | 8 | Samuel Hurst | metafinanz Informationssysteme GmbH | 6.75 | 0.84375 | 1350 | 1139.0625
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-08-13 | 8 | Jonathan Reynolds | metafinanz Informationssysteme GmbH | 2 | 0.25 | 1000 | 250
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-08-13 | 8 | Samuel Hurst | metafinanz Informationssysteme GmbH | 7.25 | 0.90625 | 1350 | 1223.4375
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-08-16 | 8 | Samuel Hurst | metafinanz Informationssysteme GmbH | 8.75 | 1.0938 | 1350 | 1476.5625
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-08-17 | 8 | Samuel Hurst | metafinanz Informationssysteme GmbH | 5.75 | 0.71875 | 1350 | 970.3125
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-08-18 | 8 | Frank Markussen | metafinanz Informationssysteme GmbH | 1 | 0.125 | 1000 | 125
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-08-18 | 8 | Samuel Hurst | metafinanz Informationssysteme GmbH | 7.25 | 0.90625 | 1350 | 1223.4375
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-08-19 | 8 | Jonathan Reynolds | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1000 | 500
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-08-19 | 8 | Samuel Hurst | metafinanz Informationssysteme GmbH | 7 | 0.875 | 1350 | 1181.25
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-08-20 | 8 | Jonathan Reynolds | metafinanz Informationssysteme GmbH | 2 | 0.25 | 1000 | 250
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-08-20 | 8 | Samuel Hurst | metafinanz Informationssysteme GmbH | 3 | 0.375 | 1350 | 506.25
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-08-23 | 8 | Jonathan Reynolds | metafinanz Informationssysteme GmbH | 3 | 0.375 | 1000 | 375
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-08-23 | 8 | Samuel Hurst | metafinanz Informationssysteme GmbH | 8 | 1 | 1350 | 1350
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-08-24 | 8 | Jonathan Reynolds | metafinanz Informationssysteme GmbH | 3 | 0.375 | 1000 | 375
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-08-24 | 8 | Samuel Hurst | metafinanz Informationssysteme GmbH | 3.5 | 0.4375 | 1350 | 590.625
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-08-25 | 8 | Jonathan Reynolds | metafinanz Informationssysteme GmbH | 2 | 0.25 | 1000 | 250
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-08-26 | 8 | Jonathan Reynolds | metafinanz Informationssysteme GmbH | 2 | 0.25 | 1000 | 250
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-08-30 | 8 | Jonathan Reynolds | metafinanz Informationssysteme GmbH | 3 | 0.375 | 1000 | 375
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-08-31 | 8 | Jonathan Reynolds | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1000 | 500
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-09-01 | 9 | Kris Harms | SimplyVision GmbH | 8 | 1 | 1450 | 1450
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-09-01 | 9 | Jonathan Reynolds | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1000 | 500
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-09-02 | 9 | Kris Harms | SimplyVision GmbH | 9 | 1.125 | 1450 | 1631.25
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-09-02 | 9 | Nora von Schenckendorff | HipSquare GmbH | 5 | 0.625 | 1350 | 843.75
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-09-03 | 9 | Kris Harms | SimplyVision GmbH | 8 | 1 | 1450 | 1450
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-09-03 | 9 | Jonathan Reynolds | metafinanz Informationssysteme GmbH | 3 | 0.375 | 1000 | 375
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-09-04 | 9 | Kris Harms | SimplyVision GmbH | 5 | 0.625 | 1450 | 906.25
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-09-05 | 9 | Kris Harms | SimplyVision GmbH | 10 | 1.25 | 1450 | 1812.5
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-09-06 | 9 | Kris Harms | SimplyVision GmbH | 8 | 1 | 1450 | 1450
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-09-06 | 9 | Jonathan Reynolds | metafinanz Informationssysteme GmbH | 3 | 0.375 | 1000 | 375
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-09-07 | 9 | Kris Harms | SimplyVision GmbH | 10 | 1.25 | 1450 | 1812.5
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-09-07 | 9 | Nora von Schenckendorff | HipSquare GmbH | 8.25 | 1.0312 | 1350 | 1392.1875
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-09-08 | 9 | Kris Harms | SimplyVision GmbH | 10 | 1.25 | 1450 | 1812.5
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-09-08 | 9 | Nora von Schenckendorff | HipSquare GmbH | 8.75 | 1.0938 | 1350 | 1476.5625
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-09-08 | 9 | Frank Markussen | metafinanz Informationssysteme GmbH | 0.75 | 0.09375 | 1000 | 93.75
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-09-09 | 9 | Kris Harms | SimplyVision GmbH | 11 | 1.375 | 1450 | 1993.75
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-09-09 | 9 | Nora von Schenckendorff | HipSquare GmbH | 5.5 | 0.6875 | 1350 | 928.125
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-09-10 | 9 | Kris Harms | SimplyVision GmbH | 9 | 1.125 | 1450 | 1631.25
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-09-10 | 9 | Nora von Schenckendorff | HipSquare GmbH | 7.25 | 0.90625 | 1350 | 1223.4375
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-09-10 | 9 | Nora von Schenckendorff | HipSquare GmbH | 0.25 | 0.03125 | 1350 | 42.1875
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-09-11 | 9 | Kris Harms | SimplyVision GmbH | 10 | 1.25 | 1450 | 1812.5
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-09-12 | 9 | Kris Harms | SimplyVision GmbH | 2 | 0.25 | 1450 | 362.5
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-09-13 | 9 | Kris Harms | SimplyVision GmbH | 8 | 1 | 1450 | 1450
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-09-14 | 9 | Kris Harms | SimplyVision GmbH | 6 | 0.75 | 1450 | 1087.5
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-09-14 | 9 | Nora von Schenckendorff | HipSquare GmbH | 6.25 | 0.78125 | 1350 | 1054.6875
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-09-14 | 9 | Nora von Schenckendorff | HipSquare GmbH | 1 | 0.125 | 1350 | 168.75
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-09-15 | 9 | Jacqueline Tyc | Allianz Technology SE | 38 | 4.75 | 1200 | 5700
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-09-15 | 9 | Kris Harms | SimplyVision GmbH | 11 | 1.375 | 1450 | 1993.75
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-09-15 | 9 | Frank Markussen | metafinanz Informationssysteme GmbH | 0.5 | 0.0625 | 1000 | 62.5
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-09-15 | 9 | Samuel Hurst | metafinanz Informationssysteme GmbH | 5 | 0.625 | 1350 | 843.75
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-09-16 | 9 | Kris Harms | SimplyVision GmbH | 10 | 1.25 | 1450 | 1812.5
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-09-16 | 9 | Nora von Schenckendorff | HipSquare GmbH | 0.75 | 0.09375 | 1350 | 126.5625
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-09-16 | 9 | Samuel Hurst | metafinanz Informationssysteme GmbH | 2 | 0.25 | 1350 | 337.5
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-09-17 | 9 | Kris Harms | SimplyVision GmbH | 8 | 1 | 1450 | 1450
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-09-17 | 9 | Nora von Schenckendorff | HipSquare GmbH | 0.25 | 0.03125 | 1350 | 42.1875
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-09-20 | 9 | Kris Harms | SimplyVision GmbH | 8 | 1 | 1450 | 1450
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-09-20 | 9 | Samuel Hurst | metafinanz Informationssysteme GmbH | 2.5 | 0.3125 | 1350 | 421.875
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-09-21 | 9 | Kris Harms | SimplyVision GmbH | 10 | 1.25 | 1450 | 1812.5
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-09-21 | 9 | Samuel Hurst | metafinanz Informationssysteme GmbH | 3 | 0.375 | 1350 | 506.25
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-09-22 | 9 | Kris Harms | SimplyVision GmbH | 8 | 1 | 1450 | 1450
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-09-22 | 9 | Samuel Hurst | metafinanz Informationssysteme GmbH | 3 | 0.375 | 1350 | 506.25
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-09-23 | 9 | Kris Harms | SimplyVision GmbH | 8 | 1 | 1450 | 1450
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-09-23 | 9 | Samuel Hurst | metafinanz Informationssysteme GmbH | 8.25 | 1.0312 | 1350 | 1392.1875
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-09-24 | 9 | Kris Harms | SimplyVision GmbH | 7 | 0.875 | 1450 | 1268.75
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-09-24 | 9 | Samuel Hurst | metafinanz Informationssysteme GmbH | 8.5 | 1.0625 | 1350 | 1434.375
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-09-25 | 9 | Kris Harms | SimplyVision GmbH | 7 | 0.875 | 1450 | 1268.75
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-09-26 | 9 | Kris Harms | SimplyVision GmbH | 5 | 0.625 | 1450 | 906.25
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-09-27 | 9 | Kris Harms | SimplyVision GmbH | 8.5 | 1.0625 | 1450 | 1540.625
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-09-27 | 9 | Nora von Schenckendorff | HipSquare GmbH | 0.5 | 0.0625 | 1350 | 84.375
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-09-27 | 9 | Frank Markussen | metafinanz Informationssysteme GmbH | 0.5 | 0.0625 | 1000 | 62.5
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-09-27 | 9 | Samuel Hurst | metafinanz Informationssysteme GmbH | 5.75 | 0.71875 | 1350 | 970.3125
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-09-28 | 9 | Kris Harms | SimplyVision GmbH | 7 | 0.875 | 1450 | 1268.75
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-09-28 | 9 | Samuel Hurst | metafinanz Informationssysteme GmbH | 5 | 0.625 | 1350 | 843.75
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-09-29 | 9 | Kris Harms | SimplyVision GmbH | 9 | 1.125 | 1450 | 1631.25
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-09-29 | 9 | Samuel Hurst | metafinanz Informationssysteme GmbH | 6 | 0.75 | 1350 | 1012.5
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-09-30 | 9 | Kris Harms | SimplyVision GmbH | 9 | 1.125 | 1450 | 1631.25
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-10-01 | 10 | Kris Harms | SimplyVision GmbH | 6.5 | 0.8125 | 1450 | 1178.125
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-10-01 | 10 | Frank Markussen | metafinanz Informationssysteme GmbH | 3 | 0.375 | 1000 | 375
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-10-02 | 10 | Kris Harms | SimplyVision GmbH | 9 | 1.125 | 1450 | 1631.25
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-10-04 | 10 | Kris Harms | SimplyVision GmbH | 8 | 1 | 1450 | 1450
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-10-04 | 10 | Frank Markussen | metafinanz Informationssysteme GmbH | 1 | 0.125 | 1000 | 125
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-10-04 | 10 | Samuel Hurst | metafinanz Informationssysteme GmbH | 7.5 | 0.9375 | 1350 | 1265.625
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-10-05 | 10 | Kris Harms | SimplyVision GmbH | 10 | 1.25 | 1450 | 1812.5
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-10-05 | 10 | Frank Markussen | metafinanz Informationssysteme GmbH | 1 | 0.125 | 1000 | 125
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-10-05 | 10 | Samuel Hurst | metafinanz Informationssysteme GmbH | 7.75 | 0.96875 | 1350 | 1307.8125
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-10-06 | 10 | Kris Harms | SimplyVision GmbH | 9 | 1.125 | 1450 | 1631.25
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-10-06 | 10 | Samuel Hurst | metafinanz Informationssysteme GmbH | 9.25 | 1.1562 | 1350 | 1560.9375
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-10-07 | 10 | Kris Harms | SimplyVision GmbH | 8 | 1 | 1450 | 1450
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-10-07 | 10 | Samuel Hurst | metafinanz Informationssysteme GmbH | 8 | 1 | 1350 | 1350
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-10-08 | 10 | Kris Harms | SimplyVision GmbH | 8 | 1 | 1450 | 1450
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-10-08 | 10 | Samuel Hurst | metafinanz Informationssysteme GmbH | 6.5 | 0.8125 | 1350 | 1096.875
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-10-10 | 10 | Kris Harms | SimplyVision GmbH | 3 | 0.375 | 1450 | 543.75
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-10-11 | 10 | Kris Harms | SimplyVision GmbH | 5 | 0.625 | 1450 | 906.25
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-10-11 | 10 | Frank Markussen | metafinanz Informationssysteme GmbH | 0.5 | 0.0625 | 1000 | 62.5
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-10-11 | 10 | Samuel Hurst | metafinanz Informationssysteme GmbH | 8 | 1 | 1350 | 1350
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-10-12 | 10 | Kris Harms | SimplyVision GmbH | 6 | 0.75 | 1450 | 1087.5
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-10-12 | 10 | Frank Markussen | metafinanz Informationssysteme GmbH | 0.75 | 0.09375 | 1000 | 93.75
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-10-12 | 10 | Samuel Hurst | metafinanz Informationssysteme GmbH | 8.75 | 1.0938 | 1350 | 1476.5625
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-10-13 | 10 | Kris Harms | SimplyVision GmbH | 5 | 0.625 | 1450 | 906.25
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-10-13 | 10 | Samuel Hurst | metafinanz Informationssysteme GmbH | 8 | 1 | 1350 | 1350
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-10-14 | 10 | Kris Harms | SimplyVision GmbH | 4 | 0.5 | 1450 | 725
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-10-14 | 10 | Samuel Hurst | metafinanz Informationssysteme GmbH | 8.25 | 1.0312 | 1350 | 1392.1875
21 1068 | Measure 300 | 21 1068 Measure 300 - Metrics phase @WeProtect scale up on skills (diverse) | 2021-07-01 | 2021-12-31 | 2021-10-15 | 10 | Kris Harms | SimplyVision GmbH | 1 | 0.125 | 1450 | 181.25
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-07-16 | 7 | Sanat Gautam | metafinanz Informationssysteme GmbH | 2 | 0.25 | 1000 | 250
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-07-19 | 7 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 1 | 0.125 | 1350 | 168.75
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-07-19 | 7 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 2.5 | 0.3125 | 1350 | 421.875
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-07-19 | 7 | Nadine Butzhammer | metafinanz Informationssysteme GmbH | 0.5 | 0.0625 | 1000 | 62.5
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-07-20 | 7 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 0.5 | 0.0625 | 1350 | 84.375
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-07-20 | 7 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 3.25 | 0.40625 | 1350 | 548.4375
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-07-20 | 7 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 2.75 | 0.34375 | 1350 | 464.0625
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-07-21 | 7 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 6.25 | 0.78125 | 1350 | 1054.6875
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-07-21 | 7 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 1.75 | 0.21875 | 1350 | 295.3125
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-07-21 | 7 | Jade Poteat | metafinanz Informationssysteme GmbH | 0.5 | 0.0625 | 1000 | 62.5
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-07-22 | 7 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 8.25 | 1.0312 | 1350 | 1392.1875
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-07-22 | 7 | Jade Poteat | metafinanz Informationssysteme GmbH | 1 | 0.125 | 1000 | 125
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-07-22 | 7 | Nadine Butzhammer | metafinanz Informationssysteme GmbH | 2 | 0.25 | 1000 | 250
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-07-23 | 7 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 1 | 0.125 | 1350 | 168.75
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-07-23 | 7 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 4.75 | 0.59375 | 1350 | 801.5625
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-07-26 | 7 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 1.25 | 0.15625 | 1350 | 210.9375
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-07-26 | 7 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 0.75 | 0.09375 | 1350 | 126.5625
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-07-26 | 7 | Jade Poteat | metafinanz Informationssysteme GmbH | 0.5 | 0.0625 | 1000 | 62.5
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-07-26 | 7 | Sanat Gautam | metafinanz Informationssysteme GmbH | 2 | 0.25 | 1000 | 250
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-07-27 | 7 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 8.25 | 1.0312 | 1350 | 1392.1875
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-07-27 | 7 | Jade Poteat | metafinanz Informationssysteme GmbH | 3 | 0.375 | 1000 | 375
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-07-28 | 7 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 2.75 | 0.34375 | 1350 | 464.0625
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-07-28 | 7 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 3 | 0.375 | 1350 | 506.25
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-07-28 | 7 | Jade Poteat | metafinanz Informationssysteme GmbH | 3 | 0.375 | 1000 | 375
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-07-28 | 7 | Sanat Gautam | metafinanz Informationssysteme GmbH | 1 | 0.125 | 1000 | 125
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-07-29 | 7 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 0.5 | 0.0625 | 1350 | 84.375
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-07-29 | 7 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 0.5 | 0.0625 | 1350 | 84.375
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-07-29 | 7 | Jade Poteat | metafinanz Informationssysteme GmbH | 2.5 | 0.3125 | 1000 | 312.5
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-07-29 | 7 | Sanat Gautam | metafinanz Informationssysteme GmbH | 2 | 0.25 | 1000 | 250
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-07-30 | 7 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 1 | 0.125 | 1350 | 168.75
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-07-30 | 7 | Sanat Gautam | metafinanz Informationssysteme GmbH | 2 | 0.25 | 1000 | 250
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-08-02 | 8 | Daniel Wörner | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1000 | 500
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-08-02 | 8 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 0.75 | 0.09375 | 1350 | 126.5625
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-08-02 | 8 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 1.5 | 0.1875 | 1350 | 253.125
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-08-02 | 8 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 0.5 | 0.0625 | 1350 | 84.375
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-08-02 | 8 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 3.25 | 0.40625 | 1350 | 548.4375
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-08-02 | 8 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 0.5 | 0.0625 | 1350 | 84.375
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-08-02 | 8 | Jade Poteat | metafinanz Informationssysteme GmbH | 1.5 | 0.1875 | 1000 | 187.5
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-08-03 | 8 | Daniel Wörner | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1000 | 500
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-08-03 | 8 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 1.5 | 0.1875 | 1350 | 253.125
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-08-03 | 8 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 0.5 | 0.0625 | 1350 | 84.375
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-08-03 | 8 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 0.75 | 0.09375 | 1350 | 126.5625
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-08-03 | 8 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 2.25 | 0.28125 | 1350 | 379.6875
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-08-03 | 8 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 1.5 | 0.1875 | 1350 | 253.125
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-08-03 | 8 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 1.75 | 0.21875 | 1350 | 295.3125
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-08-03 | 8 | Jade Poteat | metafinanz Informationssysteme GmbH | 1 | 0.125 | 1000 | 125
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-08-04 | 8 | Daniel Wörner | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1000 | 500
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-08-04 | 8 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 1 | 0.125 | 1350 | 168.75
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-08-04 | 8 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 0.5 | 0.0625 | 1350 | 84.375
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-08-04 | 8 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 0.5 | 0.0625 | 1350 | 84.375
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-08-04 | 8 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 0.75 | 0.09375 | 1350 | 126.5625
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-08-04 | 8 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 1.25 | 0.15625 | 1350 | 210.9375
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-08-04 | 8 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 0.75 | 0.09375 | 1350 | 126.5625
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-08-04 | 8 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 1.25 | 0.15625 | 1350 | 210.9375
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-08-04 | 8 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 2 | 0.25 | 1350 | 337.5
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-08-04 | 8 | Jade Poteat | metafinanz Informationssysteme GmbH | 0.5 | 0.0625 | 1000 | 62.5
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-08-05 | 8 | Daniel Wörner | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1000 | 500
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-08-05 | 8 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 0.5 | 0.0625 | 1350 | 84.375
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-08-05 | 8 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 0.5 | 0.0625 | 1350 | 84.375
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-08-05 | 8 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 1.5 | 0.1875 | 1350 | 253.125
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-08-05 | 8 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 1 | 0.125 | 1350 | 168.75
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-08-05 | 8 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 0.5 | 0.0625 | 1350 | 84.375
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-08-05 | 8 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 1.5 | 0.1875 | 1350 | 253.125
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-08-05 | 8 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 0.5 | 0.0625 | 1350 | 84.375
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-08-05 | 8 | Jade Poteat | metafinanz Informationssysteme GmbH | 0.5 | 0.0625 | 1000 | 62.5
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-08-06 | 8 | Daniel Wörner | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1000 | 500
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-08-09 | 8 | Daniel Wörner | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1000 | 500
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-08-10 | 8 | Daniel Wörner | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1000 | 500
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-08-10 | 8 | Jade Poteat | metafinanz Informationssysteme GmbH | 2 | 0.25 | 1000 | 250
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-08-11 | 8 | Daniel Wörner | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1000 | 500
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-08-11 | 8 | Jade Poteat | metafinanz Informationssysteme GmbH | 1 | 0.125 | 1000 | 125
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-08-12 | 8 | Daniel Wörner | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1000 | 500
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-08-12 | 8 | Jade Poteat | metafinanz Informationssysteme GmbH | 2 | 0.25 | 1000 | 250
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-08-13 | 8 | Daniel Wörner | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1000 | 500
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-08-13 | 8 | Jade Poteat | metafinanz Informationssysteme GmbH | 2 | 0.25 | 1000 | 250
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-08-16 | 8 | Daniel Wörner | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1000 | 500
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-08-16 | 8 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 0.5 | 0.0625 | 1350 | 84.375
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-08-16 | 8 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 1.5 | 0.1875 | 1350 | 253.125
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-08-16 | 8 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 3 | 0.375 | 1350 | 506.25
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-08-16 | 8 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 0.25 | 0.03125 | 1350 | 42.1875
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-08-16 | 8 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 2.5 | 0.3125 | 1350 | 421.875
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-08-16 | 8 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 0.5 | 0.0625 | 1350 | 84.375
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-08-17 | 8 | Daniel Wörner | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1000 | 500
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-08-17 | 8 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 1 | 0.125 | 1350 | 168.75
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-08-17 | 8 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 1.25 | 0.15625 | 1350 | 210.9375
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-08-17 | 8 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 0.25 | 0.03125 | 1350 | 42.1875
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-08-17 | 8 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 0.75 | 0.09375 | 1350 | 126.5625
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-08-17 | 8 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 3.75 | 0.46875 | 1350 | 632.8125
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-08-17 | 8 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 1 | 0.125 | 1350 | 168.75
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-08-18 | 8 | Daniel Wörner | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1000 | 500
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-08-18 | 8 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 1.25 | 0.15625 | 1350 | 210.9375
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-08-18 | 8 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 4.75 | 0.59375 | 1350 | 801.5625
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-08-18 | 8 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 0.5 | 0.0625 | 1350 | 84.375
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-08-18 | 8 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 1.5 | 0.1875 | 1350 | 253.125
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-08-18 | 8 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 0.5 | 0.0625 | 1350 | 84.375
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-08-19 | 8 | Daniel Wörner | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1000 | 500
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-08-19 | 8 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 2.5 | 0.3125 | 1350 | 421.875
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-08-19 | 8 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 3.25 | 0.40625 | 1350 | 548.4375
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-08-19 | 8 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 1.75 | 0.21875 | 1350 | 295.3125
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-08-19 | 8 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 0.5 | 0.0625 | 1350 | 84.375
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-08-20 | 8 | Daniel Wörner | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1000 | 500
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-08-20 | 8 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 1 | 0.125 | 1350 | 168.75
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-08-20 | 8 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 0.75 | 0.09375 | 1350 | 126.5625
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-08-20 | 8 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 2.25 | 0.28125 | 1350 | 379.6875
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-08-20 | 8 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 0.25 | 0.03125 | 1350 | 42.1875
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-08-20 | 8 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 1.25 | 0.15625 | 1350 | 210.9375
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-08-20 | 8 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 0.75 | 0.09375 | 1350 | 126.5625
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-08-20 | 8 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 1.75 | 0.21875 | 1350 | 295.3125
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-08-23 | 8 | Daniel Wörner | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1000 | 500
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-08-23 | 8 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 0.75 | 0.09375 | 1350 | 126.5625
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-08-23 | 8 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 0.5 | 0.0625 | 1350 | 84.375
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-08-23 | 8 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 0.75 | 0.09375 | 1350 | 126.5625
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-08-23 | 8 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 1.25 | 0.15625 | 1350 | 210.9375
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-08-23 | 8 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 0.75 | 0.09375 | 1350 | 126.5625
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-08-23 | 8 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 0.75 | 0.09375 | 1350 | 126.5625
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-08-23 | 8 | Jade Poteat | metafinanz Informationssysteme GmbH | 1 | 0.125 | 1000 | 125
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-08-24 | 8 | Daniel Wörner | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1000 | 500
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-08-25 | 8 | Daniel Wörner | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1000 | 500
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-08-26 | 8 | Daniel Wörner | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1000 | 500
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-08-26 | 8 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 0.75 | 0.09375 | 1350 | 126.5625
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-08-27 | 8 | Daniel Wörner | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1000 | 500
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-08-27 | 8 | Jade Poteat | metafinanz Informationssysteme GmbH | 2 | 0.25 | 1000 | 250
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-08-30 | 8 | Daniel Wörner | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1000 | 500
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-08-30 | 8 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 0.5 | 0.0625 | 1350 | 84.375
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-08-30 | 8 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 3.75 | 0.46875 | 1350 | 632.8125
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-08-30 | 8 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 1.5 | 0.1875 | 1350 | 253.125
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-08-30 | 8 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 0.75 | 0.09375 | 1350 | 126.5625
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-08-30 | 8 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 0.5 | 0.0625 | 1350 | 84.375
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-08-30 | 8 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 0.5 | 0.0625 | 1350 | 84.375
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-08-30 | 8 | Jade Poteat | metafinanz Informationssysteme GmbH | 3 | 0.375 | 1000 | 375
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-08-31 | 8 | Daniel Wörner | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1000 | 500
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-08-31 | 8 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 0.5 | 0.0625 | 1350 | 84.375
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-08-31 | 8 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 1.5 | 0.1875 | 1350 | 253.125
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-08-31 | 8 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 3.25 | 0.40625 | 1350 | 548.4375
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-08-31 | 8 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 2.75 | 0.34375 | 1350 | 464.0625
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-08-31 | 8 | Jade Poteat | metafinanz Informationssysteme GmbH | 1 | 0.125 | 1000 | 125
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-08-31 | 8 | Sanat Gautam | metafinanz Informationssysteme GmbH | 2 | 0.25 | 1000 | 250
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-09-01 | 9 | Daniel Wörner | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1000 | 500
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-09-01 | 9 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 5.75 | 0.71875 | 1350 | 970.3125
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-09-01 | 9 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 1 | 0.125 | 1350 | 168.75
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-09-02 | 9 | Daniel Wörner | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1000 | 500
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-09-03 | 9 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 0.5 | 0.0625 | 1350 | 84.375
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-09-03 | 9 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 8.75 | 1.0938 | 1350 | 1476.5625
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-09-06 | 9 | Daniel Wörner | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1000 | 500
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-09-06 | 9 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 8 | 1 | 1350 | 1350
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-09-06 | 9 | Jade Poteat | metafinanz Informationssysteme GmbH | 1 | 0.125 | 1000 | 125
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-09-06 | 9 | Sanat Gautam | metafinanz Informationssysteme GmbH | 4.5 | 0.5625 | 1000 | 562.5
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-09-07 | 9 | Daniel Wörner | metafinanz Informationssysteme GmbH | 5 | 0.625 | 1000 | 625
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-09-07 | 9 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 0.5 | 0.0625 | 1350 | 84.375
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-09-07 | 9 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 7.75 | 0.96875 | 1350 | 1307.8125
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-09-07 | 9 | Jade Poteat | metafinanz Informationssysteme GmbH | 2 | 0.25 | 1000 | 250
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-09-08 | 9 | Daniel Wörner | metafinanz Informationssysteme GmbH | 5 | 0.625 | 1000 | 625
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-09-08 | 9 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 3.5 | 0.4375 | 1350 | 590.625
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-09-08 | 9 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 0.5 | 0.0625 | 1350 | 84.375
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-09-08 | 9 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 1 | 0.125 | 1350 | 168.75
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-09-09 | 9 | Daniel Wörner | metafinanz Informationssysteme GmbH | 5 | 0.625 | 1000 | 625
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-09-09 | 9 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 6.75 | 0.84375 | 1350 | 1139.0625
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-09-09 | 9 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 1 | 0.125 | 1350 | 168.75
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-09-09 | 9 | Jade Poteat | metafinanz Informationssysteme GmbH | 2 | 0.25 | 1000 | 250
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-09-10 | 9 | Daniel Wörner | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1000 | 500
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-09-10 | 9 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 8 | 1 | 1350 | 1350
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-09-10 | 9 | Jade Poteat | metafinanz Informationssysteme GmbH | 1 | 0.125 | 1000 | 125
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-09-13 | 9 | Daniel Wörner | metafinanz Informationssysteme GmbH | 6 | 0.75 | 1000 | 750
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-09-13 | 9 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 7.75 | 0.96875 | 1350 | 1307.8125
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-09-14 | 9 | Daniel Wörner | metafinanz Informationssysteme GmbH | 6 | 0.75 | 1000 | 750
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-09-14 | 9 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 1 | 0.125 | 1350 | 168.75
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-09-14 | 9 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 1 | 0.125 | 1350 | 168.75
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-09-14 | 9 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 5.75 | 0.71875 | 1350 | 970.3125
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-09-14 | 9 | Sanat Gautam | metafinanz Informationssysteme GmbH | 5 | 0.625 | 1000 | 625
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-09-15 | 9 | Daniel Wörner | metafinanz Informationssysteme GmbH | 6 | 0.75 | 1000 | 750
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-09-15 | 9 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 0.5 | 0.0625 | 1350 | 84.375
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-09-15 | 9 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 1 | 0.125 | 1350 | 168.75
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-09-15 | 9 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 3.25 | 0.40625 | 1350 | 548.4375
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-09-15 | 9 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 2 | 0.25 | 1350 | 337.5
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-09-15 | 9 | Sanat Gautam | metafinanz Informationssysteme GmbH | 6 | 0.75 | 1000 | 750
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-09-16 | 9 | Daniel Wörner | metafinanz Informationssysteme GmbH | 6 | 0.75 | 1000 | 750
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-09-16 | 9 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 6.75 | 0.84375 | 1350 | 1139.0625
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-09-16 | 9 | Sanat Gautam | metafinanz Informationssysteme GmbH | 3 | 0.375 | 1000 | 375
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-09-17 | 9 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1350 | 675
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-09-20 | 9 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 6.5 | 0.8125 | 1350 | 1096.875
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-09-20 | 9 | Jade Poteat | metafinanz Informationssysteme GmbH | 2 | 0.25 | 1000 | 250
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-09-20 | 9 | Sanat Gautam | metafinanz Informationssysteme GmbH | 6 | 0.75 | 1000 | 750
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-09-21 | 9 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 0.5 | 0.0625 | 1350 | 84.375
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-09-21 | 9 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 7.75 | 0.96875 | 1350 | 1307.8125
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-09-21 | 9 | Jade Poteat | metafinanz Informationssysteme GmbH | 2 | 0.25 | 1000 | 250
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-09-21 | 9 | Sanat Gautam | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1000 | 500
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-09-22 | 9 | Daniel Wörner | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1000 | 500
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-09-22 | 9 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 1 | 0.125 | 1350 | 168.75
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-09-22 | 9 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 7 | 0.875 | 1350 | 1181.25
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-09-22 | 9 | Jade Poteat | metafinanz Informationssysteme GmbH | 2 | 0.25 | 1000 | 250
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-09-22 | 9 | Sanat Gautam | metafinanz Informationssysteme GmbH | 6 | 0.75 | 1000 | 750
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-09-23 | 9 | Daniel Wörner | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1000 | 500
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-09-23 | 9 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 8.25 | 1.0312 | 1350 | 1392.1875
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-09-23 | 9 | Jade Poteat | metafinanz Informationssysteme GmbH | 2 | 0.25 | 1000 | 250
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-09-23 | 9 | Sanat Gautam | metafinanz Informationssysteme GmbH | 6 | 0.75 | 1000 | 750
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-09-24 | 9 | Daniel Wörner | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1000 | 500
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-09-24 | 9 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 0.5 | 0.0625 | 1350 | 84.375
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-09-24 | 9 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 0.5 | 0.0625 | 1350 | 84.375
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-09-24 | 9 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 0.5 | 0.0625 | 1350 | 84.375
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-09-24 | 9 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 6.5 | 0.8125 | 1350 | 1096.875
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-09-24 | 9 | Jade Poteat | metafinanz Informationssysteme GmbH | 2 | 0.25 | 1000 | 250
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-09-24 | 9 | Sanat Gautam | metafinanz Informationssysteme GmbH | 5 | 0.625 | 1000 | 625
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-09-27 | 9 | Daniel Wörner | metafinanz Informationssysteme GmbH | 2 | 0.25 | 1000 | 250
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-09-27 | 9 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 8 | 1 | 1350 | 1350
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-09-28 | 9 | Daniel Wörner | metafinanz Informationssysteme GmbH | 2 | 0.25 | 1000 | 250
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-09-28 | 9 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 0.75 | 0.09375 | 1350 | 126.5625
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-09-28 | 9 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 0.75 | 0.09375 | 1350 | 126.5625
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-09-28 | 9 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 6 | 0.75 | 1350 | 1012.5
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-09-28 | 9 | Jade Poteat | metafinanz Informationssysteme GmbH | 1 | 0.125 | 1000 | 125
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-09-28 | 9 | Sanat Gautam | metafinanz Informationssysteme GmbH | 6 | 0.75 | 1000 | 750
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-09-29 | 9 | Daniel Wörner | metafinanz Informationssysteme GmbH | 1 | 0.125 | 1000 | 125
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-09-29 | 9 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 6.25 | 0.78125 | 1350 | 1054.6875
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-09-29 | 9 | Jade Poteat | metafinanz Informationssysteme GmbH | 1 | 0.125 | 1000 | 125
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-09-29 | 9 | Sanat Gautam | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1000 | 500
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-09-30 | 9 | Daniel Wörner | metafinanz Informationssysteme GmbH | 1 | 0.125 | 1000 | 125
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-09-30 | 9 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 7.25 | 0.90625 | 1350 | 1223.4375
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-10-01 | 10 | Daniel Wörner | metafinanz Informationssysteme GmbH | 1 | 0.125 | 1000 | 125
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-10-01 | 10 | George Dietrichsbruckner | metafinanz Informationssysteme GmbH | 6.5 | 0.8125 | 1350 | 1096.875
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-10-01 | 10 | Jade Poteat | metafinanz Informationssysteme GmbH | 5 | 0.625 | 1000 | 625
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-10-04 | 10 | Jade Poteat | metafinanz Informationssysteme GmbH | 2 | 0.25 | 1000 | 250
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-10-04 | 10 | Sanat Gautam | metafinanz Informationssysteme GmbH | 6 | 0.75 | 1000 | 750
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-10-05 | 10 | Jade Poteat | metafinanz Informationssysteme GmbH | 2 | 0.25 | 1000 | 250
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-10-05 | 10 | Sanat Gautam | metafinanz Informationssysteme GmbH | 6 | 0.75 | 1000 | 750
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-10-06 | 10 | Jade Poteat | metafinanz Informationssysteme GmbH | 2 | 0.25 | 1000 | 250
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-10-06 | 10 | Sanat Gautam | metafinanz Informationssysteme GmbH | 4.5 | 0.5625 | 1000 | 562.5
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-10-07 | 10 | Jade Poteat | metafinanz Informationssysteme GmbH | 2 | 0.25 | 1000 | 250
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-10-07 | 10 | Sanat Gautam | metafinanz Informationssysteme GmbH | 4 | 0.5 | 1000 | 500
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-10-08 | 10 | Jade Poteat | metafinanz Informationssysteme GmbH | 2 | 0.25 | 1000 | 250
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-10-08 | 10 | Sanat Gautam | metafinanz Informationssysteme GmbH | 6 | 0.75 | 1000 | 750
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-10-11 | 10 | Daniel Wörner | metafinanz Informationssysteme GmbH | 2 | 0.25 | 1000 | 250
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-10-11 | 10 | Sanat Gautam | metafinanz Informationssysteme GmbH | 2 | 0.25 | 1000 | 250
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-10-12 | 10 | Daniel Wörner | metafinanz Informationssysteme GmbH | 2 | 0.25 | 1000 | 250
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-10-12 | 10 | Sanat Gautam | metafinanz Informationssysteme GmbH | 7 | 0.875 | 1000 | 875
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-10-13 | 10 | Daniel Wörner | metafinanz Informationssysteme GmbH | 2 | 0.25 | 1000 | 250
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-10-13 | 10 | Heinrich Schlotthauer | metafinanz Informationssysteme GmbH | 8 | 1 | 1350 | 1350
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-10-13 | 10 | Sanat Gautam | metafinanz Informationssysteme GmbH | 5 | 0.625 | 1000 | 625
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-10-14 | 10 | Daniel Wörner | metafinanz Informationssysteme GmbH | 2 | 0.25 | 1000 | 250
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-10-14 | 10 | Sanat Gautam | metafinanz Informationssysteme GmbH | 6 | 0.75 | 1000 | 750
21 1079 | Measure 295 | 21 1079 Measure 295 - Global Security Platform GITSO blueprint (meta) | 2021-07-01 | 2021-12-31 | 2021-10-15 | 10 | Daniel Wörner | metafinanz Informationssysteme GmbH | 2 | 0.25 | 1000 | 250

## Input Resources Meta. Fix
(Nicht ändern) Zahlungstermin | (Nicht ändern) Zeilenprüfsumme | (Nicht ändern) Geändert am | Projektnummer | Vertragsnummer | Budget (Plan) Gesamt | Measure | Titel Intern | Start geplant | Ende geplant | Name | Arbeitspaket | Monat | Datum | Lieferant | Summe
21b1772f-067a-e811-811e-00505697052b | IZDZU/QOkOp4wB5uaCJneEYdJO3AzkONwpLTmGm1O/KpCin6e1Btsw8OdppytgTeBuau6t35jGS7C7HtHCTIrw== | 2018-06-27 14:33
ef96b141-067a-e811-811e-00505697052b | 7vrigOl6UpptO1OIFDbU9FsAFA37KEnjmGgDWZGT2KXXbO3s3x2D5ho9PWOAyw+AY0HN4Vz+/24fZ1Fhk0Mv8A== | 2018-06-27 14:33
8f9d5bad-c99e-e811-8121-00505697052b | JhSHRSWQP94ZrRR2ru1WwqXLWT+O1aE0lFQJVEaiDCZPTm5mk5IhJREFzgFTNAM4M33pJnY/uZXVXBcFX+Wj3w== | 2018-08-13 09:23
3810bf70-0b7a-e811-811e-00505697052b | xpo5rx2E3eZzGzRp8v50loupm8Inbu8AwCRcetuOu+p2lnDzPSqKL1+ija/f14eAQXgyDRVqQ8UdDOmo8w3lEQ== | 2018-06-27 15:10
3810bf70-0b7a-e811-811e-00505697052b | xpo5rx2E3eZzGzRp8v50loupm8Inbu8AwCRcetuOu+p2lnDzPSqKL1+ija/f14eAQXgyDRVqQ8UdDOmo8w3lEQ== | 2018-06-27 15:10
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1

## Input Resources Meta. Travel
(Nicht ändern) Reise | (Nicht ändern) Zeilenprüfsumme | (Nicht ändern) Geändert am | Dokumente in der Ablage | Reisenummer | Contract | Measure | Root Projekt | Titel der Reise | Mitarbeiter | Reise von | Reise bis | Abgerechnet | Statusgrund | Verrechneter Betrag | Erstellt am | Monat
7b838a4e-51cd-e811-a953-000d3a3a14c5 | J3QBo4/tO4f4XDC/URpfDtf5hGyAOogQ8p5n4+DVo9dersZc6ylKtMATjTeuhhUsyCubqVEZJJu9kJCcjx6q/A== | 2018-10-15 11:17
6695583b-abc8-e811-a952-000d3a38f64f | t5gO5ZLFgdtIo9Ek6yJ0b4FIC7KBRZd9bkObUMdyMe6CL8Wk7EU3ohCPxHaFiBLfbYEQJoM9l86HxlGClECAVg== | 2018-10-10 16:36
926c10e9-8fbd-e811-8123-00505697052b | khg91AAvcXAnYje/h0nIgea1UR1ha7Dvl8CPbvtyXescxBjjdYsRgiRsp+PeocdgH4Xrfb+cqdCY0ufDdeBROQ== | 2018-10-16 08:08
bce5a56c-70bd-e811-8123-00505697052b | pLqU8ciQ9yUpoeUfnvyjs8ZttfdV5//pXiJ4IFh3Hm8QFCnT8c+aXkYwWwmJ/3rB6mBADh4jH4bECcqa7iMgfA== | 2018-10-10 16:18
09af91d8-89b0-e811-8121-00505697052b | 07MpcN7Hf8OdTjWgmql1PiHVhZ2qaJdMSpLBOl4DcsQ+/Wwb/jsCFHzfgC1ucKVFxfHvzxoqJLEJz9uCKeP65Q== | 2018-10-15 08:58
2a6e6518-6db0-e811-8121-00505697052b | fBjWPisL3JP9eXpjaWk8+LXu+XgPhyfYI75C9FMcDCh1XXWOHH0i7IDZp7hpJ9ROWaXGE12D+o4REgQZ2xp54w== | 2018-10-16 08:09
901d218f-80ab-e811-8121-00505697052b | 8oazFPGC4d1UHocU1hS3CYw5vLSB3stGZnvdtV+m3xE3N3I2bhG+PnPJAVCk1FMXz5fe8OItMfQbzIvOJrZPPA== | 2018-10-15 08:58
2166827b-deaa-e811-8121-00505697052b | IP+U9shyJEjju2lIo4oJYcCX+rryN/gLdMX1wK08ApfydeWjZvsAkx6da2lpSuOduhYMXU2qswB7CxVnB8q9kw== | 2018-10-03 12:16
2021668f-aea6-e811-8121-00505697052b | VCRDXPd2d5dcm5JutoaX47pLd58kyIm4KGP/PbJXyo7VymWzvtY7iXoE8u/OpCxlBjNa3jCmoVzMzZsanHk+hQ== | 2018-10-09 13:55
4161c9ac-aca6-e811-8121-00505697052b | lqhWJl1+Emt0cCDPA3yX7esnHE+AAMQ9vfRrA3BZucBNKMHCjBnv67znPtchf6qccONyA8gHDYl9VtEzV4LEIg== | 2018-10-16 14:19
35d4e9cf-60a1-e811-8121-00505697052b | UDlItRBUvYgTpC6K+Is7BL2M1YZTgk302uAIkp7mvAglna7c4vKz4JlIFkoP3ENzRk1EpB61WSanKYv3CUMu5Q== | 2018-10-15 08:57
91bdd5db-32a1-e811-8121-00505697052b | ro84rztIPlqqvhghkxXawLCuEg/WNLSVXGN176tvchK7BlM7JKPfG7D0+LFn0Mxl8CkxOoMM+cfISp80xX8JmQ== | 2018-10-15 08:58
d4b72107-2fa1-e811-8121-00505697052b | B32dn7AtOUo71+kmXyqLIZYXKfIFZm/ZDyl5kChoDrF3JWiXqzsyZ6A8IUA3nHyKu5q3BZLGLlgwdCsMFkkWTA== | 2018-10-03 12:14
f3cef8de-bd9f-e811-8121-00505697052b | t/B7/gu6wm7aHvZ62LkowUACKU5EcXmRHWObNdlI5ZplSZBI0EPjsu7Kv0TGZxNX1pjI+peaMelZ4JyMED2VMA== | 2018-10-03 12:15
0f6231e5-e79a-e811-8121-00505697052b | tM2J0P6bzdbfkReulpwm3kk36szTH7wx2gRu5IsuNGb+v+5qmvcIhwRBb0o+ie0RGlBuj3MbXSkSe9LHiavUUw== | 2018-10-03 12:18
bfaf229a-bc95-e811-8120-00505697052b | JhkJunTPPczCM0HtWZVCRyz2CuGvDntzE2pCQywf3AgeAH9lQAumAPCRI5VXT0IaWikepok0lIHGFTb2uO0QFw== | 2018-10-03 12:18
e2464fea-b891-e811-8120-00505697052b | IZHDTzM/BqNkP3N2nX42WGH1kJYj8f6VyKOW/VVcJonFeULzmIH5sKa93WymlcgcV/CmJF6+TebOoFnzVo8CAA== | 2018-10-03 12:15
1b190a73-458f-e811-8120-00505697052b | s318nWdYp2W14iA0Zy8tuD4cozV0n0tsd5Q+nnKxugEBE1pfrWO0XmVUYd8/eQCe5k2SIZf9eN/PzUgfpTHlBA== | 2018-10-15 08:50
7351c319-1e8c-e811-8120-00505697052b | BvASNYuv1gnAhoxj/z3KYdqB4hzNHx8tOOUccBP0kNwsOuNC1OtcRR8VOUqlqNIvwVX/8tcVNF/NZ8kz9wE+aQ== | 2018-10-03 12:15
27c79204-198c-e811-8120-00505697052b | ylUD/eI5NOoZvRmERvFK5whk71/7iE68kjbd74k2R9yPWzGDI5mEt1Nj3OSHefl2oB1kaX2FEYlmNxt7AgmNhw== | 2018-10-03 12:15
d1346b16-178c-e811-8120-00505697052b | XttAbP3ZU3GX3CGwcrYDTRLWFK2erSTBX/YGUDifBX0kQoaeyLs2uT4tUsOrSJEQ55WjtDDiem67MvJOlj+QHQ== | 2018-10-03 12:15
4040f98c-b88a-e811-8120-00505697052b | sn1O/VTzS4iJgJr9x6GXk7iyc3xvT4N4Aczeb/R82IIZEDzt1e3UBAzr9TniJALVDWV35xMZMTggTY7Rbwcy5w== | 2018-10-16 08:08
11f665d1-5380-e811-811e-00505697052b | BePmId9ELM/QCMcbyP+WMHxy7UOxeVOCjP4aODXMJ+LCDChDcIWICL04nWsayuQfVulPffLjZD+QUqx9LxGP9g== | 2018-10-03 12:17
a2b75745-027e-e811-811e-00505697052b | MNFm4R0vKZG7+nyONHAhRyXNDHouKBMknmgwpIfoxXmxNOtDoO73a7fwLpV6vmqscYYNV1Ns1fMIbQKJ78DQSg== | 2018-10-03 12:14
1fb67e5e-d67d-e811-811e-00505697052b | 3gv2udQQNAyRemPeIfn4O4r5N1DKmzqjn3s+CyfdMQyldkPychLL8p/8ThGDgRpT91lT6PbxVjA6CSI3F9I72A== | 2018-10-03 12:17
dd7942f8-f76a-e811-811e-00505697052b | 6QqvDoaheZjcrzniokyGrbuMacU0on9YwjhwmHhhIofke1i0cx5e9b5l/o/cqt6FYjJRm8gcoKTZGxiGaVFuug== | 2018-10-03 12:16
557c58cb-e06a-e811-811e-00505697052b | qMleS5z/80J2R2ZAz1PIW4WCuOJGdNXpgEJZby0GpUGsyiMFuwn6K1WbSTiID+fYPUQQglvvK6yqY1LeE1r8PQ== | 2018-10-03 12:18
885a530e-cb67-e811-811e-00505697052b | 6yatiFEwzyTgA8ML6oZXu2XxNl6WcExyYqwSyUoqvquLXSk+td1OjtHbGD7grXKXSWE6l4P4FgR+WdszFYuGVg== | 2018-10-03 12:15
421776cb-c967-e811-811e-00505697052b | Ff/8WZW30cEx7RBNxu054H7GHXcdaU/z6pU183ZQLhJojNZ+zUcnRqLcxB/XvopKavcss5q2hpYd6EjLdDCthw== | 2018-10-03 12:15
ed177569-c967-e811-811e-00505697052b | dLkDThJhvSwPJtJCYnEFg7oPpxChL07JN47OSp2z7kZae5Ngpff5NHX6ZfASiHiJqOeKHNbd0P8a7TxR+iS2MA== | 2018-10-10 09:39
8e3e6da6-4863-e811-811c-00505697052b | Qox1oIbiY3EUY1ORu7DoxYElI59XtdMxpUcZiAUuvKqMtQqIi6f33Qpzq5RjFQ5r0oiPOX6cDQJ6MhEFR5bZtA== | 2018-10-03 12:14
2f34f747-a75a-e811-811c-00505697052b | NMKMzndovTpdALMqgwlD1S6afr25tEQX8O2GpzeFxN45z5Ltwnyv0xRkX6StLI2PqNwj1i/teDpRdxzd0NX20g== | 2018-10-03 12:15
3e0509ff-fb51-e811-811c-00505697052b | T6SVTUL0OCQIIFGARiQep9YzlEI/cBawN3SOSkhCVxl4uVWcDSTwKNrQSt6Y9KuY2TdiSY+49zPviIKvZVe/0g== | 2018-10-03 12:16
2a28d276-cf4e-e811-811a-00505697052b | 8NgrByoEBrCX5PjeZPZmssNGt23SzDcZUb/beC6YDASddUQ6Ae+jguYgQyrzHHKrItfpwHxdg8Z8jG2RveYLbA== | 2018-10-03 12:16
906aa1fb-ea49-e811-811a-00505697052b | N7ZH2zsGAOlWvfJMp851n8HSHfMvs58od+3dq3TvuLWb3acJq/0O8Y74bzj0n/7sP9Yf9TwUuWHAY8szKyb0mA== | 2018-10-03 12:16
10185495-5a49-e811-811a-00505697052b | vP58hubkHL65LA0PKCUsdcnO6uXEPm0HyaG43rsYKc/O1B0pIX6Hm2IgiwK+YEMHDdjUQMOLS8Ckzs6EXjllng== | 2018-10-03 12:14
0280f39b-ca3c-e811-811a-00505697052b | xJ6viuomIo8Gir85m6nzpKpC4l6JfySWFp+OOuMX7KgqOMAdBdnoISnBPtFnGyztzFtRoHwo4sSHS5YbsdCJ4A== | 2018-10-03 12:14
7026e9b6-5f39-e811-811a-00505697052b | lFFug4XT2X6OtpIATu2YoZZB8b3dnJKxTQdxXzmac+tOAswUx8LbGbG8Mr/1q9FPKHF8Ea6wt1C+nH93qwQfLA== | 2018-10-03 12:18
d5c46b89-bf38-e811-8118-00505697052b | NDbxH8wKJJNTgjwadQMIrS7j01zpX77B1HsblfIKToWK2ty8NezTX2jnfMdLDcICV4wm5HEHHXN/dHb9UBy29Q== | 2018-10-03 12:17
8007e820-0c38-e811-8118-00505697052b | rboGEl1z4ZSNHSqeU0b8/2gdNmWbDfeswdhtM5riaKQLqcGxFfltmtSFCK6h5d3Eulv0Pps34gx+/ShSmKHtEA== | 2018-10-03 12:14
1c0ec79d-3d33-e811-8118-00505697052b | 9qVNaQ3g628jaPzv2O65kST/WfYKB9uempl0Jz5soZ0e9JgVpz7XTCLWi5ccUx57LR7WTlYhHsCUHhR3QhHHAQ== | 2018-10-03 12:14
a45c16ea-3833-e811-8118-00505697052b | EGYQA1jjtGW366QZ4pEgRaJgOZjRcphuWj5vQun3fGgt04UNLQ1Cad7LVLT2I841eiaqWBKGJe3WnHi3G+MutA== | 2018-10-03 12:14
1188ac49-0731-e811-8118-00505697052b | 2YQUGIQFKVb3cNY/rbgaq5vl0jGVptrExjSOUetmzCsg/Q9KaLO6osEb4/gaApa5chduU4j8L+K87N3xipbKfg== | 2018-10-03 12:13
221d8968-0631-e811-8118-00505697052b | jB4uSpg/PyIzKkNxD+Or+PAtz0RtlsUyTtrI4vYiyGjCW5daR6CA5gWZ5nX9rL9EkfXPrzzAcykNhY3o8zxlhA== | 2018-10-03 12:13
98dc95d4-0531-e811-8118-00505697052b | 4jzmD+z1KE7FccfR5RDSR4y/RJ0TTa/L8ctJZcev4HNR/Xudq2up/ZlaW6dHa+D+AqKtD7ShkwSYwgkEfe4QQw== | 2018-10-03 12:13
f72afd16-af2d-e811-8118-00505697052b | iJo2rqyTCzLHoAgjw1hyG18rmZfZbaxsqu+wwNdv985H9yJyTLUm8LwH4sTSzxVXI0lgSGVP12NmE/Dd7o70mQ== | 2018-10-03 12:17
48296d84-ae2d-e811-8118-00505697052b | 6sQKjTd0s56szX1ysyYWX9zr3cZ1Ir7dpPgQppX6NnGPjvywkTUs4IbDfe0MsCHuyQ1lRRFmoc0Bq97/xsIBTQ== | 2018-10-03 12:18
fac7a465-e628-e811-8118-00505697052b | UYodiB0NzcrndquIICyE4UFoIb4AakT4+lv2djPpuFAdc8k8Ygy9gK6z4t74Vq8ykxwU+VTW3sz0H1vJGbKo/Q== | 2018-10-03 12:18
913f1e1f-cf22-e811-8116-00505697052b | c9hDwQbM6Soty2K80GGSDZh5Y4fCd70DCgnwJpW/a8XcFazPfj3AYp8MmOmp6JAsouK6//UJ7xbpQlSyiMTTjw== | 2018-10-03 12:16
0a1e29ad-141e-e811-8115-00505697052b | Faj6wJzhYxVFNLyqyCLevRt3nLBHMN5kdS0xXMwLLiyLdJSVjY16zEvrky+AhOHHnb4JGHPfrbb7++s1MCmGSg== | 2018-10-03 12:14
32e8524d-f41a-e811-8115-00505697052b | +J/LbSHwrMwOcXaFtb/NH9nrwyWb3klKy1cysQD2w4etORMlUxP/yHZix32giy/GznG5OqsdiimgfJdxQU8a5Q== | 2018-10-03 12:16
4254949c-0908-e811-8115-00505697052b | nI9sRuQdSf7rO7VQmeK60yxZMi1MivVRD9lcygpzDO8kMoTeBANmEd/gsSXLW5r4viP5BHc8JLX6emAlCTVcZw== | 2018-10-03 12:14
27f51d20-4bf4-e711-8113-00505697052b | 3BTNRplf8TXrNK5kDvXpolwnLWv1UmynO3eOmICzOPalUTN9wDAibRmCC3EmcnqWEn38keFz/+3ITZz0Kjj3tQ== | 2018-10-03 12:15