## Overview (hidden)
[7 empty] | Focus Area | #REF! |  | #REF! |  | #REF! |  | #REF! |  | Increase Detection |  | Increase Detection |  | Increase Detection |  | Increase Detection |  | Reduce Damage |  | Reduce Damage |  | Reduce Damage |  | Reduce Damage |  | Reduce Damage |  | Streamline Compliance |  | Streamline Compliance |  |  | Streamline Compliance |  |  | Build Security Organization / Skills |  | Build Security Organization / Skills |  | Build Security Organization / Skills
IT Security Initiative | [7 empty] | #REF! |  | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  |  | #REF! |  |  | #REF! |  | #REF! | 0 | #REF! | 0
Progress KPI Reporting 2020 | [7 empty] | #REF! |  | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  |  | #REF! |  |  | #REF! |  | #REF! | 1 | #REF! | 1
as of 04.09.2020 | [7 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Board Members | H Ressort | ITC Mapping |  | Group Iso Function | OEs ID | CIM ID | OE | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
.
Bäte | H1 CEO | 1 | Allianz SE, Allianz Europe | Shared Services | 1 | AZSE | Allianz SE | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
. |  |  |  |  | ∑ | ∑ | 1 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [16 empty] | 0 |  |  | 0 |  |  | #REF! | #REF!
. | [17 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
Thallinger | H3 Investments Management | 2 | Allianz Investment | Shared Services | 2 | ADEUS | ADEUS Aktienregister-Service-GmbH | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
|  |  |  | Europe 3 | 3 | AGL | Allianz Global Life | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
|  |  |  | Shared Services | 4 | AIM | Allianz Investment Management (AIM) | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
|  |  |  | Shared Services | 5 | ARE | Allianz Real Estate (ARE) | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
|  |  |  | Shared Services | 6 | IDS | Investment Data Services (IDS) | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
. |  |  |  |  | ∑ | ∑ | 5 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [16 empty] | 0 |  |  | 0 |  |  | #REF! | #REF!
. | [17 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
Mascher | H4 Operations | 3 | Allianz Technology | AZ Technology | 7 | AMOS | Allianz Technology | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
. |  |  |  |  | ∑ | ∑ | 1 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [16 empty] | 0 |  |  | 0 |  |  | #REF! | #REF!
. | [17 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
Balbinot | H5 Insurance Western & Southern Europe, AZAP | 4 | AZAP | AZAP | 8 | CNPC | Allianz China - P&C | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
| H2 Finance, Controlling, Risk |  |  | AZAP | 9 | CNH | Allianz China - Holding | [10 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
| H2 Finance, Controlling, Risk |  |  | AZAP | 10 | ID | Allianz Indonesia | [10 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
| H2 Finance, Controlling, Risk |  |  | AZAP | 11 | JPLH | Allianz Japan - Life | [10 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
| H2 Finance, Controlling, Risk |  |  | AZAP | 12 | LAPC | Allianz Laos | [10 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
| H2 Finance, Controlling, Risk |  |  | AZAP | 13 | MY | Allianz Malaysia | [10 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
| H2 Finance, Controlling, Risk |  |  | AZAP | 14 | PH | Allianz Philippine - L&H | [10 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
| H2 Finance, Controlling, Risk |  |  | AZAP | 15 | LK | Allianz Sri Lanka | [10 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
| H2 Finance, Controlling, Risk |  |  | AZAP | 16 | AS | Allianz Singapore | [10 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
| H2 Finance, Controlling, Risk |  |  | AZAP | 17 | TWL | Allianz Taiwan - Life | [10 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
| H2 Finance, Controlling, Risk |  |  | AZAP | 18 | TH | Allianz Thailand | [10 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
| H2 Finance, Controlling, Risk |  |  | AZAP | 19 | FIN | FinOS - Holding | [10 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
| H2 Finance, Controlling, Risk |  |  |  | ∑ | ∑ | 12 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [16 empty] | 0 |  |  | 0 |  |  | #REF! | #REF!
| H2 Finance, Controlling, Risk | 5 | Allianz Benelux | Europe 2 | 21 | BLX | Allianz Benelux | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
| H2 Finance, Controlling, Risk | 6 | Allianz France | Europe 2 | 22 | FR | Allianz France | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
| H2 Finance, Controlling, Risk | 7 | Allianz Greece | Europe 3 | 23 | GR | Allianz Greece | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
| H2 Finance, Controlling, Risk | 8 | Allianz Italy | Europe 3 | 24 | IT | Allianz Italy | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
| H2 Finance, Controlling, Risk | 9 | Allianz Turkey | Europe 3 | 25 | TR | Allianz Turkey | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
. |  |  |  |  | ∑ | ∑ | 17 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [16 empty] | 0 |  |  | 0 |  |  | #REF! | #REF!
. | [17 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
Theis | H7 Insurance German Speaking Countries & CEE | 10 | Allianz Germany | Europe 1 | 26 | AZD | Allianz Germany | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
| H2 Finance, Controlling, Risk | 11 | CEE | CEE | 27 | AT | Allianz Austria (Elementar) | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
| H2 Finance, Controlling, Risk |  |  | CEE | 28 | BG | Allianz Bulgaria | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
| H2 Finance, Controlling, Risk |  |  | CEE | 29 | CZ | Allianz Czechia | [10 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
| H2 Finance, Controlling, Risk |  |  | CEE | 30 | HU | Allianz Hungary | [10 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
| H2 Finance, Controlling, Risk |  |  | CEE | 31 | HR | Allianz Croatia (Zagreb) | [10 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
| H2 Finance, Controlling, Risk |  |  | CEE | 32 | PL | Allianz Poland | [10 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
| H2 Finance, Controlling, Risk |  |  | CEE | 33 | RO | Allianz Romania (Tiriac) | [10 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
| H2 Finance, Controlling, Risk |  |  | CEE | 34 | RU | Allianz Russia | [10 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
| H2 Finance, Controlling, Risk |  |  | CEE | 35 | SK | Allianz Slovakia | [10 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
| H2 Finance, Controlling, Risk |  |  | CEE | 36 | UKR | Allianz Ukraine | [10 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
| H2 Finance, Controlling, Risk |  |  |  | ∑ | ∑ | 11 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [16 empty] | 0 |  |  | 0 |  |  | #REF! | #REF!
| H2 Finance, Controlling, Risk | 12 | Allianz Suisse | Europe 1 | 37 | CH | Allianz Switzerland | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
. |  |  |  |  | ∑ | ∑ | 12 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [16 empty] | 0 |  |  | 0 |  |  | #REF! | #REF!
. | [17 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
Hunt | H8 Asset Management, USA Life Insurance | 13 | Allianz Asset Management Holding (AAM) | Asset & Overseas | 38 | AAM | Allianz Asset Management Holding (AAM) | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
| H2 Finance, Controlling, Risk | 15 | Allianz Global Investors (AGI) | Asset & Overseas | 39 | AGI | Allianz Global Investors (AGI) | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
| H2 Finance, Controlling, Risk | 16 | Pacific Invest.Manag. Comp.(PIMCO) | Asset & Overseas | 40 | PIMCO | Pacific Investement Management Company (PIMCO) | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
| H2 Finance, Controlling, Risk | 17 | Allianz Life | Asset & Overseas | 41 | USL | Allianz Life US | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
. |  |  |  |  | ∑ | ∑ | 4 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [16 empty] | 0 |  |  | 0 |  |  | #REF! | #REF!
. | [17 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
Peiris | H9 Global Lines & Anglo Markets, MENA, Africa | 18 | Allianz Africa | AZ Africa | 42 | AFR | Allianz Africa | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
|  |  |  | AZ Africa | 43 | MA | Allianz Morocco | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
[5 empty] | ∑ | ∑ | 2 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
|  | 19 | MENA | MENA | 44 | EGLH | Allianz Egypt L&H | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
|  |  |  | MENA | 45 | EGPC | Allianz Egypt P&C | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
|  |  |  | MENA | 46 | LB | Allianz Lebanon | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
|  |  |  | MENA | 47 | SA | Allianz Saudi Arabia | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
[5 empty] | ∑ | ∑ | 4 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
|  | 20 | Allianz Global Corporate & Specialty (AGCS) | Europe 1 | 48 | AGCS | Allianz Global Corporate & Specialty (AGCS) | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
|  | 21 | Reinsurance | Europe 1 | 49 | AZRE | Allianz Reinsurance | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
|  | 22 | Allianz Australia | Asset & Overseas | 50 | AU | Allianz Australia | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
|  | 23 | Allianz Ireland | Europe 3 | 51 | IE | Allianz Ireland | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
|  | 24 | Allianz UK | Europe 3 | 52 | UK | Allianz UK | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
|  | 25 | Euler Hermes Group | Europe 2 | 53 | EH | Euler Hermes | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
. |  |  |  |  | ∑ | ∑ | 12 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
.
de la Sota | H10 Business Transformation | 26 | Allianz Ibero & Latin America | IbertoLatAm | 54 | AR | Allianz Argentina | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
|  |  |  | IbertoLatAm | 55 | BR | Allianz Brazil | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
|  |  |  | IbertoLatAm | 56 | CO | Allianz Colombia | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
|  |  |  | IbertoLatAm | 57 | MX | Allianz Mexico | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
|  |  |  | IbertoLatAm | 58 | PT | Allianz Portugal | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
|  |  |  | IbertoLatAm | 59 | ES | Allianz Spain (Seguros) | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
[5 empty] | ∑ | ∑ | 6 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
|  | 27 | Allianz Partners | Europe 2 | 60 | AWP | Allianz Partners | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
|  | 28 | tbd | Shared Services | 60 | AZX | AllianzX | n.a. | n.a. | [8 empty] | n.a. | n.a. | #REF! | #REF! | [22 empty] | #REF! | #REF!
[5 empty] | ∑ | ∑ | 8 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
[5 empty] | ∑ | ∑ | 60 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
To be discussed: brauche wir die Übersicht-Seite. M.E. nicht unbedingt.

## Status Overview
ç | IT Security Investment Initiative
| Status overview |  | HY1 2021
# | Focus Area | # | MID | Global Security Initiative Measure | Progress KPIs | (Baseline/Target) | Measure Lead | Approved Budget | Labor | Non-Labor | Risk | Budget | Artefacts | Risks | Budget | Artefacts
1 | Slow Down Hackers | M274 | M274 | Extend currently running TIBER exercise | # of scenarios tested | (0/4) | Andreas Wagner | 1838.72 | 1838.72 | 0 |  |  |  | 0 | 0 | 0
2 | Slow Down Hackers | M275 | M275 | Cloud Security Competence Center + Secret Mgmt. | # of Security Consultations | (0/10) | Marc Bochtler | 800 | 800 | 0 |  |  |  | 0 | 0 | 0
3 | Slow Down Hackers | M 276 | M276 | Global & Scalable Application Pen Test Service Setup | # of application penetration tests performed | (0/30) | Clemens Friedrich | 950 | 890 | 60 |  |  |  | 0 | 0 | 0
4 | Slow Down Hackers | M277 | M277 | Realtime auditing & sec monitoring for Active Directory | # of event propagation from the source to the SIEM response | (0/3) | Alexander Heinze | 670 | 550 | 120 |  |  |  | 0 | 0 | 0
5 | Slow Down Hackers | M278 | M278 | IAM Password Hash Synchronization to Azure Active Directory | # of artefacts completed | (0/5) | Alexander Heinze | 448 | 448 | 0 |  |  |  | 0 | 0 | 0
6 | Slow Down Hackers | M279 | M279 | PTA (Privileged Threat Analytics) | # of artefacts achieved and requirements analyzed | (0/9) | Alexander Heinze | 670 | 550 | 120 |  |  |  | 0 | 0 | 0
| Slow Down Hackers |  | M302 | IAM Role Management & Machine Learning Analytics | # of reached milestones | (0/5) | Alexander Heinze | 811 | 751 | 60 |  |  |  | 0 | 0 | 0
7 | Increase Detection | M280 | M280 | Advanced Network-based detection and response | # of new generation ADH deployment | (0/10) | Thomas Wolf | 353 | 250 | 103 |  |  |  | 0 | 0 | 0
8 | Increase Detection | M281 | M281 | Passive DNS Monitoring & DNS Firewalling | # of DNS Server logs consumed | (0/2) | Lucas Tscherter | 337 | 210 | 127 |  |  |  | 0 | 0 | 0
9 | Increase Detection | M282_1 | M282 | Global Deception rollout | # of DCs and endpoints covered with deception | (0/6) | Lucas Tscherter | 1620 | 1350 | 270 |  |  |  | 0 | 0 | 0
10 | Increase Detection | M283 | M283 | Enhance Cloud response & Secure Allianz critical Apps | # of implemented cloud use cases | (0/10) | Lucas Tscherter | 505 | 475 | 30 |  |  |  | 0 | 0 | 0
11 | Increase Detection | M284 | M284 | SOAR Rollout and case management implementation | # of integrations or play books implemented | (0/8) | Lucas Tscherter | 690 | 610 | 80 |  |  |  | 0 | 0 | 0
12 | Increase Detection | M285 | M285 | Increase Effectiveness of Micro Segmentation and Rollout in EU | # of business critical applications moved to Enforce-Mode | (0/30) | Clemens Friedrich | 420 | 420 | 0 |  |  |  | 1 | 0 | 1
13 | Increase Detection | M286 | M286 | Build Central Dashboard to Increase Transparency and Real Time Monitoring | # of Reporting User Stories designed and User Stories implemented | (0/12) | Clemens Friedrich | 285 | 285 | 0 |  |  |  | 0 | 0 | 0
14 | Reduce Damage | M287_1 | M287 | Extension of vulnerability mgmt. to clients and global policy compliance rollout | # of OEs covered with Qualys agents on clients | (0/20) | Clemens Friedrich | 1250 | 1150 | 100 |  |  |  | 0 | 0 | 0
15 | Reduce Damage | M288 | M288 | AGN Secure Network Access and Segregation | # of reached milestones | (0/4) | Michael Kahlfuss | 588 | 538 | 50 |  |  |  | 0 | 0 | 0
16 | Reduce Damage | M289 | M289 | Acceleration of Password Manager service | # of users rolled-out to password manager service | (0/1000) | Rainer Mahlo | 350 | 350 | 0 |  |  |  | 0 | 0 | 0
17 | Reduce Damage | M290 | M290 | Re-Design Of Cloud Application Discovery Service | # of Service design documents for future CAD service developed | (0/6) | Clemens Friedrich | 155 | 155 | 0 |  |  |  | 0 | 0 | 0
18 | Reduce Damage | M291 | M291 | Privileged Access Management for Cloud | # of validate possible integrations | (0/4) | Alexander Heinze | 200 | 200 | 0 |  |  |  | 0 | 0 | 0
19 | Reduce Damage | M302 | M301 | Global Tier 0 Hosting Platform Preparation & APAC Pilot | # of Global Service AD (ADTRootdom.net & Rootdom.net Domain Controllers) extended to Tier 0 Hosting Platform in APAC # of Local APAC units of Allianz Partners: Domain Controllers onboarded to Tier 0 Hosting Platform | (0/8) (0/4) | Alexander Heinze | 1000 | 750 | 250 |  |  |  | 0 | 0 | 0
20 | Streamline Compliance |  | M292 | Double Key Encryption / Extended Security & Compliance for M365 | # of reached artefacts | (0/5) | Julian Bönigk | 750 | 690 | 60 |  |  |  | 0 | 0 | 0
21 | Streamline Compliance | M293 | M293 | Automated Toxic Tracking for Client-based Assets | # of Toxic Asset Dashboard including client IT asset data (e.g. AVC, AMC, fat client, smart mobile de-vices) for minimum of 25 OEs | (0/25) | Benjamin Warnholz | 360 | 300 | 60 |  |  |  | 0 | 0 | 0
22 | Streamline Compliance | M294 | M294 | Integrated Information Risk Management early Live​ | # of reached milestones | (0/5) | Michael Habel | 650 | 650 | 0 |  |  |  | 0 | 0 | 0
23 | Streamline Compliance | M295 | M295 | Global Security Platform GITSO blueprint | # of KPI + SLA vetting draft for 6 Security Services | (0/12) | George Dietrichsbruckner | 300 | 298 | 2 |  |  |  | 0 | 0 | 0
24 | Build Security Organization / Skills | M296 | M296 | Financial Loss Quantification | # of OEs evaluated within BitSight financial model | (0/10) | Thomas Thuspass | 400 | 400 | 0 |  |  |  | 0 | 0 | 0
25 | Build Security Organization / Skills | M297 | M297 | Measure and Enhance Global Phishing Resilience | # of learning nuggets and OE dashboards created | (0/10) | Clemens Friedrich | 995 | 720 | 275 |  |  |  | 0 | 0 | 0
26 | Build Security Organization / Skills | M298 | M298 | Strategic THREAT Intelligence and Resulting risk Identification Program | # of reached artefacts | (0/3) | Thomas Wolf | 480 | 480 | 0 |  |  |  | 0 | 0 | 0
27 | Build Security Organization / Skills | M299_1 | M299 | Enforcement of Security Architecture | # of architectural documents (e.g. pattern / analysis / methodology) published | (0/7) | Jan General | 430 | 430 | 0 |  |  |  | 0 | 0 | 0
28 | Build Security Organization / Skills | M300 | M300 | Metrics phase @We protect scale up on skills | # of high qualitative metrics for ROI | (0/5) | Samuel Hurst | 540 | 390 | 150 |  |  |  | 0 | 0 | 0
Export Status Reports
Import Status Reports
Import specific Status Report
Export Status Reports
Import Status Reports
Import specific Status Report

## M274
M274 |  | Measure Report - HY2 2021
[11 empty] | Status report is up to date: |  |  |  | No |  |  | Help required: |  | No
Measure Name: |  |  | Focus Area: |  |  |  |  | Measure Lead: |  |  |  | Measure Duration: |  |  |  | Status:
Extend currently running TIBER exercise |  |  | Slow Down Hackers |  |  |  |  | Andreas Wagner |  |  |  | 01.07.2021 - 31.12.2021 |  |  |  | as per 29.10.2021
[9 empty] | Approved (HY2 2021) |  |  |  | 1.839k€ |  | Spent (as per 15.10.2021) |  |  |  | 409k€ |  | Click this button to create a powerpoint presentation:
Risk
Overall Status |  |  |  | Budget |  |  |  |  | Budget (labor) |  |  |  | 1839k€ |  | Budget (labor) |  |  |  | 409k€
|  |  |  | Artefacts |  |  |  |  | Budget (non-labor) |  |  |  | 0k€ |  | Budget (non-labor) |  |  |  | 0k€
ARTEFACTS
ID | Artefact Description |  |  | Progress |  | Approved Budget (labor) | Achievements | [7 empty] | Work to be done | [6 empty] | 35%
65%
0%
1 | Conduct TIBER execution for the OEs |  |  | 35% |  | 829k€ | [7 empty] | Conduct test scenarios according to plan | [7 empty] | 100%
10%
90%
2 | Coordinate wrap-up / test closure |  |  | 0% |  | 410k€ | [15 empty] | 0%
100%
0%
3 | Execute Post-findings-review |  |  | 10% |  | 300k€ | First findings in review | [14 empty] | 100%
4 | Plan & start finding Remediation |  |  | 0% |  | 300k€
5 |  |  |  | 0%
KPI |  |  | RISK |  | DESCRIPTION |  |  |  |  | CRITICALITY* |  | MITIGATION ACTIVITIES |  |  |  |  | RESOLUTION DATE
ID | KPI Description (Actuals/Target) |  | - | [6 empty] | -
1 | # of scenarios tested (0/4)
2 | (/)
|  |  | - | [6 empty] | -
On track
Actions required
|  | Management attention required | - | [6 empty] | -
* Criticality: |  | High = Major negative impact on artefacts/timline |  |  | Medium = Considerable impact on artefacts/timeline |  |  |  |  | Low = Minor negative impact on artefacts/timeline
Create Powerpoint

## M275
M275 |  | Measure Report - HY2 2021
[11 empty] | Status report is up to date: |  |  |  | No |  |  | Help required: |  | No
Measure Name: |  |  | Focus Area: |  |  |  |  | Measure Lead: |  |  |  | Measure Duration: |  |  |  | Status:
Cloud Security Competence Center + Secret Mgmt. |  |  | Slow Down Hackers |  |  |  |  | Marc Bochtler |  |  |  | 01.07.2021 - 31.12.2021 |  |  |  | as per 29.10.2021
[9 empty] | Approved (HY2 2021) |  |  |  | 800k€ |  | Spent (as per 15.10.2021) |  |  |  | 365k€ |  | Click this button to create a powerpoint presentation:
Risk
Overall Status |  |  |  | Budget |  |  |  |  | Budget (labor) |  |  |  | 800k€ |  | Budget (labor) |  |  |  | 365k€
|  |  |  | Artefacts |  |  |  |  | Budget (non-labor) |  |  |  | 0k€ |  | Budget (non-labor) |  |  |  | 0k€
ARTEFACTS
ID | Artefact Description |  |  | Progress |  | Approved Budget (labor) | Achievements | [7 empty] | Work to be done | [6 empty] | 40%
60%
35%
1 | Extend feature set of already available security features in Prisma Cloud platform (specifically onboarded serverless functions) |  |  | 40% |  | 200k€ | Serverless functions enabled. | [6 empty] | Rollout to customers | [7 empty] | 65%
35%
65%
2 | Cover capacity challenges in Cloud Security Competence Center ramp up (Funding, hiring) |  |  | 35% |  | 200k€ | 3 external ressources (as in 1 HY measure) hired and funded. Cloud Security Competence Center will be allocated within Robin Bühlers business area in 2022. | [6 empty] | Alignment about Headcounts and funding. | [7 empty] | 0%
100%
0%
3 | Design secret management service for cloud native applications (not limited to TLS) |  |  | 35% |  | 200k€ | Some options for final architectural decision identified (Co-located vs standalone, options for Vault cluster built (Virtual Machines vs Kubernetes). Agreed patterns: Vault clusters on EKS/AKS; standalone deployment model with dedicated tenancy | [6 empty] | Shaping and reviewing the options for the final architectural decision.Review of architectural flows. Roadshow to show the acutal status of the project and service to Key Stakeholder. | [7 empty] | 100%
4 | Perform POC of the HashiCorp Vault implementation and integration readiness for two usecases |  |  | 0% |  | 200k€ | [7 empty] | Secret management service has to be designed first.
5 |  |  |  | 0%
KPI |  |  | RISK |  | DESCRIPTION |  |  |  |  | CRITICALITY* |  | MITIGATION ACTIVITIES |  |  |  |  | RESOLUTION DATE
ID | KPI Description (Actuals/Target) |  | - | [6 empty] | -
1 | # of Security Consultations (3/10)
2 | (/)
On track
Actions required
Management attention required
* Criticality: |  | High = Major negative impact on artefacts/timline |  |  | Medium = Considerable impact on artefacts/timeline |  |  |  |  | Low = Minor negative impact on artefacts/timeline
Create Powerpoint

## M276
M276 |  | Measure Report - HY2 2021
[11 empty] | Status report is up to date: |  |  |  | No |  |  | Help required: |  | No
Measure Name: |  |  | Focus Area: |  |  |  |  | Measure Lead: |  |  |  | Measure Duration: |  |  |  | Status:
Global & Scalable Application Pen Test Service Setup |  |  | Slow Down Hackers |  |  |  |  | Clemens Friedrich |  |  |  | 01.07.2021 - 31.12.2021 |  |  |  | as per 29.10.2021
[9 empty] | Approved (HY2 2021) |  |  |  | 1.150k€ |  | Spent (as per 15.10.2021) |  |  |  | 277k€ |  | Click this button to create a powerpoint presentation:
Risk
Overall Status |  |  |  | Budget |  |  |  |  | Budget (labor) |  |  |  | 1.090k€ |  | Budget (labor) |  |  |  | 277k€
|  |  |  | Artefacts |  |  |  |  | Budget (non-labor) |  |  |  | 60k€ |  | Budget (non-labor) |  |  |  | 0k€
ARTEFACTS
ID | Artefact Description |  |  | Progress |  | Approved Budget (labor) | Achievements | [7 empty] | Work to be done | [6 empty] | 80%
20%
45%
1 | Establish the Application Penetration Testing service offering (SPM Process) |  |  | 80% |  | 130k€ | - 21 / 25 SPM Process Steps finalized | [6 empty] | - Finalizing of still open Process Steps | [7 empty] | 55%
30%
70%
2 | Finalize design & integration of the service in the Allianz ecosystem incl. reporting capabilities |  |  | 45% |  | 110k€ | - Integration Process of findings into Splunk approved - SNOW final Design discussed and approved - Full Copy of data between Splunk and Archer appoved | [6 empty] | - Align Implementation Plan of Splunk and Archer - Implementation of Integration (Results from Tests, Splunk to Archer) | [7 empty] | 70%
30%
30%
3 | Set-up of the technical pen-test factory (‘Hack Lab’) |  |  | 30% |  | 350k€ | - Hacklabs for first waves of penests set up - Updated Hacklack IT-Architecture inlcuding Splunk & Archer & Implementation Plan | [6 empty] | - Prepare ITFAM TRB Presenatation - Recieve general FCC agreement for IPT Service | [7 empty] | 70%
4 | Contracting of external partners and establish provider management |  |  | 70% |  | 70k€ | - Contracts with EY and Deloitte are closed - PO has been created and updated on AZ Tech side and sent to both vendors - Management JF with Deloitte & EY established | [6 empty] | - Establish standardised planning process and vendor management; - Procurement for 2022 ongoing, incl. Adding of Retest Process
5 | Perform penetration tests to ramp-up the service offering |  |  | 30% |  | 430k€ | - Calls with ISOs and App Owner performed - EGRC & EDR Test completed - October Wave of Pentest planned | [6 empty] | - Identify new Apps to be tested, to make sure at least 30 apps can be testes until end of the year and fill leadpipeline for 2022 - Continuus planning of application tests
KPI |  |  | RISK |  | DESCRIPTION |  |  |  |  | CRITICALITY* |  | MITIGATION ACTIVITIES |  |  |  |  | RESOLUTION DATE
ID | KPI Description (Actuals/Target) |  | Artefact Risk |  | Risk of not achieving KPI by end of the year due to missing applications and commitment for Pen-Testing |  |  |  |  | Low |  | Start of a campaing to attract more ISOs and App Owner; Get Management Suppot for this campaing. Campaing must start during September, to still take effect in 2021 |  |  |  |  | 2021-09-30
1 | # of application penetration tests performed (2/30)
2 | (/)
On track
Actions required
|  | Management attention required | - | [6 empty] | -
* Criticality: |  | High = Major negative impact on artefacts/timline |  |  | Medium = Considerable impact on artefacts/timeline |  |  |  |  | Low = Minor negative impact on artefacts/timeline
Create Powerpoint

## M277
M277 |  | Measure Report - HY2 2021
[11 empty] | Status report is up to date: |  |  |  | No |  |  | Help required: |  | No
Measure Name: |  |  | Focus Area: |  |  |  |  | Measure Lead: |  |  |  | Measure Duration: |  |  |  | Status:
Realtime auditing & sec monitoring for Active Directory |  |  | Slow Down Hackers |  |  |  |  | Alexander Heinze |  |  |  | 01.07.2021 - 31.12.2021 |  |  |  | as per 29.10.2021
[9 empty] | Approved (HY2 2021) |  |  |  | 670k€ |  | Spent (as per 15.10.2021) |  |  |  | 157k€ |  | Click this button to create a powerpoint presentation:
Risk
Overall Status |  |  |  | Budget |  |  |  |  | Budget (labor) |  |  |  | 550k€ |  | Budget (labor) |  |  |  | 157k€
|  |  |  | Artefacts |  |  |  |  | Budget (non-labor) |  |  |  | 120k€ |  | Budget (non-labor) |  |  |  | 0k€
ARTEFACTS
ID | Artefact Description |  |  | Progress |  | Approved Budget (labor) | Achievements | [7 empty] | Work to be done | [6 empty] | 100%
0%
10%
1 | Identification of requirements for the solution and scope definition (.docx) |  |  | 100% |  | 100k€ | - Requirement gathering - Requirement consolidation - Requirement confirmation by the stakeholders | [6 empty] | / | [7 empty] | 90%
8%
92%
2 | Implementation of realtime audit and monitoring for pilot AD/AAD with the N3K Cygna Auditor solution (.docx) |  |  | 10% |  | 160k€ | - Initial Workshop and alignmentm with N3K - gathering of pre-implementation documentation for Cygna - implementation of Cygna on pilot scope (partially done) | [6 empty] | - Implementation of Cygna on pilot scope - Event forwarding to SIEM - Consolidation with stakeholders | [7 empty] | 70%
30%
30%
3 | Requirement fulfilment analysis, that includes a validation of the capabilities of the implemented solution (.docx) |  |  | 8% |  | 130k€ | - Fullfilment analysis (partially completed) | [6 empty] | - Fullfulment analysis - Alignment with vendor - Alignment with stakeholders | [7 empty] | 70%
4 | High-Level integration concept, Roadmap and effort estimation for an integration into the ACDC landscape (.docx) |  |  | 70% |  | 200k€ | - High level concept (partially completed) - SIEM integration roadmap (partially completed) - Low level concept (partially done) | [6 empty] | - Low level concept - SIEM integration roadmap + effort estimation - Alignment with stakeholders
5 | Peer-group comparison of Cygna (.docx) |  |  | 30% |  | 80k€ | - Supplier identification - Supplier commissioning (partially completed) - Consolidation of results (partially completed) | [6 empty] | - Consolidation of results
KPI |  |  | RISK |  | DESCRIPTION |  |  |  |  | CRITICALITY* |  | MITIGATION ACTIVITIES |  |  |  |  | RESOLUTION DATE
ID | KPI Description (Actuals/Target) |  | Artefact Risk |  | Vendor commitment to the agreed implementation roadmap. This includes the availability of resources during the implementation timeframes. |  |  |  |  | High |  | No effective mitigation identified. |  |  |  |  | /
1 | # of event propagation from the source to the SIEM response (0/3)
2 | (/)
|  |  | Artefact Risk |  | Implementation speed of FCCs. These are required to enable a communication of the Cygna components, AD/AAD and ACDC. As a result the implementation within the pilot scope can be dalayed. |  |  |  |  | Medium |  | No effective mitigation identified. |  |  |  |  | /
On track
Actions required
Management attention required
* Criticality: |  | High = Major negative impact on artefacts/timline |  |  | Medium = Considerable impact on artefacts/timeline |  |  |  |  | Low = Minor negative impact on artefacts/timeline
Create Powerpoint

## M278
M278 |  | Measure Report - HY2 2021
[11 empty] | Status report is up to date: |  |  |  | No |  |  | Help required: |  | No
Measure Name: |  |  | Focus Area: |  |  |  |  | Measure Lead: |  |  |  | Measure Duration: |  |  |  | Status:
IAM Password Hash Synchronization to Azure Active Directory |  |  | Slow Down Hackers |  |  |  |  | Alexander Heinze |  |  |  | 01.07.2021 - 31.12.2021 |  |  |  | as per 29.10.2021
[9 empty] | Approved (HY2 2021) |  |  |  | 448k€ |  | Spent (as per 15.10.2021) |  |  |  | 173k€ |  | Click this button to create a powerpoint presentation:
Risk
Overall Status |  |  |  | Budget |  |  |  |  | Budget (labor) |  |  |  | 448k€ |  | Budget (labor) |  |  |  | 173k€
|  |  |  | Artefacts |  |  |  |  | Budget (non-labor) |  |  |  | 0k€ |  | Budget (non-labor) |  |  |  | 0k€
ARTEFACTS
ID | Artefact Description |  |  | Progress |  | Approved Budget (labor) | Achievements | [7 empty] | Work to be done | [6 empty] | 100%
0%
100%
1 | Conceptualization, high-level and low-level design for password hash synchronization (.docx) |  |  | 100% |  | € 75 k | - Feedback from stakeholds | [6 empty] | -Sign off final document | [7 empty] | 0%
70%
30%
2 | Design for Microsoft Identity Protection (MIP) and integration architecture to ACDC (.ppt) |  |  | 100% |  | € 75 k | - Feedback from stakeholds | [6 empty] | -Sign off final document | [7 empty] | 100%
0%
5%
3 | Proof of Concept (PoC) implementation of password hash synchronization for Pilot OE |  |  | 70% |  | € 200 k | - Password Hashing synch successfully activated for AZ Suisse'test AD ('e-dom') - Interface between MIP and Sentinel available and in test - Password hashing change and synchronise with the password id happen every 2 minutes | [6 empty] | - Align with MS re. Rules configuration for subset of users prior to synch activation - Enable autmate reporting on he user level or forest level - Test case reporing for PHS | [7 empty] | 95%
4 | Initiation of ACDC use-case for credential abuse alerts from MIP to ACDC (.docx) |  |  | 100% |  | € 50 k | - Verify that MIP log events are reaching the Sentinel | [6 empty] | - Recommendation for post-incident handling in Sentinel - Define a process to confirm the credential leak event
5 | Creation of sample reporting (via MIP tool) |  |  | 5% |  | € 48 k | - Link to the reporting created | [6 empty] | - To design a report focused on non-synched account
KPI |  |  | RISK |  | DESCRIPTION |  |  |  |  | CRITICALITY* |  | MITIGATION ACTIVITIES |  |  |  |  | RESOLUTION DATE
ID | KPI Description (Actuals/Target) |  | - | [6 empty] | -
1 | # of artefacts completed (0/5)
2 | (/)
|  |  | - | [6 empty] | -
On track
Actions required
|  | Management attention required | - | [6 empty] | -
* Criticality: |  | High = Major negative impact on artefacts/timline |  |  | Medium = Considerable impact on artefacts/timeline |  |  |  |  | Low = Minor negative impact on artefacts/timeline
Create Powerpoint

## M279
M279 |  | Measure Report - HY2 2021
[11 empty] | Status report is up to date: |  |  |  | No |  |  | Help required: |  | No
Measure Name: |  |  | Focus Area: |  |  |  |  | Measure Lead: |  |  |  | Measure Duration: |  |  |  | Status:
PTA (Privileged Threat Analytics) |  |  | Slow Down Hackers |  |  |  |  | Alexander Heinze |  |  |  | 01.07.2021 - 31.12.2021 |  |  |  | as per 29.10.2021
[9 empty] | Approved (HY2 2021) |  |  |  | 670k€ |  | Spent (as per 15.10.2021) |  |  |  | 103k€ |  | Click this button to create a powerpoint presentation:
Risk
Overall Status |  |  |  | Budget |  |  |  |  | Budget (labor) |  |  |  | 550k€ |  | Budget (labor) |  |  |  | 103k€
|  |  |  | Artefacts |  |  |  |  | Budget (non-labor) |  |  |  | 120k€ |  | Budget (non-labor) |  |  |  | 0k€
ARTEFACTS
ID | Artefact Description |  |  | Progress |  | Approved Budget (labor) | Achievements | [7 empty] | Work to be done | [6 empty] | 100%
0%
90%
1 | Requirement identification and usecase definition |  |  | 100% |  | € 55 k | Requirments identifed and approved by internal team | [6 empty] | N/A | [7 empty] | 10%
90%
10%
2 | Vendors evaluation and selection |  |  | 90% |  | € 80 k | Evaluation of vendors progressed Initial overview is ready | [6 empty] | Final workshop with LogRythm Receiving comrehensive info frmo LogRythm | [7 empty] | 30%
70%
0%
3 | Architectural design and technical suitability analysis |  |  | 90% |  | € 145 k | Full architecture design document template including high level design and low level design prepared and passed to GPAM team for approval | [6 empty] | To receive the final approval from GPAM team | [7 empty] | 100%
4 | POC implementation and features testing |  |  | 30% |  | € 155 k | PoC infrastructure is prepared Test users are requested and in process of receiving them Test case scripts are getting prepared | [6 empty] | Getting required infrastrature in place (Mid oct) Getting the actual PoC in place
5 | Evaluation of integration with SIEM and events analysis |  |  | 0% |  | € 115 k | Start of this artifact depends on completion of artifact 4 | [6 empty] | Start of this artifact depends on completion of artifact 4
KPI |  |  | RISK |  | DESCRIPTION |  |  |  |  | CRITICALITY* |  | MITIGATION ACTIVITIES |  |  |  |  | RESOLUTION DATE
ID | KPI Description (Actuals/Target) |  | - | [6 empty] | -
1 | # of artefacts achieved and requirements analyzed (3/9)
2 | (/)
|  |  | - | [6 empty] | -
On track
Actions required
|  | Management attention required | - | [6 empty] | -
* Criticality: |  | High = Major negative impact on artefacts/timline |  |  | Medium = Considerable impact on artefacts/timeline |  |  |  |  | Low = Minor negative impact on artefacts/timeline
Create Powerpoint

## M302
M302 |  | Measure Report - HY2 2021
[11 empty] | Status report is up to date: |  |  |  | No |  |  | Help required: |  | No
Measure Name: |  |  | Focus Area: |  |  |  |  | Measure Lead: |  |  |  | Measure Duration: |  |  |  | Status:
IAM Role Management & Machine Learning Analytics |  |  | Slow Down Hackers |  |  |  |  | Alexander Heinze |  |  |  | 15.09.2021 - 31.12.2021 |  |  |  | as per 29.10.2021
[9 empty] | Approved (HY2 2021) |  |  |  | 811k€ |  | Spent (as per 15.10.2021) |  |  |  | 0k€ |  | Click this button to create a powerpoint presentation:
Risk
Overall Status |  |  |  | Budget |  |  |  |  | Budget (labor) |  |  |  | 751k€ |  | Budget (labor) |  |  |  | 0k€
|  |  |  | Artefacts |  |  |  |  | Budget (non-labor) |  |  |  | 60k€ |  | Budget (non-labor) |  |  |  | 0k€
ARTEFACTS
ID | Artefact Description |  |  | Progress |  | Approved Budget (labor) | Achievements | [7 empty] | Work to be done | [6 empty] | 15%
85%
0%
1 | Concept of Role Management and Role Governance including integration architecture to GIAM |  |  | 15% |  | 75k€ | Data workshops done | [6 empty] | Continuing with data analysis onboarding of project members | [7 empty] | 100%
10%
90%
2 | Automation concept in the context of access management (confidence rating definition) |  |  | 0% |  | 75k€ | [15 empty] | 0%
100%
0%
3 | Pilot Installation in AZ Technology or AZ SE with integration to GIAM; Focus on five critical systems (rootdom.net Active Directory, PKI, SAP, VPN, TBD) |  |  | 10% |  | 300k€ | [7 empty] | Ordering for necessary infrastructure Clarfication pilot licenses with ForgeRock | [7 empty] | 100%
4 | Showcase: (1) a regulator and audit compliant reporting capability (2) the benefits of integrating technical role management with organizational and business role management. |  |  | 0% |  | 150k€
5 | Design Role Management Service – i.e. high-level use cases and related RACI between OEs and AZT |  |  | 0% |  | 150k€
KPI |  |  | RISK |  | DESCRIPTION |  |  |  |  | CRITICALITY* |  | MITIGATION ACTIVITIES |  |  |  |  | RESOLUTION DATE
ID | KPI Description (Actuals/Target) |  | Artefact Risk |  | Hardware not available in time |  |  |  |  | Medium |  | Involvement of senior management |  |  |  |  | 2021-10-15
1 | # of reached milestones (0/5)
2 | (/)
|  |  | - | [6 empty] | -
On track
Actions required
|  | Management attention required | - | [6 empty] | -
* Criticality: |  | High = Major negative impact on artefacts/timline |  |  | Medium = Considerable impact on artefacts/timeline |  |  |  |  | Low = Minor negative impact on artefacts/timeline
Create Powerpoint

## M280
M280 |  | Measure Report - HY2 2021
[11 empty] | Status report is up to date: |  |  |  | No |  |  | Help required: |  | No
Measure Name: |  |  | Focus Area: |  |  |  |  | Measure Lead: |  |  |  | Measure Duration: |  |  |  | Status:
Advanced Network-based detection and response |  |  | Increase Detection |  |  |  |  | Thomas Wolf |  |  |  | 01.07.2021 - 31.12.2021 |  |  |  | as per 29.10.2021
[9 empty] | Approved (HY2 2021) |  |  |  | 353k€ |  | Spent (as per 15.10.2021) |  |  |  | 132k€ |  | Click this button to create a powerpoint presentation:
Risk
Overall Status |  |  |  | Budget |  |  |  |  | Budget (labor) |  |  |  | 250k€ |  | Budget (labor) |  |  |  | 132k€
|  |  |  | Artefacts |  |  |  |  | Budget (non-labor) |  |  |  | 103k€ |  | Budget (non-labor) |  |  |  | 0k€
ARTEFACTS
ID | Artefact Description |  |  | Progress |  | Approved Budget (labor) | Achievements | [7 empty] | Work to be done | [6 empty] | 30%
70%
20%
1 | Connection between Cynet and ADH Edge Node |  |  | 30% |  | € 85 k | Strategy aligned, need for gateway and additional box identified DER gateway process in progress New E1 box for ADH communicatin in alignment | [6 empty] | Install additional DCSO box (non-network) and gateway within EDR zone Implement data exchange | [7 empty] | 80%
35%
65%
2 | Deployment new ADH generation |  |  | 20% |  | € 60 k | Decision on 1:1 exchange taken (architectural improbement out-of scope for M280, bd in follow-up project 2022) Exchange processin E1 and other global DCs in progress | [6 empty] | Complete exchange process and old equipoment return in 10 or more DCs Prepare exhange in other DCs as far as possible | [7 empty] | 25%
75%
0%
3 | Integrated ACDC Infrastructure and processes |  |  | 35% |  | € 70 k | Strategy aligned So far, no required process alterations identified from previous state To be verified during project | [6 empty] | PoV execution and comparison with other vendor/approach Documentation | [7 empty] | 100%
4 | ADH connection to Cynet central endpoint data repositories established |  |  | 25% |  | € 35 k | Architecture and ADH/DCSO requirements aligned Cynet API interface and sample date provided | [6 empty] | Complete data model and interface Wait for prerequisutes: Artifact ID 1, partly ID 2 Create / Test connection, rollout, documentation
5 |  |  |  | 0%
KPI |  |  | RISK |  | DESCRIPTION |  |  |  |  | CRITICALITY* |  | MITIGATION ACTIVITIES |  |  |  |  | RESOLUTION DATE
ID | KPI Description (Actuals/Target) |  | Artefact Risk |  | ID 2: More ADH boxes to be exchanged (19) than anticipated (10) were identified. Insufficient documentation from predecessor project and resource shortage make it unlikely all 19 boxes can be exchanged within project run time. Some boxes might need follow-up activities after project. |  |  |  |  | Medium |  | DC Oprations were contacted to perform additional activities with priority. In alignment with program management and Group CIO, the decision was taken to keep KPI of 10 boxes minimum to be exchanged within project time, more on best effort. |  |  |  |  | tbd, not before 15.11.2011
1 | # of new generation ADH deployment (0/10)
2 | (/)
|  |  | - | [6 empty] | -
On track
Actions required
|  | Management attention required | - | [6 empty] | -
* Criticality: |  | High = Major negative impact on artefacts/timline |  |  | Medium = Considerable impact on artefacts/timeline |  |  |  |  | Low = Minor negative impact on artefacts/timeline
Create Powerpoint

## M281
M281 |  | Measure Report - HY2 2021
[11 empty] | Status report is up to date: |  |  |  | No |  |  | Help required: |  | No
Measure Name: |  |  | Focus Area: |  |  |  |  | Measure Lead: |  |  |  | Measure Duration: |  |  |  | Status:
Passive DNS Monitoring & DNS Firewalling |  |  | Increase Detection |  |  |  |  | Lucas Tscherter |  |  |  | 01.07.2021 - 31.12.2021 |  |  |  | as per 29.10.2021
[9 empty] | Approved (HY2 2021) |  |  |  | 337k€ |  | Spent (as per 15.10.2021) |  |  |  | 17k€ |  | Click this button to create a powerpoint presentation:
Risk
Overall Status |  |  |  | Budget |  |  |  |  | Budget (labor) |  |  |  | 210k€ |  | Budget (labor) |  |  |  | 17k€
|  |  |  | Artefacts |  |  |  |  | Budget (non-labor) |  |  |  | 127k€ |  | Budget (non-labor) |  |  |  | 0k€
ARTEFACTS
ID | Artefact Description |  |  | Progress |  | Approved Budget (labor) | Achievements | [7 empty] | Work to be done | [6 empty] | 45%
55%
30%
1 | Creation of logging and analytics architecture and implementation |  |  | 45% |  | € 80 k | Alignment completed and target architecture defined AGN DNS team deployed the required architecture Elastic to be used to aggregate logs and do analytics incl. alerting Integration with SOAR | [6 empty] | Architecuture setup almost complete. Last configuration to be done. Elastic X-Pack procurement ongoing | [7 empty] | 70%
40%
60%
2 | Connection of PoC DNS servers and creation/testing of use-cases |  |  | 30% |  | € 100 k | Initial use case definition done Use case developing ongoing | [6 empty] | Use case implementation to be completed ACDC process integration and overall alignment | [7 empty] | 0%
100%
0%
3 | DNS Sinkholing requirements and vendor discovery |  |  | 40% |  | € 30 k | Requirements clarified and analysis completed Sinkholing solution can be implemented AZ Tech internally | [6 empty] | Implement sinkholing solution List of bad domains (black list) to be integrated into existing configuration Vendor for domain black listing in analysis. Vendor calls to be scheduled | [7 empty] | 100%
4 |  |  |  | 0%
5 |  |  |  | 0%
KPI |  |  | RISK |  | DESCRIPTION |  |  |  |  | CRITICALITY* |  | MITIGATION ACTIVITIES |  |  |  |  | RESOLUTION DATE
ID | KPI Description (Actuals/Target) |  | - | [6 empty] | -
1 | # of DNS Server logs consumed (0/2)
2 | (/)
|  |  | - | [6 empty] | -
On track
Actions required
|  | Management attention required | - | [6 empty] | -
* Criticality: |  | High = Major negative impact on artefacts/timline |  |  | Medium = Considerable impact on artefacts/timeline |  |  |  |  | Low = Minor negative impact on artefacts/timeline
Create Powerpoint

## M282
M282 |  | Measure Report - HY2 2021
[11 empty] | Status report is up to date: |  |  |  | No |  |  | Help required: |  | No
Measure Name: |  |  | Focus Area: |  |  |  |  | Measure Lead: |  |  |  | Measure Duration: |  |  |  | Status:
Global Deception rollout |  |  | Increase Detection |  |  |  |  | Lucas Tscherter |  |  |  | 01.07.2021 - 31.12.2021 |  |  |  | as per 29.10.2021
[9 empty] | Approved (HY2 2021) |  |  |  | 1620k€ |  | Spent (as per 15.10.2021) |  |  |  | 22k€ |  | Click this button to create a powerpoint presentation:
Risk
Overall Status |  |  |  | Budget |  |  |  |  | Budget (labor) |  |  |  | 1350k€ |  | Budget (labor) |  |  |  | 22k€
|  |  |  | Artefacts |  |  |  |  | Budget (non-labor) |  |  |  | 270k€ |  | Budget (non-labor) |  |  |  | 0k€
ARTEFACTS
ID | Artefact Description |  |  | Progress |  | Approved Budget (labor) | Achievements | [7 empty] | Work to be done | [6 empty] | 60%
40%
45%
1 | Setup Deception infrastructure incl. rollout to Asia Pacific and North American DCs (AP1 & AP2 and NA1 & NA2) |  |  | 60% |  | € 560 k | Installation / Cabling in AP1 Data Center completed Appliances have arrived at the NA Datacenters on 5.10.21 | [6 empty] | Appliances in Transit to AP2 (Sydney), est. Delivery 21.10.21 Ongoing: Setup/Installation AP1 appliances Ongoing IP address reservation Installation in progress (expected by 22.10.) Finalize Cable Matrix for NA1 & NA2 | [7 empty] | 55%
40%
60%
2 | Cover FMO & CMP servers and AVC clients in AP1 & AP2 and NA1 & NA2 datacenters |  |  | 45% |  | € 600 k | Four teams identified for Server install Contact identified for AVC Regional ISO meeting scheduled for 18.10. Initiated alignment with regional FMO, CMP, AVC teams | [6 empty] | Alignment with Global Endpoint Teams in progress Alignment & communication with respective teams in progress | [7 empty] | 50%
50%
0%
3 | Conduct ADC Public Cloud Pilot |  |  | 40% |  | € 115 k | Alignment call with vendor PoC scope defined | [6 empty] | Setup PoC environment Cloud alignment in progress (w/ Architect, Vendor, …) | [7 empty] | 100%
4 | ACDC SOAR Integration |  |  | 50% |  | € 75 k | SOAR integration live for first use case (Decoy interaction), | [6 empty] | SOAR integration in preparation for Decoy Interaction
5 |  |  |  | 0%
KPI |  |  | RISK |  | DESCRIPTION |  |  |  |  | CRITICALITY* |  | MITIGATION ACTIVITIES |  |  |  |  | RESOLUTION DATE
ID | KPI Description (Actuals/Target) |  | - | [6 empty] | -
1 | # of DCs and endpoints covered with deception (0/6)
2 | (/)
|  |  | - | [6 empty] | -
On track
Actions required
|  | Management attention required | - | [6 empty] | -
* Criticality: |  | High = Major negative impact on artefacts/timline |  |  | Medium = Considerable impact on artefacts/timeline |  |  |  |  | Low = Minor negative impact on artefacts/timeline
Create Powerpoint

## M283
M283 |  | Measure Report - HY2 2021
[11 empty] | Status report is up to date: |  |  |  | No |  |  | Help required: |  | No
Measure Name: |  |  | Focus Area: |  |  |  |  | Measure Lead: |  |  |  | Measure Duration: |  |  |  | Status:
Enhance Cloud response & Secure Allianz critical Apps |  |  | Increase Detection |  |  |  |  | Lucas Tscherter |  |  |  | 01.07.2021 - 31.12.2021 |  |  |  | as per 29.10.2021
[9 empty] | Approved (HY2 2021) |  |  |  | 505k€ |  | Spent (as per 15.10.2021) |  |  |  | 222k€ |  | Click this button to create a powerpoint presentation:
Risk
Overall Status |  |  |  | Budget |  |  |  |  | Budget (labor) |  |  |  | 475k€ |  | Budget (labor) |  |  |  | 222k€
|  |  |  | Artefacts |  |  |  |  | Budget (non-labor) |  |  |  | 30k€ |  | Budget (non-labor) |  |  |  | 0k€
ARTEFACTS
ID | Artefact Description |  |  | Progress |  | Approved Budget (labor) | Achievements | [7 empty] | Work to be done | [6 empty] | 50%
50%
45%
1 | Develop, implement and document Cloud Use Cases |  |  | 50% |  | € 110 k | 4 use cases implemented | [6 empty] | 7 use case in implementation Further analysis and prioritization of use cases | [7 empty] | 55%
60%
40%
2 | Create new and updated incident response run books for Cloud log sources |  |  | 45% |  | € 75 k | 3 run books implemented | [6 empty] | 5 run books in implementation | [7 empty] | 85%
15%
0%
3 | Review and fine tune the Cloud SIEM Sentinel |  |  | 60% |  | € 75 k | MS engineers finished analysis of existing Sentinel setup Sentinel retention concept under development Office365 and Active AD configuration being analyzed | [6 empty] | Review and finalize retention concept Continue with analysis and configuration of Sentinel O365 and Azure AD configuration/use cases to be aligned with IAM measures | [7 empty] | 100%
4 | Identify most security related events/information in Allianz business critical applications |  |  | 85% |  | € 110 k | Evaluation and prioritization done Questionnaire sent to all prioritized applications First feedback being collected and reviewed | [6 empty] | Evaluation and prioritization done Questionnaire sent to all prioritized applications First feedback collected and analyzed
5 | Prepare SIEM onboarding of identified business critical applications |  |  | 0% |  | € 105 k | Not yet started
KPI |  |  | RISK |  | DESCRIPTION |  |  |  |  | CRITICALITY* |  | MITIGATION ACTIVITIES |  |  |  |  | RESOLUTION DATE
ID | KPI Description (Actuals/Target) |  | - | [6 empty] | -
1 | # of implemented cloud use cases (3/10)
2 | (/)
|  |  | - | [6 empty] | -
On track
Actions required
|  | Management attention required | - | [6 empty] | -
* Criticality: |  | High = Major negative impact on artefacts/timline |  |  | Medium = Considerable impact on artefacts/timeline |  |  |  |  | Low = Minor negative impact on artefacts/timeline
Create Powerpoint

## M284
M284 |  | Measure Report - HY2 2021
[11 empty] | Status report is up to date: |  |  |  | No |  |  | Help required: |  | No
Measure Name: |  |  | Focus Area: |  |  |  |  | Measure Lead: |  |  |  | Measure Duration: |  |  |  | Status:
SOAR Rollout and case management implementation |  |  | Increase Detection |  |  |  |  | Lucas Tscherter |  |  |  | 01.07.2021 - 31.12.2021 |  |  |  | as per 29.10.2021
[9 empty] | Approved (HY2 2021) |  |  |  | 690k€ |  | Spent (as per 15.10.2021) |  |  |  | 346k€ |  | Click this button to create a powerpoint presentation:
Risk
Overall Status |  |  |  | Budget |  |  |  |  | Budget (labor) |  |  |  | 610k€ |  | Budget (labor) |  |  |  | 271k€
|  |  |  | Artefacts |  |  |  |  | Budget (non-labor) |  |  |  | 80k€ |  | Budget (non-labor) |  |  |  | 75k€
ARTEFACTS
ID | Artefact Description |  |  | Progress |  | Approved Budget (labor) | Achievements | [7 empty] | Work to be done | [6 empty] | 65%
35%
55%
1 | Implement SOAR integrations and play books |  |  | 65% |  | € 300 k | Implementation of additional playbooks and integrations continuing | [6 empty] | One new playbook added to the production system Alignment on mail integration ongoing | [7 empty] | 45%
75%
25%
2 | Drive the shift from Incident to Case Management |  |  | 55% |  | € 140 k | Collected feedback from the development team of SOAR on the concept of Case Management | [6 empty] | Follow-Up Workshop to present the initial draft for feedback by the ACDC team moved to 15.10.2021 because of the lack of availability of the ACDC team. | [7 empty] | 0%
100%
0%
3 | Increase user adoption of SOAR within ACDC and onboard local security teams through trainings and guided use case development |  |  | 75% |  | € 170 k | Teams from AZ France (6 members) and AZ IBL (5 members) onboarded to the SOAR platform | [6 empty] | Training and onboarding the IH teams in North America (Allianz Technology America) | [7 empty] | 100%
4 |  |  |  | 0%
5 |  |  |  | 0%
KPI |  |  | RISK |  | DESCRIPTION |  |  |  |  | CRITICALITY* |  | MITIGATION ACTIVITIES |  |  |  |  | RESOLUTION DATE
ID | KPI Description (Actuals/Target)
1 | # of integrations or play books implemented (5/8)
2 | (/)
On track
Actions required
|  | Management attention required | - | [6 empty] | -
* Criticality: |  | High = Major negative impact on artefacts/timline |  |  | Medium = Considerable impact on artefacts/timeline |  |  |  |  | Low = Minor negative impact on artefacts/timeline
Create Powerpoint

## M285
M285 |  | Measure Report - HY2 2021
[11 empty] | Status report is up to date: |  |  |  | No |  |  | Help required: |  | Yes
Measure Name: |  |  | Focus Area: |  |  |  |  | Measure Lead: |  |  |  | Measure Duration: |  |  |  | Status:
Increase Effectiveness of Micro Segmentation and Rollout in EU |  |  | Increase Detection |  |  |  |  | Clemens Friedrich |  |  |  | 01.07.2021 - 31.12.2021 |  |  |  | as per 29.10.2021
[9 empty] | Approved (HY2 2021) |  |  |  | 420k€ |  | Spent (as per 15.10.2021) |  |  |  | 153k€ |  | Click this button to create a powerpoint presentation:
Risk
Overall Status |  |  |  | Budget |  |  |  |  | Budget (labor) |  |  |  | 420k€ |  | Budget (labor) |  |  |  | 153k€
|  |  |  | Artefacts |  |  |  |  | Budget (non-labor) |  |  |  | 0k€ |  | Budget (non-labor) |  |  |  | 0k€
ARTEFACTS
ID | Artefact Description |  |  | Progress |  | Approved Budget (labor) | Achievements | [7 empty] | Work to be done | [6 empty] | 20%
80%
30%
1 | Move 30 business critical applications from Build- to Enforce-Mode and develop a standardized process |  |  | 20% |  | € 205 k | - 4 apps enforced - 12 apps in enforcement pipeline - AZ MO - 2 apps enforced - AZ Tech - 2 apps enforced - Artefact at risk due to missing commitment and new timeline in UK - AZ Czech - Enforcement progressed according to Plan, test and integration of first app enforced - AZ SK - Rule creation progressed - AZ FR - Work on technical rules progressed - AZ PL - Kicked Off Enforcement Discussions, clarified open questions and concerns - AZ D - Assessed Use Case and kicked off discussion | [6 empty] | - AZ MO - Plan enforcement for upcoming apps - AZ CZ – Move apps to enforcement according to planned timeline - AZ SK - Support alignment between OE and local Tech Branch and finalize enforcement - AZ FR – Continue work on technical rules, Define and Prepare Enforcement-PoC - AZ PL – Move to Policy Creation Phase​ - EH - Provide Enforcement Demo to the team - AZ D - Progress Topic in collaboration with the OE | [7 empty] | 70%
55%
45%
2 | Onboarding of additional 25 business critical applications to AMS in Europe |  |  | 30% |  | € 145 k | - 8 Applications onboarded - AZ Suisse – 3 applications onboarded, further onboarding in pipeline - AZ MO - Onboarding of Integration environment for 2 apps done - AZ GR - Prerequisite Checks for new app performed | [6 empty] | - AZ Suisse – Further collaborate with the OE for other Onboardings - AZ MO - Plan and perform onboarding of Prod environment of 2 apps - AZ GR - Plan and perform onboarding - AZ Reinsurance – Chase OE for feedback on scope - AGCS / AZ P- Continue alignment | [7 empty] | 0%
100%
0%
3 | Finalize SNOW- and AdoIT-Integration to improve operational processes and governance |  |  | 55% |  | € 70 k | - SNOW-Integration: Confirmed that interface is working as expected, development of minimum valuable product kicked off - AdoIT-Integration: App linking progressed | [6 empty] | - Finalize MVP - Finalize App Linking in AdoIT - Finalize Reporting-Model once all apps are linked | [7 empty] | 100%
4 |  |  |  | 0%
5 |  |  |  | 0%
KPI |  |  | RISK |  | DESCRIPTION |  |  |  |  | CRITICALITY* |  | MITIGATION ACTIVITIES |  |  |  |  | RESOLUTION DATE
ID | KPI Description (Actuals/Target) |  | Artefact Risk |  | Missing commitment and delayed timeline for AZ UK is putting Artefact 1 at risk / as unachievable |  |  |  |  | High |  | -Escalation kicked off, resulted in receiving feedback of delayed timeline - Looking into possibilties on how to achieve the KPI |  |  |  |  | -
1 | # of business critical applications moved to Enforce-Mode (4/30)
2 | (/)
|  |  | - | [6 empty] | -
On track
Actions required
|  | Management attention required | - | [6 empty] | -
* Criticality: |  | High = Major negative impact on artefacts/timline |  |  | Medium = Considerable impact on artefacts/timeline |  |  |  |  | Low = Minor negative impact on artefacts/timeline
Create Powerpoint

## M286
M286 |  | Measure Report - HY2 2021
[11 empty] | Status report is up to date: |  |  |  | No |  |  | Help required: |  | No
Measure Name: |  |  | Focus Area: |  |  |  |  | Measure Lead: |  |  |  | Measure Duration: |  |  |  | Status:
Build Central Dashboard to Increase Transparency and Real Time Monitoring |  |  | Increase Detection |  |  |  |  | Clemens Friedrich |  |  |  | 01.07.2021 - 31.12.2021 |  |  |  | as per 29.10.2021
[9 empty] | Approved (HY2 2021) |  |  |  | 285k€ |  | Spent (as per 15.10.2021) |  |  |  | 8k€ |  | Click this button to create a powerpoint presentation:
Risk
Overall Status |  |  |  | Budget |  |  |  |  | Budget (labor) |  |  |  | 285k€ |  | Budget (labor) |  |  |  | 8k€
|  |  |  | Artefacts |  |  |  |  | Budget (non-labor) |  |  |  | 0k€ |  | Budget (non-labor) |  |  |  | 0k€
ARTEFACTS
ID | Artefact Description |  |  | Progress |  | Approved Budget (labor) | Achievements | [7 empty] | Work to be done | [6 empty] | 100%
0%
15%
1 | Development of 6 Real Time Reporting User Stories based on selected sensors |  |  | 100% |  | 100k€ | Initial combined Architecture Design User stories defined (6/6) Synced with M294 on data and API fields Alignment meetings with M294 and ACDC/EDR prepared | [6 empty] | Artefact complete | [7 empty] | 85%
5%
95%
2 | Implementation of data delivery towards Governance & Control Dashboard |  |  | 15% |  | € 60 k | Tests with time series data lake done to create basis for historic data views (InfluxDB, TimeScaleDB) Meetings with Sensor Owners started (SIEM, Cynet, more to follow) Access to sensor data lake requested Access to API defined with M294 | [6 empty] | API towards User Interface Sensor Access available Backend extended and Source Code delivered | [7 empty] | 0%
100%
0%
3 | Development of 6 Reporting Dashboards based on defined User Stories |  |  | 5% |  | € 125 k | Presented current front-end implementation to stakeholders Updated existing prototype data (“under the hood”) to prepare for results from WP2 Implementation started | [6 empty] | 6 User Stories implemented in Front-End SSO integrated Friendly User Test Source Code and Documentation Migration from Public Cloud (AWS) to Hybrid Cloud environments (CMP) necessary to access sensors / data sources | [7 empty] | 100%
4 |  |  |  | 0%
5 |  |  |  | 0%
KPI |  |  | RISK |  | DESCRIPTION |  |  |  |  | CRITICALITY* |  | MITIGATION ACTIVITIES |  |  |  |  | RESOLUTION DATE
ID | KPI Description (Actuals/Target) |  | - | [6 empty] | -
1 | # of Reporting User Stories designed and User Stories implemented (6/12)
2 | (/)
|  |  | - | [6 empty] | -
On track
Actions required
|  | Management attention required | - | [6 empty] | -
* Criticality: |  | High = Major negative impact on artefacts/timline |  |  | Medium = Considerable impact on artefacts/timeline |  |  |  |  | Low = Minor negative impact on artefacts/timeline
Create Powerpoint

## M287
M287 |  | Measure Report - HY2 2021
[11 empty] | Status report is up to date: |  |  |  | No |  |  | Help required: |  | No
Measure Name: |  |  | Focus Area: |  |  |  |  | Measure Lead: |  |  |  | Measure Duration: |  |  |  | Status:
Extension of vulnerability mgmt. to clients and global policy compliance rollout |  |  | Reduce Damage |  |  |  |  | Clemens Friedrich |  |  |  | 01.07.2021 - 31.12.2021 |  |  |  | as per 29.10.2021
[9 empty] | Approved (HY2 2021) |  |  |  | 1250k€ |  | Spent (as per 15.10.2021) |  |  |  | 336k€ |  | Click this button to create a powerpoint presentation:
Risk
Overall Status |  |  |  | Budget |  |  |  |  | Budget (labor) |  |  |  | 1150k€ |  | Budget (labor) |  |  |  | 336k€
|  |  |  | Artefacts |  |  |  |  | Budget (non-labor) |  |  |  | 100k€ |  | Budget (non-labor) |  |  |  | 0k€
ARTEFACTS
ID | Artefact Description |  |  | Progress |  | Approved Budget (labor) | Achievements | [7 empty] | Work to be done | [6 empty] | 80%
20%
45%
1 | Extension of AVM Scope to cover clients |  |  | 80% |  | € 150 k | Scripts and data models have been adjusted. 2 Prototype dashboards created in Splunk. | [6 empty] | Next dashboards will be AGI, Romania & Australia Scripts for automating the replication of further dashboards in progress. | [7 empty] | 55%
80%
20%
2 | Rollout of the Qualys Agent to clients in 20 OEs to enable Vulnerability Scanning |  |  | 45% |  | € 570 k | Commitment of 20+ OEs received for Qualys Agent Rollout on Clients Three OEs in CEE completed (Romania, Czech Republic, Bulgaria); AGI & ADEUS complete Deployment on AMC completed | [6 empty] | Align on global AVC approach (Stand. AZTech Image & BYOI) Support Malaysia, Sri Lanka and China Life during their rollouts. Alignment with Adeus to analyse status quo. | [7 empty] | 40%
60%
45%
3 | Enable OS Level Policy Compliance scanning & reporting on 10.000 FMO & HC servers |  |  | 80% |  | € 260 k | GPAM solution for Linux and WIN tested successfully PC activation done for 9000 servers (mainly FMO NA & HC) | [6 empty] | Rollout of technical users for FMO EU, close collaboration betweeen OE, GPAM and AVM necessary | [7 empty] | 55%
4 | Develop proposal and concept for tool-based remediation tracking process |  |  | 40% |  | € 90 k | First alignments done and prerequisites defined | [6 empty] | Clarification if CMDB coverage for local assets is sufficient Clarification of license costs Develop interims solution for automating the process
5 | Creation of documentation for definition of AVM Scope (Cloud Agents / Policy Compliance) as a Class 1 Standard |  |  | 45% |  | € 80 k | First alignements and expectation management done. Clarification of current status done (AVM no class 1 standard yet) | [6 empty] | General decision if class 1 standardized will provide benefit
KPI |  |  | RISK |  | DESCRIPTION |  |  |  |  | CRITICALITY* |  | MITIGATION ACTIVITIES |  |  |  |  | RESOLUTION DATE
ID | KPI Description (Actuals/Target) |  | - | [6 empty] | -
1 | # of OEs covered with Qualys agents on clients (6/20)
2 | (/)
|  |  | - | [6 empty] | -
On track
Actions required
|  | Management attention required | - | [6 empty] | -
* Criticality: |  | High = Major negative impact on artefacts/timline |  |  | Medium = Considerable impact on artefacts/timeline |  |  |  |  | Low = Minor negative impact on artefacts/timeline
Create Powerpoint

## M288
M288 |  | Measure Report - HY2 2021
[11 empty] | Status report is up to date: |  |  |  | No |  |  | Help required: |  | No
Measure Name: |  |  | Focus Area: |  |  |  |  | Measure Lead: |  |  |  | Measure Duration: |  |  |  | Status:
AGN Secure Network Access and Segregation |  |  | Reduce Damage |  |  |  |  | Michael Kahlfuss |  |  |  | 01.07.2021 - 31.12.2021 |  |  |  | as per 29.10.2021
[9 empty] | Approved (HY2 2021) |  |  |  | 1.085k€ |  | Spent (as per 15.10.2021) |  |  |  | 343k€ |  | Click this button to create a powerpoint presentation:
Risk
Overall Status |  |  |  | Budget |  |  |  |  | Budget (labor) |  |  |  | 688k€ |  | Budget (labor) |  |  |  | 343k€
|  |  |  | Artefacts |  |  |  |  | Budget (non-labor) |  |  |  | 397k€ |  | Budget (non-labor) |  |  |  | 0k€
ARTEFACTS
ID | Artefact Description |  |  | Progress |  | Approved Budget (labor) | Achievements | [7 empty] | Work to be done | [6 empty] | 20%
80%
15%
1 | Finalizes the current NAC concept for Network Access Control |  |  | 20% |  | € 124,8 k | - First workshops started to define the onboarding process for AMC and printer to 802.1X - Receive feedback on the printers in Ireland (which models are 802.1x capable) | [6 empty] | - Sup-PKI mus be setup (planned fot 18th October) - AMC configuration for 802.1X must be discussed with the vendor - discuss the other devices with ISO Ireland | [7 empty] | 85%
30%
70%
2 | Support from Accenture and Cisco to work on the concept and the implementation strategy |  |  | 15% |  | € 288 k | - ODM is created and the scope is aligned with Accenture - Accenture delivered the offer (for voice and video endpoints) | [6 empty] | - ODM process started to commission the Accenture offer - order Telephony devices so that we can start testing - Service contract with Cisco must be agreed | [7 empty] | 10%
90%
0%
3 | Run and test implementation for a pilot site |  |  | 30% |  | € 62,4 k | - LAN test eqipiment available - 802.1x configuration tested with printer | [6 empty] | - Get various device classes for the test environment - Plan the test of AGN telephones and video endpoints with Accenture | [7 empty] | 100%
4 | Preparation, Planning and Go-Live for 1 x OE |  |  | 10% |  | € 62,6 k | - Scope discussed in detail with the Irish colleagues and feedback was received on the locally operated printers with regard to 802.1x capability. - Discussion started with the ISO in Ireland | [6 empty] | - Plan a weekly or bi-weekly meeting with ISO Ireland to discuss and finalize further configurations
5 | Implementation of security gateway for all global Guest Wi-Fi services incl. alerting to ACDC |  |  | 0% |  | € 150 k
KPI |  |  | RISK |  | DESCRIPTION |  |  |  |  | CRITICALITY* |  | MITIGATION ACTIVITIES |  |  |  |  | RESOLUTION DATE
ID | KPI Description (Actuals/Target) |  | General Risk |  | Availability of internal resources (AMC, PKI); these are also required by other projects |  |  |  |  | Medium |  | Define substitutions so that there is no bottleneck |  |  |  |  | 2021-09-30
1 | # of reached milestones (1/4)
2 | (/)
|  |  | General Risk |  | Without access to Group Directory we cannot validate if the email address in the certificate is 1) still active and 2) the OE that it belongs to |  |  |  |  | Low |  | If we get no access to GD, then the only things we can validate are: - certificate no expired - certificate signed by Allianz CA |  |  |  |  | 2021-12-31
On track
Actions required
|  | Management attention required | General Risk
* Criticality: |  | High = Major negative impact on artefacts/timline |  |  | Medium = Considerable impact on artefacts/timeline |  |  |  |  | Low = Minor negative impact on artefacts/timeline
Create Powerpoint
Create Powerpoint

## M289
M289 |  | Measure Report - HY2 2021
[11 empty] | Status report is up to date: |  |  |  | No |  |  | Help required: |  | No
Measure Name: |  |  | Focus Area: |  |  |  |  | Measure Lead: |  |  |  | Measure Duration: |  |  |  | Status:
Acceleration of Password Manager service |  |  | Reduce Damage |  |  |  |  | Rainer Mahlo |  |  |  | 01.07.2021 - 31.12.2021 |  |  |  | as per 29.10.2021
[9 empty] | Approved (HY2 2021) |  |  |  | 350k€ |  | Spent (as per 15.10.2021) |  |  |  | 204k€ |  | Click this button to create a powerpoint presentation:
Risk
Overall Status |  |  |  | Budget |  |  |  |  | Budget (labor) |  |  |  | 350k€ |  | Budget (labor) |  |  |  | 204k€
|  |  |  | Artefacts |  |  |  |  | Budget (non-labor) |  |  |  | 0k€ |  | Budget (non-labor) |  |  |  | 0k€
ARTEFACTS
ID | Artefact Description |  |  | Progress |  | Approved Budget (labor) | Achievements | [7 empty] | Work to be done | [6 empty] | 75%
25%
75%
1 | Completion of the Testing Phase with System Integration Test |  |  | 75% |  | € 90 k | - System integration test with Veridium ongoing | [6 empty] | - Complete Veridium integration and testing | [7 empty] | 25%
25%
75%
2 | Vendor Selection and Contracting with Vendor |  |  | 75% |  | € 15 k | - Agreed vendor decision with all relevant stakeholders | [6 empty] | - Get final contract | [7 empty] | 25%
75%
0%
3 | Service Creation to enable the solution for the OE’s |  |  | 25% |  | € 120 k | - 2/17 SPM subprocesses completed - SNOW implementation ongoing | [6 empty] | - Completion SPM-Process - Technical integration in SNOW | [7 empty] | 100%
4 | Technical Integration and Roll-out |  |  | 25% |  | € 125 k | - Project internal test to integrate Veridium as a MFA solution - Re Evaluate MS Authenticator as possible MFA solution due to technical constraints occured with Veridium | [6 empty] | - Completion of the target solution design - Completion of the rollout planning - Workers council approval
5 |  |  |  | 0%
KPI |  |  | RISK |  | DESCRIPTION |  |  |  |  | CRITICALITY* |  | MITIGATION ACTIVITIES |  |  |  |  | RESOLUTION DATE
ID | KPI Description (Actuals/Target) |  | Artefact Risk |  | New device detection on pooled VDI environment (AVC) |  |  |  |  | High |  | User Test in Q3 |  |  |  |  | 2021-12-31
1 | # of users rolled-out to password manager service (0/1000)
2 | (/)
|  |  | General Risk |  | Solutions’ ability to fulfill AZ requirements |  |  |  |  | High |  | User Test in Q3; Ergonomics Test in Q4 |  |  |  |  | 2021-12-31
On track
Actions required
|  | Management attention required | Artefact Risk |  | Resources to support with POC technical set-up & initial launch in production |  |  |  |  | Medium |  | APM support needed for SW package deployment |  |  |  |  | 2021-12-31
-
-
* Criticality: |  | High = Major negative impact on artefacts/timline |  |  | Medium = Considerable impact on artefacts/timeline |  |  |  |  | Low = Minor negative impact on artefacts/timeline
Create Powerpoint

## M290
M290 |  | Measure Report - HY2 2021
[11 empty] | Status report is up to date: |  |  |  | No |  |  | Help required: |  | No
Measure Name: |  |  | Focus Area: |  |  |  |  | Measure Lead: |  |  |  | Measure Duration: |  |  |  | Status:
Re-Design Of Cloud Application Discovery Service |  |  | Reduce Damage |  |  |  |  | Clemens Friedrich |  |  |  | 01.07.2021 - 31.12.2021 |  |  |  | as per 29.10.2021
[9 empty] | Approved (HY2 2021) |  |  |  | 430k€ |  | Spent (as per 15.10.2021) |  |  |  | 33k€ |  | Click this button to create a powerpoint presentation:
Risk
Overall Status |  |  |  | Budget |  |  |  |  | Budget (labor) |  |  |  | 410k€ |  | Budget (labor) |  |  |  | 33k€
|  |  |  | Artefacts |  |  |  |  | Budget (non-labor) |  |  |  | 20k€ |  | Budget (non-labor) |  |  |  | 0k€
ARTEFACTS
ID | Artefact Description |  |  | Progress |  | Approved Budget (labor) | Achievements | [7 empty] | Work to be done | [6 empty] | 100%
0%
100%
1 | Development of technical & business needs and constraints |  |  | 100% |  | € 50 k | Artefact deliverd | [14 empty] | 0%
100%
0%
2 | Development of future service design of CAD service |  |  | 100% |  | € 65 k | Artefact deliverd | [14 empty] | 10%
90%
5%
3 | Design of interim-solution for 2022 |  |  | 100% |  | € 40 k | Artefact deliverd | [14 empty] | 95%
4 | Prepare Implementation of Interim Solution, based on selected product |  |  | 10% |  | € 195 k | Basis for decision for new CASB tool and choose the new tool developed (McAfee) | [6 empty] | Identify technical requirements from Allianz & McAfee Conduct implementation preparations (e.g. POC testing) of the new solution
5 | Establish Infrastructure Readiness for technical solution |  |  | 5% |  | € 60 k | Kick-Off with McAfee performed | [6 empty] | Setup CASB tenant and on-prem infrastructure Configure the on-prem infrastructure, CASB tool and needed integrations OE Onboarding to new solution
KPI |  |  | RISK |  | DESCRIPTION |  |  |  |  | CRITICALITY* |  | MITIGATION ACTIVITIES |  |  |  |  | RESOLUTION DATE
ID | KPI Description (Actuals/Target)
1 | # of Service design documents for future CAD service developed (6/6)
2 | # of OEs/BUs onboarded to interim solution (0/3)
|  |  | - | [6 empty] | -
On track
Actions required
|  | Management attention required | - | [6 empty] | -
* Criticality: |  | High = Major negative impact on artefacts/timline |  |  | Medium = Considerable impact on artefacts/timeline |  |  |  |  | Low = Minor negative impact on artefacts/timeline
Create Powerpoint

## M291
M291 |  | Measure Report - HY2 2021
[11 empty] | Status report is up to date: |  |  |  | No |  |  | Help required: |  | No
Measure Name: |  |  | Focus Area: |  |  |  |  | Measure Lead: |  |  |  | Measure Duration: |  |  |  | Status:
Privileged Access Management for Cloud |  |  | Reduce Damage |  |  |  |  | Alexander Heinze |  |  |  | 01.07.2021 - 31.12.2021 |  |  |  | as per 29.10.2021
[9 empty] | Approved (HY2 2021) |  |  |  | 200k€ |  | Spent (as per 15.10.2021) |  |  |  | 35k€ |  | Click this button to create a powerpoint presentation:
Risk
Overall Status |  |  |  | Budget |  |  |  |  | Budget (labor) |  |  |  | 200k€ |  | Budget (labor) |  |  |  | 35k€
|  |  |  | Artefacts |  |  |  |  | Budget (non-labor) |  |  |  | 0k€ |  | Budget (non-labor) |  |  |  | 0k€
ARTEFACTS
ID | Artefact Description |  |  | Progress |  | Approved Budget (labor) | Achievements | [7 empty] | Work to be done | [6 empty] | 25%
75%
0%
1 | Design a concept for privileged access management solution for cloud |  |  | 25% |  | € 67 k | Workshop to collect Use Cases executed. | [6 empty] | Alignment how the architecure should look like. Design high level architecture. | [7 empty] | 100%
0%
100%
2 | Implement a POC for the privileged access management for selected accounts on Azure, AWS and databases |  |  | 0% |  | € 67 k | [7 empty] | Implementing of POC has to be planned. | [7 empty] | 0%
100%
0%
3 | Create a proposal to implement the solution as a standard service |  |  | 0% |  | € 66 k | [7 empty] | Creating of a proposal has to be planned. | [7 empty] | 100%
4 |  |  |  | 0%
5 |  |  |  | 0%
KPI |  |  | RISK |  | DESCRIPTION |  |  |  |  | CRITICALITY* |  | MITIGATION ACTIVITIES |  |  |  |  | RESOLUTION DATE
ID | KPI Description (Actuals/Target) |  | General Risk |  | Lack of adequate resource support , e.g. internal experts due to the amount of projects and operational involvement. |  |  |  |  | Low |  | Management awareness and commitment of internal ressources |  |  |  |  | End of September 2021
1 | # of validate possible integrations (0/4)
2 | (/)
|  |  | - | [6 empty] | -
On track
Actions required
|  | Management attention required | - | [6 empty] | -
* Criticality: |  | High = Major negative impact on artefacts/timline |  |  | Medium = Considerable impact on artefacts/timeline |  |  |  |  | Low = Minor negative impact on artefacts/timeline
Create Powerpoint

## M301
M301 |  | Measure Report - HY2 2021
[11 empty] | Status report is up to date: |  |  |  | No |  |  | Help required: |  | No
Measure Name: |  |  | Focus Area: |  |  |  |  | Measure Lead: |  |  |  | Measure Duration: |  |  |  | Status:
Global Tier 0 Hosting Platform Preparation & APAC Pilot |  |  | Reduce Damage |  |  |  |  | Alexander Heinze |  |  |  | 15.08.2021 - 31.12.2021 |  |  |  | as per 29.10.2021
[9 empty] | Approved (HY2 2021) |  |  |  | 1000k€ |  | Spent (as per 15.10.2021) |  |  |  | 2k€ |  | Click this button to create a powerpoint presentation:
Risk
Overall Status |  |  |  | Budget |  |  |  |  | Budget (labor) |  |  |  | 750k€ |  | Budget (labor) |  |  |  | 2k€
|  |  |  | Artefacts |  |  |  |  | Budget (non-labor) |  |  |  | 250k€ |  | Budget (non-labor) |  |  |  | 0k€
ARTEFACTS
ID | Artefact Description |  |  | Progress |  | Approved Budget (labor) | Achievements | [7 empty] | Work to be done | [6 empty] | 30%
70%
25%
1 | Global architecture reviewed and readjusted to latest conditions |  |  | 30% |  | € 50 k | Topics that need follow-up discussion(s) successfully identified; Technical changes aligned with AZT. | [6 empty] | Follow-up on SCCM/SCOM discussion, once Hyper-V servers have been successfully installed. | [7 empty] | 75%
0%
100%
2 | Tier 0 Hosting Platform Implemented in APAC (AP1 & AP2 datacenter) |  |  | 25% |  | € 375 k | Hardware racked & stacked in AP1 + AP2; Microsoft technician onboarded (system access established from UF); In progress: Latest firmware updates installed on Lenovo servers. | [6 empty] | Testing of FCCs once OS is installed; OS, Hyper-V, HGS installation & configuration; Backlog refinement for next installation steps. | [7 empty] | 20%
80%
90%
3 | APAC Pilot Implemented |  |  | 0% |  | € 155 k | not yet started (dependency on artefacts 1 and 2) | [6 empty] | n/a | [7 empty] | 10%
4 | Concept for Service Extension to Fully Managed Model (PaaS/SaaS) Designed |  |  | 20% |  | € 125 k | Service change demand for SaaS requested; Alignments with SPM teams ongoing; Overview/outlook presented to OEs on AD Round Table event. | [6 empty] | In progress: Identification of SPM processes that need to be adjusted when extending the current service by additional components (PaaS, SaaS)
5 | Effective and streamlined liaison with local AD administrators established |  |  | 90% |  | € 45 k | AD Community established and active. | [6 empty] | In progress: Formalized 1-page documentation about AD Community, its communication channels, responsibilities and routines.
KPI |  |  | RISK |  | DESCRIPTION |  |  |  |  | CRITICALITY* |  | MITIGATION ACTIVITIES |  |  |  |  | RESOLUTION DATE
ID | KPI Description (Actuals/Target) |  | - | [6 empty] | -
1 | # of Global Tier 0 Hosting Platform Design and APAC Pilot (0/8)
2 | # of Local APAC units of Allianz Partners: Domain Controllers onboarded to Tier 0 Hosting Platform (0/4)
|  |  | - | [6 empty] | -
On track
Actions required
|  | Management attention required | - | [6 empty] | -
* Criticality: |  | High = Major negative impact on artefacts/timline |  |  | Medium = Considerable impact on artefacts/timeline |  |  |  |  | Low = Minor negative impact on artefacts/timeline
Create Powerpoint

## M292
M292 |  | Measure Report - HY2 2021
[11 empty] | Status report is up to date: |  |  |  | No |  |  | Help required: |  | No
Measure Name: |  |  | Focus Area: |  |  |  |  | Measure Lead: |  |  |  | Measure Duration: |  |  |  | Status:
Double Key Encryption / Extended Security & Compliance for M365 |  |  | Streamline Compliance |  |  |  |  | Julian Bönigk |  |  |  | 01.07.2021 - 31.12.2021 |  |  |  | as per 29.10.2021
[9 empty] | Approved (HY2 2021) |  |  |  | 750k€ |  | Spent (as per 15.10.2021) |  |  |  | 445k€ |  | Click this button to create a powerpoint presentation:
Risk
Overall Status |  |  |  | Budget |  |  |  |  | Budget (labor) |  |  |  | 690k€ |  | Budget (labor) |  |  |  | 445k€
|  |  |  | Artefacts |  |  |  |  | Budget (non-labor) |  |  |  | 60k€ |  | Budget (non-labor) |  |  |  | 0k€
ARTEFACTS
ID | Artefact Description |  |  | Progress |  | Approved Budget (labor) | Achievements | [7 empty] | Work to be done | [6 empty] | 100%
0%
100%
1 | Documented and approved service design |  |  | 100% |  | € 120 k | High Level Service Design & Low Level Service Design approved NBM approved Demand survey conducted, service price defined, incl. material number | [14 empty] | 0%
85%
15%
2 | Data privacy and security assessments done |  |  | 100% |  | € 100 k | PIA approved. ARA signed for 2021 by ISO Creation of BCM documentation | [6 empty] | Include SSS in the next ARA | [7 empty] | 40%
60%
60%
3 | DLP configuration defined for MS Teams, SPO, OD4B |  |  | 85% |  | € 100 k | Technical evaluation of communication DLP for MS Teams done, core team testing ongoing | [6 empty] | Assess technical possibilities for MS Teams, SPO, OD4B Reconsider active DLP blocking in policies, evaluate OE-specific possibilities for policies & reporting | [7 empty] | 40%
4 | Enhanced MIP features prepared in production according to final service design |  |  | 40% |  | € 200 k | DKE design finalized, DKE tested on AMC, order of Luna HSM done | [6 empty] | Validate when O365 ProPlus will be rolled out on AVC Prepare backend for the productive rollout next year
5 | Enhanced document management features available in production |  |  | 60% |  | € 230 k | Define SPO site design that is in-line with ASIDM, AGCS feedback sessions conducted, price negotiation with Harmon.ie finalized & packaging initiated | [6 empty] | Special release of Harmon.ie on 10/8/21 on AVC, Rollout of new O365 basic sites starting on 10/15/21, prepare backend for retention policies, O365 DMS sites released mid of November
KPI |  |  | RISK |  | DESCRIPTION |  |  |  |  | CRITICALITY* |  | MITIGATION ACTIVITIES |  |  |  |  | RESOLUTION DATE
ID | KPI Description (Actuals/Target) |  | General Risk |  | Office 365 ProPlus will not be rolled out on AVC in HY2 2021 |  |  |  |  | High |  | Actively support AVC team, track progress of implementation |  |  |  |  | 2021-12-31
1 | # of reached artefacts (3/5)
2 | (/)
|  |  | General Risk |  | Contract for Harmon.ie needs to be signed before go-live. Risk of delays, due to missing contract. |  |  |  |  | Medium |  | Actively track vendor |  |  |  |  | 2021-10-01
On track
Actions required
|  | Management attention required | General Risk |  | Not enough resources for operations |  |  |  |  | High |  | Recruting ongoing in different regions |  |  |  |  | 2021-10-15
* Criticality: |  | High = Major negative impact on artefacts/timline |  |  | Medium = Considerable impact on artefacts/timeline |  |  |  |  | Low = Minor negative impact on artefacts/timeline
Create Powerpoint

## M293
M293 |  | Measure Report - HY2 2021
[11 empty] | Status report is up to date: |  |  |  | No |  |  | Help required: |  | No
Measure Name: |  |  | Focus Area: |  |  |  |  | Measure Lead: |  |  |  | Measure Duration: |  |  |  | Status:
Automated Toxic Tracking for Client-based Assets |  |  | Streamline Compliance |  |  |  |  | Benjamin Warnholz |  |  |  | 01.07.2021 - 31.12.2021 |  |  |  | as per 29.10.2021
[9 empty] | Approved (HY2 2021) |  |  |  | 360k€ |  | Spent (as per 15.10.2021) |  |  |  | 126k€ |  | Click this button to create a powerpoint presentation:
Risk
Overall Status |  |  |  | Budget |  |  |  |  | Budget (labor) |  |  |  | 300k€ |  | Budget (labor) |  |  |  | 126k€
|  |  |  | Artefacts |  |  |  |  | Budget (non-labor) |  |  |  | 60k€ |  | Budget (non-labor) |  |  |  | 0k€
ARTEFACTS
ID | Artefact Description |  |  | Progress |  | Approved Budget (labor) | Achievements | [7 empty] | Work to be done | [6 empty] | 30%
70%
15%
1 | Toxicity baseline dashboard(s)1 integrating additional client data sources in SNOW |  |  | 30% |  | € 180k | Data sources and Tasks identified. High Level Design of target solution is finalized and aligned with all working teams. Workshops with involved technical teams done. | [6 empty] | The efforts needs to be approved by relevant teams. | [7 empty] | 85%
10%
90%
2 | Adoption of SAM Pro software models and SAM Pro lifecycle definitions in alignment with group toxic definitions (and retirement of related custom tables where possible) |  |  | 15% |  | € 40k | SAM Team technicaly enabled to perform the normalization. | [6 empty] | Normalization to be performed by SAM team. | [7 empty] | 5%
95%
0%
3 | Toxic Asset Management process documentation, incl. the interface to the SAM process regards normalization, software models, lifecycle definitions, etc. |  |  | 10% |  | € 60k | documentation requirements are identified and had begun. | [6 empty] | Finalize to get the data from Qualys API for APAC region over Public Cloud Platform, validate mapping of Qualys data to CMDB in order to support process documentation. | [7 empty] | 100%
4 | User Training Material (e.g., presentation) |  |  | 5% |  | € 20k | Training conecpt is in preperation. | [6 empty] | align on training concept and design modules.
5 |  |  |  | 0%
KPI |  |  | RISK |  | DESCRIPTION |  |  |  |  | CRITICALITY* |  | MITIGATION ACTIVITIES |  |  |  |  | RESOLUTION DATE
ID | KPI Description (Actuals/Target) |  | - | [6 empty] | -
1 | # of Toxic Asset Dashboard including client IT asset data (e.g. AVC, AMC, fat client, smart mobile de-vices) for minimum of 25 OEs (0/25)
2 | (/)
|  |  | - | [6 empty] | -
On track
Actions required
|  | Management attention required | - | [6 empty] | -
* Criticality: |  | High = Major negative impact on artefacts/timline |  |  | Medium = Considerable impact on artefacts/timeline |  |  |  |  | Low = Minor negative impact on artefacts/timeline
Create Powerpoint

## M294
M294 |  | Measure Report - HY2 2021
[11 empty] | Status report is up to date: |  |  |  | No |  |  | Help required: |  | No
Measure Name: |  |  | Focus Area: |  |  |  |  | Measure Lead: |  |  |  | Measure Duration: |  |  |  | Status:
Integrated Information Risk Management early Live​ |  |  | Streamline Compliance |  |  |  |  | Michael Habel |  |  |  | 01.07.2021 - 31.12.2021 |  |  |  | as per 29.10.2021
[9 empty] | Approved (HY2 2021) |  |  |  | 650k€ |  | Spent (as per 15.10.2021) |  |  |  | 212k€ |  | Click this button to create a powerpoint presentation:
Risk
Overall Status |  |  |  | Budget |  |  |  |  | Budget (labor) |  |  |  | 650k€ |  | Budget (labor) |  |  |  | 212k€
|  |  |  | Artefacts |  |  |  |  | Budget (non-labor) |  |  |  | 0k€ |  | Budget (non-labor) |  |  |  | 0k€
ARTEFACTS
ID | Artefact Description |  |  | Progress |  | Approved Budget (labor) | Achievements | [7 empty] | Work to be done | [6 empty] | 60%
40%
75%
1 | Harmonized scoping questionnaires integrated with existing CIA assessments |  |  | 60% |  | € 160 k | - process for a two-staged scoping process designed and aligned - Impact of “Schutzbedarfsanalyse” on ITOM questionnaire analysed Propositions and consequences elaborated on OE/ LE scoping and compliance self assessment Business Application questionnaire redesigned to reflect “HR application” triggered requirements ITOM questionnaire redesigned reflecting IT capabilities structure | [6 empty] | - Align on two-staged scoping process with Group IS Function and Group CIO - Analyse consequences of OE/ LE IT capability distribution on self assessment - Analyse capability oriented ITOM scoping questions with customer and align on final set of questions - Analyse recalibration of calculation method for Business Applications with customer and align on | [7 empty] | 25%
80%
20%
2 | Additional training material and sessions for IIRM (early live support) |  |  | 75% |  | € 130 k | - 14 Hands-on session conducted, Follow-Up as well as Reminders sent out to OEs specific OEs via email, - Building blocks and structure for stakeholder specific trainings defined and aligned - 3 Training Session conducted(out of 3) for Compliance self assessment | [6 empty] | - Unmanaged Risks Reporting in preparation - New Requirements for IIRM and neighboring solutions in discussion - Provide OE support towards ITOM risks | [7 empty] | 55%
45%
40%
3 | Design “internal” CIO and ISO IIRM KPIs |  |  | 80% |  | € 55 k | - CIO and ISO KPIs aligned [unmanaged risk KPI and upcoming work] | [6 empty] | - Create dashboard / report in EGRC Tool - Normalize Unmanaged Risk KPI and reflect in EGRC Cockpit | [7 empty] | 60%
4 | IT and IS EGRC Control Center and Interface is handed over to AZTech GRC Service |  |  | 55% |  | € 205 k | - Service transitionplan including hand over and shadowing phase created and communicated to EGRC Service - Technical skills for technical Service Ressource defined and communicated | [6 empty] | - Support AZTech in Operations by mf ressources until end of the year. - Alignment with GRC Service - Find Technical Ressource for hand over at GRC Service
5 | Cloud assessment training and rollout to all 60 OEs |  |  | 40% |  | € 100 k | -Trigger of Cloud path in IIRM analysed, change request in alignment - ISCG slides & Training Timeline approved by GITIS (Scholz, Lewandowski) and GITGO (Schweda), presented on ISCG, announced via AZ Connect and email (approved Text sent to ISOs and CIOs) - Dry Run and special training for Group It & IS (wave 1) scheduled - Invitations to training sessions of wave 2 sent | [6 empty] | - Review of approved Training slides due to changes ongoing - Invitations OEs to Rollout Training sessions according to the plan ongoing - Rescheduling and OE support ongoing
KPI |  |  | RISK |  | DESCRIPTION |  |  |  |  | CRITICALITY* |  | MITIGATION ACTIVITIES |  |  |  |  | RESOLUTION DATE
ID | KPI Description (Actuals/Target) |  | Artefact Risk
1 | # of reached milestones (2/5)
2 | (/)
Artefact Risk
On track
Actions required
|  | Management attention required | Artefact Risk
* Criticality: |  | High = Major negative impact on artefacts/timline |  |  | Medium = Considerable impact on artefacts/timeline |  |  |  |  | Low = Minor negative impact on artefacts/timeline
Create Powerpoint

## M295
M295 |  | Measure Report - HY2 2021
[11 empty] | Status report is up to date: |  |  |  | No |  |  | Help required: |  | No
Measure Name: |  |  | Focus Area: |  |  |  |  | Measure Lead: |  |  |  | Measure Duration: |  |  |  | Status:
Global Security Platform GITSO blueprint |  |  | Streamline Compliance |  |  |  |  | George Dietrichsbruckner |  |  |  | 01.07.2021 - 31.12.2021 |  |  |  | as per 29.10.2021
[9 empty] | Approved (HY2 2021) |  |  |  | 300k€ |  | Spent (as per 15.10.2021) |  |  |  | 97k€ |  | Click this button to create a powerpoint presentation:
Risk
Overall Status |  |  |  | Budget |  |  |  |  | Budget (labor) |  |  |  | 298k€ |  | Budget (labor) |  |  |  | 97k€
|  |  |  | Artefacts |  |  |  |  | Budget (non-labor) |  |  |  | 2k€ |  | Budget (non-labor) |  |  |  | 0k€
ARTEFACTS
ID | Artefact Description |  |  | Progress |  | Approved Budget (labor) | Achievements | [7 empty] | Work to be done | [6 empty] | 51%
49%
21%
1 | Key Performance Indicator for each of the 6 selected Security Services |  |  | 51% |  | €48 k | KPI suggestions requested from Service Managers/ Owners; KPI suggestions drafted for 12 Services, ready to be evaluated, extended and possibly extended by vetting circle. SIEM KPIs deemed sufficient. | [6 empty] | KPI Suggestions to be evaluated, extended and vetted by vettings circle; once done, OE vetting | [7 empty] | 79%
0%
100%
2 | Service Level Agreement vetting draft for each of the 6 selected Security Services |  |  | 21% |  | € 180 k | latest Service Descriptions requested from Service Owners; 1 service without SD; 7 SDs received; reminders for the others sent; EGRC SD redraft and gap fill in progress. | [6 empty] | SD (re)draft and gap fill based on AZ TEC Service Description template for the other services; request from AZTEC Service Catalogue owner for SDs not received | [7 empty] | 0%
100%
0%
3 | IS Implementation Guidance for Secure System Configuration Management |  |  |  |  | € 26 k | [15 empty] | 100%
4 | Analysis of AFRIS for control gaps in relations to Gearshift with Focus on SSP-OE relationship |  |  |  |  | € 44 k
5
|  |  | RISK |  | DESCRIPTION |  |  |  |  | CRITICALITY* |  | MITIGATION ACTIVITIES |  |  |  |  | RESOLUTION DATE
KPI |  |  | Artefact Risk |  | infomation/documentation/contracts not readily available; requests lenghty and SMEs/owners on holiday leave. |  |  |  |  | Medium
ID | KPI Description (Actuals/Target) |  | Artefact Risk |  | infomation/documentation/contracts not readily available; requests lenghty and SMEs/owners on holiday leave. |  |  |  |  | Medium |  | information requested through various sources from various stakeholders; partially received and reminders sent; catalogue owner contacted for remainder. |  |  |  |  | tbd
1 | # of KPI + SLA vetting draft for 6 Security Services (0/12)
2 | (/)
On track
Actions required
Management attention required
* Criticality: |  | High = Major negative impact on artefacts/timline
Create Powerpoint

## M296
M296 |  | Measure Report - HY2 2021
[11 empty] | Status report is up to date: |  |  |  | No |  |  | Help required: |  | No
Measure Name: |  |  | Focus Area: |  |  |  |  | Measure Lead: |  |  |  | Measure Duration: |  |  |  | Status:
Financial Loss Quantification |  |  | Build Security Organization / Skills |  |  |  |  | Thomas Thuspass |  |  |  | 01.07.2021 - 31.12.2021 |  |  |  | as per 29.10.2021
[9 empty] | Approved (HY2 2021) |  |  |  | 400k€ |  | Spent (as per 15.10.2021) |  |  |  | 361k€ |  | Click this button to create a powerpoint presentation:
Risk
Overall Status |  |  |  | Budget |  |  |  |  | Budget (labor) |  |  |  | 400k€ |  | Budget (labor) |  |  |  | 361k€
|  |  |  | Artefacts |  |  |  |  | Budget (non-labor) |  |  |  | 0k€ |  | Budget (non-labor) |  |  |  | 0k€
ARTEFACTS
ID | Artefact Description |  |  | Progress |  | Approved Budget (labor) | Achievements | [7 empty] | Work to be done | [6 empty] | 65%
35%
0%
1 | Evaluation of Financial Quantification of Enterprise Cyber Risk. |  |  | 65% |  | € 350 k | * Extension of pilot scope from 10 to 16 Allianz Entities * Modell questionnaires collected from 15/16 Allianz Entities. * Implementation of financial quantification model carried out for 15/16 Allianz Entities. * Evaluation of financial quantification results ongoing. * Update workshops with all 16 Allianz Entities are planned for 18.10.2021 | [6 empty] | * Collection of model questionaires for one remaining Allianz Entity. * Implementation of the financial quantifaction model for one remaining Allianz Entity. * Clarification of last remaining methodological questions with BitSight/Kovrr. * Evaluation of financial quantification results. | [7 empty] | 100%
0%
100%
2 | Recommendation regarding a group-wide roll-out of the Cyber Risk Quantification approach. |  |  | 0% |  | € 50 k | The start of this measure phase is planned for the next week. | [6 empty] | Alignment of a recommendation for a group-wide roll-out of the Cyber Risk Quantification approach. | [7 empty] | 0%
100%
0%
3 |  |  |  | 0% | [17 empty] | 100%
4 |  |  |  | 0%
5 |  |  |  | 0%
KPI |  |  | RISK |  | DESCRIPTION |  |  |  |  | CRITICALITY* |  | MITIGATION ACTIVITIES |  |  |  |  | RESOLUTION DATE
ID | KPI Description (Actuals/Target) |  | - | [6 empty] | -
1 | # of OEs evaluated within BitSight financial model (9/10)
2 | (/)
|  |  | - | [6 empty] | -
On track
Actions required
|  | Management attention required | - | [6 empty] | -
* Criticality: |  | High = Major negative impact on artefacts/timline |  |  | Medium = Considerable impact on artefacts/timeline |  |  |  |  | Low = Minor negative impact on artefacts/timeline
Create Powerpoint

## M297
M297 |  | Measure Report - HY2 2021
[11 empty] | Status report is up to date: |  |  |  | No |  |  | Help required: |  | No
Measure Name: |  |  | Focus Area: |  |  |  |  | Measure Lead: |  |  |  | Measure Duration: |  |  |  | Status:
Measure and Enhance Global Phishing Resilience |  |  | Build Security Organization / Skills |  |  |  |  | Clemens Friedrich |  |  |  | 01.07.2021 - 31.12.2021 |  |  |  | as per 29.10.2021
[9 empty] | Approved (HY2 2021) |  |  |  | 995k€ |  | Spent (as per 15.10.2021) |  |  |  | 190k€ |  | Click this button to create a powerpoint presentation:
Risk
Overall Status |  |  |  | Budget |  |  |  |  | Budget (labor) |  |  |  | 720k€ |  | Budget (labor) |  |  |  | 158k€
|  |  |  | Artefacts |  |  |  |  | Budget (non-labor) |  |  |  | 275k€ |  | Budget (non-labor) |  |  |  | 32k€
ARTEFACTS
ID | Artefact Description |  |  | Progress |  | Approved Budget (labor) | Achievements | [7 empty] | Work to be done | [6 empty] | 45%
55%
40%
1 | Design and Implementation of Cyber Security Awareness OE Dashboards and a normalized metric for security awareness per OE |  |  | 45% |  | € 245 k | ▪Technical integration of reporting data sources to Splunk achieved ▪First MVP for Triage and PhishMe report designed ▪OE mapping integrated | [6 empty] | ▪Complete automization and data segreation per OE dashboard ▪Integration of benchmarking data and KPI ▪Creation of aggregated global dashboard for Allianz worldwide | [7 empty] | 60%
40%
60%
2 | Creation of GUA building blocks (e.g., Learning Nuggets) supported by AZ brand storyline and as per IS practice #12 |  |  | 40% |  | € 295 k | ▪Alignment with internal stakeholders (Pilot OEs, GCORE, Group Strategy, Marketing and Distribution) on Global Brand Character concept ▪Production of first learning nugget ('Introduction Blue Knight') achieved (KPI: 1) ▪Concept defined in alignment with H4 for content integration in IS Training Hub | [6 empty] | ▪Finalize production for second learning nugget (aimed for CW44) ▪Introduction of Global Brand Character in IS Training Hub and integration of first learning material (aimed for CW45) ▪Enhancement of subtitles with addititional languages (German, French, Spanish, Italian) ▪Drive integration and promotion on internal platforms (Allianz Connect, Information Security Training Hub) | [7 empty] | 35%
65%
0%
3 | Execution of 6 Spear Phishing Campaigns and development of a service concept for enhanced Target Group Phishing as a Service |  |  | 40% |  | € 90 k | ▪Successful finalization of PoC prerequisites with Pilot OEs ▪Start of PoC conducted on 11.10.2021 with first phishing simulations sent out to test user groups (2-3 e-mails per user/ month) ▪Pilot OEs in scope: Az Technology incl. branches, Az France, Az Ireland | [6 empty] | ▪Next Spear Phishing training planned for CW 42/ 43 incl. Az SE BoM and RACo CEOs ▪3 target group campaigns for Allianz Group to be conducted in October as part of CSAM2021 ▪Extended Spear Phishing trainings and introduction of maturity level starting in November | [7 empty] | 100%
4 | Security Services offering enhancement with social media protection solution |  |  | 35% |  | € 90 k | ▪Pricing model with different scenarios (pay per OE vs. enterprise license) developed and presented to H4 ▪Evaluation of received offer for enterprise license | [6 empty] | ▪Clarification of financials and creation of implementation concept ▪Negotiation of offer from business, legal and commercial perspective
5 |  |  |  | 0%
KPI |  |  | RISK |  | DESCRIPTION |  |  |  |  | CRITICALITY* |  | MITIGATION ACTIVITIES |  |  |  |  | RESOLUTION DATE
ID | KPI Description (Actuals/Target) |  | - | [6 empty] | -
1 | # of learning nuggets and OE dashboards created (1/10)
2 | (/)
|  |  | - | [6 empty] | -
On track
Actions required
|  | Management attention required | - | [6 empty] | -
* Criticality: |  | High = Major negative impact on artefacts/timline |  |  | Medium = Considerable impact on artefacts/timeline |  |  |  |  | Low = Minor negative impact on artefacts/timeline
Create Powerpoint

## M298
M298 |  | Measure Report - HY2 2021
[11 empty] | Status report is up to date: |  |  |  | No |  |  | Help required: |  | No
Measure Name: |  |  | Focus Area: |  |  |  |  | Measure Lead: |  |  |  | Measure Duration: |  |  |  | Status:
Strategic THREAT Intelligence and Resulting risk Identification Program |  |  | Build Security Organization / Skills |  |  |  |  | Thomas Wolf |  |  |  | 01.07.2021 - 31.12.2021 |  |  |  | as per 29.10.2021
[9 empty] | Approved (HY2 2021) |  |  |  | 480k€ |  | Spent (as per 15.10.2021) |  |  |  | 238k€ |  | Click this button to create a powerpoint presentation:
Risk
Overall Status |  |  |  | Budget |  |  |  |  | Budget (labor) |  |  |  | 480k€ |  | Budget (labor) |  |  |  | 238k€
|  |  |  | Artefacts |  |  |  |  | Budget (non-labor) |  |  |  | 0k€ |  | Budget (non-labor) |  |  |  | 0k€
ARTEFACTS
ID | Artefact Description |  |  | Progress |  | Approved Budget (labor) | Achievements | [7 empty] | Work to be done | [6 empty] | 30%
70%
20%
1 | Threat Intelligence / cyber risk management strategy |  |  | 30% |  | € 240 k | Approach aligned,activity and interrim results handed on by Stefan Balzer Decision taken for Thomas Wolf to take over artifact creation with risk aspects not in scope (Ralf Schneider) | [6 empty] | Creation of Strawman based on Stefan Balzer draft Stakeholder interviews and alginment Document creation and finalization | [7 empty] | 80%
40%
60%
2 | Advanced threats (insider / state-sponsored) strategy |  |  | 20% |  | € 150 k | Approach aligned Document content / structure defined Decepton strategy in clarification / feature expansion | [6 empty] | Stakeholder interviews and alginment Strategy high -> Low level creation Advanced social defense alignment | [7 empty] | 0%
100%
0%
3 | AI model for strategic threat intelligence (PoV) |  |  | 40% |  | € 90 k | Infrastructure alignment done, infrastructure in buildup Data source connection: high-level aligned Interrim process (batch-based) established | [6 empty] | Infrastructure completion, implementation of online instead of batch access model improvement | [7 empty] | 100%
4 |  |  |  | 0%
5 |  |  |  | 0%
KPI |  |  | RISK |  | DESCRIPTION |  |  |  |  | CRITICALITY* |  | MITIGATION ACTIVITIES |  |  |  |  | RESOLUTION DATE
ID | KPI Description (Actuals/Target) |  | - | [6 empty] | -
1 | # of reached artefacts (0/3)
2 | (/)
|  |  | - | [6 empty] | -
On track
Actions required
|  | Management attention required | - | [6 empty] | -
* Criticality: |  | High = Major negative impact on artefacts/timline |  |  | Medium = Considerable impact on artefacts/timeline |  |  |  |  | Low = Minor negative impact on artefacts/timeline
Create Powerpoint

## M299
M299 |  | Measure Report - HY2 2021
[11 empty] | Status report is up to date: |  |  |  | No |  |  | Help required: |  | No
Measure Name: |  |  | Focus Area: |  |  |  |  | Measure Lead: |  |  |  | Measure Duration: |  |  |  | Status:
Enforcement of Security Architecture |  |  | Build Security Organization / Skills |  |  |  |  | Jan General |  |  |  | 01.07.2021 - 31.12.2021 |  |  |  | as per 29.10.2021
[9 empty] | Approved (HY2 2021) |  |  |  | 430k€ |  | Spent (as per 15.10.2021) |  |  |  | 187k€ |  | Click this button to create a powerpoint presentation:
Risk
Overall Status |  |  |  | Budget |  |  |  |  | Budget (labor) |  |  |  | 430k€ |  | Budget (labor) |  |  |  | 187k€
|  |  |  | Artefacts |  |  |  |  | Budget (non-labor) |  |  |  | 0k€ |  | Budget (non-labor) |  |  |  | 0k€
ARTEFACTS
ID | Artefact Description |  |  | Progress |  | Approved Budget (labor) | Achievements | [7 empty] | Work to be done | [6 empty] | 20%
80%
15%
1 | Gap analysis and enforcement of implementation to secure with API and Container Patterns |  |  | 20% |  | € 135 k | Candidates for GAP identified. Content for container training defined. | [6 empty] | Prepare GAP assessment and create Assessment templates. Schedule training session for API Pattern. Create training documents for container pattern. | [7 empty] | 85%
60%
40%
2 | An architectural view on IS Economics |  |  | 15% |  | € 85 k | Workshops executed and detail approach | [6 empty] | Document and align IS Economics methodology Cluster architectural controls | [7 empty] | 25%
75%
25%
3 | Event Brokering Security Patterns |  |  | 60% |  | € 90 k | Workshops executed and document sent for review | [6 empty] | Rework Document based on feedback | [7 empty] | 75%
4 | Threat modelling deployment and trainings in Allianz Technology |  |  | 25% |  | € 80 k | Feedback from AzTech on methdology recieved | [6 empty] | Meeting with OE to receive feedback on methodology and templates
5 | Moving Enterprise Security Reference Architecture into ADOIT |  |  | 25% |  | € 40 k | Prepare Test controls for import into dev. | [6 empty] | Test import of a limited numbers of controls
KPI |  |  | RISK |  | DESCRIPTION |  |  |  |  | CRITICALITY* |  | MITIGATION ACTIVITIES |  |  |  |  | RESOLUTION DATE
ID | KPI Description (Actuals/Target) |  | - | [6 empty] | -
1 | # of learning nuggets and OE dashboards created (1/10)
2 | (/)
|  |  | - | [6 empty] | -
On track
Actions required
|  | Management attention required | - | [6 empty] | -
* Criticality: |  | High = Major negative impact on artefacts/timline |  |  | Medium = Considerable impact on artefacts/timeline |  |  |  |  | Low = Minor negative impact on artefacts/timeline
Create Powerpoint

## M300
M300 |  | Measure Report - HY2 2021
[11 empty] | Status report is up to date: |  |  |  | No |  |  | Help required: |  | No
Measure Name: |  |  | Focus Area: |  |  |  |  | Measure Lead: |  |  |  | Measure Duration: |  |  |  | Status:
Metrics phase @We protect scale up on skills |  |  | Build Security Organization / Skills |  |  |  |  | Samuel Hurst |  |  |  | 01.07.2021 - 31.12.2021 |  |  |  | as per 29.10.2021
[9 empty] | Approved (HY2 2021) |  |  |  | 540k€ |  | Spent (as per 15.10.2021) |  |  |  | 171k€ |  | Click this button to create a powerpoint presentation:
Risk
Overall Status |  |  |  | Budget |  |  |  |  | Budget (labor) |  |  |  | 390k€ |  | Budget (labor) |  |  |  | 148k€
|  |  |  | Artefacts |  |  |  |  | Budget (non-labor) |  |  |  | 150k€ |  | Budget (non-labor) |  |  |  | 23k€
ARTEFACTS
ID | Artefact Description |  |  | Progress |  | Approved Budget (labor) | Achievements | [7 empty] | Work to be done | [6 empty] | 55%
45%
75%
1 | Develop performance metrics to maximize ROI |  |  | 55% |  | 140k€ | All metrics have been agreed with Measure Sponsor. Visualization of metrics aligned. All datasets available. | [6 empty] | Monthly reporting of metrics. Final metrics report. | [7 empty] | 25%
40%
60%
2 | Organization and communication of CSAM events |  |  | 75% |  | 110k€ | A panel discussion with P&R, InfoSec, DP. An event with Euler Hermes (one in German to accommodate AZ D, and one in English) is planned. | [6 empty] | Comms - updated Group CSAM Connect page and German translation of AZ Tech promotional material. | [7 empty] | 25%
75%
10%
3 | Steering of CoT education initiatives & TrustNet |  |  | 40% |  | 105k€ | Ransomware event organized by the TrustNet community, with speakers from Atos, Critical Impact and BSI. | [6 empty] | A mobile security event is planned. | [7 empty] | 90%
4 | Mandatory InfoSec eLearning on SuccessFactors |  |  | 25% |  | 20k€ | eLearning modules scoped. HvS have submitted a proposal and quote. HR have been informed about SuccessFactors integration. | [6 empty] | HvS quote to be reviewed by Measure Sponsor. Once accepted, a PowerPoint will be sent for review.
5 | Publication of SPF guideline and quiz |  |  | 10% |  | 15k€ | Draft SPF document created. | [6 empty] | Mitigation activities planned with Nora taking lead.
KPI |  |  | RISK |  | DESCRIPTION |  |  |  |  | CRITICALITY* |  | MITIGATION ACTIVITIES |  |  |  |  | RESOLUTION DATE
ID | KPI Description (Actuals/Target)
1 | # of high qualitative metrics for ROI (0/5)
2 | (/)
On track
Actions required
Management attention required
* Criticality: |  | High = Major negative impact on artefacts/timline |  |  | Medium = Considerable impact on artefacts/timeline |  |  |  |  | Low = Minor negative impact on artefacts/timeline
Create Powerpoint